## PRJ WP Site
Project--ID | Project--ProjectName | Project--SystemRecordID | Project--ProjectPlanStartDate | Project--ProjectPlanEndDate | Project--ProjectExecutionCountry | Project--Customer | Project--Status | Workplan--Country | Workplan--WorkPlanID | Workplan--FASID | Workplan--SystemRecordID | Workplan--WorkPlanStatus | Workplan--ProjectName | Workplan--Prefix | Workplan--Suffix | Workplan--CustomerDeliverableID | Workplan--RelatedNetworkElement | Workplan--CustomerScopeID | Workplan--WorkPlanType | Sites--ID | Sites--Name | Sites--RecordName | Sites--SystemRecordID | Sites--Customer | Sites--SiteType | Sites--City | Sites--Country | Sites--Status | Sites--StreetAddress | Sites--LatitudeDecimal | Sites--LatitudeDMS | Sites--LongitudeDecimal | Sites--LongitudeDMS
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668884 |  | 698632435 | Completed | 50125605-延安吴起县营业厅-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安吴起县营业厅-延安吴起县营业厅\延安吴起县营业厅-延安吴起县营业厅 |  | Radio Site | 延安吴起县营业厅 | 延安吴起县营业厅_1 | 延安吴起县营业厅-延安吴起县营业厅 | 698624197 |  |  | Yanan | China | Draft |  | 108.1737 | 108'10'25' | 36.9221 | 36'55'19'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2000-01-01 | China | China Mobile Shaanxi | Issued | China | 3668885 |  | 698632437 | Released | 50125605-梁家河-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\梁家河-梁家河\梁家河-梁家河 |  | Radio Site | 梁家河 | 梁家河_1 | 梁家河-梁家河 | 698624189 |  |  | Yanan | China | Draft |  | 110.0572 | 110'3'26' | 36.8222 | 36'49'19'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668886 |  | 698632438 | Completed | 50125605-延安子长瓦窑堡宾馆-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安子长瓦窑堡宾馆-延安子长瓦窑堡宾馆\延安子长瓦窑堡宾馆-延安子长瓦窑堡宾馆 |  | Radio Site | 延安子长瓦窑堡宾馆 | 延安子长瓦窑堡宾馆_1 | 延安子长瓦窑堡宾馆-延安子长瓦窑堡宾馆 | 698624198 |  |  | Yanan | China | Draft |  | 109.67 | 109'40'12' | 37.1406 | 37'8'26'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668887 |  | 698632442 | Completed | 50125605-延安延长电信局-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安延长电信局-延安延长电信局\延安延长电信局-延安延长电信局 |  | Radio Site | 延安延长电信局 | 延安延长电信局_1 | 延安延长电信局-延安延长电信局 | 698624193 |  |  | Yanan | China | Draft |  | 110.0074 | 110'0'27' | 36.58 | 36'34'48'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668888 |  | 698632441 | Completed | 50125605-延安黄龙县营业厅-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安黄龙县营业厅-延安黄龙县营业厅\延安黄龙县营业厅-延安黄龙县营业厅 |  | Radio Site | 延安黄龙县营业厅 | 延安黄龙县营业厅_1 | 延安黄龙县营业厅-延安黄龙县营业厅 | 698624196 |  |  | Yanan | China | Draft |  | 109.8326 | 109'49'57' | 35.5841 | 35'35'2'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-11-19 | China | China Mobile Shaanxi | Issued | China | 3668890 |  | 698632444 | Completed | 50125605-延安延川1号-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安延川1号-延安延川1号\延安延川1号-延安延川1号 |  | Radio Site | 延安延川1号 | 延安延川1号_1 | 延安延川1号-延安延川1号 | 698624194 |  |  | Yanan | China | Draft |  | 110.1873 | 110'11'14' | 36.8786 | 36'52'42'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668891 |  | 698632445 | Completed | 50125605-延安志丹1号-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安志丹1号-延安志丹1号\延安志丹1号-延安志丹1号 |  | Radio Site | 延安志丹1号 | 延安志丹1号_1 | 延安志丹1号-延安志丹1号 | 698624195 |  |  | Yanan | China | Draft |  | 108.7639 | 108'45'50' | 36.8216 | 36'49'17'
1011939 | CN_CM_COMBJ_SAX_5G RAN_CP1_50125605_2019(2020P1)+NEW | 698631010 | 2000-01-01 | 2019-10-10 | China | China Mobile Shaanxi | Issued | China | 3668892 |  | 698632448 | Completed | 50125605-延安安塞县中学-SV_MACRO | 50125605 | SV_MACRO |  | \Locations\延安安塞县中学-延安安塞县中学\延安安塞县中学-延安安塞县中学 |  | Radio Site | 延安安塞县中学 | 延安安塞县中学_1 | 延安安塞县中学-延安安塞县中学 | 698624188 |  |  | Yanan | China | Draft |  | 109.3243 | 109'19'27' | 36.8631 | 36'51'47'

## PLO dates
WP ID | Workplan--SystemRecordID | Customised PLO name | PLO--Name | PLO--Status | Object type | PLO--SystemRecordID | act--BaselineEndDate | act--ForecastEndDate | act--ActualStartDate | act--ActualEndDate | ms--BaselineEndDate | ms--ForecastEndDate | ms--ActualStartDate | ms--ActualEndDate
3668884 | 698632435 | act--02 Integration | 02 Integration | Completed | Activity | 698632587 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 12:18:51 | 10/09/2019 13:41:51
3668884 | 698632435 | act--04 SSV | 04 SSV | Completed | Activity | 698632643 | 12/04/2019 15:57:36 | 12/04/2019 15:57:36 | 12/03/2019 07:57:36 | 12/04/2019 15:57:36
3668884 | 698632435 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632692 | 12/29/2019 07:57:36 | 12/29/2019 07:57:36 | 12/21/2019 07:57:36 | 12/29/2019 07:57:36
3668884 | 698632435 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632559 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 11:50:51
3668884 | 698632435 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632536 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 05:52:34
3668884 | 698632435 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632453 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 14:04:51
3668884 | 698632435 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632496 |  |  |  |  | 12/06/2019 15:57:36 | 12/06/2019 15:57:36 |  | 12/06/2019 15:57:36
3668885 | 698632437 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 698632589 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
3668885 | 698632437 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 698632641 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
3668885 | 698632437 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 698632690 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
3668885 | 698632437 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 698632558 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
3668885 | 698632437 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 698632538 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
3668885 | 698632437 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 698632457 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
3668885 | 698632437 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 698632494 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
3668886 | 698632438 | act--02 Integration | 02 Integration | Completed | Activity | 698632588 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 11:57:12 | 10/09/2019 13:21:12
3668886 | 698632438 | act--04 SSV | 04 SSV | Completed | Activity | 698632642 | 12/05/2019 15:57:36 | 12/05/2019 15:57:36 | 12/04/2019 07:57:36 | 12/05/2019 15:57:36
3668886 | 698632438 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632691 | 12/30/2019 07:57:36 | 12/30/2019 07:57:36 | 12/22/2019 07:57:36 | 12/30/2019 07:57:36
3668886 | 698632438 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632557 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 11:30:12
3668886 | 698632438 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632537 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 05:35:12
3668886 | 698632438 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632455 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 13:46:12
3668886 | 698632438 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632495 |  |  |  |  | 12/07/2019 15:57:36 | 12/07/2019 15:57:36 |  | 12/07/2019 15:57:36
3668887 | 698632442 | act--02 Integration | 02 Integration | Completed | Activity | 698632604 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 12:32:25 | 10/09/2019 13:56:25
3668887 | 698632442 | act--04 SSV | 04 SSV | Completed | Activity | 698632652 | 12/05/2019 14:57:13 | 12/05/2019 14:57:13 | 12/04/2019 06:57:13 | 12/05/2019 14:57:13
3668887 | 698632442 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632704 | 12/30/2019 06:57:13 | 12/30/2019 06:57:13 | 12/22/2019 06:57:13 | 12/30/2019 06:57:13
3668887 | 698632442 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632566 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 12:06:25
3668887 | 698632442 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632548 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 06:10:02
3668887 | 698632442 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632459 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 14:16:25
3668887 | 698632442 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632509 |  |  |  |  | 12/07/2019 14:57:13 | 12/07/2019 14:57:13 |  | 12/07/2019 14:57:13
3668888 | 698632441 | act--02 Integration | 02 Integration | Completed | Activity | 698632602 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 11:57:12 | 10/09/2019 13:24:12
3668888 | 698632441 | act--04 SSV | 04 SSV | Completed | Activity | 698632651 | 12/04/2019 15:49:51 | 12/04/2019 15:49:51 | 12/03/2019 07:49:51 | 12/04/2019 15:49:51
3668888 | 698632441 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632702 | 12/29/2019 07:49:51 | 12/29/2019 07:49:51 | 12/21/2019 07:49:51 | 12/29/2019 07:49:51
3668888 | 698632441 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632564 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 11:31:12
3668888 | 698632441 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632550 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 05:35:12
3668888 | 698632441 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632462 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 13:51:12
3668888 | 698632441 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632507 |  |  |  |  | 12/06/2019 15:49:51 | 12/06/2019 15:49:51 |  | 12/06/2019 15:49:51
3668890 | 698632444 | act--02 Integration | 02 Integration | Completed | Activity | 698632601 | 11/19/2019 14:30:00 | 11/19/2019 14:30:00 | 11/18/2019 12:03:42 | 11/18/2019 13:29:42
3668890 | 698632444 | act--04 SSV | 04 SSV | Completed | Activity | 698632650 | 12/05/2019 15:19:23 | 12/05/2019 15:19:23 | 12/04/2019 07:19:23 | 12/05/2019 15:19:23
3668890 | 698632444 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632700 | 12/30/2019 07:19:23 | 12/30/2019 07:19:23 | 12/22/2019 07:19:23 | 12/30/2019 07:19:23
3668890 | 698632444 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632563 |  |  |  |  | 11/19/2019 12:30:00 | 11/19/2019 12:30:00 |  | 11/18/2019 11:35:42
3668890 | 698632444 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632547 |  |  |  |  | 11/19/2019 06:30:00 | 11/19/2019 06:30:00 |  | 11/18/2019 05:41:42
3668890 | 698632444 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632461 |  |  |  |  | 11/19/2019 15:00:00 | 11/19/2019 15:00:00 |  | 11/18/2019 13:57:42
3668890 | 698632444 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632505 |  |  |  |  | 12/07/2019 15:19:23 | 12/07/2019 15:19:23 |  | 12/07/2019 15:19:23
3668891 | 698632445 | act--02 Integration | 02 Integration | Completed | Activity | 698632600 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 11:59:53 | 10/09/2019 13:25:53
3668891 | 698632445 | act--04 SSV | 04 SSV | Completed | Activity | 698632653 | 12/05/2019 15:49:51 | 12/05/2019 15:49:51 | 12/04/2019 07:49:51 | 12/05/2019 15:49:51
3668891 | 698632445 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632703 | 12/30/2019 07:49:51 | 12/30/2019 07:49:51 | 12/22/2019 07:49:51 | 12/30/2019 07:49:51
3668891 | 698632445 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632565 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 11:32:53
3668891 | 698632445 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632549 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 05:40:52
3668891 | 698632445 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632463 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 13:52:53
3668891 | 698632445 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632508 |  |  |  |  | 12/07/2019 15:49:51 | 12/07/2019 15:49:51 |  | 12/07/2019 15:49:51
3668892 | 698632448 | act--02 Integration | 02 Integration | Completed | Activity | 698632603 | 10/10/2019 14:30:00 | 10/10/2019 14:30:00 | 10/09/2019 12:01:05 | 10/09/2019 13:28:05
3668892 | 698632448 | act--04 SSV | 04 SSV | Completed | Activity | 698632654 | 12/04/2019 14:57:13 | 12/04/2019 14:57:13 | 12/03/2019 06:57:13 | 12/04/2019 14:57:13
3668892 | 698632448 | act--06 Tuning | 06 Tuning | Completed | Activity | 698632701 | 12/29/2019 06:57:13 | 12/29/2019 06:57:13 | 12/21/2019 06:57:13 | 12/29/2019 06:57:13
3668892 | 698632448 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 698632567 |  |  |  |  | 10/10/2019 12:30:00 | 10/10/2019 12:30:00 |  | 10/09/2019 11:37:05
3668892 | 698632448 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 698632551 |  |  |  |  | 10/10/2019 06:30:00 | 10/10/2019 06:30:00 |  | 10/09/2019 05:40:52
3668892 | 698632448 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 698632460 |  |  |  |  | 10/10/2019 15:00:00 | 10/10/2019 15:00:00 |  | 10/09/2019 13:53:05
3668892 | 698632448 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 698632506 |  |  |  |  | 12/06/2019 14:57:13 | 12/06/2019 14:57:13 |  | 12/06/2019 14:57:13

## UDF ITEM
WP ID | Workplan--SystemRecordID | PLO name | PLO--SystemRecordID | UDF Name | UDF - System Record ID | UDF Category Name | UDF CategorySystem Record ID | UDF item Name | UDF Item--SystemRecordID | UDF Value
3668884 | 698632435 | 01 Installation End | 698632559 | 01 Lead Time Comments | 698632574 | 01 Lead Time | 698632577 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632579
3668884 | 698632435 | 02 Integration | 698632587 | 02 Lead Time Comments | 698632611 | 02 Lead Time | 698632614 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632617
3668884 | 698632435 | 02 Integration | 698632587 | 02 Lead Time Comments | 698632611 | 02 Lead Time | 698632614 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632630
3668884 | 698632435 | 03 Integration Confirmed By NRO Technical Leader | 698632453 | 03 Lead Time Comments | 698632473 | 03 Lead Time | 698632476 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632479
3668884 | 698632435 | 04 SSV | 698632643 | 04 Lead Time Comments | 698632660 | 04 Lead Time | 698632663 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632666
3668884 | 698632435 | 04 SSV | 698632643 | 04 Lead Time Comments | 698632660 | 04 Lead Time | 698632663 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632679
3668884 | 698632435 | 05 SSV Confirmed By NDO Technical Leader | 698632496 | 05 Lead Time Comments | 698632516 | 05 Lead Time | 698632520 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632523
3668884 | 698632435 | 06 Tuning | 698632692 | 06 Lead Time Comments | 698632710 | 06 Lead Time | 698632713 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632717
3668884 | 698632435 | 06 Tuning | 698632692 | 06 Lead Time Comments | 698632710 | 06 Lead Time | 698632713 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632734
3668885 | 698632437 | 01 Installation End | 698632558 | 01 Lead Time Comments | 698632575 | 01 Lead Time | 698632578 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632581
3668885 | 698632437 | 02 Integration | 698632589 | 02 Lead Time Comments | 698632610 | 02 Lead Time | 698632612 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632616
3668885 | 698632437 | 02 Integration | 698632589 | 02 Lead Time Comments | 698632610 | 02 Lead Time | 698632612 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632629
3668885 | 698632437 | 03 Integration Confirmed By NRO Technical Leader | 698632457 | 03 Lead Time Comments | 698632474 | 03 Lead Time | 698632477 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632481
3668885 | 698632437 | 04 SSV | 698632641 | 04 Lead Time Comments | 698632659 | 04 Lead Time | 698632662 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632664
3668885 | 698632437 | 04 SSV | 698632641 | 04 Lead Time Comments | 698632659 | 04 Lead Time | 698632662 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632677
3668885 | 698632437 | 05 SSV Confirmed By NDO Technical Leader | 698632494 | 05 Lead Time Comments | 698632518 | 05 Lead Time | 698632522 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632524
3668885 | 698632437 | 06 Tuning | 698632690 | 06 Lead Time Comments | 698632708 | 06 Lead Time | 698632711 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632714
3668885 | 698632437 | 06 Tuning | 698632690 | 06 Lead Time Comments | 698632708 | 06 Lead Time | 698632711 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632727
3668886 | 698632438 | 01 Installation End | 698632557 | 01 Lead Time Comments | 698632573 | 01 Lead Time | 698632576 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632580
3668886 | 698632438 | 02 Integration | 698632588 | 02 Lead Time Comments | 698632609 | 02 Lead Time | 698632613 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632615
3668886 | 698632438 | 02 Integration | 698632588 | 02 Lead Time Comments | 698632609 | 02 Lead Time | 698632613 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632628
3668886 | 698632438 | 03 Integration Confirmed By NRO Technical Leader | 698632455 | 03 Lead Time Comments | 698632472 | 03 Lead Time | 698632475 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632480
3668886 | 698632438 | 04 SSV | 698632642 | 04 Lead Time Comments | 698632658 | 04 Lead Time | 698632661 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632665
3668886 | 698632438 | 04 SSV | 698632642 | 04 Lead Time Comments | 698632658 | 04 Lead Time | 698632661 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632678
3668886 | 698632438 | 05 SSV Confirmed By NDO Technical Leader | 698632495 | 05 Lead Time Comments | 698632517 | 05 Lead Time | 698632521 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632525
3668886 | 698632438 | 06 Tuning | 698632691 | 06 Lead Time Comments | 698632709 | 06 Lead Time | 698632712 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632715
3668886 | 698632438 | 06 Tuning | 698632691 | 06 Lead Time Comments | 698632709 | 06 Lead Time | 698632712 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632728
3668887 | 698632442 | 01 Installation End | 698632566 | 01 Lead Time Comments | 698632584 | 01 Lead Time | 698632594 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632598
3668887 | 698632442 | 02 Integration | 698632604 | 02 Lead Time Comments | 698632627 | 02 Lead Time | 698632635 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632640
3668887 | 698632442 | 02 Integration | 698632604 | 02 Lead Time Comments | 698632627 | 02 Lead Time | 698632635 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632648
3668887 | 698632442 | 03 Integration Confirmed By NRO Technical Leader | 698632459 | 03 Lead Time Comments | 698632482 | 03 Lead Time | 698632492 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632504
3668887 | 698632442 | 04 SSV | 698632652 | 04 Lead Time Comments | 698632676 | 04 Lead Time | 698632684 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632688
3668887 | 698632442 | 04 SSV | 698632652 | 04 Lead Time Comments | 698632676 | 04 Lead Time | 698632684 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632699
3668887 | 698632442 | 05 SSV Confirmed By NDO Technical Leader | 698632509 | 05 Lead Time Comments | 698632526 | 05 Lead Time | 698632532 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632543
3668887 | 698632442 | 06 Tuning | 698632704 | 06 Lead Time Comments | 698632725 | 06 Lead Time | 698632732 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632739
3668887 | 698632442 | 06 Tuning | 698632704 | 06 Lead Time Comments | 698632725 | 06 Lead Time | 698632732 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632746
3668888 | 698632441 | 01 Installation End | 698632564 | 01 Lead Time Comments | 698632586 | 01 Lead Time | 698632593 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632597
3668888 | 698632441 | 02 Integration | 698632602 | 02 Lead Time Comments | 698632623 | 02 Lead Time | 698632632 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632639
3668888 | 698632441 | 02 Integration | 698632602 | 02 Lead Time Comments | 698632623 | 02 Lead Time | 698632632 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632646
3668888 | 698632441 | 03 Integration Confirmed By NRO Technical Leader | 698632462 | 03 Lead Time Comments | 698632484 | 03 Lead Time | 698632490 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632500
3668888 | 698632441 | 04 SSV | 698632651 | 04 Lead Time Comments | 698632674 | 04 Lead Time | 698632683 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632687
3668888 | 698632441 | 04 SSV | 698632651 | 04 Lead Time Comments | 698632674 | 04 Lead Time | 698632683 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632697
3668888 | 698632441 | 05 SSV Confirmed By NDO Technical Leader | 698632507 | 05 Lead Time Comments | 698632530 | 05 Lead Time | 698632535 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632545
3668888 | 698632441 | 06 Tuning | 698632702 | 06 Lead Time Comments | 698632726 | 06 Lead Time | 698632733 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632740
3668888 | 698632441 | 06 Tuning | 698632702 | 06 Lead Time Comments | 698632726 | 06 Lead Time | 698632733 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632750
3668890 | 698632444 | 01 Installation End | 698632563 | 01 Lead Time Comments | 698632585 | 01 Lead Time | 698632592 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632596
3668890 | 698632444 | 02 Integration | 698632601 | 02 Lead Time Comments | 698632624 | 02 Lead Time | 698632631 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632636
3668890 | 698632444 | 02 Integration | 698632601 | 02 Lead Time Comments | 698632624 | 02 Lead Time | 698632631 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632644
3668890 | 698632444 | 03 Integration Confirmed By NRO Technical Leader | 698632461 | 03 Lead Time Comments | 698632483 | 03 Lead Time | 698632493 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632502
3668890 | 698632444 | 04 SSV | 698632650 | 04 Lead Time Comments | 698632672 | 04 Lead Time | 698632680 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632685
3668890 | 698632444 | 04 SSV | 698632650 | 04 Lead Time Comments | 698632672 | 04 Lead Time | 698632680 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632694
3668890 | 698632444 | 05 SSV Confirmed By NDO Technical Leader | 698632505 | 05 Lead Time Comments | 698632527 | 05 Lead Time | 698632531 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632542
3668890 | 698632444 | 06 Tuning | 698632700 | 06 Lead Time Comments | 698632722 | 06 Lead Time | 698632729 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632736
3668890 | 698632444 | 06 Tuning | 698632700 | 06 Lead Time Comments | 698632722 | 06 Lead Time | 698632729 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632744
3668891 | 698632445 | 01 Installation End | 698632565 | 01 Lead Time Comments | 698632582 | 01 Lead Time | 698632590 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632599
3668891 | 698632445 | 02 Integration | 698632600 | 02 Lead Time Comments | 698632626 | 02 Lead Time | 698632633 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632638
3668891 | 698632445 | 02 Integration | 698632600 | 02 Lead Time Comments | 698632626 | 02 Lead Time | 698632633 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632647
3668891 | 698632445 | 03 Integration Confirmed By NRO Technical Leader | 698632463 | 03 Lead Time Comments | 698632486 | 03 Lead Time | 698632491 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632501
3668891 | 698632445 | 04 SSV | 698632653 | 04 Lead Time Comments | 698632675 | 04 Lead Time | 698632682 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632686
3668891 | 698632445 | 04 SSV | 698632653 | 04 Lead Time Comments | 698632675 | 04 Lead Time | 698632682 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632698
3668891 | 698632445 | 05 SSV Confirmed By NDO Technical Leader | 698632508 | 05 Lead Time Comments | 698632528 | 05 Lead Time | 698632533 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632544
3668891 | 698632445 | 06 Tuning | 698632703 | 06 Lead Time Comments | 698632723 | 06 Lead Time | 698632731 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632738
3668891 | 698632445 | 06 Tuning | 698632703 | 06 Lead Time Comments | 698632723 | 06 Lead Time | 698632731 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632748
3668892 | 698632448 | 01 Installation End | 698632567 | 01 Lead Time Comments | 698632583 | 01 Lead Time | 698632591 | mscl--01 Installation End--01 Lead Time Comments--Duration | 698632595
3668892 | 698632448 | 02 Integration | 698632603 | 02 Lead Time Comments | 698632625 | 02 Lead Time | 698632634 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 698632637
3668892 | 698632448 | 02 Integration | 698632603 | 02 Lead Time Comments | 698632625 | 02 Lead Time | 698632634 | actcl--02 Integration--02 Lead Time Comments--Duration | 698632645
3668892 | 698632448 | 03 Integration Confirmed By NRO Technical Leader | 698632460 | 03 Lead Time Comments | 698632485 | 03 Lead Time | 698632489 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 698632503
3668892 | 698632448 | 04 SSV | 698632654 | 04 Lead Time Comments | 698632673 | 04 Lead Time | 698632681 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 698632689
3668892 | 698632448 | 04 SSV | 698632654 | 04 Lead Time Comments | 698632673 | 04 Lead Time | 698632681 | actcl--04 SSV--04 Lead Time Comments--Duration | 698632696
3668892 | 698632448 | 05 SSV Confirmed By NDO Technical Leader | 698632506 | 05 Lead Time Comments | 698632529 | 05 Lead Time | 698632534 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 698632546
3668892 | 698632448 | 06 Tuning | 698632701 | 06 Lead Time Comments | 698632724 | 06 Lead Time | 698632730 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 698632737
3668892 | 698632448 | 06 Tuning | 698632701 | 06 Lead Time Comments | 698632724 | 06 Lead Time | 698632730 | actcl--06 Tuning--06 Lead Time Comments--Duration | 698632745