## PRJ WP Site
Project--ID | Project--ProjectName | Project--SystemRecordID | Project--ProjectPlanStartDate | Project--ProjectPlanEndDate | Project--ProjectExecutionCountry | Project--Customer | Project--Status | Workplan--Country | Workplan--WorkPlanID | Workplan--FASID | Workplan--SystemRecordID | Workplan--WorkPlanStatus | Workplan--ProjectName | Workplan--Prefix | Workplan--Suffix | Workplan--CustomerDeliverableID | Workplan--RelatedNetworkElement | Workplan--CustomerScopeID | Workplan--WorkPlanType | Sites--ID | Sites--Name | Sites--RecordName | Sites--SystemRecordID | Sites--Customer | Sites--SiteType | Sites--City | Sites--Country | Sites--Status | Sites--StreetAddress | Sites--LatitudeDecimal | Sites--LatitudeDMS | Sites--LongitudeDecimal | Sites--LongitudeDMS
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-28 | China | China Telecom Guangxi | Completed | China | 2582393 |  | 245000927 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡覃屋1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGPXunWangXiangQinWu-桂平寻旺乡覃屋\NDXLEFGPXunWangXiangQinWu1800O-桂平寻旺乡覃屋1800O |  | Radio Site | NDXLEFGPXunWangXiangQinWu1800O | 桂平寻旺乡覃屋1800O_1 | NDXLEFGPXunWangXiangQinWu1800O-桂平寻旺乡覃屋1800O | 245012200 |  |  | Guigang | China | Draft | 贵港桂平市寻旺谭屋附近 | 110.1636 | 110'9'49' | 23.3897 | 23'23'22'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-06 | China | China Telecom Guangxi | Completed | China | 2582394 |  | 245000930 | Completed | CTGXLTE1.8Gproject-桂平石咀镇小汶村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPShiJuZhenXiaoWenC-桂平石咀镇小汶村\GPShiJuZhenXiaoWenC1800O-桂平石咀镇小汶村1800O |  | Radio Site | GPShiJuZhenXiaoWenC1800O | 桂平石咀镇小汶村1800O_1 | GPShiJuZhenXiaoWenC1800O-桂平石咀镇小汶村1800O | 245012193 |  |  | Guigang | China | Draft | 贵港桂平市石咀镇小汶村里一田地 | 110.134 | 110'8'2' | 23.4348 | 23'26'5'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-10 | China | China Telecom Guangxi | Completed | China | 2582395 |  | 245000929 | Completed | CTGXLTE1.8Gproject-贵港根竹乡岭南高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXiangLingNGT-贵港根竹乡岭南高铁\GGGenZhuXiangLingNGT1800O-贵港根竹乡岭南高铁1800O |  | Radio Site | GGGenZhuXiangLingNGT1800O | 贵港根竹乡岭南高铁1800O_1 | GGGenZhuXiangLingNGT1800O-贵港根竹乡岭南高铁1800O | 245012185 |  |  | Guigang | China | Draft | 贵港市港北区根竹乡江口村西南方向约0.95公里 | 109.5255 | 109'31'32' | 23.1076 | 23'6'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-25 | China | China Telecom Guangxi | Completed | China | 2582396 |  | 245000931 | Completed | CTGXLTE1.8Gproject-贵港大圩镇大桥高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGGDaXuZhenDaQiaoGaoT-贵港大圩镇大桥高铁\NDXLEFGGDaXuZhenDaQiaoGaoT1800O-贵港大圩镇大桥高铁1800O |  | Radio Site | NDXLEFGGDaXuZhenDaQiaoGaoT1800O | 贵港大圩镇大桥高铁1800O_1 | NDXLEFGGDaXuZhenDaQiaoGaoT1800O-贵港大圩镇大桥高铁1800O | 245012199 |  |  | Guigang | China | Draft | 贵港市港北区大圩镇大圩交警考试场东南方向1公里 | 109.7455 | 109'44'44' | 23.1685 | 23'10'6'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-28 | China | China Telecom Guangxi | Completed | China | 2582397 |  | 245000926 | Completed | CTGXLTE1.8Gproject-贵港市港城旺岭雁明屯高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGShiGangChengWLYMTGT-贵港市港城旺岭雁明屯高铁\GGShiGangChengWLYMTGT1800O-贵港市港城旺岭雁明屯高铁1800O |  | Radio Site | GGShiGangChengWLYMTGT1800O | 贵港市港城旺岭雁明屯高铁1800O_1 | GGShiGangChengWLYMTGT1800O-贵港市港城旺岭雁明屯高铁1800O | 245012221 |  |  | Guigang | China | Draft | 贵港市港北区港城镇雁明屯 往西约488米 | 109.6799 | 109'40'48' | 23.1311 | 23'7'51'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-30 | China | China Telecom Guangxi | Completed | China | 2582398 |  | 245000933 | Completed | CTGXLTE1.8Gproject-贵港市港城旺岭中山村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGShiGangChengWLZSCGT-贵港市港城旺岭中山村高铁\GGShiGangChengWLZSCGT1800O-贵港市港城旺岭中山村高铁1800O |  | Radio Site | GGShiGangChengWLZSCGT1800O | 贵港市港城旺岭中山村高铁1800O_1 | GGShiGangChengWLZSCGT1800O-贵港市港城旺岭中山村高铁1800O | 245012229 |  |  | Guigang | China | Draft | 贵港港城旺岭中山村旁 | 109.6744 | 109'40'28' | 23.1236 | 23'7'24'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-26 | China | China Telecom Guangxi | Completed | China | 2582399 |  | 245000928 | Completed | CTGXLTE1.8Gproject-贵港大圩镇甘岭村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGGDaXuZhenGanLingCGT-贵港大圩镇甘岭村高铁\NDXLEFGGDaXuZhenGanLingCGT1800O-贵港大圩镇甘岭村高铁1800O |  | Radio Site | NDXLEFGGDaXuZhenGanLingCGT1800O | 贵港大圩镇甘岭村高铁1800O_1 | NDXLEFGGDaXuZhenGanLingCGT1800O-贵港大圩镇甘岭村高铁1800O | 245012195 |  |  | Guigang | China | Draft | 贵港大圩甘岭村旁 | 109.8045 | 109'48'16' | 23.19 | 23'11'24'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-05 | China | China Telecom Guangxi | Completed | China | 2582400 |  | 245000934 | Completed | CTGXLTE1.8Gproject-桂平社坡镇佛子冲高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPShePoZhenFoZiCGT-桂平社坡镇佛子冲高铁\GPShePoZhenFoZiCGT1800O-桂平社坡镇佛子冲高铁1800O |  | Radio Site | GPShePoZhenFoZiCGT1800O | 桂平社坡镇佛子冲高铁1800O_1 | GPShePoZhenFoZiCGT1800O-桂平社坡镇佛子冲高铁1800O | 245012196 |  |  | Guigang | China | Draft | 佛子冲南面400米处 | 110.2606 | 110'15'38' | 23.3574 | 23'21'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-18 | China | China Telecom Guangxi | Completed | China | 2582401 |  | 245000936 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇林村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLinCunGT-贵港覃塘镇林村高铁\GGQinTangZhenLinCunGT1800O-贵港覃塘镇林村高铁1800O |  | Radio Site | GGQinTangZhenLinCunGT1800O | 贵港覃塘镇林村高铁1800O_1 | GGQinTangZhenLinCunGT1800O-贵港覃塘镇林村高铁1800O | 245012201 |  |  | Guigang | China | Draft | 贵港市覃塘区覃塘镇林村往东约460米 | 109.3902 | 109'23'25' | 23.1564 | 23'9'23'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-24 | China | China Telecom Guangxi | Completed | China | 2582402 |  | 245000937 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇旺弄高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenWangNGT-贵港覃塘镇旺弄高铁\GGQinTangZhenWangNGT1800O-贵港覃塘镇旺弄高铁1800O |  | Radio Site | GGQinTangZhenWangNGT1800O | 贵港覃塘镇旺弄高铁1800O_1 | GGQinTangZhenWangNGT1800O-贵港覃塘镇旺弄高铁1800O | 245012198 |  |  | Guigang | China | Draft | 贵港市覃塘区覃塘镇姚山小学往西约565米 | 109.3729 | 109'22'22' | 23.163 | 23'9'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-24 | China | China Telecom Guangxi | Completed | China | 2582403 |  | 245000932 | Completed | CTGXLTE1.8Gproject-贵港大圩镇大岭顶高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGGDaXuZhenDaLingDGT-贵港大圩镇大岭顶高铁\NDXLEFGGDaXuZhenDaLingDGT1800O-贵港大圩镇大岭顶高铁1800O |  | Radio Site | NDXLEFGGDaXuZhenDaLingDGT1800O | 贵港大圩镇大岭顶高铁1800O_1 | NDXLEFGGDaXuZhenDaLingDGT1800O-贵港大圩镇大岭顶高铁1800O | 245012194 |  |  | Guigang | China | Draft | 贵港大圩大岭村旁 | 109.7359 | 109'44'9' | 23.1625 | 23'9'45'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-01 | China | China Telecom Guangxi | Completed | China | 2582404 |  | 245000938 | Completed | CTGXLTE1.8Gproject-贵港市西江农场剑麻队高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGShiXiJiangNCJMDGT-贵港市西江农场剑麻队高铁\GGShiXiJiangNCJMDGT1800O-贵港市西江农场剑麻队高铁1800O |  | Radio Site | GGShiXiJiangNCJMDGT1800O | 贵港市西江农场剑麻队高铁1800O_1 | GGShiXiJiangNCJMDGT1800O-贵港市西江农场剑麻队高铁1800O | 245012192 |  |  | Guigang | China | Draft | 贵港市港北区大圩镇广西贵港市港利养殖有限公司往东约542米 | 109.7231 | 109'43'23' | 23.1584 | 23'9'30'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-25 | China | China Telecom Guangxi | Completed | China | 2582405 |  | 245000935 | Completed | CTGXLTE1.8Gproject-贵港西江农场团结大队高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGXiJiangNCTJDDGT-贵港西江农场团结大队高铁\GGXiJiangNCTJDDGT1800O-贵港西江农场团结大队高铁1800O |  | Radio Site | GGXiJiangNCTJDDGT1800O | 贵港西江农场团结大队高铁1800O_1 | GGXiJiangNCTJDDGT1800O-贵港西江农场团结大队高铁1800O | 245012197 |  |  | Guigang | China | Draft | 贵港西江农场团结大队高铁旁 | 109.7569 | 109'45'25' | 23.174 | 23'10'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-01 | China | China Telecom Guangxi | Completed | China | 2582406 |  | 245000939 | Completed | CTGXLTE1.8Gproject-桂平木圭镇金垌村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuGuiZhenJinDongCun-桂平木圭镇金垌村\GPMuGuiZhenJinDongCun1800O-桂平木圭镇金垌村1800O |  | Radio Site | GPMuGuiZhenJinDongCun1800O | 桂平木圭镇金垌村1800O_1 | GPMuGuiZhenJinDongCun1800O-桂平木圭镇金垌村1800O | 245012223 |  |  | Guigang | China | Draft | 贵港市桂平市木圭镇龙安村北方向约1.77公里 | 110.2972 | 110'17'50' | 23.4796 | 23'28'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-30 | China | China Telecom Guangxi | Completed | China | 2582407 |  | 245000942 | Completed | CTGXLTE1.8Gproject-贵港大圩镇二三七农场高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenErSanQiNCGT-贵港大圩镇二三七农场高铁\GGDaXuZhenErSanQiNCGT1800O-贵港大圩镇二三七农场高铁1800O |  | Radio Site | GGDaXuZhenErSanQiNCGT1800O | 贵港大圩镇二三七农场高铁1800O_1 | GGDaXuZhenErSanQiNCGT1800O-贵港大圩镇二三七农场高铁1800O | 245012218 |  |  | Guigang | China | Draft | 贵港市港北区大圩镇寻香寨往北约930米 | 109.6957 | 109'41'44' | 23.1413 | 23'8'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-02 | China | China Telecom Guangxi | Completed | China | 2582408 |  | 245000941 | Completed | CTGXLTE1.8Gproject-贵港大圩镇苗圃高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenMiaoPuGT-贵港大圩镇苗圃高铁\GGDaXuZhenMiaoPuGT1800O-贵港大圩镇苗圃高铁1800O |  | Radio Site | GGDaXuZhenMiaoPuGT1800O | 贵港大圩镇苗圃高铁1800O_1 | GGDaXuZhenMiaoPuGT1800O-贵港大圩镇苗圃高铁1800O | 245012184 |  |  | Guigang | China | Draft | 贵港大圩苗圃村旁 | 109.7674 | 109'46'3' | 23.1753 | 23'10'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-29 | China | China Telecom Guangxi | Completed | China | 2582409 |  | 245000940 | Completed | CTGXLTE1.8Gproject-桂平中沙镇太平村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGPZhongShaZhenTaiPC-桂平中沙镇太平村\NDXLEFGPZhongShaZhenTaiPC1800O-桂平中沙镇太平村1800O |  | Radio Site | NDXLEFGPZhongShaZhenTaiPC1800O | 桂平中沙镇太平村1800O_1 | NDXLEFGPZhongShaZhenTaiPC1800O-桂平中沙镇太平村1800O | 245012191 |  |  | Guigang | China | Draft | 桂平中沙新宪村东南方向200米山顶 | 110.1983 | 110'11'54' | 22.9367 | 22'56'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-14 | China | China Telecom Guangxi | Completed | China | 2582410 |  | 245000943 | Completed | CTGXLTE1.8Gproject-贵港根竹乡社塘高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXiangSheTGT-贵港根竹乡社塘高铁\GGGenZhuXiangSheTGT1800O-贵港根竹乡社塘高铁1800O |  | Radio Site | GGGenZhuXiangSheTGT1800O | 贵港根竹乡社塘高铁1800O_1 | GGGenZhuXiangSheTGT1800O-贵港根竹乡社塘高铁1800O | 245012186 |  |  | Guigang | China | Draft | 贵港市港北区根竹乡罗屋园往北约262米 | 109.4844 | 109'29'4' | 23.1166 | 23'6'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-20 | China | China Telecom Guangxi | Completed | China | 2582411 |  | 245000947 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇六村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLiuCunGT-贵港覃塘镇六村高铁\GGQinTangZhenLiuCunGT1800O-贵港覃塘镇六村高铁1800O |  | Radio Site | GGQinTangZhenLiuCunGT1800O | 贵港覃塘镇六村高铁1800O_1 | GGQinTangZhenLiuCunGT1800O-贵港覃塘镇六村高铁1800O | 245012222 |  |  | Guigang | China | Draft | 贵港市覃塘区覃塘镇罗卜岭往西南方向约296米 | 109.4265 | 109'25'35' | 23.1422 | 23'8'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-16 | China | China Telecom Guangxi | Completed | China | 2582412 |  | 245001561 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇官埔高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenGuanPGT-贵港覃塘镇官埔高铁\GGQinTangZhenGuanPGT1800O-贵港覃塘镇官埔高铁1800O |  | Radio Site | GGQinTangZhenGuanPGT1800O | 贵港覃塘镇官埔高铁1800O_1 | GGQinTangZhenGuanPGT1800O-贵港覃塘镇官埔高铁1800O | 245012225 |  |  | Guigang | China | Draft | 贵港市覃塘区覃塘镇大坪东北方向约180米 | 109.444 | 109'26'38' | 23.1358 | 23'8'8'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-27 | China | China Telecom Guangxi | Completed | China | 2582413 |  | 245001564 | Completed | CTGXLTE1.8Gproject-贵港市西江农场七队1800O | CTGXLTE1.8Gproject |  |  | \Locations\NDXLEFGGShiXiJiangNongCQD-贵港市西江农场七队\NDXLEFGGShiXiJiangNongCQD1800O-贵港市西江农场七队1800O |  | Radio Site | NDXLEFGGShiXiJiangNongCQD1800O | 贵港市西江农场七队1800O_1 | NDXLEFGGShiXiJiangNongCQD1800O-贵港市西江农场七队1800O | 245013059 |  |  | Guigang | China | Draft | 贵港市旺岭石螺岭西北方向约1公里高铁旁 | 109.685 | 109'41'6' | 23.1349 | 23'8'5'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-30 | China | China Telecom Guangxi | Completed | China | 2582414 |  | 245001562 | Completed | CTGXLTE1.8Gproject-桂平蒙圩镇棉宠十队高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMengWeiZhenMCSDGT-桂平蒙圩镇棉宠十队高铁\GPMengWeiZhenMCSDGT1800O-桂平蒙圩镇棉宠十队高铁1800O |  | Radio Site | GPMengWeiZhenMCSDGT1800O | 桂平蒙圩镇棉宠十队高铁1800O_1 | GPMengWeiZhenMCSDGT1800O-桂平蒙圩镇棉宠十队高铁1800O | 245012226 |  |  | Guigang | China | Draft | 桂平蒙圩镇棉宠村十队农田里 | 110.002 | 110'0'7' | 23.2741 | 23'16'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-09 | China | China Telecom Guangxi | Completed | China | 2582415 |  | 245001567 | Completed | CTGXLTE1.8Gproject-桂平西山镇福山村上屯高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenFuSCSTGT-桂平西山镇福山村上屯高铁\GPXiShanZhenFuSCSTGT1800O-桂平西山镇福山村上屯高铁1800O |  | Radio Site | GPXiShanZhenFuSCSTGT1800O | 桂平西山镇福山村上屯高铁1800O_1 | GPXiShanZhenFuSCSTGT1800O-桂平西山镇福山村上屯高铁1800O | 245012264 |  |  | Guigang | China | Draft | 桂平市西山镇福山村上屯东南200米河边 | 110.0735 | 110'4'25' | 23.3015 | 23'18'5'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-22 | China | China Telecom Guangxi | Completed | China | 2582416 |  | 245001563 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇上雷高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenShangLGT-贵港覃塘镇上雷高铁\GGQinTangZhenShangLGT1800O-贵港覃塘镇上雷高铁1800O |  | Radio Site | GGQinTangZhenShangLGT1800O | 贵港覃塘镇上雷高铁1800O_1 | GGQinTangZhenShangLGT1800O-贵港覃塘镇上雷高铁1800O | 245012227 |  |  | Guigang | China | Draft | 贵港市覃塘区赖屋西北方向约254米 | 109.4082 | 109'24'29' | 23.1487 | 23'8'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-29 | China | China Telecom Guangxi | Completed | China | 2582417 |  | 245001565 | Completed | CTGXLTE1.8Gproject-桂平蒙圩镇棉宠村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMengWeiZhenMCCGT-桂平蒙圩镇棉宠村高铁\GPMengWeiZhenMCCGT1800O-桂平蒙圩镇棉宠村高铁1800O |  | Radio Site | GPMengWeiZhenMCCGT1800O | 桂平蒙圩镇棉宠村高铁1800O_1 | GPMengWeiZhenMCCGT1800O-桂平蒙圩镇棉宠村高铁1800O | 245012228 |  |  | Guigang | China | Draft | 桂平白沙棉宠村附近 | 109.9852 | 109'59'7' | 23.2633 | 23'15'48'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-02 | China | China Telecom Guangxi | Completed | China | 2582418 |  | 245001568 | Completed | CTGXLTE1.8Gproject-桂平木乐镇良村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenLiangCun-桂平木乐镇良村\GPMuLeZhenLiangCun1800O-桂平木乐镇良村1800O |  | Radio Site | GPMuLeZhenLiangCun1800O | 桂平木乐镇良村1800O_1 | GPMuLeZhenLiangCun1800O-桂平木乐镇良村1800O | 245012219 |  |  | Guigang | China | Draft | 贵港桂平市木乐镇良村附近一田里 | 110.3298 | 110'19'47' | 23.4391 | 23'26'20'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-11 | China | China Telecom Guangxi | Completed | China | 2582419 |  | 245001566 | Completed | CTGXLTE1.8Gproject-桂平西山镇福山村东屯高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiSZhenFuSCDTGT-桂平西山镇福山村东屯高铁\GPXiSZhenFuSCDTGT1800O-桂平西山镇福山村东屯高铁1800O |  | Radio Site | GPXiSZhenFuSCDTGT1800O | 桂平西山镇福山村东屯高铁1800O_1 | GPXiSZhenFuSCDTGT1800O-桂平西山镇福山村东屯高铁1800O | 245012217 |  |  | Guigang | China | Draft | 桂平福山村西南面 | 110.0605 | 110'3'38' | 23.2976 | 23'17'51'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-08 | China | China Telecom Guangxi | Completed | China | 2582420 |  | 245001572 | Completed | CTGXLTE1.8Gproject-贵港根竹乡江口村高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXiangJKCGT-贵港根竹乡江口村高铁\GGGenZhuXiangJKCGT1800O-贵港根竹乡江口村高铁1800O |  | Radio Site | GGGenZhuXiangJKCGT1800O | 贵港根竹乡江口村高铁1800O_1 | GGGenZhuXiangJKCGT1800O-贵港根竹乡江口村高铁1800O | 245012265 |  |  | Guigang | China | Draft | 贵港市港北区根竹乡江口村南方向约1.05公里 | 109.531 | 109'31'52' | 23.106 | 23'6'21'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-10 | China | China Telecom Guangxi | Completed | China | 2582421 |  | 245001576 | Completed | CTGXLTE1.8Gproject-桂平西山镇牛骨岭高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenNiuGuLGT-桂平西山镇牛骨岭高铁\GPXiShanZhenNiuGuLGT1800O-桂平西山镇牛骨岭高铁1800O |  | Radio Site | GPXiShanZhenNiuGuLGT1800O | 桂平西山镇牛骨岭高铁1800O_1 | GPXiShanZhenNiuGuLGT1800O-桂平西山镇牛骨岭高铁1800O | 245012271 |  |  | Guigang | China | Draft | 桂平西山莲塘村北面土坡上 | 110.1246 | 110'7'29' | 23.3219 | 23'19'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-03 | China | China Telecom Guangxi | Completed | China | 2582422 |  | 245001571 | Completed | CTGXLTE1.8Gproject-桂平木乐镇罗盘冲高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenLuoPanCGT-桂平木乐镇罗盘冲高铁\GPMuLeZhenLuoPanCGT1800O-桂平木乐镇罗盘冲高铁1800O |  | Radio Site | GPMuLeZhenLuoPanCGT1800O | 桂平木乐镇罗盘冲高铁1800O_1 | GPMuLeZhenLuoPanCGT1800O-桂平木乐镇罗盘冲高铁1800O | 245012224 |  |  | Guigang | China | Draft | 桂平木乐罗盘冲东南方向700米处山顶 | 110.3298 | 110'19'47' | 23.3994 | 23'23'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-31 | China | China Telecom Guangxi | Completed | China | 2582423 |  | 245001569 | Completed | CTGXLTE1.8Gproject-桂平蒙圩镇高铁大桥东1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPMengXuZhenGTDQD-桂平蒙圩镇高铁大桥东\GPMengXuZhenGTDQD1800O-桂平蒙圩镇高铁大桥东1800O |  | Radio Site | GPMengXuZhenGTDQD1800O | 桂平蒙圩镇高铁大桥东1800O_1 | GPMengXuZhenGTDQD1800O-桂平蒙圩镇高铁大桥东1800O | 245012230 |  |  | Guigang | China | Draft | 桂平市福山村往高铁大桥600米处土丘上 | 110.0469 | 110'2'49' | 23.2923 | 23'17'32'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-26 | China | China Telecom Guangxi | Completed | China | 2582424 |  | 245001573 | Completed | CTGXLTE1.8Gproject-桂平白沙镇岭头塘高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenLingTTGT-桂平白沙镇岭头塘高铁\GPBaiShaZhenLingTTGT1800O-桂平白沙镇岭头塘高铁1800O |  | Radio Site | GPBaiShaZhenLingTTGT1800O | 桂平白沙镇岭头塘高铁1800O_1 | GPBaiShaZhenLingTTGT1800O-桂平白沙镇岭头塘高铁1800O | 245012260 |  |  | Guigang | China | Draft | 桂平白沙岭头塘北面高铁旁 | 109.9526 | 109'57'9' | 23.2424 | 23'14'32'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-12 | China | China Telecom Guangxi | Completed | China | 2582425 |  | 245001575 | Completed | CTGXLTE1.8Gproject-贵港根竹乡庞屋高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXiangPangWuGT-贵港根竹乡庞屋高铁\GGGenZhuXiangPangWuGT1800O-贵港根竹乡庞屋高铁1800O |  | Radio Site | GGGenZhuXiangPangWuGT1800O | 贵港根竹乡庞屋高铁1800O_1 | GGGenZhuXiangPangWuGT1800O-贵港根竹乡庞屋高铁1800O | 245012267 |  |  | Guigang | China | Draft | 贵港市港北区根竹乡民权村东北方向约1公里 | 109.5091 | 109'30'33' | 23.1126 | 23'6'45'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-04 | China | China Telecom Guangxi | Completed | China | 2582426 |  | 245001570 | Completed | CTGXLTE1.8Gproject-桂平南木镇四中1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPNanMuZhenSiZhong-桂平南木镇四中\GPNanMuZhenSiZhong1800O-桂平南木镇四中1800O |  | Radio Site | GPNanMuZhenSiZhong1800O | 桂平南木镇四中1800O_1 | GPNanMuZhenSiZhong1800O-桂平南木镇四中1800O | 245012220 |  |  | Guigang | China | Draft | 贵港市桂平市南木镇思竹村东南方向约1.24公里 | 110.1018 | 110'6'6' | 23.5402 | 23'32'24'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-13 | China | China Telecom Guangxi | Completed | China | 2582427 |  | 245001574 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡峡岭二1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangXiaLE-桂平寻旺乡峡岭二\GPXunWangXiangXiaLE1800O-桂平寻旺乡峡岭二1800O |  | Radio Site | GPXunWangXiangXiaLE1800O | 桂平寻旺乡峡岭二1800O_1 | GPXunWangXiangXiaLE1800O-桂平寻旺乡峡岭二1800O | 245012261 |  |  | Guigang | China | Draft | 桂平市寻旺镇燕枝村南边200米高铁上 | 110.1368 | 110'8'12' | 23.3277 | 23'19'39'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-27 | China | China Telecom Guangxi | Completed | China | 2582428 |  | 245001578 | Completed | CTGXLTE1.8Gproject-桂平白沙镇欧塘寨高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenOuTangZGT-桂平白沙镇欧塘寨高铁\GPBaiShaZhenOuTangZGT1800O-桂平白沙镇欧塘寨高铁1800O |  | Radio Site | GPBaiShaZhenOuTangZGT1800O | 桂平白沙镇欧塘寨高铁1800O_1 | GPBaiShaZhenOuTangZGT1800O-桂平白沙镇欧塘寨高铁1800O | 245012259 |  |  | Guigang | China | Draft | 桂平白沙欧塘寨西北面高铁旁 | 109.9607 | 109'57'39' | 23.2503 | 23'15'1'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-28 | China | China Telecom Guangxi | Completed | China | 2582429 |  | 245001585 | Completed | CTGXLTE1.8Gproject-桂平理端乡桥头湾高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPLiDuanXiangQiaoTWGT-桂平理端乡桥头湾高铁\GPLiDuanXiangQiaoTWGT1800O-桂平理端乡桥头湾高铁1800O |  | Radio Site | GPLiDuanXiangQiaoTWGT1800O | 桂平理端乡桥头湾高铁1800O_1 | GPLiDuanXiangQiaoTWGT1800O-桂平理端乡桥头湾高铁1800O | 245012272 |  |  | Guigang | China | Draft | 桂平里端王母大村东边650米高铁旁 | 110.2966 | 110'17'48' | 23.3717 | 23'22'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-12 | China | China Telecom Guangxi | Completed | China | 2582430 |  | 245001587 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡清水塘高铁1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangQSTGT-桂平寻旺乡清水塘高铁\GPXunWangXiangQSTGT1800O-桂平寻旺乡清水塘高铁1800O |  | Radio Site | GPXunWangXiangQSTGT1800O | 桂平寻旺乡清水塘高铁1800O_1 | GPXunWangXiangQSTGT1800O-桂平寻旺乡清水塘高铁1800O | 245012262 |  |  | Guigang | China | Draft | 桂平寻旺清水塘附近山头 | 110.1693 | 110'10'9' | 23.3413 | 23'20'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-06 | China | China Telecom Guangxi | Completed | China | 2582431 |  | 245002190 | Completed | CTGXLTE1.8Gproject-贵港大圩镇油榨村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenYouZhaCun-贵港大圩镇油榨村\GGDaXuZhenYouZhaCun1800O-贵港大圩镇油榨村1800O |  | Radio Site | GGDaXuZhenYouZhaCun1800O | 贵港大圩镇油榨村1800O_1 | GGDaXuZhenYouZhaCun1800O-贵港大圩镇油榨村1800O | 245012270 |  |  | Guigang | China | Draft | 贵港大圩油榨村东豪屯东北方向约284米农田 | 109.6732 | 109'40'23' | 23.1922 | 23'11'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582432 |  | 245002191 | Completed | CTGXLTE1.8Gproject-南宁兴宁区三塘古埌村西南1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNSanTangGuLangCXN-南宁兴宁区三塘古埌村西南\NNXNSanTangGuLangCXN1800O-南宁兴宁区三塘古埌村西南1800O |  | Radio Site | NNXNSanTangGuLangCXN1800O | 南宁兴宁区三塘古埌村西南1800O_1 | NNXNSanTangGuLangCXN1800O-南宁兴宁区三塘古埌村西南1800O | 245012300 |  |  | Nanning | China | Draft | 南宁兴宁区三塘古埌村西南 | 108.4845 | 108'29'4' | 22.8543 | 22'51'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-04 | China | China Telecom Guangxi | Completed | China | 2582433 |  | 245002188 | Completed | CTGXLTE1.8Gproject-贵港大圩镇曲苍村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenQuCangCun-贵港大圩镇曲苍村\GGDaXuZhenQuCangCun1800O-贵港大圩镇曲苍村1800O |  | Radio Site | GGDaXuZhenQuCangCun1800O | 贵港大圩镇曲苍村1800O_1 | GGDaXuZhenQuCangCun1800O-贵港大圩镇曲苍村1800O | 245012263 |  |  | Guigang | China | Draft | 贵港大圩周村东南方向约200米水利旁边 | 109.692 | 109'41'31' | 23.2089 | 23'12'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582434 |  | 245002192 | Completed | CTGXLTE1.8Gproject-南宁兴宁区三塘古埌村西南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNSanTangGuLangCXN-南宁兴宁区三塘古埌村西南\NNXNSanTangGuLangCXN2100O-南宁兴宁区三塘古埌村西南2100O |  | Radio Site | NNXNSanTangGuLangCXN2100O | 南宁兴宁区三塘古埌村西南2100O_1 | NNXNSanTangGuLangCXN2100O-南宁兴宁区三塘古埌村西南2100O | 245012680 |  |  | Nanning | China | Draft | 南宁兴宁区三塘古埌村西南 | 108.4845 | 108'29'4' | 22.8543 | 22'51'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-27 | China | China Telecom Guangxi | Completed | China | 2582435 |  | 245002195 | Completed | CTGXLTE1.8Gproject-宾阳宾州七里尖岭村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouQiLiJianLingCun-宾阳宾州七里尖岭村\BYBinZhouQiLiJianLingCun1800O-宾阳宾州七里尖岭村1800O |  | Radio Site | BYBinZhouQiLiJianLingCun1800O | 宾阳宾州七里尖岭村1800O_1 | BYBinZhouQiLiJianLingCun1800O-宾阳宾州七里尖岭村1800O | 245012297 |  |  | Nanning | China | Draft | 南宁宾阳县宾州镇七里尖岭村附近一土山顶 | 108.8705 | 108'52'14' | 23.2544 | 23'15'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-26 | China | China Telecom Guangxi | Completed | China | 2582436 |  | 245002189 | Completed | CTGXLTE1.8Gproject-贵港奇石乡六马村六良屯1800O | CTGXLTE1.8Gproject |  |  | \Locations\GGQiShiXiangLiuMaCLLT-贵港奇石乡六马村六良屯\GGQiShiXiangLiuMaCLLT1800O-贵港奇石乡六马村六良屯1800O |  | Radio Site | GGQiShiXiangLiuMaCLLT1800O | 贵港奇石乡六马村六良屯1800O_1 | GGQiShiXiangLiuMaCLLT1800O-贵港奇石乡六马村六良屯1800O | 245012266 |  |  | Guigang | China | Draft | 贵港奇石六良村东面200米山头 | 109.6376 | 109'38'15' | 23.3658 | 23'21'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-31 | China | China Telecom Guangxi | Completed | China | 2582437 |  | 245002198 | Completed | CTGXLTE1.8Gproject-宾阳宾州展志下郑村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouZhanZhiXiaZC-宾阳宾州展志下郑村\BYBinZhouZhanZhiXiaZC1800O-宾阳宾州展志下郑村1800O |  | Radio Site | BYBinZhouZhanZhiXiaZC1800O | 宾阳宾州展志下郑村1800O_1 | BYBinZhouZhanZhiXiaZC1800O-宾阳宾州展志下郑村1800O | 245012295 |  |  | Nanning | China | Draft | 南宁市宾阳县宾州镇石塘门（宾阳宾州镇展志下郑村）北300米的小土坡上 | 108.8517 | 108'51'6' | 23.2864 | 23'17'10'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-07 | China | China Telecom Guangxi | Completed | China | 2582438 |  | 245002194 | Completed | CTGXLTE1.8Gproject-桂平石龙镇东岗村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPShiLongZhenDongGC-桂平石龙镇东岗村\GPShiLongZhenDongGC1800O-桂平石龙镇东岗村1800O |  | Radio Site | GPShiLongZhenDongGC1800O | 桂平石龙镇东岗村1800O_1 | GPShiLongZhenDongGC1800O-桂平石龙镇东岗村1800O | 245012268 |  |  | Guigang | China | Draft | 桂平市石龙镇东岗村东南方向约0.90公里 | 109.7497 | 109'44'59' | 23.4529 | 23'27'10'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-08 | China | China Telecom Guangxi | Completed | China | 2582439 |  | 245002193 | Completed | CTGXLTE1.8Gproject-桂平石龙镇新源村1800O | CTGXLTE1.8Gproject |  |  | \Locations\GPShiLongZhenXinYuanC-桂平石龙镇新源村\GPShiLongZhenXinYuanC1800O-桂平石龙镇新源村1800O |  | Radio Site | GPShiLongZhenXinYuanC1800O | 桂平石龙镇新源村1800O_1 | GPShiLongZhenXinYuanC1800O-桂平石龙镇新源村1800O | 245012269 |  |  | Guigang | China | Draft | 桂平石龙新源村山头 | 109.7727 | 109'46'22' | 23.4535 | 23'27'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-28 | China | China Telecom Guangxi | Completed | China | 2582440 |  | 245002197 | Completed | CTGXLTE1.8Gproject-宾阳宾州吴村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouWuCun-宾阳宾州吴村\BYBinZhouWuCun1800O-宾阳宾州吴村1800O |  | Radio Site | BYBinZhouWuCun1800O | 宾阳宾州吴村1800O_1 | BYBinZhouWuCun1800O-宾阳宾州吴村1800O | 245012290 |  |  | Nanning | China | Draft | 宾阳县宾州镇吴村东南方向大概1400米处的草地上 | 108.8281 | 108'49'41' | 23.1777 | 23'10'39'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-29 | China | China Telecom Guangxi | Completed | China | 2582441 |  | 245002196 | Completed | CTGXLTE1.8Gproject-宾阳宾州吴村东南1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouWuCunDongNan-宾阳宾州吴村东南\BYBinZhouWuCunDongNan1800O-宾阳宾州吴村东南1800O |  | Radio Site | BYBinZhouWuCunDongNan1800O | 宾阳宾州吴村东南1800O_1 | BYBinZhouWuCunDongNan1800O-宾阳宾州吴村东南1800O | 245012287 |  |  | Nanning | China | Draft | 南宁宾阳宾州镇吴村东南角大概75米处的桉树林内 | 108.8192 | 108'49'9' | 23.1818 | 23'10'54'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-04 | China | China Telecom Guangxi | Completed | China | 2582442 |  | 245002200 | Completed | CTGXLTE1.8Gproject-宾阳新桥立新六合村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoLiXinLiuHeCun-宾阳新桥立新六合村\BYXinQiaoLiXinLiuHeCun1800O-宾阳新桥立新六合村1800O |  | Radio Site | BYXinQiaoLiXinLiuHeCun1800O | 宾阳新桥立新六合村1800O_1 | BYXinQiaoLiXinLiuHeCun1800O-宾阳新桥立新六合村1800O | 245012298 |  |  | Nanning | China | Draft | 南宁宾阳县新桥镇昆仑路中段北边大概660米处立新六合村一居民楼 | 108.7728 | 108'46'22' | 23.2239 | 23'13'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-02 | China | China Telecom Guangxi | Completed | China | 2582443 |  | 245002202 | Completed | CTGXLTE1.8Gproject-宾阳陈平平天村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYChenPingPingTianCun-宾阳陈平平天村\NNBYChenPingPingTianCun1800O-宾阳陈平平天村1800O |  | Radio Site | NNBYChenPingPingTianCun1800O | 宾阳陈平平天村1800O_1 | NNBYChenPingPingTianCun1800O-宾阳陈平平天村1800O | 245013056 |  |  | Nanning | China | Draft | 南宁市宾阳县陈平平天村后山山顶(陈平社区东南方向1800米处的山上) | 108.8223 | 108'49'20' | 23.0159 | 23'0'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-31 | China | China Telecom Guangxi | Completed | China | 2582444 |  | 245002199 | Completed | CTGXLTE1.8Gproject-宾阳县风景路天祥电子厂1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXianFengJingLuTianXDZC-宾阳县风景路天祥电子厂\BYXianFengJingLuTianXDZC1800O-宾阳县风景路天祥电子厂1800O |  | Radio Site | BYXianFengJingLuTianXDZC1800O | 宾阳县风景路天祥电子厂1800O_1 | BYXianFengJingLuTianXDZC1800O-宾阳县风景路天祥电子厂1800O | 245012296 |  |  | Nanning | China | Draft | 南宁市宾阳县天祥电子厂6楼天面 | 108.8373 | 108'50'14' | 23.243 | 23'14'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-18 | China | China Telecom Guangxi | Completed | China | 2582445 |  | 245002203 | Completed | CTGXLTE1.8Gproject-宾阳新圩共和六蒙村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinXuGongHeLiuMengCun-宾阳新圩共和六蒙村\BYXinXuGongHeLiuMengCun1800O-宾阳新圩共和六蒙村1800O |  | Radio Site | BYXinXuGongHeLiuMengCun1800O | 宾阳新圩共和六蒙村1800O_1 | BYXinXuGongHeLiuMengCun1800O-宾阳新圩共和六蒙村1800O | 245012293 |  |  | Nanning | China | Draft | 南宁市宾阳县新圩镇共和六蒙村北边大概150米处一山头上 | 108.7754 | 108'46'32' | 23.3034 | 23'18'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-25 | China | China Telecom Guangxi | Completed | China | 2582446 |  | 245002201 | Completed | CTGXLTE1.8Gproject-宾阳宾州蒙田冸塘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouMengTianPanTC-宾阳宾州蒙田冸塘村\BYBinZhouMengTianPanTC1800O-宾阳宾州蒙田冸塘村1800O |  | Radio Site | BYBinZhouMengTianPanTC1800O | 宾阳宾州蒙田冸塘村1800O_1 | BYBinZhouMengTianPanTC1800O-宾阳宾州蒙田冸塘村1800O | 245012291 |  |  | Nanning | China | Draft | 南宁市宾阳宾州镇蒙田冸塘村附近空地上 | 108.8462 | 108'50'46' | 23.1957 | 23'11'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-06 | China | China Telecom Guangxi | Completed | China | 2582447 |  | 245002211 | Completed | CTGXLTE1.8Gproject-宾阳甘棠那冷田陈村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGanTangNaLengTianChenC-宾阳甘棠那冷田陈村\BYGanTangNaLengTianChenC1800O-宾阳甘棠那冷田陈村1800O |  | Radio Site | BYGanTangNaLengTianChenC1800O | 宾阳甘棠那冷田陈村1800O_1 | BYGanTangNaLengTianChenC1800O-宾阳甘棠那冷田陈村1800O | 245012289 |  |  | Nanning | China | Draft | 南宁市宾阳甘棠镇那冷田陈村南500米高速路旁的空地上 | 108.9451 | 108'56'42' | 22.9534 | 22'57'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-01 | China | China Telecom Guangxi | Completed | China | 2582448 |  | 245002216 | Completed | CTGXLTE1.8Gproject-宾阳陈平平天石义村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYChenPingPingTianShiYC-宾阳陈平平天石义村\BYChenPingPingTianShiYC1800O-宾阳陈平平天石义村1800O |  | Radio Site | BYChenPingPingTianShiYC1800O | 宾阳陈平平天石义村1800O_1 | BYChenPingPingTianShiYC1800O-宾阳陈平平天石义村1800O | 245012294 |  |  | Nanning | China | Draft | 南宁宾阳陈平平天石义村附近山头 | 108.8251 | 108'49'30' | 23.0073 | 23'0'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-05 | China | China Telecom Guangxi | Completed | China | 2582449 |  | 245002215 | Completed | CTGXLTE1.8Gproject-宾阳大桥连朋湴塘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYDaQiaoLianPengPanTC-宾阳大桥连朋湴塘村\NNBYDaQiaoLianPengPanTC1800O-宾阳大桥连朋湴塘村1800O |  | Radio Site | NNBYDaQiaoLianPengPanTC1800O | 宾阳大桥连朋湴塘村1800O_1 | NNBYDaQiaoLianPengPanTC1800O-宾阳大桥连朋湴塘村1800O | 245012292 |  |  | Nanning | China | Draft | 南宁市宾阳大桥镇连朋湴塘村中间旱地上 | 108.8916 | 108'53'30' | 23.1961 | 23'11'45'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-03 | China | China Telecom Guangxi | Completed | China | 2582450 |  | 245002817 | Completed | CTGXLTE1.8Gproject-宾阳大桥连朋郭村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYDaQiaoLianPengGuoCun-宾阳大桥连朋郭村\BYDaQiaoLianPengGuoCun1800O-宾阳大桥连朋郭村1800O |  | Radio Site | BYDaQiaoLianPengGuoCun1800O | 宾阳大桥连朋郭村1800O_1 | BYDaQiaoLianPengGuoCun1800O-宾阳大桥连朋郭村1800O | 245012301 |  |  | Nanning | China | Draft | 南宁市宾阳县大桥镇连朋村委郭村附近一水田地上 | 108.9093 | 108'54'34' | 23.1924 | 23'11'32'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-19 | China | China Telecom Guangxi | Completed | China | 2582451 |  | 245002824 | Completed | CTGXLTE1.8Gproject-宾阳和吉新安茶表村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiXinAnChaBiaoCun-宾阳和吉新安茶表村\BYHeJiXinAnChaBiaoCun1800O-宾阳和吉新安茶表村1800O |  | Radio Site | BYHeJiXinAnChaBiaoCun1800O | 宾阳和吉新安茶表村1800O_1 | BYHeJiXinAnChaBiaoCun1800O-宾阳和吉新安茶表村1800O | 245012327 |  |  | Nanning | China | Draft | 南宁市宾阳和吉镇新安茶表村附近水田里 | 109.1045 | 109'6'16' | 23.2754 | 23'16'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-07 | China | China Telecom Guangxi | Completed | China | 2582452 |  | 245002821 | Completed | CTGXLTE1.8Gproject-宾阳甘棠那宁村灯光球场1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGanTangNaNingCunDGQC-宾阳甘棠那宁村灯光球场\BYGanTangNaNingCunDGQC1800O-宾阳甘棠那宁村灯光球场1800O |  | Radio Site | BYGanTangNaNingCunDGQC1800O | 宾阳甘棠那宁村灯光球场1800O_1 | BYGanTangNaNingCunDGQC1800O-宾阳甘棠那宁村灯光球场1800O | 245012299 |  |  | Nanning | China | Draft | 南宁市宾阳县甘棠镇那宁村灯光球场后面一居民楼3楼顶 | 108.9684 | 108'58'6' | 22.9613 | 22'57'40'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-18 | China | China Telecom Guangxi | Completed | China | 2582453 |  | 245002819 | Completed | CTGXLTE1.8Gproject-宾阳和吉三民新马香村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiSanMinXinMaXiangC-宾阳和吉三民新马香村\BYHeJiSanMinXinMaXiangC1800O-宾阳和吉三民新马香村1800O |  | Radio Site | BYHeJiSanMinXinMaXiangC1800O | 宾阳和吉三民新马香村1800O_1 | BYHeJiSanMinXinMaXiangC1800O-宾阳和吉三民新马香村1800O | 245012329 |  |  | Nanning | China | Draft | 南宁市宾阳县和吉镇三民村委新马香村南边大概1000米处的桉树林里面的旱地 | 109.128 | 109'7'41' | 23.2338 | 23'14'1'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-22 | China | China Telecom Guangxi | Completed | China | 2582454 |  | 245002820 | Completed | CTGXLTE1.8Gproject-宾阳黎塘补塘新埠村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYLiTangBuTangXinBuCun-宾阳黎塘补塘新埠村\BYLiTangBuTangXinBuCun1800O-宾阳黎塘补塘新埠村1800O |  | Radio Site | BYLiTangBuTangXinBuCun1800O | 宾阳黎塘补塘新埠村1800O_1 | BYLiTangBuTangXinBuCun1800O-宾阳黎塘补塘新埠村1800O | 245012323 |  |  | Nanning | China | Draft | 南宁宾阳县黎塘镇补塘新埠村东北方向大概一百米远一平地 | 109.0682 | 109'4'5' | 23.1872 | 23'11'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-10 | China | China Telecom Guangxi | Completed | China | 2582455 |  | 245002822 | Completed | CTGXLTE1.8Gproject-宾阳和吉新安石龙村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiXinAnShiLongCun-宾阳和吉新安石龙村\NNBYHeJiXinAnShiLongCun1800O-宾阳和吉新安石龙村1800O |  | Radio Site | NNBYHeJiXinAnShiLongCun1800O | 宾阳和吉新安石龙村1800O_1 | NNBYHeJiXinAnShiLongCun1800O-宾阳和吉新安石龙村1800O | 245012317 |  |  | Nanning | China | Draft | 南宁市宾阳县和吉镇新安石龙村小溪旁平地上 | 109.1126 | 109'6'45' | 23.2622 | 23'15'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-13 | China | China Telecom Guangxi | Completed | China | 2582456 |  | 245002818 | Completed | CTGXLTE1.8Gproject-宾阳古辣镇联泉村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGuLaZhenLianQuanCun-宾阳古辣镇联泉村\BYGuLaZhenLianQuanCun1800O-宾阳古辣镇联泉村1800O |  | Radio Site | BYGuLaZhenLianQuanCun1800O | 宾阳古辣镇联泉村1800O_1 | BYGuLaZhenLianQuanCun1800O-宾阳古辣镇联泉村1800O | 245012320 |  |  | Nanning | China | Draft | 南宁市宾阳县古辣镇联泉南偏西30度方向大概1000米小山坡丛林里 | 108.9889 | 108'59'20' | 23.1433 | 23'8'35'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-28 | China | China Telecom Guangxi | Completed | China | 2582457 |  | 245002826 | Completed | CTGXLTE1.8Gproject-宾阳思陇益宪甘枧村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYSiLongYiXianGanJianCun-宾阳思陇益宪甘枧村\BYSiLongYiXianGanJianCun1800O-宾阳思陇益宪甘枧村1800O |  | Radio Site | BYSiLongYiXianGanJianCun1800O | 宾阳思陇益宪甘枧村1800O_1 | BYSiLongYiXianGanJianCun1800O-宾阳思陇益宪甘枧村1800O | 245012319 |  |  | Nanning | China | Draft | 南宁市宾阳县思陇镇益宪甘枧村正南方向200土坡上 | 108.6928 | 108'41'34' | 23.2037 | 23'12'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-27 | China | China Telecom Guangxi | Completed | China | 2582458 |  | 245002827 | Completed | CTGXLTE1.8Gproject-宾阳思陇秀英村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYSiLongXiuYingCun-宾阳思陇秀英村\BYSiLongXiuYingCun1800O-宾阳思陇秀英村1800O |  | Radio Site | BYSiLongXiuYingCun1800O | 宾阳思陇秀英村1800O_1 | BYSiLongXiuYingCun1800O-宾阳思陇秀英村1800O | 245012328 |  |  | Nanning | China | Draft | 南宁市宾阳县思陇镇秀英村东北方向50米后土山 | 108.6881 | 108'41'17' | 23.1879 | 23'11'16'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-01 | China | China Telecom Guangxi | Completed | China | 2582459 |  | 245002828 | Completed | CTGXLTE1.8Gproject-宾阳王灵义和莫村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWangLingYiHeMoCun-宾阳王灵义和莫村\BYWangLingYiHeMoCun1800O-宾阳王灵义和莫村1800O |  | Radio Site | BYWangLingYiHeMoCun1800O | 宾阳王灵义和莫村1800O_1 | BYWangLingYiHeMoCun1800O-宾阳王灵义和莫村1800O | 245012322 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇义和村委莫村附近平地上 | 109.0794 | 109'4'46' | 23.147 | 23'8'49'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-10 | China | China Telecom Guangxi | Completed | China | 2582460 |  | 245002823 | Completed | CTGXLTE1.8Gproject-宾阳古辣平龙军屯村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGuLaPingLongJunTunCun-宾阳古辣平龙军屯村\BYGuLaPingLongJunTunCun1800O-宾阳古辣平龙军屯村1800O |  | Radio Site | BYGuLaPingLongJunTunCun1800O | 宾阳古辣平龙军屯村1800O_1 | BYGuLaPingLongJunTunCun1800O-宾阳古辣平龙军屯村1800O | 245012324 |  |  | Nanning | China | Draft | 南宁宾阳县古辣镇平龙村军屯村一居民楼3F顶 | 108.9925 | 108'59'33' | 23.0738 | 23'4'25'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-18 | China | China Telecom Guangxi | Completed | China | 2582461 |  | 245002825 | Completed | CTGXLTE1.8Gproject-宾阳王灵张安福旺村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingZhangAnFuWC-宾阳王灵张安福旺村\NNBYWangLingZhangAnFuWC1800O-宾阳王灵张安福旺村1800O |  | Radio Site | NNBYWangLingZhangAnFuWC1800O | 宾阳王灵张安福旺村1800O_1 | NNBYWangLingZhangAnFuWC1800O-宾阳王灵张安福旺村1800O | 245012318 |  |  | Nanning | China | Draft | 南宁宾阳王灵张安福旺一土山上 | 109.1072 | 109'6'26' | 23.1175 | 23'7'2'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-30 | China | China Telecom Guangxi | Completed | China | 2582462 |  | 245002829 | Completed | CTGXLTE1.8Gproject-宾阳王灵义和村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWangLingYiHeCun-宾阳王灵义和村\BYWangLingYiHeCun1800O-宾阳王灵义和村1800O |  | Radio Site | BYWangLingYiHeCun1800O | 宾阳王灵义和村1800O_1 | BYWangLingYiHeCun1800O-宾阳王灵义和村1800O | 245012325 |  |  | Nanning | China | Draft | 南宁市宾阳县王灵镇义和村东北方向495县道边平地 | 109.0702 | 109'4'13' | 23.1536 | 23'9'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-29 | China | China Telecom Guangxi | Completed | China | 2582463 |  | 245002831 | Completed | CTGXLTE1.8Gproject-宾阳王灵七新龙家村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWangLingQiXinLongJiaC-宾阳王灵七新龙家村\BYWangLingQiXinLongJiaC1800O-宾阳王灵七新龙家村1800O |  | Radio Site | BYWangLingQiXinLongJiaC1800O | 宾阳王灵七新龙家村1800O_1 | BYWangLingQiXinLongJiaC1800O-宾阳王灵七新龙家村1800O | 245013060 |  |  | Nanning | China | Draft | 南宁市宾阳县王灵镇七新村委龙家村东边大概130米处一甘蔗地上 | 109.016 | 109'0'58' | 23.2253 | 23'13'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-16 | China | China Telecom Guangxi | Completed | China | 2582464 |  | 245002833 | Completed | CTGXLTE1.8Gproject-宾阳新桥镇林堡学校1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoZhenLinBaoXueX-宾阳新桥镇林堡学校\BYXinQiaoZhenLinBaoXueX1800O-宾阳新桥镇林堡学校1800O |  | Radio Site | BYXinQiaoZhenLinBaoXueX1800O | 宾阳新桥镇林堡学校1800O_1 | BYXinQiaoZhenLinBaoXueX1800O-宾阳新桥镇林堡学校1800O | 245012359 |  |  | Nanning | China | Draft | 南宁宾阳县新桥林堡学校教学楼顶 | 108.7261 | 108'43'34' | 23.2384 | 23'14'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-22 | China | China Telecom Guangxi | Completed | China | 2582465 |  | 245002836 | Completed | CTGXLTE1.8Gproject-宾阳新圩四镇大欧村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinXuSiZhenDaOuCun-宾阳新圩四镇大欧村\BYXinXuSiZhenDaOuCun1800O-宾阳新圩四镇大欧村1800O |  | Radio Site | BYXinXuSiZhenDaOuCun1800O | 宾阳新圩四镇大欧村1800O_1 | BYXinXuSiZhenDaOuCun1800O-宾阳新圩四镇大欧村1800O | 245012356 |  |  | Nanning | China | Draft | 宾阳县新圩镇四镇大欧村旁大概130米处的一片草地上 | 108.7749 | 108'46'30' | 23.3331 | 23'19'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-25 | China | China Telecom Guangxi | Completed | China | 2582466 |  | 245002832 | Completed | CTGXLTE1.8Gproject-宾阳武陵理化寻里村委1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWuLingLiHuaXunLiCunW-宾阳武陵理化寻里村委\BYWuLingLiHuaXunLiCunW1800O-宾阳武陵理化寻里村委1800O |  | Radio Site | BYWuLingLiHuaXunLiCunW1800O | 宾阳武陵理化寻里村委1800O_1 | BYWuLingLiHuaXunLiCunW1800O-宾阳武陵理化寻里村委1800O | 245012321 |  |  | Nanning | China | Draft | 南宁市宾阳县武陵镇理化村委寻里村村委办公楼2楼顶 | 108.8594 | 108'51'34' | 23.1678 | 23'10'4'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-10 | China | China Telecom Guangxi | Completed | China | 2582467 |  | 245002834 | Completed | CTGXLTE1.8Gproject-宾阳新桥三才竹匠村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoSanCaiZhuJiangC-宾阳新桥三才竹匠村\BYXinQiaoSanCaiZhuJiangC1800O-宾阳新桥三才竹匠村1800O |  | Radio Site | BYXinQiaoSanCaiZhuJiangC1800O | 宾阳新桥三才竹匠村1800O_1 | BYXinQiaoSanCaiZhuJiangC1800O-宾阳新桥三才竹匠村1800O | 245012357 |  |  | Nanning | China | Draft | 南宁宾阳新桥镇三才竹匠村附近田地里 | 108.7654 | 108'45'56' | 23.203 | 23'12'10'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-20 | China | China Telecom Guangxi | Completed | China | 2582468 |  | 245002846 | Completed | CTGXLTE1.8Gproject-宾阳新圩黄凤村西头屯22号1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinXuHuangFengCXTT22H-宾阳新圩黄凤村西头屯22号\BYXinXuHuangFengCXTT22H1800O-宾阳新圩黄凤村西头屯22号1800O |  | Radio Site | BYXinXuHuangFengCXTT22H1800O | 宾阳新圩黄凤村西头屯22号1800O_1 | BYXinXuHuangFengCXTT22H1800O-宾阳新圩黄凤村西头屯22号1800O | 245012361 |  |  | Nanning | China | Draft | 南宁市宾阳县新圩镇黄凤村西头屯22号居民楼2楼顶上 | 108.8005 | 108'48'2' | 23.3166 | 23'18'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-14 | China | China Telecom Guangxi | Completed | China | 2582469 |  | 245003472 | Completed | CTGXLTE1.8Gproject-宾阳新桥新和朱良贤村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoXinHeZhuLiangXC-宾阳新桥新和朱良贤村\BYXinQiaoXinHeZhuLiangXC1800O-宾阳新桥新和朱良贤村1800O |  | Radio Site | BYXinQiaoXinHeZhuLiangXC1800O | 宾阳新桥新和朱良贤村1800O_1 | BYXinQiaoXinHeZhuLiangXC1800O-宾阳新桥新和朱良贤村1800O | 245012350 |  |  | Nanning | China | Draft | 南宁市宾阳县新桥镇新和朱良贤村旁边 | 108.7526 | 108'45'9' | 23.2457 | 23'14'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-02 | China | China Telecom Guangxi | Completed | China | 2582470 |  | 245003471 | Completed | CTGXLTE1.8Gproject-宾阳新桥甘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoGanCun-宾阳新桥甘村\BYXinQiaoGanCun1800O-宾阳新桥甘村1800O |  | Radio Site | BYXinQiaoGanCun1800O | 宾阳新桥甘村1800O_1 | BYXinQiaoGanCun1800O-宾阳新桥甘村1800O | 245012326 |  |  | Nanning | China | Draft | 南宁市宾阳县新桥镇甘村正南方向100米村道边 | 108.728 | 108'43'41' | 23.2288 | 23'13'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-24 | China | China Telecom Guangxi | Completed | China | 2582471 |  | 245003470 | Completed | CTGXLTE1.8Gproject-宾阳新圩镇上国村二站1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinXuZhenShangGuoCunEZ-宾阳新圩镇上国村二站\BYXinXuZhenShangGuoCunEZ1800O-宾阳新圩镇上国村二站1800O |  | Radio Site | BYXinXuZhenShangGuoCunEZ1800O | 宾阳新圩镇上国村二站1800O_1 | BYXinXuZhenShangGuoCunEZ1800O-宾阳新圩镇上国村二站1800O | 245012351 |  |  | Nanning | China | Draft | 南宁市宾阳县邹圩镇永和村新水柳南偏西60度方向大概500小草坡 | 108.754 | 108'45'15' | 23.3264 | 23'19'35'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-05 | China | China Telecom Guangxi | Completed | China | 2582472 |  | 245003474 | Completed | CTGXLTE1.8Gproject-宾阳中华三军覃村2100O | CTGXLTE1.8Gproject |  |  | \Locations\BYZhongHuaSanJunQinCun-宾阳中华三军覃村\BYZhongHuaSanJunQinCun2100O-宾阳中华三军覃村2100O |  | Radio Site | BYZhongHuaSanJunQinCun2100O | 宾阳中华三军覃村2100O_1 | BYZhongHuaSanJunQinCun2100O-宾阳中华三军覃村2100O | 245012686 |  |  | Nanning | China | Draft | 南宁市宾阳中华镇三军覃村附近的高山上 | 108.9046 | 108'54'17' | 23.0657 | 23'3'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-20 | China | China Telecom Guangxi | Completed | China | 2582473 |  | 245003476 | Completed | CTGXLTE1.8Gproject-宾阳新桥白花村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYXinQiaoBaiHuaCun-宾阳新桥白花村\NNBYXinQiaoBaiHuaCun1800O-宾阳新桥白花村1800O |  | Radio Site | NNBYXinQiaoBaiHuaCun1800O | 宾阳新桥白花村1800O_1 | NNBYXinQiaoBaiHuaCun1800O-宾阳新桥白花村1800O | 245012355 |  |  | Nanning | China | Draft | 南宁市宾阳县新桥镇白花村南250米的山坡上 | 108.7613 | 108'45'41' | 23.2635 | 23'15'48'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582474 |  | 245003473 | Completed | CTGXLTE1.8Gproject-宾阳中华三军覃村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYZhongHuaSanJunQinCun-宾阳中华三军覃村\BYZhongHuaSanJunQinCun1800O-宾阳中华三军覃村1800O |  | Radio Site | BYZhongHuaSanJunQinCun1800O | 宾阳中华三军覃村1800O_1 | BYZhongHuaSanJunQinCun1800O-宾阳中华三军覃村1800O | 245012345 |  |  | Nanning | China | Draft | 南宁市宾阳中华镇三军覃村附近的高山上 | 108.9046 | 108'54'17' | 23.0657 | 23'3'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-26 | China | China Telecom Guangxi | Completed | China | 2582475 |  | 245003477 | Completed | CTGXLTE1.8Gproject-宾阳中华三军村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYZhongHuaSanJunCun-宾阳中华三军村\BYZhongHuaSanJunCun1800O-宾阳中华三军村1800O |  | Radio Site | BYZhongHuaSanJunCun1800O | 宾阳中华三军村1800O_1 | BYZhongHuaSanJunCun1800O-宾阳中华三军村1800O | 245012349 |  |  | Nanning | China | Draft | 南宁市宾阳县中华镇三军村学校的后山上 | 108.926 | 108'55'33' | 23.0787 | 23'4'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-26 | China | China Telecom Guangxi | Completed | China | 2582476 |  | 245003478 | Completed | CTGXLTE1.8Gproject-宾阳宾州南山村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouNanShanCun-宾阳宾州南山村\BYBinZhouNanShanCun1800O-宾阳宾州南山村1800O |  | Radio Site | BYBinZhouNanShanCun1800O | 宾阳宾州南山村1800O_1 | BYBinZhouNanShanCun1800O-宾阳宾州南山村1800O | 245012352 |  |  | Nanning | China | Draft | 南宁市宾阳县宾州镇南山村东北500米的山上 | 108.7741 | 108'46'27' | 23.1549 | 23'9'17'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-30 | China | China Telecom Guangxi | Completed | China | 2582477 |  | 245003479 | Completed | CTGXLTE1.8Gproject-宾阳宾州长岗洪塘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYBinZhouZhangGangHongTC-宾阳宾州长岗洪塘村\BYBinZhouZhangGangHongTC1800O-宾阳宾州长岗洪塘村1800O |  | Radio Site | BYBinZhouZhangGangHongTC1800O | 宾阳宾州长岗洪塘村1800O_1 | BYBinZhouZhangGangHongTC1800O-宾阳宾州长岗洪塘村1800O | 245012346 |  |  | Nanning | China | Draft | 南宁宾阳宾州镇长岗村委洪塘村东边大概170米处一土坡上 | 108.8505 | 108'51'2' | 23.2956 | 23'17'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-19 | China | China Telecom Guangxi | Completed | China | 2582478 |  | 245003475 | Completed | CTGXLTE1.8Gproject-宾阳县宾州环城路旁明堂新城汽车维修店1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYXBZHCLPMTXCQCWXDO-宾阳县宾州环城路旁明堂新城汽车维修店\NNBYXBZHCLPMTXCQCWXDO1800O-宾阳县宾州环城路旁明堂新城汽车维修店1800O |  | Radio Site | NNBYXBZHCLPMTXCQCWXDO1800O | 宾阳县宾州环城路旁明堂新城汽车维修店1800O_1 | NNBYXBZHCLPMTXCQCWXDO1800O-宾阳县宾州环城路旁明堂新城汽车维修店1800O | 245012354 |  |  | Nanning | China | Draft | 南宁宾阳县宾州镇环城路旁明堂新城汽车维修店4楼顶 | 108.8453 | 108'50'43' | 23.2314 | 23'13'53'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-11 | China | China Telecom Guangxi | Completed | China | 2582479 |  | 245003480 | Completed | CTGXLTE1.8Gproject-宾阳古辣稔竹平地村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGuLaRenZhuPingDiCun-宾阳古辣稔竹平地村\BYGuLaRenZhuPingDiCun1800O-宾阳古辣稔竹平地村1800O |  | Radio Site | BYGuLaRenZhuPingDiCun1800O | 宾阳古辣稔竹平地村1800O_1 | BYGuLaRenZhuPingDiCun1800O-宾阳古辣稔竹平地村1800O | 245012385 |  |  | Nanning | China | Draft | 南宁市宾阳古辣镇稔竹村委平地村北边50米的空地上 | 109.0284 | 109'1'42' | 23.1182 | 23'7'5'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-04 | China | China Telecom Guangxi | Completed | China | 2582480 |  | 245003481 | Completed | CTGXLTE1.8Gproject-宾阳甘棠洪信村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGanTangHongXinCun-宾阳甘棠洪信村\BYGanTangHongXinCun1800O-宾阳甘棠洪信村1800O |  | Radio Site | BYGanTangHongXinCun1800O | 宾阳甘棠洪信村1800O_1 | BYGanTangHongXinCun1800O-宾阳甘棠洪信村1800O | 245012360 |  |  | Nanning | China | Draft | 南宁市宾阳县甘棠镇洪信村北边大概780米处的高山上 | 108.9606 | 108'57'38' | 23.0159 | 23'0'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-08 | China | China Telecom Guangxi | Completed | China | 2582481 |  | 245003483 | Completed | CTGXLTE1.8Gproject-宾阳甘棠新宁村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGanTangXinNingCun-宾阳甘棠新宁村\BYGanTangXinNingCun1800O-宾阳甘棠新宁村1800O |  | Radio Site | BYGanTangXinNingCun1800O | 宾阳甘棠新宁村1800O_1 | BYGanTangXinNingCun1800O-宾阳甘棠新宁村1800O | 245012353 |  |  | Nanning | China | Draft | 南宁市宾阳县甘棠镇新宁村村口居民楼顶 | 109.0506 | 109'3'2' | 22.941 | 22'56'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-03 | China | China Telecom Guangxi | Completed | China | 2582482 |  | 245003484 | Completed | CTGXLTE1.8Gproject-宾阳陈平五星村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYChenPingWuXingCun-宾阳陈平五星村\NNBYChenPingWuXingCun1800O-宾阳陈平五星村1800O |  | Radio Site | NNBYChenPingWuXingCun1800O | 宾阳陈平五星村1800O_1 | NNBYChenPingWuXingCun1800O-宾阳陈平五星村1800O | 245012347 |  |  | Nanning | China | Draft | 南宁宾阳县陈平乡五星村北偏东六十度大概300米山坡上 | 108.7966 | 108'47'48' | 22.9965 | 22'59'47'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-02 | China | China Telecom Guangxi | Completed | China | 2582483 |  | 245003489 | Completed | CTGXLTE1.8Gproject-宾阳陈平乡陈平客运站1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYChenPingXiangChenPKYZ-宾阳陈平乡陈平客运站\BYChenPingXiangChenPKYZ1800O-宾阳陈平乡陈平客运站1800O |  | Radio Site | BYChenPingXiangChenPKYZ1800O | 宾阳陈平乡陈平客运站1800O_1 | BYChenPingXiangChenPKYZ1800O-宾阳陈平乡陈平客运站1800O | 245012362 |  |  | Nanning | China | Draft | 南宁市宾阳县陈平街陈平客运站二楼楼顶 | 108.7912 | 108'47'28' | 23.0384 | 23'2'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-05 | China | China Telecom Guangxi | Completed | China | 2582484 |  | 245003486 | Completed | CTGXLTE1.8Gproject-宾阳甘棠那河木塘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGanTangNaHeMuTangCun-宾阳甘棠那河木塘村\BYGanTangNaHeMuTangCun1800O-宾阳甘棠那河木塘村1800O |  | Radio Site | BYGanTangNaHeMuTangCun1800O | 宾阳甘棠那河木塘村1800O_1 | BYGanTangNaHeMuTangCun1800O-宾阳甘棠那河木塘村1800O | 245012358 |  |  | Nanning | China | Draft | 南宁市宾阳甘棠镇那河村委木塘村东北方向大概400米处的土山上 | 108.9355 | 108'56'8' | 22.9367 | 22'56'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-07 | China | China Telecom Guangxi | Completed | China | 2582485 |  | 245003488 | Completed | CTGXLTE1.8Gproject-宾阳甘棠镇百合村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGanTangZhenBaiHeCun-宾阳甘棠镇百合村\NNBYGanTangZhenBaiHeCun1800O-宾阳甘棠镇百合村1800O |  | Radio Site | NNBYGanTangZhenBaiHeCun1800O | 宾阳甘棠镇百合村1800O_1 | NNBYGanTangZhenBaiHeCun1800O-宾阳甘棠镇百合村1800O | 245012348 |  |  | Nanning | China | Draft | 南宁宾阳县甘棠镇百合西偏南20度方向大概600米山坡上 | 109.0178 | 109'1'4' | 22.9785 | 22'58'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-08 | China | China Telecom Guangxi | Completed | China | 2582486 |  | 245003490 | Completed | CTGXLTE1.8Gproject-宾阳古辣六窑榃侄村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaLiuYaoTanZhiCun-宾阳古辣六窑榃侄村\NNBYGuLaLiuYaoTanZhiCun1800O-宾阳古辣六窑榃侄村1800O |  | Radio Site | NNBYGuLaLiuYaoTanZhiCun1800O | 宾阳古辣六窑榃侄村1800O_1 | NNBYGuLaLiuYaoTanZhiCun1800O-宾阳古辣六窑榃侄村1800O | 245012397 |  |  | Nanning | China | Draft | 南宁宾阳古辣六窑榃侄村后山山顶 | 109.0486 | 109'2'55' | 23.0851 | 23'5'6'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-09 | China | China Telecom Guangxi | Completed | China | 2582487 |  | 245003495 | Completed | CTGXLTE1.8Gproject-宾阳古辣三文村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaSanWenCun-宾阳古辣三文村\NNBYGuLaSanWenCun1800O-宾阳古辣三文村1800O |  | Radio Site | NNBYGuLaSanWenCun1800O | 宾阳古辣三文村1800O_1 | NNBYGuLaSanWenCun1800O-宾阳古辣三文村1800O | 245012384 |  |  | Nanning | China | Draft | 南宁宾阳县古辣镇三文村往东边大概150米处的旱地上 | 108.9961 | 108'59'46' | 23.1157 | 23'6'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-12 | China | China Telecom Guangxi | Completed | China | 2582488 |  | 245004104 | Completed | CTGXLTE1.8Gproject-宾阳古辣新兴龙母村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGuLaXinXingLongMuCun-宾阳古辣新兴龙母村\BYGuLaXinXingLongMuCun1800O-宾阳古辣新兴龙母村1800O |  | Radio Site | BYGuLaXinXingLongMuCun1800O | 宾阳古辣新兴龙母村1800O_1 | BYGuLaXinXingLongMuCun1800O-宾阳古辣新兴龙母村1800O | 245012391 |  |  | Nanning | China | Draft | 南宁市宾阳古辣镇新兴村委龙母村北170米的空地上 | 109.0424 | 109'2'33' | 23.1287 | 23'7'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-11 | China | China Telecom Guangxi | Completed | China | 2582489 |  | 245004105 | Completed | CTGXLTE1.8Gproject-宾阳黎塘补基村委补基村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangBuJiCunWeiBuJC-宾阳黎塘补基村委补基村\NNBYLiTangBuJiCunWeiBuJC1800O-宾阳黎塘补基村委补基村1800O |  | Radio Site | NNBYLiTangBuJiCunWeiBuJC1800O | 宾阳黎塘补基村委补基村1800O_1 | NNBYLiTangBuJiCunWeiBuJC1800O-宾阳黎塘补基村委补基村1800O | 245012399 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇补基村委补基村附近一甘蔗地上 | 109.0811 | 109'4'52' | 23.1741 | 23'10'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-12 | China | China Telecom Guangxi | Completed | China | 2582490 |  | 245004106 | Completed | CTGXLTE1.8Gproject-宾阳黎塘龙胜朱山村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangLongShengZSC-宾阳黎塘龙胜朱山村\NNBYLiTangLongShengZSC1800O-宾阳黎塘龙胜朱山村1800O |  | Radio Site | NNBYLiTangLongShengZSC1800O | 宾阳黎塘龙胜朱山村1800O_1 | NNBYLiTangLongShengZSC1800O-宾阳黎塘龙胜朱山村1800O | 245012388 |  |  | Nanning | China | Draft | 南宁宾阳黎塘龙胜朱山村附近公路旁宾阳高铁站出来800米 | 109.0983 | 109'5'54' | 23.2095 | 23'12'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-17 | China | China Telecom Guangxi | Completed | China | 2582491 |  | 245004107 | Completed | CTGXLTE1.8Gproject-宾阳王灵三择新村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingSanZeXinCun-宾阳王灵三择新村\NNBYWangLingSanZeXinCun1800O-宾阳王灵三择新村1800O |  | Radio Site | NNBYWangLingSanZeXinCun1800O | 宾阳王灵三择新村1800O_1 | NNBYWangLingSanZeXinCun1800O-宾阳王灵三择新村1800O | 245012383 |  |  | Nanning | China | Draft | 南宁市宾阳县王灵镇三择新村西北方向200平地上 | 109.0292 | 109'1'45' | 23.1462 | 23'8'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-23 | China | China Telecom Guangxi | Completed | China | 2582492 |  | 245004113 | Completed | CTGXLTE1.8Gproject-宾阳黎塘三和村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYLiTangSanHeCun-宾阳黎塘三和村\BYLiTangSanHeCun1800O-宾阳黎塘三和村1800O |  | Radio Site | BYLiTangSanHeCun1800O | 宾阳黎塘三和村1800O_1 | BYLiTangSanHeCun1800O-宾阳黎塘三和村1800O | 245012398 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇三和村委路口进去大概1500米处的旱地上 | 109.1042 | 109'6'15' | 23.1742 | 23'10'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-14 | China | China Telecom Guangxi | Completed | China | 2582493 |  | 245004109 | Completed | CTGXLTE1.8Gproject-宾阳和吉惠良六莫村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiHuiLiangLiuMoCun-宾阳和吉惠良六莫村\BYHeJiHuiLiangLiuMoCun1800O-宾阳和吉惠良六莫村1800O |  | Radio Site | BYHeJiHuiLiangLiuMoCun1800O | 宾阳和吉惠良六莫村1800O_1 | BYHeJiHuiLiangLiuMoCun1800O-宾阳和吉惠良六莫村1800O | 245012390 |  |  | Nanning | China | Draft | 南宁市南宁宾阳和吉镇惠良村委六莫村附近小土坡上 | 109.0651 | 109'3'54' | 23.2763 | 23'16'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-15 | China | China Telecom Guangxi | Completed | China | 2582494 |  | 245004115 | Completed | CTGXLTE1.8Gproject-宾阳和吉莲花新村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiLianHuaXinCun-宾阳和吉莲花新村\BYHeJiLianHuaXinCun1800O-宾阳和吉莲花新村1800O |  | Radio Site | BYHeJiLianHuaXinCun1800O | 宾阳和吉莲花新村1800O_1 | BYHeJiLianHuaXinCun1800O-宾阳和吉莲花新村1800O | 245012393 |  |  | Nanning | China | Draft | 南宁宾阳县大桥镇老杨村北偏东10度大概530米的旱地上 | 109.0502 | 109'3'1' | 23.2287 | 23'13'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-21 | China | China Telecom Guangxi | Completed | China | 2582495 |  | 245004110 | Completed | CTGXLTE1.8Gproject-宾阳和吉镇伶俐村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiZhenLingLiCun-宾阳和吉镇伶俐村\BYHeJiZhenLingLiCun1800O-宾阳和吉镇伶俐村1800O |  | Radio Site | BYHeJiZhenLingLiCun1800O | 宾阳和吉镇伶俐村1800O_1 | BYHeJiZhenLingLiCun1800O-宾阳和吉镇伶俐村1800O | 245012392 |  |  | Nanning | China | Draft | 南宁宾阳县和吉镇伶俐村北偏东750米处旱地上 | 109.1503 | 109'9'1' | 23.2738 | 23'16'25'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-09 | China | China Telecom Guangxi | Completed | China | 2582496 |  | 245004108 | Completed | CTGXLTE1.8Gproject-宾阳古辣龙额甘赵村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYGuLaLongEGanZhaoCun-宾阳古辣龙额甘赵村\BYGuLaLongEGanZhaoCun1800O-宾阳古辣龙额甘赵村1800O |  | Radio Site | BYGuLaLongEGanZhaoCun1800O | 宾阳古辣龙额甘赵村1800O_1 | BYGuLaLongEGanZhaoCun1800O-宾阳古辣龙额甘赵村1800O | 245012382 |  |  | Nanning | China | Draft | 南宁市宾阳古辣镇龙额村委甘赵村东南方向500米高速路旁的山坡上 | 109.0089 | 109'0'32' | 23.0737 | 23'4'25'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-02 | China | China Telecom Guangxi | Completed | China | 2582497 |  | 245004111 | Completed | CTGXLTE1.8Gproject-宾阳王灵义和青草村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWangLingYiHeQingCaoCun-宾阳王灵义和青草村\BYWangLingYiHeQingCaoCun1800O-宾阳王灵义和青草村1800O |  | Radio Site | BYWangLingYiHeQingCaoCun1800O | 宾阳王灵义和青草村1800O_1 | BYWangLingYiHeQingCaoCun1800O-宾阳王灵义和青草村1800O | 245012387 |  |  | Nanning | China | Draft | 南宁宾阳县黎塘青草村西面约300米铁路旁玉米地 | 109.0817 | 109'4'54' | 23.1624 | 23'9'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-17 | China | China Telecom Guangxi | Completed | China | 2582498 |  | 245004114 | Completed | CTGXLTE1.8Gproject-宾阳和吉三民三六村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiSanMinSanLiuCun-宾阳和吉三民三六村\BYHeJiSanMinSanLiuCun1800O-宾阳和吉三民三六村1800O |  | Radio Site | BYHeJiSanMinSanLiuCun1800O | 宾阳和吉三民三六村1800O_1 | BYHeJiSanMinSanLiuCun1800O-宾阳和吉三民三六村1800O | 245012389 |  |  | Nanning | China | Draft | 南宁宾阳县和吉三民三六村南边大概120米处附近一甘蔗地 | 109.1382 | 109'8'18' | 23.2524 | 23'15'8'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-05 | China | China Telecom Guangxi | Completed | China | 2582499 |  | 245004118 | Completed | CTGXLTE1.8Gproject-宾阳武陵六蒙六河村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWuLingLiuMengLiuHeCun-宾阳武陵六蒙六河村\BYWuLingLiuMengLiuHeCun1800O-宾阳武陵六蒙六河村1800O |  | Radio Site | BYWuLingLiuMengLiuHeCun1800O | 宾阳武陵六蒙六河村1800O_1 | BYWuLingLiuMengLiuHeCun1800O-宾阳武陵六蒙六河村1800O | 245012418 |  |  | Nanning | China | Draft | 南宁市宾阳县武陵镇六蒙六河村小学往高铁桥洞走大概260米处山上 | 108.8655 | 108'51'56' | 23.0462 | 23'2'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-14 | China | China Telecom Guangxi | Completed | China | 2582500 |  | 245004116 | Completed | CTGXLTE1.8Gproject-宾阳黎塘司马司村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangSiMaSiCun-宾阳黎塘司马司村\NNBYLiTangSiMaSiCun1800O-宾阳黎塘司马司村1800O |  | Radio Site | NNBYLiTangSiMaSiCun1800O | 宾阳黎塘司马司村1800O_1 | NNBYLiTangSiMaSiCun1800O-宾阳黎塘司马司村1800O | 245012394 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇司马司村东北方向约100米G324国道旁一农田里 | 109.132 | 109'7'55' | 23.1829 | 23'10'58'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-21 | China | China Telecom Guangxi | Completed | China | 2582501 |  | 245004121 | Completed | CTGXLTE1.8Gproject-宾阳中华镇中华自来水厂1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZhongHuaZhenZHZLSC-宾阳中华镇中华自来水厂\NNBYZhongHuaZhenZHZLSC1800O-宾阳中华镇中华自来水厂1800O |  | Radio Site | NNBYZhongHuaZhenZHZLSC1800O | 宾阳中华镇中华自来水厂1800O_1 | NNBYZhongHuaZhenZHZLSC1800O-宾阳中华镇中华自来水厂1800O | 245012430 |  |  | Nanning | China | Draft | 南宁市宾阳县中华镇中华自来水厂对面距离公路100米处 | 108.9455 | 108'56'44' | 23.1327 | 23'7'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-06 | China | China Telecom Guangxi | Completed | China | 2582502 |  | 245004122 | Completed | CTGXLTE1.8Gproject-宾阳新桥民范村西面山坡1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoMinFanCunXiMSP-宾阳新桥民范村西面山坡\BYXinQiaoMinFanCunXiMSP1800O-宾阳新桥民范村西面山坡1800O |  | Radio Site | BYXinQiaoMinFanCunXiMSP1800O | 宾阳新桥民范村西面山坡1800O_1 | BYXinQiaoMinFanCunXiMSP1800O-宾阳新桥民范村西面山坡1800O | 245013062 |  |  | Nanning | China | Draft | 南宁宾阳县新桥镇民范村西面方向大概350米处的土山上 | 108.7099 | 108'42'36' | 23.2087 | 23'12'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582503 |  | 245004120 | Completed | CTGXLTE1.8Gproject-宾阳武陵六蒙六河村2100O | CTGXLTE1.8Gproject |  |  | \Locations\BYWuLingLiuMengLiuHeCun-宾阳武陵六蒙六河村\BYWuLingLiuMengLiuHeCun2100O-宾阳武陵六蒙六河村2100O |  | Radio Site | BYWuLingLiuMengLiuHeCun2100O | 宾阳武陵六蒙六河村2100O_1 | BYWuLingLiuMengLiuHeCun2100O-宾阳武陵六蒙六河村2100O | 245012681 |  |  | Nanning | China | Draft | 南宁市宾阳县武陵镇六蒙六河村小学往高铁桥洞走大概260米处山上 | 108.8655 | 108'51'56' | 23.0462 | 23'2'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-24 | China | China Telecom Guangxi | Completed | China | 2582504 |  | 245004124 | Completed | CTGXLTE1.8Gproject-宾阳黎塘镇金龙大道联通黎塘经营部1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYLiTangZhenJLDDLTLTJYB-宾阳黎塘镇金龙大道联通黎塘经营部\BYLiTangZhenJLDDLTLTJYB1800O-宾阳黎塘镇金龙大道联通黎塘经营部1800O |  | Radio Site | BYLiTangZhenJLDDLTLTJYB1800O | 宾阳黎塘镇金龙大道联通黎塘经营部1800O_1 | BYLiTangZhenJLDDLTLTJYB1800O-宾阳黎塘镇金龙大道联通黎塘经营部1800O | 245013061 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇金龙大道二里20号6楼顶 | 109.124 | 109'7'26' | 23.199 | 23'11'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-12 | China | China Telecom Guangxi | Completed | China | 2582505 |  | 245004126 | Completed | CTGXLTE1.8Gproject-宾阳新桥三友村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoSanYouCun-宾阳新桥三友村\BYXinQiaoSanYouCun1800O-宾阳新桥三友村1800O |  | Radio Site | BYXinQiaoSanYouCun1800O | 宾阳新桥三友村1800O_1 | BYXinQiaoSanYouCun1800O-宾阳新桥三友村1800O | 245012386 |  |  | Nanning | China | Draft | 南宁宾阳三友一居民楼楼顶 | 108.7413 | 108'44'29' | 23.2305 | 23'13'49'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-08 | China | China Telecom Guangxi | Completed | China | 2582506 |  | 245004125 | Completed | CTGXLTE1.8Gproject-宾阳新桥民范六达村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYXinQiaoMinFanLiuDaCun-宾阳新桥民范六达村\BYXinQiaoMinFanLiuDaCun1800O-宾阳新桥民范六达村1800O |  | Radio Site | BYXinQiaoMinFanLiuDaCun1800O | 宾阳新桥民范六达村1800O_1 | BYXinQiaoMinFanLiuDaCun1800O-宾阳新桥民范六达村1800O | 245012395 |  |  | Nanning | China | Draft | 南宁市宾阳县思陇镇太守村六达东120米的山坡上 | 108.699 | 108'41'57' | 23.2179 | 23'13'4'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-25 | China | China Telecom Guangxi | Completed | China | 2582507 |  | 245004753 | Completed | CTGXLTE1.8Gproject-宾阳邹圩镇高龙村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZouXuZhenGaoLongCun-宾阳邹圩镇高龙村\NNBYZouXuZhenGaoLongCun1800O-宾阳邹圩镇高龙村1800O |  | Radio Site | NNBYZouXuZhenGaoLongCun1800O | 宾阳邹圩镇高龙村1800O_1 | NNBYZouXuZhenGaoLongCun1800O-宾阳邹圩镇高龙村1800O | 245013057 |  |  | Nanning | China | Draft | 南宁市宾阳县古辣镇高龙村背后的山坡上 | 108.8619 | 108'51'43' | 23.3132 | 23'18'47'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-20 | China | China Telecom Guangxi | Completed | China | 2582508 |  | 245004751 | Completed | CTGXLTE1.8Gproject-宾阳和吉燕山村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiYanShanCun-宾阳和吉燕山村\BYHeJiYanShanCun1800O-宾阳和吉燕山村1800O |  | Radio Site | BYHeJiYanShanCun1800O | 宾阳和吉燕山村1800O_1 | BYHeJiYanShanCun1800O-宾阳和吉燕山村1800O | 245012421 |  |  | Nanning | China | Draft | 南宁市宾阳县和吉镇燕山村西南约700米土坡上 | 109.1674 | 109'10'3' | 23.2491 | 23'14'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-26 | China | China Telecom Guangxi | Completed | China | 2582509 |  | 245004752 | Completed | CTGXLTE1.8Gproject-宾阳露圩亚伶村北面山顶1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYLuXuYaLingCunBeiMSD-宾阳露圩亚伶村北面山顶\BYLuXuYaLingCunBeiMSD1800O-宾阳露圩亚伶村北面山顶1800O |  | Radio Site | BYLuXuYaLingCunBeiMSD1800O | 宾阳露圩亚伶村北面山顶1800O_1 | BYLuXuYaLingCunBeiMSD1800O-宾阳露圩亚伶村北面山顶1800O | 245012429 |  |  | Nanning | China | Draft | 南宁市宾阳县露圩镇往古辣方向走2公里后左拐到高速路旁（宾阳露圩亚伶村北面山顶）山顶 | 109.0149 | 109'0'54' | 23.0343 | 23'2'3'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-30 | China | China Telecom Guangxi | Completed | China | 2582510 |  | 245004756 | Completed | CTGXLTE1.8Gproject-宾阳黎塘帽子村居民楼1800O | CTGXLTE1.8Gproject |  |  | \Locations\newBYLiTangMaoZiCunJuMinLou-宾阳黎塘帽子村居民楼\newBYLiTangMaoZiCunJuMinLou1800O-宾阳黎塘帽子村居民楼1800O |  | Radio Site | newBYLiTangMaoZiCunJuMinLou1800O | 宾阳黎塘帽子村居民楼1800O_1 | newBYLiTangMaoZiCunJuMinLou1800O-宾阳黎塘帽子村居民楼1800O | 245012433 |  |  | Nanning | China | Draft | 宾阳黎塘帽子村居民楼 | 109.1423 | 109'8'32' | 23.2263 | 23'13'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-16 | China | China Telecom Guangxi | Completed | China | 2582511 |  | 245004755 | Completed | CTGXLTE1.8Gproject-宾阳思陇马岭阮屋村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYSiLongMaLingRuanWC-宾阳思陇马岭阮屋村\NNBYSiLongMaLingRuanWC1800O-宾阳思陇马岭阮屋村1800O |  | Radio Site | NNBYSiLongMaLingRuanWC1800O | 宾阳思陇马岭阮屋村1800O_1 | NNBYSiLongMaLingRuanWC1800O-宾阳思陇马岭阮屋村1800O | 245012427 |  |  | Nanning | China | Draft | 南宁市宾阳思陇镇马岭村委阮屋村附近土山的山顶上 | 108.6642 | 108'39'51' | 23.1534 | 23'9'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-01 | China | China Telecom Guangxi | Completed | China | 2582512 |  | 245004754 | Completed | CTGXLTE1.8Gproject-宾阳思陇平安外覃村1800O | CTGXLTE1.8Gproject |  |  | \Locations\newBYSiLongPingAnWaiQinCun-宾阳思陇平安外覃村\newBYSiLongPingAnWaiQinCun1800O-宾阳思陇平安外覃村1800O |  | Radio Site | newBYSiLongPingAnWaiQinCun1800O | 宾阳思陇平安外覃村1800O_1 | newBYSiLongPingAnWaiQinCun1800O-宾阳思陇平安外覃村1800O | 245012424 |  |  | Nanning | China | Draft | 宾阳思陇平安外覃村 | 108.6003 | 108'36'1' | 23.1812 | 23'10'52'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-04 | China | China Telecom Guangxi | Completed | China | 2582513 |  | 245004761 | Completed | CTGXLTE1.8Gproject-宾阳大桥大程村西边三管塔1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYDaQiaoDaChengCunXBSGT-宾阳大桥大程村西边三管塔\NNBYDaQiaoDaChengCunXBSGT1800O-宾阳大桥大程村西边三管塔1800O |  | Radio Site | NNBYDaQiaoDaChengCunXBSGT1800O | 宾阳大桥大程村西边三管塔1800O_1 | NNBYDaQiaoDaChengCunXBSGT1800O-宾阳大桥大程村西边三管塔1800O | 245012419 |  |  | Nanning | China | Draft | 南宁市宾阳县大桥镇大程村西边大概300米处的旱地上 | 108.8957 | 108'53'45' | 23.2139 | 23'12'50'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-23 | China | China Telecom Guangxi | Completed | China | 2582514 |  | 245004759 | Completed | CTGXLTE1.8Gproject-宾阳邹圩中南新白石村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZouWeiZhongNXBSC-宾阳邹圩中南新白石村\NNBYZouWeiZhongNXBSC1800O-宾阳邹圩中南新白石村1800O |  | Radio Site | NNBYZouWeiZhongNXBSC1800O | 宾阳邹圩中南新白石村1800O_1 | NNBYZouWeiZhongNXBSC1800O-宾阳邹圩中南新白石村1800O | 245012432 |  |  | Nanning | China | Draft | 南宁宾阳邹圩镇中南村委新白石村 | 108.8935 | 108'53'37' | 23.3393 | 23'20'21'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-25 | China | China Telecom Guangxi | Completed | China | 2582515 |  | 245004757 | Completed | CTGXLTE1.8Gproject-宾阳露圩上塘君庄村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYLuXuShangTangJunZC-宾阳露圩上塘君庄村\BYLuXuShangTangJunZC1800O-宾阳露圩上塘君庄村1800O |  | Radio Site | BYLuXuShangTangJunZC1800O | 宾阳露圩上塘君庄村1800O_1 | BYLuXuShangTangJunZC1800O-宾阳露圩上塘君庄村1800O | 245012422 |  |  | Nanning | China | Draft | 南宁市宾阳县露圩镇百合村往露圩方向700处（宾阳露圩镇上塘村委君庄村附近）的山上 | 109.0708 | 109'4'15' | 23.045 | 23'2'41'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-06 | China | China Telecom Guangxi | Completed | China | 2582516 |  | 245004758 | Completed | CTGXLTE1.8Gproject-宾阳大桥罗江吕村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYDaQiaoLuoJiangLvCunO-宾阳大桥罗江吕村\NNBYDaQiaoLuoJiangLvCunO1800O-宾阳大桥罗江吕村1800O |  | Radio Site | NNBYDaQiaoLuoJiangLvCunO1800O | 宾阳大桥罗江吕村1800O_1 | NNBYDaQiaoLuoJiangLvCunO1800O-宾阳大桥罗江吕村1800O | 245012420 |  |  | Nanning | China | Draft | 南宁宾阳大桥镇罗江村吕村一居民楼上 | 108.9062 | 108'54'22' | 23.1658 | 23'9'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-15 | China | China Telecom Guangxi | Completed | China | 2582517 |  | 245004762 | Completed | CTGXLTE1.8Gproject-宾阳黎塘镇青山村委后山1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangZhenQingSCWHS-宾阳黎塘镇青山村委后山\NNBYLiTangZhenQingSCWHS1800O-宾阳黎塘镇青山村委后山1800O |  | Radio Site | NNBYLiTangZhenQingSCWHS1800O | 宾阳黎塘镇青山村委后山1800O_1 | NNBYLiTangZhenQingSCWHS1800O-宾阳黎塘镇青山村委后山1800O | 245012426 |  |  | Nanning | China | Draft | 南宁市宾阳县黎塘镇青山村委南边大概150米处的桉树林上 | 109.1561 | 109'9'22' | 23.1976 | 23'11'51'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-24 | China | China Telecom Guangxi | Completed | China | 2582518 |  | 245004765 | Completed | CTGXLTE1.8Gproject-宾阳邹圩镇地久村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZouXuZhenDiJiuCun-宾阳邹圩镇地久村\NNBYZouXuZhenDiJiuCun1800O-宾阳邹圩镇地久村1800O |  | Radio Site | NNBYZouXuZhenDiJiuCun1800O | 宾阳邹圩镇地久村1800O_1 | NNBYZouXuZhenDiJiuCun1800O-宾阳邹圩镇地久村1800O | 245012425 |  |  | Nanning | China | Draft | 南宁宾阳县邹圩镇地久村西边大概1100米处土坡上 | 108.9184 | 108'55'6' | 23.3297 | 23'19'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-13 | China | China Telecom Guangxi | Completed | China | 2582519 |  | 245004760 | Completed | CTGXLTE1.8Gproject-宾阳黎塘帽子村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangMaoZiCun-宾阳黎塘帽子村\NNBYLiTangMaoZiCun1800O-宾阳黎塘帽子村1800O |  | Radio Site | NNBYLiTangMaoZiCun1800O | 宾阳黎塘帽子村1800O_1 | NNBYLiTangMaoZiCun1800O-宾阳黎塘帽子村1800O | 245012434 |  |  | Nanning | China | Draft | 南宁宾阳黎塘帽子村西北面空地上 | 109.1422 | 109'8'32' | 23.2316 | 23'13'53'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-05-22 | China | China Telecom Guangxi | Completed | China | 2582520 |  | 245004764 | Completed | CTGXLTE1.8Gproject-宾阳邹圩白山村东南山顶1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZouWeiBaiShanCDNSD-宾阳邹圩白山村东南山顶\NNBYZouWeiBaiShanCDNSD1800O-宾阳邹圩白山村东南山顶1800O |  | Radio Site | NNBYZouWeiBaiShanCDNSD1800O | 宾阳邹圩白山村东南山顶1800O_1 | NNBYZouWeiBaiShanCDNSD1800O-宾阳邹圩白山村东南山顶1800O | 245012423 |  |  | Nanning | China | Draft | 南宁市宾阳县白山村东300米采石场旁的石山上 | 108.8942 | 108'53'39' | 23.3987 | 23'23'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-15 | China | China Telecom Guangxi | Completed | China | 2582521 |  | 245004768 | Completed | CTGXLTE1.8Gproject-横县百合江口村委楼顶1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeJiangKouCunWeiLD-横县百合江口村委楼顶\HXBaiHeJiangKouCunWeiLD1800O-横县百合江口村委楼顶1800O |  | Radio Site | HXBaiHeJiangKouCunWeiLD1800O | 横县百合江口村委楼顶1800O_1 | HXBaiHeJiangKouCunWeiLD1800O-横县百合江口村委楼顶1800O | 245012431 |  |  | Nanning | China | Draft | 南宁市横县百合镇江口村村委2楼顶 | 109.4331 | 109'25'59' | 22.7202 | 22'43'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-18 | China | China Telecom Guangxi | Completed | China | 2582522 |  | 245004766 | Completed | CTGXLTE1.8Gproject-横县百合庙庄村后山1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeMiaoZhuangCunHS-横县百合庙庄村后山\HXBaiHeMiaoZhuangCunHS1800O-横县百合庙庄村后山1800O |  | Radio Site | HXBaiHeMiaoZhuangCunHS1800O | 横县百合庙庄村后山1800O_1 | HXBaiHeMiaoZhuangCunHS1800O-横县百合庙庄村后山1800O | 245012462 |  |  | Nanning | China | Draft | 南宁市横县百合镇庙庄村委庙脚村后山坡上 | 109.4798 | 109'28'47' | 22.6537 | 22'39'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-17 | China | China Telecom Guangxi | Completed | China | 2582523 |  | 245004770 | Completed | CTGXLTE1.8Gproject-横县百合马坪村南阳村1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeMaPingCunNanYangC-横县百合马坪村南阳村\HXBaiHeMaPingCunNanYangC1800O-横县百合马坪村南阳村1800O |  | Radio Site | HXBaiHeMaPingCunNanYangC1800O | 横县百合马坪村南阳村1800O_1 | HXBaiHeMaPingCunNanYangC1800O-横县百合马坪村南阳村1800O | 245012470 |  |  | Nanning | China | Draft | 南宁市横县百合镇马坪村南阳村村外山头 | 109.4694 | 109'28'10' | 22.7089 | 22'42'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-06 | China | China Telecom Guangxi | Completed | China | 2582524 |  | 245004774 | Completed | CTGXLTE1.8Gproject-横县校椅榃冷村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNHXXiaoYiTanLengCunO-横县校椅榃冷村\NNHXXiaoYiTanLengCunO1800O-横县校椅榃冷村1800O |  | Radio Site | NNHXXiaoYiTanLengCunO1800O | 横县校椅榃冷村1800O_1 | NNHXXiaoYiTanLengCunO1800O-横县校椅榃冷村1800O | 245012435 |  |  | Nanning | China | Draft | 南宁市横县校椅镇榃冷村东北200米山坡上 | 109.1857 | 109'11'9' | 22.923 | 22'55'22'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-19 | China | China Telecom Guangxi | Completed | China | 2582525 |  | 245004775 | Completed | CTGXLTE1.8Gproject-横县百合田共村1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeTianGongCun-横县百合田共村\HXBaiHeTianGongCun1800O-横县百合田共村1800O |  | Radio Site | HXBaiHeTianGongCun1800O | 横县百合田共村1800O_1 | HXBaiHeTianGongCun1800O-横县百合田共村1800O | 245013058 |  |  | Nanning | China | Draft | 南宁市横县百合镇田共村东方约200米土坡上 | 109.4887 | 109'29'19' | 22.6583 | 22'39'30'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-03 | China | China Telecom Guangxi | Completed | China | 2582526 |  | 245005382 | Completed | CTGXLTE1.8Gproject-横县校椅青桐村街上1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNHXXiaoYiQingTongCunJS-横县校椅青桐村街上\NNHXXiaoYiQingTongCunJS1800O-横县校椅青桐村街上1800O |  | Radio Site | NNHXXiaoYiQingTongCunJS1800O | 横县校椅青桐村街上1800O_1 | NNHXXiaoYiQingTongCunJS1800O-横县校椅青桐村街上1800O | 245012428 |  |  | Nanning | China | Draft | 南宁市横县青桐村街上一药店3楼顶 | 109.1939 | 109'11'38' | 22.8929 | 22'53'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-28 | China | China Telecom Guangxi | Completed | China | 2582527 |  | 245005384 | Completed | CTGXLTE1.8Gproject-横县百合芦塘村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNHXBaiHeLuTangCunO-横县百合芦塘村\NNHXBaiHeLuTangCunO1800O-横县百合芦塘村1800O |  | Radio Site | NNHXBaiHeLuTangCunO1800O | 横县百合芦塘村1800O_1 | NNHXBaiHeLuTangCunO1800O-横县百合芦塘村1800O | 245012464 |  |  | Nanning | China | Draft | 南宁市横县百合镇卢塘村西北侧200米土坡上 | 109.4548 | 109'27'17' | 22.7844 | 22'47'3'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-31 | China | China Telecom Guangxi | Completed | China | 2582528 |  | 245005383 | Completed | CTGXLTE1.8Gproject-横县横州长淇村1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNHXHengZhouZhangQiCun-横县横州长淇村\NNHXHengZhouZhangQiCun1800O-横县横州长淇村1800O |  | Radio Site | NNHXHengZhouZhangQiCun1800O | 横县横州长淇村1800O_1 | NNHXHengZhouZhangQiCun1800O-横县横州长淇村1800O | 245012468 |  |  | Nanning | China | Draft | 南宁市横县横州镇长淇村村口居民楼 | 109.2853 | 109'17'7' | 22.7822 | 22'46'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-25 | China | China Telecom Guangxi | Completed | China | 2582529 |  | 245005386 | Completed | CTGXLTE1.8Gproject-横县百合六答村东面山坡1800O | CTGXLTE1.8Gproject |  |  | \Locations\NNHXBaiHeLiuDaCunDMSP-横县百合六答村东面山坡\NNHXBaiHeLiuDaCunDMSP1800O-横县百合六答村东面山坡1800O |  | Radio Site | NNHXBaiHeLiuDaCunDMSP1800O | 横县百合六答村东面山坡1800O_1 | NNHXBaiHeLiuDaCunDMSP1800O-横县百合六答村东面山坡1800O | 245012459 |  |  | Nanning | China | Draft | 南宁市横县百合镇六答村东方约200米土坡上 | 109.4643 | 109'27'52' | 22.6477 | 22'38'51'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-23 | China | China Telecom Guangxi | Completed | China | 2582530 |  | 245005388 | Completed | CTGXLTE1.8Gproject-横县马岭飞马村南1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXMaLingFeiMaCunNan-横县马岭飞马村南\HXMaLingFeiMaCunNan1800O-横县马岭飞马村南1800O |  | Radio Site | HXMaLingFeiMaCunNan1800O | 横县马岭飞马村南1800O_1 | HXMaLingFeiMaCunNan1800O-横县马岭飞马村南1800O | 245012456 |  |  | Nanning | China | Draft | 南宁市横县马岭镇飞马村南边约200米路边空地 | 109.3364 | 109'20'11' | 22.8284 | 22'49'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-21 | China | China Telecom Guangxi | Completed | China | 2582531 |  | 245005387 | Completed | CTGXLTE1.8Gproject-横县百合武留村中学后山1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeWuLiuCunZhongXHS-横县百合武留村中学后山\HXBaiHeWuLiuCunZhongXHS1800O-横县百合武留村中学后山1800O |  | Radio Site | HXBaiHeWuLiuCunZhongXHS1800O | 横县百合武留村中学后山1800O_1 | HXBaiHeWuLiuCunZhongXHS1800O-横县百合武留村中学后山1800O | 245012460 |  |  | Nanning | China | Draft | 南宁市横县百合镇武留村武留中学后山上 | 109.4411 | 109'26'28' | 22.6868 | 22'41'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-14 | China | China Telecom Guangxi | Completed | China | 2582532 |  | 245005385 | Completed | CTGXLTE1.8Gproject-横县百合芳村1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeFangCun-横县百合芳村\HXBaiHeFangCun1800O-横县百合芳村1800O |  | Radio Site | HXBaiHeFangCun1800O | 横县百合芳村1800O_1 | HXBaiHeFangCun1800O-横县百合芳村1800O | 245012465 |  |  | Nanning | China | Draft | 南宁市横县百合镇芳村侯车停附近果园里 | 109.4475 | 109'26'51' | 22.7346 | 22'44'4'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-20 | China | China Telecom Guangxi | Completed | China | 2582533 |  | 245005389 | Completed | CTGXLTE1.8Gproject-横县百合同菜村东1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeTongCaiCunDong-横县百合同菜村东\HXBaiHeTongCaiCunDong1800O-横县百合同菜村东1800O |  | Radio Site | HXBaiHeTongCaiCunDong1800O | 横县百合同菜村东1800O_1 | HXBaiHeTongCaiCunDong1800O-横县百合同菜村东1800O | 245012463 |  |  | Nanning | China | Draft | 南宁市横县百合镇同菜村东方约500米土坡上 | 109.4916 | 109'29'30' | 22.8146 | 22'48'52'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-09 | China | China Telecom Guangxi | Completed | China | 2582534 |  | 245005390 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇林村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLinCN-贵港覃塘镇林村南\GGQinTangZhenLinCN2100O-贵港覃塘镇林村南2100O |  | Radio Site | GGQinTangZhenLinCN2100O | 贵港覃塘镇林村南2100O_1 | GGQinTangZhenLinCN2100O-贵港覃塘镇林村南2100O | 245012458 |  |  | Nanning | China | Draft | 贵港市覃塘区五里镇林村东南方向约1.21公里 | 109.3961 | 109'23'46' | 23.1543 | 23'9'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-12 | China | China Telecom Guangxi | Completed | China | 2582535 |  | 245005393 | Completed | CTGXLTE1.8Gproject-桂平社坡镇福和村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShePoZhenFuHeCunGT-桂平社坡镇福和村高铁\GPShePoZhenFuHeCunGT2100O-桂平社坡镇福和村高铁2100O |  | Radio Site | GPShePoZhenFuHeCunGT2100O | 桂平社坡镇福和村高铁2100O_1 | GPShePoZhenFuHeCunGT2100O-桂平社坡镇福和村高铁2100O | 245012461 |  |  | Nanning | China | Draft | 雅思根西面100m处 | 110.2477 | 110'14'52' | 23.3562 | 23'21'22'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-11 | China | China Telecom Guangxi | Completed | China | 2582536 |  | 245005392 | Completed | CTGXLTE1.8Gproject-桂平理端乡高清王母大村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPLiDuanXiangGaoQWMDC-桂平理端乡高清王母大村\GPLiDuanXiangGaoQWMDC2100O-桂平理端乡高清王母大村2100O |  | Radio Site | GPLiDuanXiangGaoQWMDC2100O | 桂平理端乡高清王母大村2100O_1 | GPLiDuanXiangGaoQWMDC2100O-桂平理端乡高清王母大村2100O | 245012469 |  |  | Nanning | China | Draft | 桂平里端高清王母大村附近 | 110.3 | 110'18'0' | 23.3746 | 23'22'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582537 |  | 245005391 | Completed | CTGXLTE1.8Gproject-贵港大圩镇土寨村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenTuZhaiCun-贵港大圩镇土寨村\GGDaXuZhenTuZhaiCun2100O-贵港大圩镇土寨村2100O |  | Radio Site | GGDaXuZhenTuZhaiCun2100O | 贵港大圩镇土寨村2100O_1 | GGDaXuZhenTuZhaiCun2100O-贵港大圩镇土寨村2100O | 245012471 |  |  | Nanning | China | Draft | 贵港市港北区大圩镇土寨村东南约1公里驾校练车场后面的稻田里 | 109.7842 | 109'47'3' | 23.1831 | 23'10'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-22 | China | China Telecom Guangxi | Completed | China | 2582538 |  | 245005394 | Completed | CTGXLTE1.8Gproject-横县莲塘圣山茶园养鸡场1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXLianTangShengShanCYYJC-横县莲塘圣山茶园养鸡场\HXLianTangShengShanCYYJC1800O-横县莲塘圣山茶园养鸡场1800O |  | Radio Site | HXLianTangShengShanCYYJC1800O | 横县莲塘圣山茶园养鸡场1800O_1 | HXLianTangShengShanCYYJC1800O-横县莲塘圣山茶园养鸡场1800O | 245012466 |  |  | Nanning | China | Draft | 南宁横县莲塘镇佛子村圣山茶园内养鸡场旁土坡 | 109.146 | 109'8'46' | 22.7521 | 22'45'7'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582539 |  | 245005397 | Completed | CTGXLTE1.8Gproject-贵港大圩镇甘岭下垌2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenGanLingXiaD-贵港大圩镇甘岭下垌\GGDaXuZhenGanLingXiaD2100O-贵港大圩镇甘岭下垌2100O |  | Radio Site | GGDaXuZhenGanLingXiaD2100O | 贵港大圩镇甘岭下垌2100O_1 | GGDaXuZhenGanLingXiaD2100O-贵港大圩镇甘岭下垌2100O | 245012472 |  |  | Nanning | China | Draft | 贵港市港北区大圩镇仁心村下垌屯北边约500米的农田 | 109.7948 | 109'47'41' | 23.1892 | 23'11'21'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-12 | China | China Telecom Guangxi | Completed | China | 2582540 |  | 245005398 | Completed | CTGXLTE1.8Gproject-桂平社坡镇福和村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShePoZhenFuHeCun-桂平社坡镇福和村\GPShePoZhenFuHeCun2100O-桂平社坡镇福和村2100O |  | Radio Site | GPShePoZhenFuHeCun2100O | 桂平社坡镇福和村2100O_1 | GPShePoZhenFuHeCun2100O-桂平社坡镇福和村2100O | 245012457 |  |  | Nanning | China | Draft | 鸭思塘东面500m处 | 110.2531 | 110'15'11' | 23.3549 | 23'21'17'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-10 | China | China Telecom Guangxi | Completed | China | 2582541 |  | 245005400 | Completed | CTGXLTE1.8Gproject-桂平白沙镇禾堂2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenHeTang-桂平白沙镇禾堂\GPBaiShaZhenHeTang2100O-桂平白沙镇禾堂2100O |  | Radio Site | GPBaiShaZhenHeTang2100O | 桂平白沙镇禾堂2100O_1 | GPBaiShaZhenHeTang2100O-桂平白沙镇禾堂2100O | 245012500 |  |  | Nanning | China | Draft | 桂平市白沙镇禾堂村东南300米处农地里 | 109.9241 | 109'55'27' | 23.2261 | 23'13'33'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-08 | China | China Telecom Guangxi | Completed | China | 2582542 |  | 245005399 | Completed | CTGXLTE1.8Gproject-贵港黄练镇潘陈村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGHuangLianZhenPanCC-贵港黄练镇潘陈村\GGHuangLianZhenPanCC2100O-贵港黄练镇潘陈村2100O |  | Radio Site | GGHuangLianZhenPanCC2100O | 贵港黄练镇潘陈村2100O_1 | GGHuangLianZhenPanCC2100O-贵港黄练镇潘陈村2100O | 245012491 |  |  | Nanning | China | Draft | 贵港市覃塘区黄练镇潘陈村东北方向约406米农田内 | 109.2828 | 109'16'58' | 23.1908 | 23'11'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-09 | China | China Telecom Guangxi | Completed | China | 2582543 |  | 245005406 | Completed | CTGXLTE1.8Gproject-桂平白沙镇大岭2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenDaLing-桂平白沙镇大岭\GPBaiShaZhenDaLing2100O-桂平白沙镇大岭2100O |  | Radio Site | GPBaiShaZhenDaLing2100O | 桂平白沙镇大岭2100O_1 | GPBaiShaZhenDaLing2100O-桂平白沙镇大岭2100O | 245012495 |  |  | Nanning | China | Draft | 贵港市桂平市白沙镇378乡道龙井往白沙镇方向约1.45公里处 | 109.8896 | 109'53'23' | 23.2146 | 23'12'52'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-08 | China | China Telecom Guangxi | Completed | China | 2582544 |  | 245005412 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇何屋高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenHeWuGT-贵港覃塘镇何屋高铁\GGQinTangZhenHeWuGT2100O-贵港覃塘镇何屋高铁2100O |  | Radio Site | GGQinTangZhenHeWuGT2100O | 贵港覃塘镇何屋高铁2100O_1 | GGQinTangZhenHeWuGT2100O-贵港覃塘镇何屋高铁2100O | 245012467 |  |  | Nanning | China | Draft | 贵港市覃塘区回里西南方向约279米 | 109.3516 | 109'21'6' | 23.1684 | 23'10'6'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-08 | China | China Telecom Guangxi | Completed | China | 2582545 |  | 245006013 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇林场2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLinChang-贵港覃塘镇林场\GGQinTangZhenLinChang2100O-贵港覃塘镇林场2100O |  | Radio Site | GGQinTangZhenLinChang2100O | 贵港覃塘镇林场2100O_1 | GGQinTangZhenLinChang2100O-贵港覃塘镇林场2100O | 245012501 |  |  | Nanning | China | Draft | 贵港覃塘镇林场 | 109.474 | 109'28'26' | 23.1208 | 23'7'14'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-15 | China | China Telecom Guangxi | Completed | China | 2582546 |  | 245006014 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇北山村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GuiGangQinTangZBSCGT-贵港覃塘镇北山村高铁\GuiGangQinTangZBSCGT2100O-贵港覃塘镇北山村高铁2100O |  | Radio Site | GuiGangQinTangZBSCGT2100O | 贵港覃塘镇北山村高铁2100O_1 | GuiGangQinTangZBSCGT2100O-贵港覃塘镇北山村高铁2100O | 245012494 |  |  | Nanning | China | Draft | 贵港覃塘谷罗小学背后约100米正东边 | 109.4325 | 109'25'57' | 23.14 | 23'8'23'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582547 |  | 245006015 | Completed | CTGXLTE1.8Gproject-贵港大圩镇甘岭甘村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenGanLingGanC-贵港大圩镇甘岭甘村\GGDaXuZhenGanLingGanC2100O-贵港大圩镇甘岭甘村2100O |  | Radio Site | GGDaXuZhenGanLingGanC2100O | 贵港大圩镇甘岭甘村2100O_1 | GGDaXuZhenGanLingGanC2100O-贵港大圩镇甘岭甘村2100O | 245012507 |  |  | Nanning | China | Draft | 贵港大圩镇甘岭甘村附近平地 | 109.8149 | 109'48'54' | 23.1948 | 23'11'41'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-08 | China | China Telecom Guangxi | Completed | China | 2582548 |  | 245006018 | Completed | CTGXLTE1.8Gproject-贵港黄练镇居仕村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGHuangLianZJSCGT-贵港黄练镇居仕村高铁\GGHuangLianZJSCGT2100O-贵港黄练镇居仕村高铁2100O |  | Radio Site | GGHuangLianZJSCGT2100O | 贵港黄练镇居仕村高铁2100O_1 | GGHuangLianZJSCGT2100O-贵港黄练镇居仕村高铁2100O | 245012508 |  |  | Nanning | China | Draft | 贵港市覃塘区黄练镇居仕村东北方向 | 109.263 | 109'15'47' | 23.1967 | 23'11'48'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-08 | China | China Telecom Guangxi | Completed | China | 2582549 |  | 245006021 | Completed | CTGXLTE1.8Gproject-贵港黄练镇郁李村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGHuangLianZhenYuLiC-贵港黄练镇郁李村\GGHuangLianZhenYuLiC2100O-贵港黄练镇郁李村2100O |  | Radio Site | GGHuangLianZhenYuLiC2100O | 贵港黄练镇郁李村2100O_1 | GGHuangLianZhenYuLiC2100O-贵港黄练镇郁李村2100O | 245012499 |  |  | Nanning | China | Draft | 贵港市覃塘区黄练镇郁李村东南方向约462米 | 109.2998 | 109'17'59' | 23.1855 | 23'11'7'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582550 |  | 245006019 | Completed | CTGXLTE1.8Gproject-贵港大圩镇仁心村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGDaXuZhenRenXinCun-贵港大圩镇仁心村\GGDaXuZhenRenXinCun2100O-贵港大圩镇仁心村2100O |  | Radio Site | GGDaXuZhenRenXinCun2100O | 贵港大圩镇仁心村2100O_1 | GGDaXuZhenRenXinCun2100O-贵港大圩镇仁心村2100O | 245012502 |  |  | Nanning | China | Draft | 贵港市港北区大圩镇仁心村垌心往西约552米 | 109.7782 | 109'46'41' | 23.1782 | 23'10'41'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582551 |  | 245006016 | Completed | CTGXLTE1.8Gproject-贵港黄练镇大坡村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGHuangLianZhenDaPoC-贵港黄练镇大坡村\GGHuangLianZhenDaPoC2100O-贵港黄练镇大坡村2100O |  | Radio Site | GGHuangLianZhenDaPoC2100O | 贵港黄练镇大坡村2100O_1 | GGHuangLianZhenDaPoC2100O-贵港黄练镇大坡村2100O | 245012496 |  |  | Nanning | China | Draft | 贵港市覃塘区黄练镇杨屋往北约529米 | 109.3094 | 109'18'34' | 23.1803 | 23'10'49'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-09 | China | China Telecom Guangxi | Completed | China | 2582552 |  | 245006017 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇林村北2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLinCunB-贵港覃塘镇林村北\GGQinTangZhenLinCunB2100O-贵港覃塘镇林村北2100O |  | Radio Site | GGQinTangZhenLinCunB2100O | 贵港覃塘镇林村北2100O_1 | GGQinTangZhenLinCunB2100O-贵港覃塘镇林村北2100O | 245012503 |  |  | Nanning | China | Draft | 贵港覃塘林村高铁附近平底 | 109.3847 | 109'23'5' | 23.1594 | 23'9'33'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582553 |  | 245006022 | Completed | CTGXLTE1.8Gproject-贵港根竹乡火车站高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXiangHuoCZGT-贵港根竹乡火车站高铁\GGGenZhuXiangHuoCZGT2100O-贵港根竹乡火车站高铁2100O |  | Radio Site | GGGenZhuXiangHuoCZGT2100O | 贵港根竹乡火车站高铁2100O_1 | GGGenZhuXiangHuoCZGT2100O-贵港根竹乡火车站高铁2100O | 245012497 |  |  | Nanning | China | Draft | 贵港根竹初级中学旁边山坡 | 109.502 | 109'30'7' | 23.1154 | 23'6'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-09 | China | China Telecom Guangxi | Completed | China | 2582554 |  | 245006020 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇姚山村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenYaoSCGT-贵港覃塘镇姚山村高铁\GGQinTangZhenYaoSCGT2100O-贵港覃塘镇姚山村高铁2100O |  | Radio Site | GGQinTangZhenYaoSCGT2100O | 贵港覃塘镇姚山村高铁2100O_1 | GGQinTangZhenYaoSCGT2100O-贵港覃塘镇姚山村高铁2100O | 245012504 |  |  | Nanning | China | Draft | 贵港市覃塘区覃塘镇姚山村西方向高铁旁 | 109.3644 | 109'21'52' | 23.1669 | 23'10'0'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-13 | China | China Telecom Guangxi | Completed | China | 2582555 |  | 245006024 | Completed | CTGXLTE1.8Gproject-桂平市火车站东2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShiHuoCheZhanDong-桂平市火车站东\GPShiHuoCheZhanDong2100O-桂平市火车站东2100O |  | Radio Site | GPShiHuoCheZhanDong2100O | 桂平市火车站东2100O_1 | GPShiHuoCheZhanDong2100O-桂平市火车站东2100O | 245012506 |  |  | Nanning | China | Draft | 桂平市火车站东300米田地 | 110.1149 | 110'6'54' | 23.3221 | 23'19'19'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-12 | China | China Telecom Guangxi | Completed | China | 2582556 |  | 245006025 | Completed | CTGXLTE1.8Gproject-桂平木乐镇新莲村二2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenXinLianCunE-桂平木乐镇新莲村二\GPMuLeZhenXinLianCunE2100O-桂平木乐镇新莲村二2100O |  | Radio Site | GPMuLeZhenXinLianCunE2100O | 桂平木乐镇新莲村二2100O_1 | GPMuLeZhenXinLianCunE2100O-桂平木乐镇新莲村二2100O | 245012534 |  |  | Nanning | China | Draft | 桂平木乐镇新莲村附近山头 | 110.3459 | 110'20'45' | 23.412 | 23'24'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-14 | China | China Telecom Guangxi | Completed | China | 2582557 |  | 245006031 | Completed | CTGXLTE1.8Gproject-桂平西山镇西长村西2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenXiChangCX-桂平西山镇西长村西\GPXiShanZhenXiChangCX2100O-桂平西山镇西长村西2100O |  | Radio Site | GPXiShanZhenXiChangCX2100O | 桂平西山镇西长村西2100O_1 | GPXiShanZhenXiChangCX2100O-桂平西山镇西长村西2100O | 245012492 |  |  | Nanning | China | Draft | 西山镇西长村西面 | 110.105 | 110'6'18' | 23.3149 | 23'18'53'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-15 | China | China Telecom Guangxi | Completed | China | 2582558 |  | 245006029 | Completed | CTGXLTE1.8Gproject-桂平理端乡清高村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GuiPingLiDuanXQGCGT-桂平理端乡清高村高铁\GuiPingLiDuanXQGCGT2100O-桂平理端乡清高村高铁2100O |  | Radio Site | GuiPingLiDuanXQGCGT2100O | 桂平理端乡清高村高铁2100O_1 | GuiPingLiDuanXQGCGT2100O-桂平理端乡清高村高铁2100O | 245012505 |  |  | Nanning | China | Draft | 桂平市里端乡桥头湾东边200米处 | 110.2851 | 110'17'7' | 23.3662 | 23'21'58'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582559 |  | 245006026 | Completed | CTGXLTE1.8Gproject-贵港根竹乡黑石岭高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGGenZhuXHSLGT-贵港根竹乡黑石岭高铁\GGGenZhuXHSLGT2100O-贵港根竹乡黑石岭高铁2100O |  | Radio Site | GGGenZhuXHSLGT2100O | 贵港根竹乡黑石岭高铁2100O_1 | GGGenZhuXHSLGT2100O-贵港根竹乡黑石岭高铁2100O | 245012498 |  |  | Nanning | China | Draft | 贵港市港北区根竹镇榕木往西北方向约212米 | 109.5139 | 109'30'50' | 23.1108 | 23'6'38'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-13 | China | China Telecom Guangxi | Completed | China | 2582560 |  | 245006032 | Completed | CTGXLTE1.8Gproject-桂平市火车站2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShiHuoCheZhan-桂平市火车站\GPShiHuoCheZhan2100O-桂平市火车站2100O |  | Radio Site | GPShiHuoCheZhan2100O | 桂平市火车站2100O_1 | GPShiHuoCheZhan2100O-桂平市火车站2100O | 245012540 |  |  | Nanning | China | Draft | 桂平市火车站广场外路灯杆 | 110.1107 | 110'6'38' | 23.3214 | 23'19'17'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-11 | China | China Telecom Guangxi | Completed | China | 2582561 |  | 245006030 | Completed | CTGXLTE1.8Gproject-桂平理端乡木背塘2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPLiDuanXiangMuBeiTang-桂平理端乡木背塘\GPLiDuanXiangMuBeiTang2100O-桂平理端乡木背塘2100O |  | Radio Site | GPLiDuanXiangMuBeiTang2100O | 桂平理端乡木背塘2100O_1 | GPLiDuanXiangMuBeiTang2100O-桂平理端乡木背塘2100O | 245012493 |  |  | Nanning | China | Draft | 理端木背塘附近小山坡 | 110.2721 | 110'16'19' | 23.3581 | 23'21'29'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-11 | China | China Telecom Guangxi | Completed | China | 2582562 |  | 245006037 | Completed | CTGXLTE1.8Gproject-桂平木乐镇莲香塘高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenLianXTGT-桂平木乐镇莲香塘高铁\GPMuLeZhenLianXTGT2100O-桂平木乐镇莲香塘高铁2100O |  | Radio Site | GPMuLeZhenLianXTGT2100O | 桂平木乐镇莲香塘高铁2100O_1 | GPMuLeZhenLianXTGT2100O-桂平木乐镇莲香塘高铁2100O | 245012530 |  |  | Nanning | China | Draft | 桂平市木乐镇莲香塘南边400米 | 110.3108 | 110'18'39' | 23.3873 | 23'23'14'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-13 | China | China Telecom Guangxi | Completed | China | 2582563 |  | 245006034 | Completed | CTGXLTE1.8Gproject-桂平社坡镇禄全村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShePoZhenLuQuanCGT-桂平社坡镇禄全村高铁\GPShePoZhenLuQuanCGT2100O-桂平社坡镇禄全村高铁2100O |  | Radio Site | GPShePoZhenLuQuanCGT2100O | 桂平社坡镇禄全村高铁2100O_1 | GPShePoZhenLuQuanCGT2100O-桂平社坡镇禄全村高铁2100O | 245012538 |  |  | Nanning | China | Draft | 桂平市社坡镇光明村南面500M处 | 110.2155 | 110'12'56' | 23.3473 | 23'20'50'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-13 | China | China Telecom Guangxi | Completed | China | 2582564 |  | 245006651 | Completed | CTGXLTE1.8Gproject-桂平社坡镇禄全村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPShePoZhenLuQuanCunN-桂平社坡镇禄全村南\GPShePoZhenLuQuanCunN2100O-桂平社坡镇禄全村南2100O |  | Radio Site | GPShePoZhenLuQuanCunN2100O | 桂平社坡镇禄全村南2100O_1 | GPShePoZhenLuQuanCunN2100O-桂平社坡镇禄全村南2100O | 245012541 |  |  | Nanning | China | Draft | 桂平社坡镇禄全村南 | 110.1985 | 110'11'55' | 23.3471 | 23'20'49'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-14 | China | China Telecom Guangxi | Completed | China | 2582565 |  | 245006655 | Completed | CTGXLTE1.8Gproject-桂平西山镇长安村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenZhangAnC-桂平西山镇长安村\GPXiShanZhenZhangAnC2100O-桂平西山镇长安村2100O |  | Radio Site | GPXiShanZhenZhangAnC2100O | 桂平西山镇长安村2100O_1 | GPXiShanZhenZhangAnC2100O-桂平西山镇长安村2100O | 245012533 |  |  | Nanning | China | Draft | 桂平西山镇长安村高铁高铁沿线 | 110.0913 | 110'5'29' | 23.3078 | 23'18'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-12 | China | China Telecom Guangxi | Completed | China | 2582566 |  | 245006652 | Completed | CTGXLTE1.8Gproject-桂平木乐镇新莲村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenXinLianCGT-桂平木乐镇新莲村高铁\GPMuLeZhenXinLianCGT2100O-桂平木乐镇新莲村高铁2100O |  | Radio Site | GPMuLeZhenXinLianCGT2100O | 桂平木乐镇新莲村高铁2100O_1 | GPMuLeZhenXinLianCGT2100O-桂平木乐镇新莲村高铁2100O | 245012527 |  |  | Nanning | China | Draft | 桂平木乐镇新莲村附近山头 | 110.3597 | 110'21'35' | 23.4131 | 23'24'47'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-10 | China | China Telecom Guangxi | Completed | China | 2582567 |  | 245006654 | Completed | CTGXLTE1.8Gproject-桂平白沙镇龙门工业园大岭2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenLMGYYDL-桂平白沙镇龙门工业园大岭\GPBaiShaZhenLMGYYDL2100O-桂平白沙镇龙门工业园大岭2100O |  | Radio Site | GPBaiShaZhenLMGYYDL2100O | 桂平白沙镇龙门工业园大岭2100O_1 | GPBaiShaZhenLMGYYDL2100O-桂平白沙镇龙门工业园大岭2100O | 245012542 |  |  | Nanning | China | Draft | 桂平白沙工业园高铁沿线 | 109.9728 | 109'58'22' | 23.2581 | 23'15'29'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-12 | China | China Telecom Guangxi | Completed | China | 2582568 |  | 245006653 | Completed | CTGXLTE1.8Gproject-桂平木乐镇松林2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPMuLeZhenSongLin-桂平木乐镇松林\GPMuLeZhenSongLin2100O-桂平木乐镇松林2100O |  | Radio Site | GPMuLeZhenSongLin2100O | 桂平木乐镇松林2100O_1 | GPMuLeZhenSongLin2100O-桂平木乐镇松林2100O | 245012531 |  |  | Nanning | China | Draft | 桂平木乐镇松林 | 110.3382 | 110'20'17' | 23.405 | 23'24'17'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-11 | China | China Telecom Guangxi | Completed | China | 2582569 |  | 245006657 | Completed | CTGXLTE1.8Gproject-桂平厚禄乡峡口村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPHouLuXiangXiaKouCGT-桂平厚禄乡峡口村高铁\GPHouLuXiangXiaKouCGT2100O-桂平厚禄乡峡口村高铁2100O |  | Radio Site | GPHouLuXiangXiaKouCGT2100O | 桂平厚禄乡峡口村高铁2100O_1 | GPHouLuXiangXiaKouCGT2100O-桂平厚禄乡峡口村高铁2100O | 245012539 |  |  | Nanning | China | Draft | 桂平厚禄乡峡口村高铁路边 | 109.8294 | 109'49'46' | 23.1994 | 23'11'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-10 | China | China Telecom Guangxi | Completed | China | 2582570 |  | 245006660 | Completed | CTGXLTE1.8Gproject-桂平白沙镇思建村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenSiJianCGT-桂平白沙镇思建村高铁\GPBaiShaZhenSiJianCGT2100O-桂平白沙镇思建村高铁2100O |  | Radio Site | GPBaiShaZhenSiJianCGT2100O | 桂平白沙镇思建村高铁2100O_1 | GPBaiShaZhenSiJianCGT2100O-桂平白沙镇思建村高铁2100O | 245012536 |  |  | Nanning | China | Draft | 桂平白沙镇思建村高铁沿线 | 109.8967 | 109'53'48' | 23.2145 | 23'12'52'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-14 | China | China Telecom Guangxi | Completed | China | 2582571 |  | 245006658 | Completed | CTGXLTE1.8Gproject-桂平西山镇白竹山2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenBaiZhuShan-桂平西山镇白竹山\GPXiShanZhenBaiZhuShan2100O-桂平西山镇白竹山2100O |  | Radio Site | GPXiShanZhenBaiZhuShan2100O | 桂平西山镇白竹山2100O_1 | GPXiShanZhenBaiZhuShan2100O-桂平西山镇白竹山2100O | 245012528 |  |  | Nanning | China | Draft | 桂平市西山镇白竹山往东南方向高铁旁 | 110.0812 | 110'4'52' | 23.3047 | 23'18'16'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-10 | China | China Telecom Guangxi | Completed | China | 2582572 |  | 245006656 | Completed | CTGXLTE1.8Gproject-桂平白沙镇龙井高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenLongJGT-桂平白沙镇龙井高铁\GPBaiShaZhenLongJGT2100O-桂平白沙镇龙井高铁2100O |  | Radio Site | GPBaiShaZhenLongJGT2100O | 桂平白沙镇龙井高铁2100O_1 | GPBaiShaZhenLongJGT2100O-桂平白沙镇龙井高铁2100O | 245012544 |  |  | Nanning | China | Draft | 桂平白沙龙井村南边高铁农田处 | 109.8803 | 109'52'49' | 23.2103 | 23'12'37'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-11 | China | China Telecom Guangxi | Completed | China | 2582573 |  | 245006662 | Completed | CTGXLTE1.8Gproject-桂平厚禄乡上蔚村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPHouLuXiangShangWCGT-桂平厚禄乡上蔚村高铁\GPHouLuXiangShangWCGT2100O-桂平厚禄乡上蔚村高铁2100O |  | Radio Site | GPHouLuXiangShangWCGT2100O | 桂平厚禄乡上蔚村高铁2100O_1 | GPHouLuXiangShangWCGT2100O-桂平厚禄乡上蔚村高铁2100O | 245012535 |  |  | Nanning | China | Draft | 桂平厚禄乡上蔚村高铁山坡旁 | 109.8686 | 109'52'7' | 23.208 | 23'12'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-14 | China | China Telecom Guangxi | Completed | China | 2582574 |  | 245006661 | Completed | CTGXLTE1.8Gproject-桂平西山镇桥头岭高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiShanZhenQiaoTLGT-桂平西山镇桥头岭高铁\GPXiShanZhenQiaoTLGT2100O-桂平西山镇桥头岭高铁2100O |  | Radio Site | GPXiShanZhenQiaoTLGT2100O | 桂平西山镇桥头岭高铁2100O_1 | GPXiShanZhenQiaoTLGT2100O-桂平西山镇桥头岭高铁2100O | 245012543 |  |  | Nanning | China | Draft | 桂平桥头岭附近 | 110.0974 | 110'5'51' | 23.3117 | 23'18'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-13 | China | China Telecom Guangxi | Completed | China | 2582575 |  | 245006664 | Completed | CTGXLTE1.8Gproject-桂平下湾镇贝团村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXiaWanZhenBeiTCGT-桂平下湾镇贝团村高铁\GPXiaWanZhenBeiTCGT2100O-桂平下湾镇贝团村高铁2100O |  | Radio Site | GPXiaWanZhenBeiTCGT2100O | 桂平下湾镇贝团村高铁2100O_1 | GPXiaWanZhenBeiTCGT2100O-桂平下湾镇贝团村高铁2100O | 245012529 |  |  | Nanning | China | Draft | 桂平贝团村高铁附近 | 110.0095 | 110'0'34' | 23.2783 | 23'16'41'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-15 | China | China Telecom Guangxi | Completed | China | 2582576 |  | 245006663 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡峡岭村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangXiaLC-桂平寻旺乡峡岭村\GPXunWangXiangXiaLC2100O-桂平寻旺乡峡岭村2100O |  | Radio Site | GPXunWangXiangXiaLC2100O | 桂平寻旺乡峡岭村2100O_1 | GPXunWangXiangXiaLC2100O-桂平寻旺乡峡岭村2100O | 245012569 |  |  | Nanning | China | Draft | 桂平寻旺乡峡岭村山坡高铁旁 | 110.1774 | 110'10'39' | 23.3444 | 23'20'39'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-09 | China | China Telecom Guangxi | Completed | China | 2582577 |  | 245006665 | Completed | CTGXLTE1.8Gproject-贵港覃塘镇六务村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGQinTangZhenLiuWuCun-贵港覃塘镇六务村\GGQinTangZhenLiuWuCun2100O-贵港覃塘镇六务村2100O |  | Radio Site | GGQinTangZhenLiuWuCun2100O | 贵港覃塘镇六务村2100O_1 | GGQinTangZhenLiuWuCun2100O-贵港覃塘镇六务村2100O | 245012532 |  |  | Nanning | China | Draft | 贵港市覃塘区覃塘镇六务村东南方向距离六务小学约212米山顶 | 109.4552 | 109'27'19' | 23.1338 | 23'8'1'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-07 | China | China Telecom Guangxi | Completed | China | 2582578 |  | 245006667 | Completed | CTGXLTE1.8Gproject-贵港黄练峡2100O | CTGXLTE1.8Gproject |  |  | \Locations\GGHuangLianXia-贵港黄练峡\GGHuangLianXia2100O-贵港黄练峡2100O |  | Radio Site | GGHuangLianXia2100O | 贵港黄练峡2100O_1 | GGHuangLianXia2100O-贵港黄练峡2100O | 245012537 |  |  | Nanning | China | Draft | 贵港市覃塘区黄练镇平寨村东北方向约2.36公里 | 109.3436 | 109'20'37' | 23.1703 | 23'10'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-22 | China | China Telecom Guangxi | Completed | China | 2582579 |  | 245006672 | Completed | CTGXLTE1.8Gproject-宾阳黎塘镇局塘高铁3-12100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangZhenJuTGT3-1-宾阳黎塘镇局塘高铁3-1\NNBYLiTangZhenJuTGT3-12100O-宾阳黎塘镇局塘高铁3-12100O |  | Radio Site | NNBYLiTangZhenJuTGT3-12100O | 宾阳黎塘镇局塘高铁3-12100O_1 | NNBYLiTangZhenJuTGT3-12100O-宾阳黎塘镇局塘高铁3-12100O | 245012570 |  |  | Nanning | China | Draft | 宾阳黎塘镇局塘高铁3-1 | 109.0714 | 109'4'17' | 23.2044 | 23'12'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-14 | China | China Telecom Guangxi | Completed | China | 2582580 |  | 245006671 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡高岭水湾村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangGaoLSWC-桂平寻旺乡高岭水湾村\GPXunWangXiangGaoLSWC2100O-桂平寻旺乡高岭水湾村2100O |  | Radio Site | GPXunWangXiangGaoLSWC2100O | 桂平寻旺乡高岭水湾村2100O_1 | GPXunWangXiangGaoLSWC2100O-桂平寻旺乡高岭水湾村2100O | 245012565 |  |  | Nanning | China | Draft | 寻旺乡高岭水湾村附近山坡 | 110.1601 | 110'9'36' | 23.3375 | 23'20'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-10 | China | China Telecom Guangxi | Completed | China | 2582581 |  | 245006670 | Completed | CTGXLTE1.8Gproject-桂平白沙镇满堂村2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPBaiShaZhenManTangC-桂平白沙镇满堂村\GPBaiShaZhenManTangC2100O-桂平白沙镇满堂村2100O |  | Radio Site | GPBaiShaZhenManTangC2100O | 桂平白沙镇满堂村2100O_1 | GPBaiShaZhenManTangC2100O-桂平白沙镇满堂村2100O | 245012563 |  |  | Nanning | China | Draft | 桂平白沙满堂村附近土坡 | 109.9357 | 109'56'8' | 23.2285 | 23'13'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-20 | China | China Telecom Guangxi | Completed | China | 2582582 |  | 245006678 | Completed | CTGXLTE1.8Gproject-宾阳黎塘龙胜谢村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangLongShengXieC-宾阳黎塘龙胜谢村\NNBYLiTangLongShengXieC2100O-宾阳黎塘龙胜谢村2100O |  | Radio Site | NNBYLiTangLongShengXieC2100O | 宾阳黎塘龙胜谢村2100O_1 | NNBYLiTangLongShengXieC2100O-宾阳黎塘龙胜谢村2100O | 245012564 |  |  | Nanning | China | Draft | 宾阳黎塘龙胜谢村 | 109.0799 | 109'4'48' | 23.2129 | 23'12'46'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-15 | China | China Telecom Guangxi | Completed | China | 2582583 |  | 245007283 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡屋岭村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangWuLCGT-桂平寻旺乡屋岭村高铁\GPXunWangXiangWuLCGT2100O-桂平寻旺乡屋岭村高铁2100O |  | Radio Site | GPXunWangXiangWuLCGT2100O | 桂平寻旺乡屋岭村高铁2100O_1 | GPXunWangXiangWuLCGT2100O-桂平寻旺乡屋岭村高铁2100O | 245012575 |  |  | Nanning | China | Draft | 寻旺乡屋岭村高铁附近 | 110.1486 | 110'8'55' | 23.3332 | 23'19'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-25 | China | China Telecom Guangxi | Completed | China | 2582584 |  | 245007285 | Completed | CTGXLTE1.8Gproject-宾阳中华三军三山隧道口东2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZhongHuaSanJunSSSDKD-宾阳中华三军三山隧道口东\NNBYZhongHuaSanJunSSSDKD2100O-宾阳中华三军三山隧道口东2100O |  | Radio Site | NNBYZhongHuaSanJunSSSDKD2100O | 宾阳中华三军三山隧道口东2100O_1 | NNBYZhongHuaSanJunSSSDKD2100O-宾阳中华三军三山隧道口东2100O | 245012578 |  |  | Nanning | China | Draft | 宾阳中华三军三山隧道口东 | 108.9019 | 108'54'7' | 23.0637 | 23'3'49'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-25 | China | China Telecom Guangxi | Completed | China | 2582585 |  | 245007284 | Completed | CTGXLTE1.8Gproject-宾阳中华三新村隧道口2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZhongHuaSanXinCunSDK-宾阳中华三新村隧道口\NNBYZhongHuaSanXinCunSDK2100O-宾阳中华三新村隧道口2100O |  | Radio Site | NNBYZhongHuaSanXinCunSDK2100O | 宾阳中华三新村隧道口2100O_1 | NNBYZhongHuaSanXinCunSDK2100O-宾阳中华三新村隧道口2100O | 245012568 |  |  | Nanning | China | Draft | 宾阳中华三新村隧道口 | 108.9174 | 108'55'3' | 23.0676 | 23'4'3'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-22 | China | China Telecom Guangxi | Completed | China | 2582586 |  | 245007286 | Completed | CTGXLTE1.8Gproject-宾阳黎塘镇宾阳高铁站广场路灯塔2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangZhenBYGTZGCLDT-宾阳黎塘镇宾阳高铁站广场路灯塔\NNBYLiTangZhenBYGTZGCLDT2100O-宾阳黎塘镇宾阳高铁站广场路灯塔2100O |  | Radio Site | NNBYLiTangZhenBYGTZGCLDT2100O | 宾阳黎塘镇宾阳高铁站广场路灯塔2100O_1 | NNBYLiTangZhenBYGTZGCLDT2100O-宾阳黎塘镇宾阳高铁站广场路灯塔2100O | 245012566 |  |  | Nanning | China | Draft | 宾阳黎塘镇宾阳高铁站广场路灯塔 | 109.0896 | 109'5'23' | 23.2173 | 23'13'2'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-18 | China | China Telecom Guangxi | Completed | China | 2582587 |  | 245007287 | Completed | CTGXLTE1.8Gproject-宾阳古辣镇义陈初中旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaZhenYiChenChuZP-宾阳古辣镇义陈初中旁\NNBYGuLaZhenYiChenChuZP2100O-宾阳古辣镇义陈初中旁2100O |  | Radio Site | NNBYGuLaZhenYiChenChuZP2100O | 宾阳古辣镇义陈初中旁2100O_1 | NNBYGuLaZhenYiChenChuZP2100O-宾阳古辣镇义陈初中旁2100O | 245012574 |  |  | Nanning | China | Draft | 宾阳古辣镇义陈初中旁 | 108.9795 | 108'58'46' | 23.1145 | 23'6'52'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-16 | China | China Telecom Guangxi | Completed | China | 2582588 |  | 245007289 | Completed | CTGXLTE1.8Gproject-宾阳陈平南阳村隧道口东2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYChenPingNanYangCSDKD-宾阳陈平南阳村隧道口东\NNBYChenPingNanYangCSDKD2100O-宾阳陈平南阳村隧道口东2100O |  | Radio Site | NNBYChenPingNanYangCSDKD2100O | 宾阳陈平南阳村隧道口东2100O_1 | NNBYChenPingNanYangCSDKD2100O-宾阳陈平南阳村隧道口东2100O | 245012567 |  |  | Nanning | China | Draft | 宾阳陈平南阳村隧道口东 | 108.8188 | 108'49'8' | 23.0216 | 23'1'17'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-22 | China | China Telecom Guangxi | Completed | China | 2582589 |  | 245007288 | Completed | CTGXLTE1.8Gproject-宾阳南柳高铁那适隧道口东2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYNanLiuGaoTieNaSSDKD-宾阳南柳高铁那适隧道口东\NNBYNanLiuGaoTieNaSSDKD2100O-宾阳南柳高铁那适隧道口东2100O |  | Radio Site | NNBYNanLiuGaoTieNaSSDKD2100O | 宾阳南柳高铁那适隧道口东2100O_1 | NNBYNanLiuGaoTieNaSSDKD2100O-宾阳南柳高铁那适隧道口东2100O | 245012579 |  |  | Nanning | China | Draft | 宾阳南柳高铁那适隧道口东 | 108.8114 | 108'48'41' | 23.0153 | 23'0'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-18 | China | China Telecom Guangxi | Completed | China | 2582590 |  | 245007291 | Completed | CTGXLTE1.8Gproject-宾阳和吉良元村东高铁旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiLiangYuanCDGTP-宾阳和吉良元村东高铁旁\NNBYHeJiLiangYuanCDGTP2100O-宾阳和吉良元村东高铁旁2100O |  | Radio Site | NNBYHeJiLiangYuanCDGTP2100O | 宾阳和吉良元村东高铁旁2100O_1 | NNBYHeJiLiangYuanCDGTP2100O-宾阳和吉良元村东高铁旁2100O | 245012577 |  |  | Nanning | China | Draft | 宾阳和吉良元村东高铁旁 | 109.184 | 109'11'2' | 23.229 | 23'13'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-21 | China | China Telecom Guangxi | Completed | China | 2582591 |  | 245007293 | Completed | CTGXLTE1.8Gproject-宾阳黎塘新陈村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangXinChenCun-宾阳黎塘新陈村\NNBYLiTangXinChenCun2100O-宾阳黎塘新陈村2100O |  | Radio Site | NNBYLiTangXinChenCun2100O | 宾阳黎塘新陈村2100O_1 | NNBYLiTangXinChenCun2100O-宾阳黎塘新陈村2100O | 245012580 |  |  | Nanning | China | Draft | 宾阳黎塘新陈村 | 109.1016 | 109'6'6' | 23.2352 | 23'14'6'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-16 | China | China Telecom Guangxi | Completed | China | 2582592 |  | 245007290 | Completed | CTGXLTE1.8Gproject-宾阳陈平乡金坑村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYChenPingXiangJinKCN-宾阳陈平乡金坑村南\NNBYChenPingXiangJinKCN2100O-宾阳陈平乡金坑村南2100O |  | Radio Site | NNBYChenPingXiangJinKCN2100O | 宾阳陈平乡金坑村南2100O_1 | NNBYChenPingXiangJinKCN2100O-宾阳陈平乡金坑村南2100O | 245012572 |  |  | Nanning | China | Draft | 宾阳陈平乡金坑村南 | 108.8005 | 108'48'2' | 23.0122 | 23'0'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-16 | China | China Telecom Guangxi | Completed | China | 2582593 |  | 245007295 | Completed | CTGXLTE1.8Gproject-宾阳陈平长田村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYChenPingChangTianCGT-宾阳陈平长田村高铁\NNBYChenPingChangTianCGT2100O-宾阳陈平长田村高铁2100O |  | Radio Site | NNBYChenPingChangTianCGT2100O | 宾阳陈平长田村高铁2100O_1 | NNBYChenPingChangTianCGT2100O-宾阳陈平长田村高铁2100O | 245012571 |  |  | Nanning | China | Draft | 宾阳陈平长田村高铁 | 108.8407 | 108'50'26' | 23.0326 | 23'1'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-24 | China | China Telecom Guangxi | Completed | China | 2582594 |  | 245007296 | Completed | CTGXLTE1.8Gproject-宾阳中华三军里仁村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYZhongHuaSanJunLiRenC-宾阳中华三军里仁村\NNBYZhongHuaSanJunLiRenC2100O-宾阳中华三军里仁村2100O |  | Radio Site | NNBYZhongHuaSanJunLiRenC2100O | 宾阳中华三军里仁村2100O_1 | NNBYZhongHuaSanJunLiRenC2100O-宾阳中华三军里仁村2100O | 245012601 |  |  | Nanning | China | Draft | 宾阳中华三军里仁村 | 108.9435 | 108'56'37' | 23.0847 | 23'5'4'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-19 | China | China Telecom Guangxi | Completed | China | 2582595 |  | 245007294 | Completed | CTGXLTE1.8Gproject-宾阳和吉三民村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiSanMinCun-宾阳和吉三民村\NNBYHeJiSanMinCun2100O-宾阳和吉三民村2100O |  | Radio Site | NNBYHeJiSanMinCun2100O | 宾阳和吉三民村2100O_1 | NNBYHeJiSanMinCun2100O-宾阳和吉三民村2100O | 245012576 |  |  | Nanning | China | Draft | 宾阳和吉三民村 | 109.1279 | 109'7'41' | 23.2553 | 23'15'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-20 | China | China Telecom Guangxi | Completed | China | 2582596 |  | 245007299 | Completed | CTGXLTE1.8Gproject-宾阳黎塘凤鸣村大塘林场2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangFengMingCDTLC-宾阳黎塘凤鸣村大塘林场\NNBYLiTangFengMingCDTLC2100O-宾阳黎塘凤鸣村大塘林场2100O |  | Radio Site | NNBYLiTangFengMingCDTLC2100O | 宾阳黎塘凤鸣村大塘林场2100O_1 | NNBYLiTangFengMingCDTLC2100O-宾阳黎塘凤鸣村大塘林场2100O | 245012603 |  |  | Nanning | China | Draft | 宾阳黎塘凤鸣村大塘林场 | 109.1985 | 109'11'54' | 23.2209 | 23'13'15'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-17 | China | China Telecom Guangxi | Completed | China | 2582597 |  | 245007298 | Completed | CTGXLTE1.8Gproject-宾阳古辣平南村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaPingNanCunGaoTie-宾阳古辣平南村高铁\NNBYGuLaPingNanCunGaoTie2100O-宾阳古辣平南村高铁2100O |  | Radio Site | NNBYGuLaPingNanCunGaoTie2100O | 宾阳古辣平南村高铁2100O_1 | NNBYGuLaPingNanCunGaoTie2100O-宾阳古辣平南村高铁2100O | 245012608 |  |  | Nanning | China | Draft | 宾阳古辣平南村高铁 | 108.9631 | 108'57'47' | 23.1026 | 23'6'9'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-24 | China | China Telecom Guangxi | Completed | China | 2582598 |  | 245007297 | Completed | CTGXLTE1.8Gproject-宾阳洋桥镇宾岭村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYYangQiaoZhenBinLingC-宾阳洋桥镇宾岭村\NNBYYangQiaoZhenBinLingC2100O-宾阳洋桥镇宾岭村2100O |  | Radio Site | NNBYYangQiaoZhenBinLingC2100O | 宾阳洋桥镇宾岭村2100O_1 | NNBYYangQiaoZhenBinLingC2100O-宾阳洋桥镇宾岭村2100O | 245012600 |  |  | Nanning | China | Draft | 宾阳洋桥镇宾岭村 | 109.142 | 109'8'31' | 23.2395 | 23'14'22'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-18 | China | China Telecom Guangxi | Completed | China | 2582599 |  | 245007302 | Completed | CTGXLTE1.8Gproject-宾阳和吉良元村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiLiangYuanCun-宾阳和吉良元村\NNBYHeJiLiangYuanCun2100O-宾阳和吉良元村2100O |  | Radio Site | NNBYHeJiLiangYuanCun2100O | 宾阳和吉良元村2100O_1 | NNBYHeJiLiangYuanCun2100O-宾阳和吉良元村2100O | 245012616 |  |  | Nanning | China | Draft | 宾阳和吉良元村 | 109.174 | 109'10'27' | 23.2341 | 23'14'2'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-17 | China | China Telecom Guangxi | Completed | China | 2582600 |  | 245007304 | Completed | CTGXLTE1.8Gproject-宾阳古辣马界甘村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaMaJieGanCun-宾阳古辣马界甘村\NNBYGuLaMaJieGanCun2100O-宾阳古辣马界甘村2100O |  | Radio Site | NNBYGuLaMaJieGanCun2100O | 宾阳古辣马界甘村2100O_1 | NNBYGuLaMaJieGanCun2100O-宾阳古辣马界甘村2100O | 245012607 |  |  | Nanning | China | Draft | 宾阳古辣马界甘村 | 108.951 | 108'57'3' | 23.0907 | 23'5'26'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-17 | China | China Telecom Guangxi | Completed | China | 2582601 |  | 245007307 | Completed | CTGXLTE1.8Gproject-宾阳古辣新胜村铁路边三管塔2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaXinShengCTLBSGT-宾阳古辣新胜村铁路边三管塔\NNBYGuLaXinShengCTLBSGT2100O-宾阳古辣新胜村铁路边三管塔2100O |  | Radio Site | NNBYGuLaXinShengCTLBSGT2100O | 宾阳古辣新胜村铁路边三管塔2100O_1 | NNBYGuLaXinShengCTLBSGT2100O-宾阳古辣新胜村铁路边三管塔2100O | 245012605 |  |  | Nanning | China | Draft | 宾阳古辣新胜村铁路边三管塔 | 108.9993 | 108'59'57' | 23.1327 | 23'7'57'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-18 | China | China Telecom Guangxi | Completed | China | 2582602 |  | 245007915 | Completed | CTGXLTE1.8Gproject-宾阳古辣镇西侧高铁旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaZhenXiCeGaoTieP-宾阳古辣镇西侧高铁旁\NNBYGuLaZhenXiCeGaoTieP2100O-宾阳古辣镇西侧高铁旁2100O |  | Radio Site | NNBYGuLaZhenXiCeGaoTieP2100O | 宾阳古辣镇西侧高铁旁2100O_1 | NNBYGuLaZhenXiCeGaoTieP2100O-宾阳古辣镇西侧高铁旁2100O | 245012602 |  |  | Nanning | China | Draft | 宾阳古辣镇西侧高铁旁 | 108.9712 | 108'58'16' | 23.1121 | 23'6'43'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-17 | China | China Telecom Guangxi | Completed | China | 2582603 |  | 245007917 | Completed | CTGXLTE1.8Gproject-宾阳古辣梨园村东北2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaLiYuanCunDongBei-宾阳古辣梨园村东北\NNBYGuLaLiYuanCunDongBei2100O-宾阳古辣梨园村东北2100O |  | Radio Site | NNBYGuLaLiYuanCunDongBei2100O | 宾阳古辣梨园村东北2100O_1 | NNBYGuLaLiYuanCunDongBei2100O-宾阳古辣梨园村东北2100O | 245012614 |  |  | Nanning | China | Draft | 宾阳古辣梨园村东北 | 108.9854 | 108'59'7' | 23.1231 | 23'7'23'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-19 | China | China Telecom Guangxi | Completed | China | 2582604 |  | 245007916 | Completed | CTGXLTE1.8Gproject-宾阳和吉三民石灰村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiSanMinShiHuiC-宾阳和吉三民石灰村\NNBYHeJiSanMinShiHuiC2100O-宾阳和吉三民石灰村2100O |  | Radio Site | NNBYHeJiSanMinShiHuiC2100O | 宾阳和吉三民石灰村2100O_1 | NNBYHeJiSanMinShiHuiC2100O-宾阳和吉三民石灰村2100O | 245012611 |  |  | Nanning | China | Draft | 宾阳和吉三民石灰村 | 109.1309 | 109'7'51' | 23.2757 | 23'16'32'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-19 | China | China Telecom Guangxi | Completed | China | 2582605 |  | 245007920 | Completed | CTGXLTE1.8Gproject-宾阳和吉新冯村北2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiXinFengCunBei-宾阳和吉新冯村北\NNBYHeJiXinFengCunBei2100O-宾阳和吉新冯村北2100O |  | Radio Site | NNBYHeJiXinFengCunBei2100O | 宾阳和吉新冯村北2100O_1 | NNBYHeJiXinFengCunBei2100O-宾阳和吉新冯村北2100O | 245012613 |  |  | Nanning | China | Draft | 宾阳和吉新冯村北 | 109.1295 | 109'7'46' | 23.2987 | 23'17'55'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-19 | China | China Telecom Guangxi | Completed | China | 2582606 |  | 245007918 | Completed | CTGXLTE1.8Gproject-宾阳和吉新陈村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiXinChenCunGaoTie-宾阳和吉新陈村高铁\NNBYHeJiXinChenCunGaoTie2100O-宾阳和吉新陈村高铁2100O |  | Radio Site | NNBYHeJiXinChenCunGaoTie2100O | 宾阳和吉新陈村高铁2100O_1 | NNBYHeJiXinChenCunGaoTie2100O-宾阳和吉新陈村高铁2100O | 245012612 |  |  | Nanning | China | Draft | 宾阳和吉新陈村高铁 | 109.1142 | 109'6'51' | 23.2401 | 23'14'24'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-20 | China | China Telecom Guangxi | Completed | China | 2582607 |  | 245007919 | Completed | CTGXLTE1.8Gproject-宾阳黎塘马香村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangMaXiangCun-宾阳黎塘马香村\NNBYLiTangMaXiangCun2100O-宾阳黎塘马香村2100O |  | Radio Site | NNBYLiTangMaXiangCun2100O | 宾阳黎塘马香村2100O_1 | NNBYLiTangMaXiangCun2100O-宾阳黎塘马香村2100O | 245012610 |  |  | Nanning | China | Draft | 宾阳黎塘马香村 | 109.1245 | 109'7'28' | 23.241 | 23'14'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-23 | China | China Telecom Guangxi | Completed | China | 2582608 |  | 245007924 | Completed | CTGXLTE1.8Gproject-宾阳南柳王灵2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYNanLiuWangLing-宾阳南柳王灵\NNBYNanLiuWangLing2100O-宾阳南柳王灵2100O |  | Radio Site | NNBYNanLiuWangLing2100O | 宾阳南柳王灵2100O_1 | NNBYNanLiuWangLing2100O-宾阳南柳王灵2100O | 245012642 |  |  | Nanning | China | Draft | 宾阳南柳王灵 | 109.0538 | 109'3'14' | 23.1784 | 23'10'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-21 | China | China Telecom Guangxi | Completed | China | 2582609 |  | 245007922 | Completed | CTGXLTE1.8Gproject-宾阳黎塘水美村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangShuiMeiCun-宾阳黎塘水美村\NNBYLiTangShuiMeiCun2100O-宾阳黎塘水美村2100O |  | Radio Site | NNBYLiTangShuiMeiCun2100O | 宾阳黎塘水美村2100O_1 | NNBYLiTangShuiMeiCun2100O-宾阳黎塘水美村2100O | 245012609 |  |  | Nanning | China | Draft | 宾阳黎塘水美村 | 109.0933 | 109'5'36' | 23.2239 | 23'13'25'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-24 | China | China Telecom Guangxi | Completed | China | 2582610 |  | 245007926 | Completed | CTGXLTE1.8Gproject-宾阳王灵秀山横寨村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingXiuShanHZC-宾阳王灵秀山横寨村\NNBYWangLingXiuShanHZC2100O-宾阳王灵秀山横寨村2100O |  | Radio Site | NNBYWangLingXiuShanHZC2100O | 宾阳王灵秀山横寨村2100O_1 | NNBYWangLingXiuShanHZC2100O-宾阳王灵秀山横寨村2100O | 245012617 |  |  | Nanning | China | Draft | 宾阳王灵秀山横寨村 | 109.041 | 109'2'28' | 23.1703 | 23'10'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-23 | China | China Telecom Guangxi | Completed | China | 2582611 |  | 245007923 | Completed | CTGXLTE1.8Gproject-宾阳王灵六队农场高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingLiuDuiNCGT-宾阳王灵六队农场高铁\NNBYWangLingLiuDuiNCGT2100O-宾阳王灵六队农场高铁2100O |  | Radio Site | NNBYWangLingLiuDuiNCGT2100O | 宾阳王灵六队农场高铁2100O_1 | NNBYWangLingLiuDuiNCGT2100O-宾阳王灵六队农场高铁2100O | 245012654 |  |  | Nanning | China | Draft | 宾阳王灵六队农场高铁 | 109.0614 | 109'3'41' | 23.1922 | 23'11'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-17 | China | China Telecom Guangxi | Completed | China | 2582612 |  | 245007928 | Completed | CTGXLTE1.8Gproject-宾阳古辣马安村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYGuLaMaAnCunGaoTie-宾阳古辣马安村高铁\NNBYGuLaMaAnCunGaoTie2100O-宾阳古辣马安村高铁2100O |  | Radio Site | NNBYGuLaMaAnCunGaoTie2100O | 宾阳古辣马安村高铁2100O_1 | NNBYGuLaMaAnCunGaoTie2100O-宾阳古辣马安村高铁2100O | 245012615 |  |  | Nanning | China | Draft | 宾阳古辣马安村高铁 | 109.0091 | 109'0'33' | 23.1405 | 23'8'25'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-23 | China | China Telecom Guangxi | Completed | China | 2582613 |  | 245007925 | Completed | CTGXLTE1.8Gproject-宾阳王灵横寨村小学旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingHengZCXXP-宾阳王灵横寨村小学旁\NNBYWangLingHengZCXXP2100O-宾阳王灵横寨村小学旁2100O |  | Radio Site | NNBYWangLingHengZCXXP2100O | 宾阳王灵横寨村小学旁2100O_1 | NNBYWangLingHengZCXXP2100O-宾阳王灵横寨村小学旁2100O | 245012604 |  |  | Nanning | China | Draft | 宾阳王灵横寨村小学旁 | 109.0315 | 109'1'53' | 23.1623 | 23'9'44'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-22 | China | China Telecom Guangxi | Completed | China | 2582614 |  | 245007929 | Completed | CTGXLTE1.8Gproject-宾阳南柳福平2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYNanLiuFuPing-宾阳南柳福平\NNBYNanLiuFuPing2100O-宾阳南柳福平2100O |  | Radio Site | NNBYNanLiuFuPing2100O | 宾阳南柳福平2100O_1 | NNBYNanLiuFuPing2100O-宾阳南柳福平2100O | 245012649 |  |  | Nanning | China | Draft | 宾阳南柳福平 | 108.8784 | 108'52'42' | 23.0534 | 23'3'12'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-23 | China | China Telecom Guangxi | Completed | China | 2582615 |  | 245007921 | Completed | CTGXLTE1.8Gproject-宾阳王灵秀山洪水村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWangLingXiuShanHSC-宾阳王灵秀山洪水村\NNBYWangLingXiuShanHSC2100O-宾阳王灵秀山洪水村2100O |  | Radio Site | NNBYWangLingXiuShanHSC2100O | 宾阳王灵秀山洪水村2100O_1 | NNBYWangLingXiuShanHSC2100O-宾阳王灵秀山洪水村2100O | 245012606 |  |  | Nanning | China | Draft | 宾阳王灵秀山洪水村 | 109.0183 | 109'1'6' | 23.1514 | 23'9'5'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-23 | China | China Telecom Guangxi | Completed | China | 2582616 |  | 245007932 | Completed | CTGXLTE1.8Gproject-宾阳南柳三军村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYNanLiuSanJunCunNan-宾阳南柳三军村南\NNBYNanLiuSanJunCunNan2100O-宾阳南柳三军村南2100O |  | Radio Site | NNBYNanLiuSanJunCunNan2100O | 宾阳南柳三军村南2100O_1 | NNBYNanLiuSanJunCunNan2100O-宾阳南柳三军村南2100O | 245012643 |  |  | Nanning | China | Draft | 宾阳南柳三军村南 | 108.9301 | 108'55'48' | 23.0743 | 23'4'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-28 | China | China Telecom Guangxi | Completed | China | 2582617 |  | 245007930 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘王竹村那遇坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangWangZhuCNYP-南宁兴宁区五塘王竹村那遇坡\NNXNWuTangWangZhuCNYP2100O-南宁兴宁区五塘王竹村那遇坡2100O |  | Radio Site | NNXNWuTangWangZhuCNYP2100O | 南宁兴宁区五塘王竹村那遇坡2100O_1 | NNXNWuTangWangZhuCNYP2100O-南宁兴宁区五塘王竹村那遇坡2100O | 245012640 |  |  | Nanning | China | Draft | 南宁兴宁区五塘王竹村那遇坡 | 108.6597 | 108'39'35' | 22.9486 | 22'56'54'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-27 | China | China Telecom Guangxi | Completed | China | 2582618 |  | 245007931 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘栗村东高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiCunDGT-南宁兴宁区五塘栗村东高铁\NNXNWuTangLiCunDGT2100O-南宁兴宁区五塘栗村东高铁2100O |  | Radio Site | NNXNWuTangLiCunDGT2100O | 南宁兴宁区五塘栗村东高铁2100O_1 | NNXNWuTangLiCunDGT2100O-南宁兴宁区五塘栗村东高铁2100O | 245012651 |  |  | Nanning | China | Draft | 南宁兴宁区五塘栗村东高铁 | 108.6834 | 108'41'0' | 22.9618 | 22'57'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-28 | China | China Telecom Guangxi | Completed | China | 2582619 |  | 245007937 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘栗村南高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiCunNGT-南宁兴宁区五塘栗村南高铁\NNXNWuTangLiCunNGT2100O-南宁兴宁区五塘栗村南高铁2100O |  | Radio Site | NNXNWuTangLiCunNGT2100O | 南宁兴宁区五塘栗村南高铁2100O_1 | NNXNWuTangLiCunNGT2100O-南宁兴宁区五塘栗村南高铁2100O | 245012645 |  |  | Nanning | China | Draft | 南宁兴宁区五塘栗村南高铁 | 108.6752 | 108'40'31' | 22.9517 | 22'57'6'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-24 | China | China Telecom Guangxi | Completed | China | 2582620 |  | 245007938 | Completed | CTGXLTE1.8Gproject-宾阳武陵四才村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWuLingSiCaiCun-宾阳武陵四才村\NNBYWuLingSiCaiCun2100O-宾阳武陵四才村2100O |  | Radio Site | NNBYWuLingSiCaiCun2100O | 宾阳武陵四才村2100O_1 | NNBYWuLingSiCaiCun2100O-宾阳武陵四才村2100O | 245012646 |  |  | Nanning | China | Draft | 宾阳武陵四才村 | 108.8719 | 108'52'19' | 23.046 | 23'2'45'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582621 |  | 245008559 | Completed | CTGXLTE1.8Gproject-南宁兴宁区三塘六村宝盖坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNSanTangLiuCunBGP-南宁兴宁区三塘六村宝盖坡\NNXNSanTangLiuCunBGP2100O-南宁兴宁区三塘六村宝盖坡2100O |  | Radio Site | NNXNSanTangLiuCunBGP2100O | 南宁兴宁区三塘六村宝盖坡2100O_1 | NNXNSanTangLiuCunBGP2100O-南宁兴宁区三塘六村宝盖坡2100O | 245012638 |  |  | Nanning | China | Draft | 南宁兴宁区三塘六村宝盖坡 | 108.5367 | 108'32'12' | 22.8694 | 22'52'9'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-25 | China | China Telecom Guangxi | Completed | China | 2582622 |  | 245008562 | Completed | CTGXLTE1.8Gproject-南宁兴宁区三塘创新村新塘坡东高铁旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNSanTangCXCXTPDGTP-南宁兴宁区三塘创新村新塘坡东高铁旁\NNXNSanTangCXCXTPDGTP2100O-南宁兴宁区三塘创新村新塘坡东高铁旁2100O |  | Radio Site | NNXNSanTangCXCXTPDGTP2100O | 南宁兴宁区三塘创新村新塘坡东高铁旁2100O_1 | NNXNSanTangCXCXTPDGTP2100O-南宁兴宁区三塘创新村新塘坡东高铁旁2100O | 245012641 |  |  | Nanning | China | Draft | 南宁兴宁区三塘创新村新塘坡东高铁旁 | 108.4722 | 108'28'20' | 22.8545 | 22'51'16'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582623 |  | 245008560 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘陈屋村东北2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangChenWuCDB-南宁兴宁区五塘陈屋村东北\NNXNWuTangChenWuCDB2100O-南宁兴宁区五塘陈屋村东北2100O |  | Radio Site | NNXNWuTangChenWuCDB2100O | 南宁兴宁区五塘陈屋村东北2100O_1 | NNXNWuTangChenWuCDB2100O-南宁兴宁区五塘陈屋村东北2100O | 245012637 |  |  | Nanning | China | Draft | 南宁兴宁区五塘陈屋村东北 | 108.5615 | 108'33'41' | 22.8828 | 22'52'58'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-16 | China | China Telecom Guangxi | Completed | China | 2582624 |  | 245008561 | Completed | CTGXLTE1.8Gproject-南宁青秀区新塘村北高铁旁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NanNingQingXiuQuXTCBGTP-南宁青秀区新塘村北高铁旁\NanNingQingXiuQuXTCBGTP2100O-南宁青秀区新塘村北高铁旁2100O |  | Radio Site | NanNingQingXiuQuXTCBGTP2100O | 南宁青秀区新塘村北高铁旁2100O_1 | NanNingQingXiuQuXTCBGTP2100O-南宁青秀区新塘村北高铁旁2100O | 245012647 |  |  | Nanning | China | Draft | 南宁青秀区新塘村北高铁旁 | 108.4498 | 108'26'59' | 22.8474 | 22'50'50'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-27 | China | China Telecom Guangxi | Completed | China | 2582625 |  | 245008563 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘两山村上青坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiangShanCSQP-南宁兴宁区五塘两山村上青坡\NNXNWuTangLiangShanCSQP2100O-南宁兴宁区五塘两山村上青坡2100O |  | Radio Site | NNXNWuTangLiangShanCSQP2100O | 南宁兴宁区五塘两山村上青坡2100O_1 | NNXNWuTangLiangShanCSQP2100O-南宁兴宁区五塘两山村上青坡2100O | 245012644 |  |  | Nanning | China | Draft | 南宁兴宁区五塘两山村上青坡 | 108.6344 | 108'38'4' | 22.9285 | 22'55'42'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-27 | China | China Telecom Guangxi | Completed | China | 2582626 |  | 245008564 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘两山村下黄坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiangShanCXHP-南宁兴宁区五塘两山村下黄坡\NNXNWuTangLiangShanCXHP2100O-南宁兴宁区五塘两山村下黄坡2100O |  | Radio Site | NNXNWuTangLiangShanCXHP2100O | 南宁兴宁区五塘两山村下黄坡2100O_1 | NNXNWuTangLiangShanCXHP2100O-南宁兴宁区五塘两山村下黄坡2100O | 245012652 |  |  | Nanning | China | Draft | 南宁兴宁区五塘两山村下黄坡 | 108.6465 | 108'38'47' | 22.9385 | 22'56'18'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582627 |  | 245008565 | Completed | CTGXLTE1.8Gproject-南宁兴宁区三塘六村坛造坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNSanTangLiuCunTZP-南宁兴宁区三塘六村坛造坡\NNXNSanTangLiuCunTZP2100O-南宁兴宁区三塘六村坛造坡2100O |  | Radio Site | NNXNSanTangLiuCunTZP2100O | 南宁兴宁区三塘六村坛造坡2100O_1 | NNXNSanTangLiuCunTZP2100O-南宁兴宁区三塘六村坛造坡2100O | 245012639 |  |  | Nanning | China | Draft | 南宁兴宁区三塘六村坛造坡 | 108.5202 | 108'31'13' | 22.8657 | 22'51'56'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-27 | China | China Telecom Guangxi | Completed | China | 2582628 |  | 245008566 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘两山村中青坡2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiangSCZQP-南宁兴宁区五塘两山村中青坡\NNXNWuTangLiangSCZQP2100O-南宁兴宁区五塘两山村中青坡2100O |  | Radio Site | NNXNWuTangLiangSCZQP2100O | 南宁兴宁区五塘两山村中青坡2100O_1 | NNXNWuTangLiangSCZQP2100O-南宁兴宁区五塘两山村中青坡2100O | 245012653 |  |  | Nanning | China | Draft | 南宁兴宁区五塘两山村中青坡 | 108.6209 | 108'37'15' | 22.9166 | 22'54'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-28 | China | China Telecom Guangxi | Completed | China | 2582629 |  | 245008567 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘沙坪村坛碰隧道口西2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangShaPCTPSDKX-南宁兴宁区五塘沙坪村坛碰隧道口西\NNXNWuTangShaPCTPSDKX2100O-南宁兴宁区五塘沙坪村坛碰隧道口西2100O |  | Radio Site | NNXNWuTangShaPCTPSDKX2100O | 南宁兴宁区五塘沙坪村坛碰隧道口西2100O_1 | NNXNWuTangShaPCTPSDKX2100O-南宁兴宁区五塘沙坪村坛碰隧道口西2100O | 245012650 |  |  | Nanning | China | Draft | 南宁兴宁区五塘沙坪村坛碰隧道口西 | 108.6046 | 108'36'17' | 22.906 | 22'54'21'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-22 | China | China Telecom Guangxi | Completed | China | 2582630 |  | 245008571 | Completed | CTGXLTE1.8Gproject-宾阳六角村北2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiuJiaoCunBei-宾阳六角村北\NNBYLiuJiaoCunBei2100O-宾阳六角村北2100O |  | Radio Site | NNBYLiuJiaoCunBei2100O | 宾阳六角村北2100O_1 | NNBYLiuJiaoCunBei2100O-宾阳六角村北2100O | 245012688 |  |  | Nanning | China | Draft | 宾阳六角村北 | 109.1205 | 109'7'14' | 23.2538 | 23'15'13'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-27 | China | China Telecom Guangxi | Completed | China | 2582631 |  | 245008570 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘两山村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangLiangShanC-南宁兴宁区五塘两山村\NNXNWuTangLiangShanC2100O-南宁兴宁区五塘两山村2100O |  | Radio Site | NNXNWuTangLiangShanC2100O | 南宁兴宁区五塘两山村2100O_1 | NNXNWuTangLiangShanC2100O-南宁兴宁区五塘两山村2100O | 245012690 |  |  | Nanning | China | Draft | 南宁兴宁区五塘两山村 | 108.6275 | 108'37'39' | 22.9242 | 22'55'27'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-26 | China | China Telecom Guangxi | Completed | China | 2582632 |  | 245008576 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘陈屋村高铁与高速路口2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangCWCGTYGSLK-南宁兴宁区五塘陈屋村高铁与高速路口\NNXNWuTangCWCGTYGSLK2100O-南宁兴宁区五塘陈屋村高铁与高速路口2100O |  | Radio Site | NNXNWuTangCWCGTYGSLK2100O | 南宁兴宁区五塘陈屋村高铁与高速路口2100O_1 | NNXNWuTangCWCGTYGSLK2100O-南宁兴宁区五塘陈屋村高铁与高速路口2100O | 245012648 |  |  | Nanning | China | Draft | 南宁兴宁区五塘陈屋村高铁与高速路口 | 108.5495 | 108'32'58' | 22.8757 | 22'52'32'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-18 | China | China Telecom Guangxi | Completed | China | 2582633 |  | 245008573 | Completed | CTGXLTE1.8Gproject-宾阳和吉黎塘石碑村高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiLiTangShiBeiCGT-宾阳和吉黎塘石碑村高铁\NNBYHeJiLiTangShiBeiCGT2100O-宾阳和吉黎塘石碑村高铁2100O |  | Radio Site | NNBYHeJiLiTangShiBeiCGT2100O | 宾阳和吉黎塘石碑村高铁2100O_1 | NNBYHeJiLiTangShiBeiCGT2100O-宾阳和吉黎塘石碑村高铁2100O | 245012683 |  |  | Nanning | China | Draft | 宾阳和吉黎塘石碑村高铁 | 109.1271 | 109'7'38' | 23.2631 | 23'15'47'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-20 | China | China Telecom Guangxi | Completed | China | 2582634 |  | 245008575 | Completed | CTGXLTE1.8Gproject-宾阳和吉燕山沙子村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiYanShanShaZiCun-宾阳和吉燕山沙子村\NNBYHeJiYanShanShaZiCun2100O-宾阳和吉燕山沙子村2100O |  | Radio Site | NNBYHeJiYanShanShaZiCun2100O | 宾阳和吉燕山沙子村2100O_1 | NNBYHeJiYanShanShaZiCun2100O-宾阳和吉燕山沙子村2100O | 245012678 |  |  | Nanning | China | Draft | 宾阳和吉燕山沙子村 | 109.1578 | 109'9'28' | 23.2422 | 23'14'31'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-20 | China | China Telecom Guangxi | Completed | China | 2582635 |  | 245008577 | Completed | CTGXLTE1.8Gproject-宾阳黎塘古托村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangGuTuoCunNan-宾阳黎塘古托村南\NNBYLiTangGuTuoCunNan2100O-宾阳黎塘古托村南2100O |  | Radio Site | NNBYLiTangGuTuoCunNan2100O | 宾阳黎塘古托村南2100O_1 | NNBYLiTangGuTuoCunNan2100O-宾阳黎塘古托村南2100O | 245012687 |  |  | Nanning | China | Draft | 宾阳黎塘古托村南 | 109.2418 | 109'14'31' | 23.2041 | 23'12'14'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-25 | China | China Telecom Guangxi | Completed | China | 2582636 |  | 245008578 | Completed | CTGXLTE1.8Gproject-南宁青秀区长塘新塘屯2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNQXZhangTangXinTangTun-南宁青秀区长塘新塘屯\NNQXZhangTangXinTangTun2100O-南宁青秀区长塘新塘屯2100O |  | Radio Site | NNQXZhangTangXinTangTun2100O | 南宁青秀区长塘新塘屯2100O_1 | NNQXZhangTangXinTangTun2100O-南宁青秀区长塘新塘屯2100O | 245012682 |  |  | Nanning | China | Draft | 南宁青秀区长塘新塘屯 | 108.4612 | 108'27'40' | 22.8497 | 22'50'59'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-24 | China | China Telecom Guangxi | Completed | China | 2582637 |  | 245008579 | Completed | CTGXLTE1.8Gproject-宾阳武陵六河高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYWuLingLiuHeGaoTie0-宾阳武陵六河高铁\NNBYWuLingLiuHeGaoTie02100O-宾阳武陵六河高铁2100O |  | Radio Site | NNBYWuLingLiuHeGaoTie02100O | 宾阳武陵六河高铁2100O_1 | NNBYWuLingLiuHeGaoTie02100O-宾阳武陵六河高铁2100O | 245012684 |  |  | Nanning | China | Draft | 宾阳武陵六河高铁 | 108.8609 | 108'51'39' | 23.0443 | 23'2'39'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-16 | China | China Telecom Guangxi | Completed | China | 2582638 |  | 245008580 | Completed | CTGXLTE1.8Gproject-南宁三塘六村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NanNingSanTangLiuCunNan-南宁三塘六村南\NanNingSanTangLiuCunNan2100O-南宁三塘六村南2100O |  | Radio Site | NanNingSanTangLiuCunNan2100O | 南宁三塘六村南2100O_1 | NanNingSanTangLiuCunNan2100O-南宁三塘六村南2100O | 245012685 |  |  | Nanning | China | Draft | 南宁三塘六村南 | 108.5034 | 108'30'12' | 22.8597 | 22'51'34'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-21 | China | China Telecom Guangxi | Completed | China | 2582639 |  | 245008584 | Completed | CTGXLTE1.8Gproject-宾阳黎塘启明陈陶村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangQiMingChenTaoC-宾阳黎塘启明陈陶村\NNBYLiTangQiMingChenTaoC2100O-宾阳黎塘启明陈陶村2100O |  | Radio Site | NNBYLiTangQiMingChenTaoC2100O | 宾阳黎塘启明陈陶村2100O_1 | NNBYLiTangQiMingChenTaoC2100O-宾阳黎塘启明陈陶村2100O | 245012693 |  |  | Nanning | China | Draft | 宾阳黎塘启明陈陶村 | 109.2328 | 109'13'58' | 23.2103 | 23'12'37'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-19 | China | China Telecom Guangxi | Completed | China | 2582640 |  | 245009203 | Completed | CTGXLTE1.8Gproject-宾阳和吉新冯村南2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYHeJiXinFengCunNan-宾阳和吉新冯村南\NNBYHeJiXinFengCunNan2100O-宾阳和吉新冯村南2100O |  | Radio Site | NNBYHeJiXinFengCunNan2100O | 宾阳和吉新冯村南2100O_1 | NNBYHeJiXinFengCunNan2100O-宾阳和吉新冯村南2100O | 245012679 |  |  | Nanning | China | Draft | 宾阳和吉新冯村南 | 109.1297 | 109'7'47' | 23.2891 | 23'17'20'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-15 | China | China Telecom Guangxi | Completed | China | 2582641 |  | 245009204 | Completed | CTGXLTE1.8Gproject-桂平寻旺乡水产高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\GPXunWangXiangShuiCGT-桂平寻旺乡水产高铁\GPXunWangXiangShuiCGT2100O-桂平寻旺乡水产高铁2100O |  | Radio Site | GPXunWangXiangShuiCGT2100O | 桂平寻旺乡水产高铁2100O_1 | GPXunWangXiangShuiCGT2100O-桂平寻旺乡水产高铁2100O | 245012692 |  |  | Guigang | China | Draft | 寻旺乡水产附近高铁 | 110.131 | 110'7'51' | 23.3269 | 23'19'36'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-28 | China | China Telecom Guangxi | Completed | China | 2582642 |  | 245009205 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘王屋村南高铁2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangWangWuCNGT-南宁兴宁区五塘王屋村南高铁\NNXNWuTangWangWuCNGT2100O-南宁兴宁区五塘王屋村南高铁2100O |  | Radio Site | NNXNWuTangWangWuCNGT2100O | 南宁兴宁区五塘王屋村南高铁2100O_1 | NNXNWuTangWangWuCNGT2100O-南宁兴宁区五塘王屋村南高铁2100O | 245012689 |  |  | Nanning | China | Draft | 南宁兴宁区五塘王屋村南高铁 | 108.5954 | 108'35'43' | 22.9021 | 22'54'7'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-21 | China | China Telecom Guangxi | Completed | China | 2582643 |  | 245012012 | Completed | CTGXLTE1.8Gproject-宾阳黎塘启明沙古村西2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangQiMingShaGuCX-宾阳黎塘启明沙古村西\NNBYLiTangQiMingShaGuCX2100O-宾阳黎塘启明沙古村西2100O |  | Radio Site | NNBYLiTangQiMingShaGuCX2100O | 宾阳黎塘启明沙古村西2100O_1 | NNBYLiTangQiMingShaGuCX2100O-宾阳黎塘启明沙古村西2100O | 245012691 |  |  | Nanning | China | Draft | 宾阳黎塘启明沙古村西 | 109.2092 | 109'12'33' | 23.2192 | 23'13'9'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-28 | China | China Telecom Guangxi | Completed | China | 2582644 |  | 245012013 | Completed | CTGXLTE1.8Gproject-南宁兴宁区五塘那律村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNWuTangNaLvCun-南宁兴宁区五塘那律村\NNXNWuTangNaLvCun2100O-南宁兴宁区五塘那律村2100O |  | Radio Site | NNXNWuTangNaLvCun2100O | 南宁兴宁区五塘那律村2100O_1 | NNXNWuTangNaLvCun2100O-南宁兴宁区五塘那律村2100O | 245012677 |  |  | Nanning | China | Draft | 南宁兴宁区五塘那律村 | 108.4975 | 108'29'51' | 22.858 | 22'51'28'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-21 | China | China Telecom Guangxi | Completed | China | 2582645 |  | 245012014 | Completed | CTGXLTE1.8Gproject-宾阳黎塘启明沙古村2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNBYLiTangQiMingShaGuCun-宾阳黎塘启明沙古村\NNBYLiTangQiMingShaGuCun2100O-宾阳黎塘启明沙古村2100O |  | Radio Site | NNBYLiTangQiMingShaGuCun2100O | 宾阳黎塘启明沙古村2100O_1 | NNBYLiTangQiMingShaGuCun2100O-宾阳黎塘启明沙古村2100O | 245012695 |  |  | Nanning | China | Draft | 宾阳黎塘启明沙古村 | 109.2185 | 109'13'6' | 23.2131 | 23'12'47'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-16 | China | China Telecom Guangxi | Completed | China | 2582646 |  | 245012015 | Completed | CTGXLTE1.8Gproject-横县百合龙塘村小学楼顶1800O | CTGXLTE1.8Gproject |  |  | \Locations\HXBaiHeLongTangCunXXLD-横县百合龙塘村小学楼顶\HXBaiHeLongTangCunXXLD1800O-横县百合龙塘村小学楼顶1800O |  | Radio Site | HXBaiHeLongTangCunXXLD1800O | 横县百合龙塘村小学楼顶1800O_1 | HXBaiHeLongTangCunXXLD1800O-横县百合龙塘村小学楼顶1800O | 245012455 |  |  | Nanning | China | Draft | 南宁市横县百合镇龙塘村小学楼顶上 | 109.4649 | 109'27'54' | 22.7664 | 22'45'58'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-03-29 | China | China Telecom Guangxi | Completed | China | 2582647 |  | 245014982 | Completed | CTGXLTE1.8Gproject-宾阳武陵镇高乔村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYWuLingZhenGaoQiaoCun-宾阳武陵镇高乔村\BYWuLingZhenGaoQiaoCun1800O-宾阳武陵镇高乔村1800O |  | Radio Site | BYWuLingZhenGaoQiaoCun1800O | 宾阳武陵镇高乔村1800O_1 | BYWuLingZhenGaoQiaoCun1800O-宾阳武陵镇高乔村1800O | 245012330 |  |  | Nanning | China | Draft | 宾阳武陵镇高乔村 | 108.9031 | 108'54'11' | 23.153 | 23'9'10'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-06-25 | China | China Telecom Guangxi | Completed | China | 2582648 |  | 245014984 | Completed | CTGXLTE1.8Gproject-南宁兴宁区昆仑平地村黄岭隧道口东2100O | CTGXLTE1.8Gproject |  |  | \Locations\NNXNKunLunPingDiCHLSDKD-南宁兴宁区昆仑平地村黄岭隧道口东\NNXNKunLunPingDiCHLSDKD2100O-南宁兴宁区昆仑平地村黄岭隧道口东2100O |  | Radio Site | NNXNKunLunPingDiCHLSDKD2100O | 南宁兴宁区昆仑平地村黄岭隧道口东2100O_1 | NNXNKunLunPingDiCHLSDKD2100O-南宁兴宁区昆仑平地村黄岭隧道口东2100O | 245012573 |  |  | Nanning | China | Draft | 南宁兴宁区昆仑平地村黄岭隧道口东 | 108.714 | 108'42'50' | 22.9783 | 22'58'41'
1001565 | CN_CT_60027580_50111975_2017_CP6.1_FDD LTE_COM GZ Site_GX_CT CUCT GX CT LTE1.8G project | 245000638 | 2000-01-01 | 2018-04-16 | China | China Telecom Guangxi | Completed | China | 2582649 |  | 245014985 | Completed | CTGXLTE1.8Gproject-宾阳和吉平桥村1800O | CTGXLTE1.8Gproject |  |  | \Locations\BYHeJiPingQiaoCun-宾阳和吉平桥村\BYHeJiPingQiaoCun1800O-宾阳和吉平桥村1800O |  | Radio Site | BYHeJiPingQiaoCun1800O | 宾阳和吉平桥村1800O_1 | BYHeJiPingQiaoCun1800O-宾阳和吉平桥村1800O | 245012396 |  |  | Nanning | China | Draft | 南宁宾阳和吉镇平桥村老桥村村头水塔对面旱地 | 109.138 | 109'8'17' | 23.2869 | 23'17'12'

## PLO dates
WP ID | Workplan--SystemRecordID | Customised PLO name | PLO--Name | PLO--Status | Object type | PLO--SystemRecordID | act--BaselineEndDate | act--ForecastEndDate | act--ActualStartDate | act--ActualEndDate | ms--BaselineEndDate | ms--ForecastEndDate | ms--ActualStartDate | ms--ActualEndDate
2582393 | 245000927 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001324 |  |  |  |  | 04/26/2018 13:00:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582393 | 245000927 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001259 |  |  |  |  | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 |  | 04/28/2018 15:00:00
2582393 | 245000927 | 0 | 07 Implementation Complete | Completed | Milestone | 245001381 |  |  |  |  | 01/01/2000 05:30:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582393 | 245000927 | act--02 Installation | 02 Installation | Completed | Activity | 245001022 | 04/23/2018 12:30:00 | 04/23/2018 15:30:00 | 04/24/2018 08:00:00 | 04/24/2018 15:00:00
2582393 | 245000927 | act--03 Integration | 03 Integration | Completed | Activity | 245001083 | 04/24/2018 12:30:00 | 04/24/2018 21:00:00 | 04/25/2018 12:30:00 | 04/25/2018 15:00:00
2582393 | 245000927 | act--04 SSV | 04 SSV | Completed | Activity | 245001139 | 04/26/2018 12:30:00 | 04/26/2018 14:30:00 | 04/27/2018 08:00:00 | 04/27/2018 15:00:00
2582393 | 245000927 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001196 |  |  |  |  | 04/23/2018 06:30:00 | 04/23/2018 08:30:00 |  | 04/23/2018 09:30:00
2582394 | 245000930 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001359 |  |  |  |  | 04/04/2018 13:00:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582394 | 245000930 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001301 |  |  |  |  | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 |  | 04/06/2018 15:00:00
2582394 | 245000930 | 0 | 07 Implementation Complete | Completed | Milestone | 245001412 |  |  |  |  | 01/01/2000 05:30:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582394 | 245000930 | act--02 Installation | 02 Installation | Completed | Activity | 245001029 | 04/01/2018 12:30:00 | 04/01/2018 15:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582394 | 245000930 | act--03 Integration | 03 Integration | Completed | Activity | 245001093 | 04/02/2018 12:30:00 | 04/02/2018 21:00:00 | 04/03/2018 12:30:00 | 04/03/2018 15:00:00
2582394 | 245000930 | act--04 SSV | 04 SSV | Completed | Activity | 245001158 | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582394 | 245000930 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001233 |  |  |  |  | 04/01/2018 06:30:00 | 04/01/2018 08:30:00 |  | 04/01/2018 09:30:00
2582395 | 245000929 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001302 |  |  |  |  | 05/08/2018 13:00:00 | 05/08/2018 15:00:00 |  | 05/08/2018 15:00:00
2582395 | 245000929 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001256 |  |  |  |  | 05/10/2018 12:30:00 | 05/10/2018 14:30:00 |  | 05/10/2018 15:00:00
2582395 | 245000929 | 0 | 07 Implementation Complete | Completed | Milestone | 245001370 |  |  |  |  | 01/01/2000 05:30:00 | 05/10/2018 15:00:00 |  | 05/10/2018 15:00:00
2582395 | 245000929 | act--02 Installation | 02 Installation | Completed | Activity | 245001027 | 05/05/2018 12:30:00 | 05/05/2018 15:30:00 | 05/06/2018 08:00:00 | 05/06/2018 15:00:00
2582395 | 245000929 | act--03 Integration | 03 Integration | Completed | Activity | 245001069 | 05/06/2018 12:30:00 | 05/06/2018 21:00:00 | 05/07/2018 12:30:00 | 05/07/2018 15:00:00
2582395 | 245000929 | act--04 SSV | 04 SSV | Completed | Activity | 245001136 | 05/08/2018 12:30:00 | 05/08/2018 14:30:00 | 05/09/2018 08:00:00 | 05/09/2018 15:00:00
2582395 | 245000929 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001187 |  |  |  |  | 05/05/2018 06:30:00 | 05/05/2018 08:30:00 |  | 05/05/2018 09:30:00
2582396 | 245000931 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001317 |  |  |  |  | 04/23/2018 13:00:00 | 04/23/2018 15:00:00 |  | 04/23/2018 15:00:00
2582396 | 245000931 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001258 |  |  |  |  | 04/25/2018 12:30:00 | 04/25/2018 14:30:00 |  | 04/25/2018 15:00:00
2582396 | 245000931 | 0 | 07 Implementation Complete | Completed | Milestone | 245001368 |  |  |  |  | 01/01/2000 05:30:00 | 04/25/2018 15:00:00 |  | 04/25/2018 15:00:00
2582396 | 245000931 | act--02 Installation | 02 Installation | Completed | Activity | 245001028 | 04/20/2018 12:30:00 | 04/20/2018 15:30:00 | 04/21/2018 08:00:00 | 04/21/2018 15:00:00
2582396 | 245000931 | act--03 Integration | 03 Integration | Completed | Activity | 245001082 | 04/21/2018 12:30:00 | 04/21/2018 21:00:00 | 04/22/2018 12:30:00 | 04/22/2018 15:00:00
2582396 | 245000931 | act--04 SSV | 04 SSV | Completed | Activity | 245001138 | 04/23/2018 12:30:00 | 04/23/2018 14:30:00 | 04/24/2018 08:00:00 | 04/24/2018 15:00:00
2582396 | 245000931 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001185 |  |  |  |  | 04/20/2018 06:30:00 | 04/20/2018 08:30:00 |  | 04/20/2018 09:30:00
2582397 | 245000926 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001345 |  |  |  |  | 05/26/2018 13:00:00 | 05/26/2018 15:00:00 |  | 05/26/2018 15:00:00
2582397 | 245000926 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001283 |  |  |  |  | 05/28/2018 12:30:00 | 05/28/2018 14:30:00 |  | 05/28/2018 15:00:00
2582397 | 245000926 | 0 | 07 Implementation Complete | Completed | Milestone | 245001406 |  |  |  |  | 01/01/2000 05:30:00 | 05/28/2018 15:00:00 |  | 05/28/2018 15:00:00
2582397 | 245000926 | act--02 Installation | 02 Installation | Completed | Activity | 245001023 | 05/23/2018 12:30:00 | 05/23/2018 15:30:00 | 05/24/2018 08:00:00 | 05/24/2018 15:00:00
2582397 | 245000926 | act--03 Integration | 03 Integration | Completed | Activity | 245001090 | 05/24/2018 12:30:00 | 05/24/2018 21:00:00 | 05/25/2018 12:30:00 | 05/25/2018 15:00:00
2582397 | 245000926 | act--04 SSV | 04 SSV | Completed | Activity | 245001150 | 05/26/2018 12:30:00 | 05/26/2018 14:30:00 | 05/27/2018 08:00:00 | 05/27/2018 15:00:00
2582397 | 245000926 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001221 |  |  |  |  | 05/23/2018 06:30:00 | 05/23/2018 08:30:00 |  | 05/23/2018 09:30:00
2582398 | 245000933 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001314 |  |  |  |  | 05/28/2018 13:00:00 | 05/28/2018 15:00:00 |  | 05/28/2018 15:00:00
2582398 | 245000933 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001265 |  |  |  |  | 05/30/2018 12:30:00 | 05/30/2018 14:30:00 |  | 05/30/2018 15:00:00
2582398 | 245000933 | 0 | 07 Implementation Complete | Completed | Milestone | 245001369 |  |  |  |  | 01/01/2000 05:30:00 | 05/30/2018 15:00:00 |  | 05/30/2018 15:00:00
2582398 | 245000933 | act--02 Installation | 02 Installation | Completed | Activity | 245001025 | 05/25/2018 12:30:00 | 05/25/2018 15:30:00 | 05/26/2018 08:00:00 | 05/26/2018 15:00:00
2582398 | 245000933 | act--03 Integration | 03 Integration | Completed | Activity | 245001094 | 05/26/2018 12:30:00 | 05/26/2018 21:00:00 | 05/27/2018 12:30:00 | 05/27/2018 15:00:00
2582398 | 245000933 | act--04 SSV | 04 SSV | Completed | Activity | 245001140 | 05/28/2018 12:30:00 | 05/28/2018 14:30:00 | 05/29/2018 08:00:00 | 05/29/2018 15:00:00
2582398 | 245000933 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001209 |  |  |  |  | 05/25/2018 06:30:00 | 05/25/2018 08:30:00 |  | 05/25/2018 09:30:00
2582399 | 245000928 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001312 |  |  |  |  | 04/24/2018 13:00:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582399 | 245000928 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001254 |  |  |  |  | 04/26/2018 12:30:00 | 04/26/2018 14:30:00 |  | 04/26/2018 15:00:00
2582399 | 245000928 | 0 | 07 Implementation Complete | Completed | Milestone | 245001365 |  |  |  |  | 01/01/2000 05:30:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582399 | 245000928 | act--02 Installation | 02 Installation | Completed | Activity | 245001024 | 04/21/2018 12:30:00 | 04/21/2018 15:30:00 | 04/22/2018 08:00:00 | 04/22/2018 15:00:00
2582399 | 245000928 | act--03 Integration | 03 Integration | Completed | Activity | 245001064 | 04/22/2018 12:30:00 | 04/22/2018 21:00:00 | 04/23/2018 12:30:00 | 04/23/2018 15:00:00
2582399 | 245000928 | act--04 SSV | 04 SSV | Completed | Activity | 245001132 | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 | 04/25/2018 08:00:00 | 04/25/2018 15:00:00
2582399 | 245000928 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001182 |  |  |  |  | 04/21/2018 06:30:00 | 04/21/2018 08:30:00 |  | 04/21/2018 09:30:00
2582400 | 245000934 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001318 |  |  |  |  | 04/03/2018 13:00:00 | 04/03/2018 15:00:00 |  | 04/03/2018 15:00:00
2582400 | 245000934 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001261 |  |  |  |  | 04/05/2018 12:30:00 | 04/05/2018 14:30:00 |  | 04/05/2018 15:00:00
2582400 | 245000934 | 0 | 07 Implementation Complete | Completed | Milestone | 245001373 |  |  |  |  | 01/01/2000 05:30:00 | 04/05/2018 15:00:00 |  | 04/05/2018 15:00:00
2582400 | 245000934 | act--02 Installation | 02 Installation | Completed | Activity | 245001021 | 03/31/2018 12:30:00 | 03/31/2018 15:30:00 | 04/01/2018 08:00:00 | 04/01/2018 15:00:00
2582400 | 245000934 | act--03 Integration | 03 Integration | Completed | Activity | 245001067 | 04/01/2018 12:30:00 | 04/01/2018 21:00:00 | 04/02/2018 12:30:00 | 04/02/2018 15:00:00
2582400 | 245000934 | act--04 SSV | 04 SSV | Completed | Activity | 245001126 | 04/03/2018 12:30:00 | 04/03/2018 14:30:00 | 04/04/2018 08:00:00 | 04/04/2018 15:00:00
2582400 | 245000934 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001192 |  |  |  |  | 03/31/2018 06:30:00 | 03/31/2018 08:30:00 |  | 03/31/2018 09:30:00
2582401 | 245000936 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001313 |  |  |  |  | 05/16/2018 13:00:00 | 05/16/2018 15:00:00 |  | 05/16/2018 15:00:00
2582401 | 245000936 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001253 |  |  |  |  | 05/18/2018 12:30:00 | 05/18/2018 14:30:00 |  | 05/18/2018 15:00:00
2582401 | 245000936 | 0 | 07 Implementation Complete | Completed | Milestone | 245001372 |  |  |  |  | 01/01/2000 05:30:00 | 05/18/2018 15:00:00 |  | 05/18/2018 15:00:00
2582401 | 245000936 | act--02 Installation | 02 Installation | Completed | Activity | 245001026 | 05/13/2018 12:30:00 | 05/13/2018 15:30:00 | 05/14/2018 08:00:00 | 05/14/2018 15:00:00
2582401 | 245000936 | act--03 Integration | 03 Integration | Completed | Activity | 245001074 | 05/14/2018 12:30:00 | 05/14/2018 21:00:00 | 05/15/2018 12:30:00 | 05/15/2018 15:00:00
2582401 | 245000936 | act--04 SSV | 04 SSV | Completed | Activity | 245001134 | 05/16/2018 12:30:00 | 05/16/2018 14:30:00 | 05/17/2018 08:00:00 | 05/17/2018 15:00:00
2582401 | 245000936 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001188 |  |  |  |  | 05/13/2018 06:30:00 | 05/13/2018 08:30:00 |  | 05/13/2018 09:30:00
2582402 | 245000937 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001347 |  |  |  |  | 05/22/2018 13:00:00 | 05/22/2018 15:00:00 |  | 05/22/2018 15:00:00
2582402 | 245000937 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001287 |  |  |  |  | 05/24/2018 12:30:00 | 05/24/2018 14:30:00 |  | 05/24/2018 15:00:00
2582402 | 245000937 | 0 | 07 Implementation Complete | Completed | Milestone | 245001408 |  |  |  |  | 01/01/2000 05:30:00 | 05/24/2018 15:00:00 |  | 05/24/2018 15:00:00
2582402 | 245000937 | act--02 Installation | 02 Installation | Completed | Activity | 245001030 | 05/19/2018 12:30:00 | 05/19/2018 15:30:00 | 05/20/2018 08:00:00 | 05/20/2018 15:00:00
2582402 | 245000937 | act--03 Integration | 03 Integration | Completed | Activity | 245001088 | 05/20/2018 12:30:00 | 05/20/2018 21:00:00 | 05/21/2018 12:30:00 | 05/21/2018 15:00:00
2582402 | 245000937 | act--04 SSV | 04 SSV | Completed | Activity | 245001147 | 05/22/2018 12:30:00 | 05/22/2018 14:30:00 | 05/23/2018 08:00:00 | 05/23/2018 15:00:00
2582402 | 245000937 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001225 |  |  |  |  | 05/19/2018 06:30:00 | 05/19/2018 08:30:00 |  | 05/19/2018 09:30:00
2582403 | 245000932 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001353 |  |  |  |  | 04/22/2018 13:00:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582403 | 245000932 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001294 |  |  |  |  | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 |  | 04/24/2018 15:00:00
2582403 | 245000932 | 0 | 07 Implementation Complete | Completed | Milestone | 245001402 |  |  |  |  | 01/01/2000 05:30:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582403 | 245000932 | act--02 Installation | 02 Installation | Completed | Activity | 245001032 | 04/19/2018 12:30:00 | 04/19/2018 15:30:00 | 04/20/2018 08:00:00 | 04/20/2018 15:00:00
2582403 | 245000932 | act--03 Integration | 03 Integration | Completed | Activity | 245001085 | 04/20/2018 12:30:00 | 04/20/2018 21:00:00 | 04/21/2018 12:30:00 | 04/21/2018 15:00:00
2582403 | 245000932 | act--04 SSV | 04 SSV | Completed | Activity | 245001153 | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 | 04/23/2018 08:00:00 | 04/23/2018 15:00:00
2582403 | 245000932 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001231 |  |  |  |  | 04/19/2018 06:30:00 | 04/19/2018 08:30:00 |  | 04/19/2018 09:30:00
2582404 | 245000938 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001349 |  |  |  |  | 05/30/2018 13:00:00 | 05/30/2018 15:00:00 |  | 05/30/2018 15:00:00
2582404 | 245000938 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001289 |  |  |  |  | 06/01/2018 12:30:00 | 06/01/2018 14:30:00 |  | 06/01/2018 15:00:00
2582404 | 245000938 | 0 | 07 Implementation Complete | Completed | Milestone | 245001411 |  |  |  |  | 01/01/2000 05:30:00 | 06/01/2018 15:00:00 |  | 06/01/2018 15:00:00
2582404 | 245000938 | act--02 Installation | 02 Installation | Completed | Activity | 245001031 | 05/27/2018 12:30:00 | 05/27/2018 15:30:00 | 05/28/2018 08:00:00 | 05/28/2018 15:00:00
2582404 | 245000938 | act--03 Integration | 03 Integration | Completed | Activity | 245001098 | 05/28/2018 12:30:00 | 05/28/2018 21:00:00 | 05/29/2018 12:30:00 | 05/29/2018 15:00:00
2582404 | 245000938 | act--04 SSV | 04 SSV | Completed | Activity | 245001161 | 05/30/2018 12:30:00 | 05/30/2018 14:30:00 | 05/31/2018 08:00:00 | 05/31/2018 15:00:00
2582404 | 245000938 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001235 |  |  |  |  | 05/27/2018 06:30:00 | 05/27/2018 08:30:00 |  | 05/27/2018 09:30:00
2582405 | 245000935 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001338 |  |  |  |  | 03/23/2018 13:00:00 | 03/23/2018 15:00:00 |  | 03/23/2018 15:00:00
2582405 | 245000935 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001280 |  |  |  |  | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 |  | 03/25/2018 15:00:00
2582405 | 245000935 | 0 | 07 Implementation Complete | Completed | Milestone | 245001396 |  |  |  |  | 01/01/2000 05:30:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582405 | 245000935 | act--02 Installation | 02 Installation | Completed | Activity | 245001033 | 03/20/2018 12:30:00 | 03/20/2018 15:30:00 | 03/21/2018 08:00:00 | 03/21/2018 15:00:00
2582405 | 245000935 | act--03 Integration | 03 Integration | Completed | Activity | 245001087 | 03/21/2018 12:30:00 | 03/21/2018 21:00:00 | 03/22/2018 12:30:00 | 03/22/2018 15:00:00
2582405 | 245000935 | act--04 SSV | 04 SSV | Completed | Activity | 245001152 | 03/23/2018 12:30:00 | 03/23/2018 14:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582405 | 245000935 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001232 |  |  |  |  | 03/20/2018 06:30:00 | 03/20/2018 08:30:00 |  | 03/20/2018 09:30:00
2582406 | 245000939 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001331 |  |  |  |  | 03/30/2018 13:00:00 | 03/30/2018 15:00:00 |  | 03/30/2018 15:00:00
2582406 | 245000939 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001279 |  |  |  |  | 04/01/2018 12:30:00 | 04/01/2018 14:30:00 |  | 04/01/2018 15:00:00
2582406 | 245000939 | 0 | 07 Implementation Complete | Completed | Milestone | 245001389 |  |  |  |  | 01/01/2000 05:30:00 | 04/01/2018 15:00:00 |  | 04/01/2018 15:00:00
2582406 | 245000939 | act--02 Installation | 02 Installation | Completed | Activity | 245001034 | 03/27/2018 12:30:00 | 03/27/2018 15:30:00 | 03/28/2018 08:00:00 | 03/28/2018 15:00:00
2582406 | 245000939 | act--03 Integration | 03 Integration | Completed | Activity | 245001097 | 03/28/2018 12:30:00 | 03/28/2018 21:00:00 | 03/29/2018 12:30:00 | 03/29/2018 15:00:00
2582406 | 245000939 | act--04 SSV | 04 SSV | Completed | Activity | 245001144 | 03/30/2018 12:30:00 | 03/30/2018 14:30:00 | 03/31/2018 08:00:00 | 03/31/2018 15:00:00
2582406 | 245000939 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001222 |  |  |  |  | 03/27/2018 06:30:00 | 03/27/2018 08:30:00 |  | 03/27/2018 09:30:00
2582407 | 245000942 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001330 |  |  |  |  | 04/28/2018 13:00:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582407 | 245000942 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001273 |  |  |  |  | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 |  | 04/30/2018 15:00:00
2582407 | 245000942 | 0 | 07 Implementation Complete | Completed | Milestone | 245001390 |  |  |  |  | 01/01/2000 05:30:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582407 | 245000942 | act--02 Installation | 02 Installation | Completed | Activity | 245001035 | 04/25/2018 12:30:00 | 04/25/2018 15:30:00 | 04/26/2018 08:00:00 | 04/26/2018 15:00:00
2582407 | 245000942 | act--03 Integration | 03 Integration | Completed | Activity | 245001084 | 04/26/2018 12:30:00 | 04/26/2018 21:00:00 | 04/27/2018 12:30:00 | 04/27/2018 15:00:00
2582407 | 245000942 | act--04 SSV | 04 SSV | Completed | Activity | 245001141 | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 | 04/29/2018 08:00:00 | 04/29/2018 15:00:00
2582407 | 245000942 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001208 |  |  |  |  | 04/25/2018 06:30:00 | 04/25/2018 08:30:00 |  | 04/25/2018 09:30:00
2582408 | 245000941 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001340 |  |  |  |  | 04/30/2018 13:00:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582408 | 245000941 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001284 |  |  |  |  | 05/02/2018 12:30:00 | 05/02/2018 14:30:00 |  | 05/02/2018 15:00:00
2582408 | 245000941 | 0 | 07 Implementation Complete | Completed | Milestone | 245001394 |  |  |  |  | 01/01/2000 05:30:00 | 05/02/2018 15:00:00 |  | 05/02/2018 15:00:00
2582408 | 245000941 | act--02 Installation | 02 Installation | Completed | Activity | 245001037 | 04/27/2018 12:30:00 | 04/27/2018 15:30:00 | 04/28/2018 08:00:00 | 04/28/2018 15:00:00
2582408 | 245000941 | act--03 Integration | 03 Integration | Completed | Activity | 245001086 | 04/28/2018 12:30:00 | 04/28/2018 21:00:00 | 04/29/2018 12:30:00 | 04/29/2018 15:00:00
2582408 | 245000941 | act--04 SSV | 04 SSV | Completed | Activity | 245001143 | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 | 05/01/2018 08:00:00 | 05/01/2018 15:00:00
2582408 | 245000941 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001224 |  |  |  |  | 04/27/2018 06:30:00 | 04/27/2018 08:30:00 |  | 04/27/2018 09:30:00
2582409 | 245000940 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001348 |  |  |  |  | 04/27/2018 13:00:00 | 04/27/2018 15:00:00 |  | 04/27/2018 15:00:00
2582409 | 245000940 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001293 |  |  |  |  | 04/29/2018 12:30:00 | 04/29/2018 14:30:00 |  | 04/29/2018 15:00:00
2582409 | 245000940 | 0 | 07 Implementation Complete | Completed | Milestone | 245001403 |  |  |  |  | 01/01/2000 05:30:00 | 04/29/2018 15:00:00 |  | 04/29/2018 15:00:00
2582409 | 245000940 | act--02 Installation | 02 Installation | Completed | Activity | 245001040 | 04/24/2018 12:30:00 | 04/24/2018 15:30:00 | 04/25/2018 08:00:00 | 04/25/2018 15:00:00
2582409 | 245000940 | act--03 Integration | 03 Integration | Completed | Activity | 245001089 | 04/25/2018 12:30:00 | 04/25/2018 21:00:00 | 04/26/2018 12:30:00 | 04/26/2018 15:00:00
2582409 | 245000940 | act--04 SSV | 04 SSV | Completed | Activity | 245001146 | 04/27/2018 12:30:00 | 04/27/2018 14:30:00 | 04/28/2018 08:00:00 | 04/28/2018 15:00:00
2582409 | 245000940 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001230 |  |  |  |  | 04/24/2018 06:30:00 | 04/24/2018 08:30:00 |  | 04/24/2018 09:30:00
2582410 | 245000943 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001326 |  |  |  |  | 05/12/2018 13:00:00 | 05/12/2018 15:00:00 |  | 05/12/2018 15:00:00
2582410 | 245000943 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001270 |  |  |  |  | 05/14/2018 12:30:00 | 05/14/2018 14:30:00 |  | 05/14/2018 15:00:00
2582410 | 245000943 | 0 | 07 Implementation Complete | Completed | Milestone | 245001386 |  |  |  |  | 01/01/2000 05:30:00 | 05/14/2018 15:00:00 |  | 05/14/2018 15:00:00
2582410 | 245000943 | act--02 Installation | 02 Installation | Completed | Activity | 245001036 | 05/09/2018 12:30:00 | 05/09/2018 15:30:00 | 05/10/2018 08:00:00 | 05/10/2018 15:00:00
2582410 | 245000943 | act--03 Integration | 03 Integration | Completed | Activity | 245001092 | 05/10/2018 12:30:00 | 05/10/2018 21:00:00 | 05/11/2018 12:30:00 | 05/11/2018 15:00:00
2582410 | 245000943 | act--04 SSV | 04 SSV | Completed | Activity | 245001145 | 05/12/2018 12:30:00 | 05/12/2018 14:30:00 | 05/13/2018 08:00:00 | 05/13/2018 15:00:00
2582410 | 245000943 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001217 |  |  |  |  | 05/09/2018 06:30:00 | 05/09/2018 08:30:00 |  | 05/09/2018 09:30:00
2582411 | 245000947 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001346 |  |  |  |  | 05/18/2018 13:00:00 | 05/18/2018 15:00:00 |  | 05/18/2018 15:00:00
2582411 | 245000947 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001288 |  |  |  |  | 05/20/2018 12:30:00 | 05/20/2018 14:30:00 |  | 05/20/2018 15:00:00
2582411 | 245000947 | 0 | 07 Implementation Complete | Completed | Milestone | 245001405 |  |  |  |  | 01/01/2000 05:30:00 | 05/20/2018 15:00:00 |  | 05/20/2018 15:00:00
2582411 | 245000947 | act--02 Installation | 02 Installation | Completed | Activity | 245001038 | 05/15/2018 12:30:00 | 05/15/2018 15:30:00 | 05/16/2018 08:00:00 | 05/16/2018 15:00:00
2582411 | 245000947 | act--03 Integration | 03 Integration | Completed | Activity | 245001100 | 05/16/2018 12:30:00 | 05/16/2018 21:00:00 | 05/17/2018 12:30:00 | 05/17/2018 15:00:00
2582411 | 245000947 | act--04 SSV | 04 SSV | Completed | Activity | 245001149 | 05/18/2018 12:30:00 | 05/18/2018 14:30:00 | 05/19/2018 08:00:00 | 05/19/2018 15:00:00
2582411 | 245000947 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001228 |  |  |  |  | 05/15/2018 06:30:00 | 05/15/2018 08:30:00 |  | 05/15/2018 09:30:00
2582412 | 245001561 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001950 |  |  |  |  | 05/14/2018 13:00:00 | 05/14/2018 15:00:00 |  | 05/14/2018 15:00:00
2582412 | 245001561 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001890 |  |  |  |  | 05/16/2018 12:30:00 | 05/16/2018 14:30:00 |  | 05/16/2018 15:00:00
2582412 | 245001561 | 0 | 07 Implementation Complete | Completed | Milestone | 245002011 |  |  |  |  | 01/01/2000 05:30:00 | 05/16/2018 15:00:00 |  | 05/16/2018 15:00:00
2582412 | 245001561 | act--02 Installation | 02 Installation | Completed | Activity | 245001658 | 05/11/2018 12:30:00 | 05/11/2018 15:30:00 | 05/12/2018 08:00:00 | 05/12/2018 15:00:00
2582412 | 245001561 | act--03 Integration | 03 Integration | Completed | Activity | 245001707 | 05/12/2018 12:30:00 | 05/12/2018 21:00:00 | 05/13/2018 12:30:00 | 05/13/2018 15:00:00
2582412 | 245001561 | act--04 SSV | 04 SSV | Completed | Activity | 245001771 | 05/14/2018 12:30:00 | 05/14/2018 14:30:00 | 05/15/2018 08:00:00 | 05/15/2018 15:00:00
2582412 | 245001561 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001828 |  |  |  |  | 05/11/2018 06:30:00 | 05/11/2018 08:30:00 |  | 05/11/2018 09:30:00
2582413 | 245001564 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001910 |  |  |  |  | 04/25/2018 13:00:00 | 04/25/2018 15:00:00 |  | 04/25/2018 15:00:00
2582413 | 245001564 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001852 |  |  |  |  | 04/27/2018 12:30:00 | 04/27/2018 14:30:00 |  | 04/27/2018 15:00:00
2582413 | 245001564 | 0 | 07 Implementation Complete | Completed | Milestone | 245001969 |  |  |  |  | 01/01/2000 05:30:00 | 04/27/2018 15:00:00 |  | 04/27/2018 15:00:00
2582413 | 245001564 | act--02 Installation | 02 Installation | Completed | Activity | 245001656 | 04/22/2018 12:30:00 | 04/22/2018 15:30:00 | 04/23/2018 08:00:00 | 04/23/2018 15:00:00
2582413 | 245001564 | act--03 Integration | 03 Integration | Completed | Activity | 245001696 | 04/23/2018 12:30:00 | 04/23/2018 21:00:00 | 04/24/2018 12:30:00 | 04/24/2018 15:00:00
2582413 | 245001564 | act--04 SSV | 04 SSV | Completed | Activity | 245001751 | 04/25/2018 12:30:00 | 04/25/2018 14:30:00 | 04/26/2018 08:00:00 | 04/26/2018 15:00:00
2582413 | 245001564 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001807 |  |  |  |  | 04/22/2018 06:30:00 | 04/22/2018 08:30:00 |  | 04/22/2018 09:30:00
2582414 | 245001562 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001984 |  |  |  |  | 03/28/2018 13:00:00 | 03/28/2018 15:00:00 |  | 03/28/2018 15:00:00
2582414 | 245001562 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001925 |  |  |  |  | 03/30/2018 12:30:00 | 03/30/2018 14:30:00 |  | 03/30/2018 15:00:00
2582414 | 245001562 | 0 | 07 Implementation Complete | Completed | Milestone | 245002039 |  |  |  |  | 01/01/2000 05:30:00 | 03/30/2018 15:00:00 |  | 03/30/2018 15:00:00
2582414 | 245001562 | act--02 Installation | 02 Installation | Completed | Activity | 245001668 | 03/25/2018 12:30:00 | 03/25/2018 15:30:00 | 03/26/2018 08:00:00 | 03/26/2018 15:00:00
2582414 | 245001562 | act--03 Integration | 03 Integration | Completed | Activity | 245001730 | 03/26/2018 12:30:00 | 03/26/2018 21:00:00 | 03/27/2018 12:30:00 | 03/27/2018 15:00:00
2582414 | 245001562 | act--04 SSV | 04 SSV | Completed | Activity | 245001786 | 03/28/2018 12:30:00 | 03/28/2018 14:30:00 | 03/29/2018 08:00:00 | 03/29/2018 15:00:00
2582414 | 245001562 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001863 |  |  |  |  | 03/25/2018 06:30:00 | 03/25/2018 08:30:00 |  | 03/25/2018 09:30:00
2582415 | 245001567 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001993 |  |  |  |  | 04/07/2018 13:00:00 | 04/07/2018 15:00:00 |  | 04/07/2018 15:00:00
2582415 | 245001567 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001933 |  |  |  |  | 04/09/2018 12:30:00 | 04/09/2018 14:30:00 |  | 04/09/2018 15:00:00
2582415 | 245001567 | 0 | 07 Implementation Complete | Completed | Milestone | 245002049 |  |  |  |  | 01/01/2000 05:30:00 | 04/09/2018 15:00:00 |  | 04/09/2018 15:00:00
2582415 | 245001567 | act--02 Installation | 02 Installation | Completed | Activity | 245001661 | 04/04/2018 12:30:00 | 04/04/2018 15:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582415 | 245001567 | act--03 Integration | 03 Integration | Completed | Activity | 245001720 | 04/05/2018 12:30:00 | 04/05/2018 21:00:00 | 04/06/2018 12:30:00 | 04/06/2018 15:00:00
2582415 | 245001567 | act--04 SSV | 04 SSV | Completed | Activity | 245001785 | 04/07/2018 12:30:00 | 04/07/2018 14:30:00 | 04/08/2018 08:00:00 | 04/08/2018 15:00:00
2582415 | 245001567 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001873 |  |  |  |  | 04/04/2018 06:30:00 | 04/04/2018 08:30:00 |  | 04/04/2018 09:30:00
2582416 | 245001563 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001949 |  |  |  |  | 05/20/2018 13:00:00 | 05/20/2018 15:00:00 |  | 05/20/2018 15:00:00
2582416 | 245001563 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001893 |  |  |  |  | 05/22/2018 12:30:00 | 05/22/2018 14:30:00 |  | 05/22/2018 15:00:00
2582416 | 245001563 | 0 | 07 Implementation Complete | Completed | Milestone | 245002007 |  |  |  |  | 01/01/2000 05:30:00 | 05/22/2018 15:00:00 |  | 05/22/2018 15:00:00
2582416 | 245001563 | act--02 Installation | 02 Installation | Completed | Activity | 245001667 | 05/17/2018 12:30:00 | 05/17/2018 15:30:00 | 05/18/2018 08:00:00 | 05/18/2018 15:00:00
2582416 | 245001563 | act--03 Integration | 03 Integration | Completed | Activity | 245001719 | 05/18/2018 12:30:00 | 05/18/2018 21:00:00 | 05/19/2018 12:30:00 | 05/19/2018 15:00:00
2582416 | 245001563 | act--04 SSV | 04 SSV | Completed | Activity | 245001769 | 05/20/2018 12:30:00 | 05/20/2018 14:30:00 | 05/21/2018 08:00:00 | 05/21/2018 15:00:00
2582416 | 245001563 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001825 |  |  |  |  | 05/17/2018 06:30:00 | 05/17/2018 08:30:00 |  | 05/17/2018 09:30:00
2582417 | 245001565 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001952 |  |  |  |  | 03/27/2018 13:00:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582417 | 245001565 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001892 |  |  |  |  | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 |  | 03/29/2018 15:00:00
2582417 | 245001565 | 0 | 07 Implementation Complete | Completed | Milestone | 245002009 |  |  |  |  | 01/01/2000 05:30:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582417 | 245001565 | act--02 Installation | 02 Installation | Completed | Activity | 245001666 | 03/24/2018 12:30:00 | 03/24/2018 15:30:00 | 03/25/2018 08:00:00 | 03/25/2018 15:00:00
2582417 | 245001565 | act--03 Integration | 03 Integration | Completed | Activity | 245001731 | 03/25/2018 12:30:00 | 03/25/2018 21:00:00 | 03/26/2018 12:30:00 | 03/26/2018 15:00:00
2582417 | 245001565 | act--04 SSV | 04 SSV | Completed | Activity | 245001770 | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 | 03/28/2018 08:00:00 | 03/28/2018 15:00:00
2582417 | 245001565 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001834 |  |  |  |  | 03/24/2018 06:30:00 | 03/24/2018 08:30:00 |  | 03/24/2018 09:30:00
2582418 | 245001568 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001895 |  |  |  |  | 03/31/2018 13:00:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582418 | 245001568 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001829 |  |  |  |  | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 |  | 04/02/2018 15:00:00
2582418 | 245001568 | 0 | 07 Implementation Complete | Completed | Milestone | 245001955 |  |  |  |  | 01/01/2000 05:30:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582418 | 245001568 | act--02 Installation | 02 Installation | Completed | Activity | 245001657 | 03/28/2018 12:30:00 | 03/28/2018 15:30:00 | 03/29/2018 08:00:00 | 03/29/2018 15:00:00
2582418 | 245001568 | act--03 Integration | 03 Integration | Completed | Activity | 245001698 | 03/29/2018 12:30:00 | 03/29/2018 21:00:00 | 03/30/2018 12:30:00 | 03/30/2018 15:00:00
2582418 | 245001568 | act--04 SSV | 04 SSV | Completed | Activity | 245001754 | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 | 04/01/2018 08:00:00 | 04/01/2018 15:00:00
2582418 | 245001568 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001809 |  |  |  |  | 03/28/2018 06:30:00 | 03/28/2018 08:30:00 |  | 03/28/2018 09:30:00
2582419 | 245001566 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001947 |  |  |  |  | 04/09/2018 13:00:00 | 04/09/2018 15:00:00 |  | 04/09/2018 15:00:00
2582419 | 245001566 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001886 |  |  |  |  | 04/11/2018 12:30:00 | 04/11/2018 14:30:00 |  | 04/11/2018 15:00:00
2582419 | 245001566 | 0 | 07 Implementation Complete | Completed | Milestone | 245002001 |  |  |  |  | 01/01/2000 05:30:00 | 04/11/2018 15:00:00 |  | 04/11/2018 15:00:00
2582419 | 245001566 | act--02 Installation | 02 Installation | Completed | Activity | 245001659 | 04/06/2018 12:30:00 | 04/06/2018 15:30:00 | 04/07/2018 08:00:00 | 04/07/2018 15:00:00
2582419 | 245001566 | act--03 Integration | 03 Integration | Completed | Activity | 245001721 | 04/07/2018 12:30:00 | 04/07/2018 21:00:00 | 04/08/2018 12:30:00 | 04/08/2018 15:00:00
2582419 | 245001566 | act--04 SSV | 04 SSV | Completed | Activity | 245001778 | 04/09/2018 12:30:00 | 04/09/2018 14:30:00 | 04/10/2018 08:00:00 | 04/10/2018 15:00:00
2582419 | 245001566 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001837 |  |  |  |  | 04/06/2018 06:30:00 | 04/06/2018 08:30:00 |  | 04/06/2018 09:30:00
2582420 | 245001572 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001978 |  |  |  |  | 05/06/2018 13:00:00 | 05/06/2018 15:00:00 |  | 05/06/2018 15:00:00
2582420 | 245001572 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001922 |  |  |  |  | 05/08/2018 12:30:00 | 05/08/2018 14:30:00 |  | 05/08/2018 15:00:00
2582420 | 245001572 | 0 | 07 Implementation Complete | Completed | Milestone | 245002031 |  |  |  |  | 01/01/2000 05:30:00 | 05/08/2018 15:00:00 |  | 05/08/2018 15:00:00
2582420 | 245001572 | act--02 Installation | 02 Installation | Completed | Activity | 245001664 | 05/03/2018 12:30:00 | 05/03/2018 15:30:00 | 05/04/2018 08:00:00 | 05/04/2018 15:00:00
2582420 | 245001572 | act--03 Integration | 03 Integration | Completed | Activity | 245001728 | 05/04/2018 12:30:00 | 05/04/2018 21:00:00 | 05/05/2018 12:30:00 | 05/05/2018 15:00:00
2582420 | 245001572 | act--04 SSV | 04 SSV | Completed | Activity | 245001779 | 05/06/2018 12:30:00 | 05/06/2018 14:30:00 | 05/07/2018 08:00:00 | 05/07/2018 15:00:00
2582420 | 245001572 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001861 |  |  |  |  | 05/03/2018 06:30:00 | 05/03/2018 08:30:00 |  | 05/03/2018 09:30:00
2582421 | 245001576 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001976 |  |  |  |  | 04/08/2018 13:00:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582421 | 245001576 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001921 |  |  |  |  | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 |  | 04/10/2018 15:00:00
2582421 | 245001576 | 0 | 07 Implementation Complete | Completed | Milestone | 245002033 |  |  |  |  | 01/01/2000 05:30:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582421 | 245001576 | act--02 Installation | 02 Installation | Completed | Activity | 245001669 | 04/05/2018 12:30:00 | 04/05/2018 15:30:00 | 04/06/2018 08:00:00 | 04/06/2018 15:00:00
2582421 | 245001576 | act--03 Integration | 03 Integration | Completed | Activity | 245001732 | 04/06/2018 12:30:00 | 04/06/2018 21:00:00 | 04/07/2018 12:30:00 | 04/07/2018 15:00:00
2582421 | 245001576 | act--04 SSV | 04 SSV | Completed | Activity | 245001797 | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 | 04/09/2018 08:00:00 | 04/09/2018 15:00:00
2582421 | 245001576 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001865 |  |  |  |  | 04/05/2018 06:30:00 | 04/05/2018 08:30:00 |  | 04/05/2018 09:30:00
2582422 | 245001571 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001963 |  |  |  |  | 04/01/2018 13:00:00 | 04/01/2018 15:00:00 |  | 04/01/2018 15:00:00
2582422 | 245001571 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001900 |  |  |  |  | 04/03/2018 12:30:00 | 04/03/2018 14:30:00 |  | 04/03/2018 15:00:00
2582422 | 245001571 | 0 | 07 Implementation Complete | Completed | Milestone | 245002022 |  |  |  |  | 01/01/2000 05:30:00 | 04/03/2018 15:00:00 |  | 04/03/2018 15:00:00
2582422 | 245001571 | act--02 Installation | 02 Installation | Completed | Activity | 245001662 | 03/29/2018 12:30:00 | 03/29/2018 15:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582422 | 245001571 | act--03 Integration | 03 Integration | Completed | Activity | 245001718 | 03/30/2018 12:30:00 | 03/30/2018 21:00:00 | 03/31/2018 12:30:00 | 03/31/2018 15:00:00
2582422 | 245001571 | act--04 SSV | 04 SSV | Completed | Activity | 245001773 | 04/01/2018 12:30:00 | 04/01/2018 14:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582422 | 245001571 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001843 |  |  |  |  | 03/29/2018 06:30:00 | 03/29/2018 08:30:00 |  | 03/29/2018 09:30:00
2582423 | 245001569 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001990 |  |  |  |  | 03/29/2018 13:00:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582423 | 245001569 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001934 |  |  |  |  | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 |  | 03/31/2018 15:00:00
2582423 | 245001569 | 0 | 07 Implementation Complete | Completed | Milestone | 245002050 |  |  |  |  | 01/01/2000 05:30:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582423 | 245001569 | act--02 Installation | 02 Installation | Completed | Activity | 245001663 | 03/26/2018 12:30:00 | 03/26/2018 15:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582423 | 245001569 | act--03 Integration | 03 Integration | Completed | Activity | 245001726 | 03/27/2018 12:30:00 | 03/27/2018 21:00:00 | 03/28/2018 12:30:00 | 03/28/2018 15:00:00
2582423 | 245001569 | act--04 SSV | 04 SSV | Completed | Activity | 245001784 | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582423 | 245001569 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001875 |  |  |  |  | 03/26/2018 06:30:00 | 03/26/2018 08:30:00 |  | 03/26/2018 09:30:00
2582424 | 245001573 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001962 |  |  |  |  | 03/24/2018 13:00:00 | 03/24/2018 15:00:00 |  | 03/24/2018 15:00:00
2582424 | 245001573 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001903 |  |  |  |  | 03/26/2018 12:30:00 | 03/26/2018 14:30:00 |  | 03/26/2018 15:00:00
2582424 | 245001573 | 0 | 07 Implementation Complete | Completed | Milestone | 245002018 |  |  |  |  | 01/01/2000 05:30:00 | 03/26/2018 15:00:00 |  | 03/26/2018 15:00:00
2582424 | 245001573 | act--02 Installation | 02 Installation | Completed | Activity | 245001673 | 03/21/2018 12:30:00 | 03/21/2018 15:30:00 | 03/22/2018 08:00:00 | 03/22/2018 15:00:00
2582424 | 245001573 | act--03 Integration | 03 Integration | Completed | Activity | 245001724 | 03/22/2018 12:30:00 | 03/22/2018 21:00:00 | 03/23/2018 12:30:00 | 03/23/2018 15:00:00
2582424 | 245001573 | act--04 SSV | 04 SSV | Completed | Activity | 245001774 | 03/24/2018 12:30:00 | 03/24/2018 14:30:00 | 03/25/2018 08:00:00 | 03/25/2018 15:00:00
2582424 | 245001573 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001838 |  |  |  |  | 03/21/2018 06:30:00 | 03/21/2018 08:30:00 |  | 03/21/2018 09:30:00
2582425 | 245001575 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001986 |  |  |  |  | 05/10/2018 13:00:00 | 05/10/2018 15:00:00 |  | 05/10/2018 15:00:00
2582425 | 245001575 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001929 |  |  |  |  | 05/12/2018 12:30:00 | 05/12/2018 14:30:00 |  | 05/12/2018 15:00:00
2582425 | 245001575 | 0 | 07 Implementation Complete | Completed | Milestone | 245002042 |  |  |  |  | 01/01/2000 05:30:00 | 05/12/2018 15:00:00 |  | 05/12/2018 15:00:00
2582425 | 245001575 | act--02 Installation | 02 Installation | Completed | Activity | 245001674 | 05/07/2018 12:30:00 | 05/07/2018 15:30:00 | 05/08/2018 08:00:00 | 05/08/2018 15:00:00
2582425 | 245001575 | act--03 Integration | 03 Integration | Completed | Activity | 245001729 | 05/08/2018 12:30:00 | 05/08/2018 21:00:00 | 05/09/2018 12:30:00 | 05/09/2018 15:00:00
2582425 | 245001575 | act--04 SSV | 04 SSV | Completed | Activity | 245001789 | 05/10/2018 12:30:00 | 05/10/2018 14:30:00 | 05/11/2018 08:00:00 | 05/11/2018 15:00:00
2582425 | 245001575 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001881 |  |  |  |  | 05/07/2018 06:30:00 | 05/07/2018 08:30:00 |  | 05/07/2018 09:30:00
2582426 | 245001570 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001985 |  |  |  |  | 04/02/2018 13:00:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582426 | 245001570 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001926 |  |  |  |  | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 |  | 04/04/2018 15:00:00
2582426 | 245001570 | 0 | 07 Implementation Complete | Completed | Milestone | 245002043 |  |  |  |  | 01/01/2000 05:30:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582426 | 245001570 | act--02 Installation | 02 Installation | Completed | Activity | 245001671 | 03/30/2018 12:30:00 | 03/30/2018 15:30:00 | 03/31/2018 08:00:00 | 03/31/2018 15:00:00
2582426 | 245001570 | act--03 Integration | 03 Integration | Completed | Activity | 245001727 | 03/31/2018 12:30:00 | 03/31/2018 21:00:00 | 04/01/2018 12:30:00 | 04/01/2018 15:00:00
2582426 | 245001570 | act--04 SSV | 04 SSV | Completed | Activity | 245001791 | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 | 04/03/2018 08:00:00 | 04/03/2018 15:00:00
2582426 | 245001570 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001872 |  |  |  |  | 03/30/2018 06:30:00 | 03/30/2018 08:30:00 |  | 03/30/2018 09:30:00
2582427 | 245001574 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001961 |  |  |  |  | 04/11/2018 13:00:00 | 04/11/2018 15:00:00 |  | 04/11/2018 15:00:00
2582427 | 245001574 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001905 |  |  |  |  | 04/13/2018 12:30:00 | 04/13/2018 14:30:00 |  | 04/13/2018 15:00:00
2582427 | 245001574 | 0 | 07 Implementation Complete | Completed | Milestone | 245002020 |  |  |  |  | 01/01/2000 05:30:00 | 04/13/2018 15:00:00 |  | 04/13/2018 15:00:00
2582427 | 245001574 | act--02 Installation | 02 Installation | Completed | Activity | 245001670 | 04/08/2018 12:30:00 | 04/08/2018 15:30:00 | 04/09/2018 08:00:00 | 04/09/2018 15:00:00
2582427 | 245001574 | act--03 Integration | 03 Integration | Completed | Activity | 245001722 | 04/09/2018 12:30:00 | 04/09/2018 21:00:00 | 04/10/2018 12:30:00 | 04/10/2018 15:00:00
2582427 | 245001574 | act--04 SSV | 04 SSV | Completed | Activity | 245001776 | 04/11/2018 12:30:00 | 04/11/2018 14:30:00 | 04/12/2018 08:00:00 | 04/12/2018 15:00:00
2582427 | 245001574 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001835 |  |  |  |  | 04/08/2018 06:30:00 | 04/08/2018 08:30:00 |  | 04/08/2018 09:30:00
2582428 | 245001578 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001944 |  |  |  |  | 03/25/2018 13:00:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582428 | 245001578 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001898 |  |  |  |  | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 |  | 03/27/2018 15:00:00
2582428 | 245001578 | 0 | 07 Implementation Complete | Completed | Milestone | 245002002 |  |  |  |  | 01/01/2000 05:30:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582428 | 245001578 | act--02 Installation | 02 Installation | Completed | Activity | 245001672 | 03/22/2018 12:30:00 | 03/22/2018 15:30:00 | 03/23/2018 08:00:00 | 03/23/2018 15:00:00
2582428 | 245001578 | act--03 Integration | 03 Integration | Completed | Activity | 245001717 | 03/23/2018 12:30:00 | 03/23/2018 21:00:00 | 03/24/2018 12:30:00 | 03/24/2018 15:00:00
2582428 | 245001578 | act--04 SSV | 04 SSV | Completed | Activity | 245001780 | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 | 03/26/2018 08:00:00 | 03/26/2018 15:00:00
2582428 | 245001578 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001845 |  |  |  |  | 03/22/2018 06:30:00 | 03/22/2018 08:30:00 |  | 03/22/2018 09:30:00
2582429 | 245001585 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001965 |  |  |  |  | 03/26/2018 13:00:00 | 03/26/2018 15:00:00 |  | 03/26/2018 15:00:00
2582429 | 245001585 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001904 |  |  |  |  | 03/28/2018 12:30:00 | 03/28/2018 14:30:00 |  | 03/28/2018 15:00:00
2582429 | 245001585 | 0 | 07 Implementation Complete | Completed | Milestone | 245002019 |  |  |  |  | 01/01/2000 05:30:00 | 03/28/2018 15:00:00 |  | 03/28/2018 15:00:00
2582429 | 245001585 | act--02 Installation | 02 Installation | Completed | Activity | 245001676 | 03/23/2018 12:30:00 | 03/23/2018 15:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582429 | 245001585 | act--03 Integration | 03 Integration | Completed | Activity | 245001725 | 03/24/2018 12:30:00 | 03/24/2018 21:00:00 | 03/25/2018 12:30:00 | 03/25/2018 15:00:00
2582429 | 245001585 | act--04 SSV | 04 SSV | Completed | Activity | 245001783 | 03/26/2018 12:30:00 | 03/26/2018 14:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582429 | 245001585 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001836 |  |  |  |  | 03/23/2018 06:30:00 | 03/23/2018 08:30:00 |  | 03/23/2018 09:30:00
2582430 | 245001587 | 0 | 05 NRO IM Accept | Completed | Milestone | 245001995 |  |  |  |  | 04/10/2018 13:00:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582430 | 245001587 | 0 | 06 NDO IM Accept | Completed | Milestone | 245001942 |  |  |  |  | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 |  | 04/12/2018 15:00:00
2582430 | 245001587 | 0 | 07 Implementation Complete | Completed | Milestone | 245002054 |  |  |  |  | 01/01/2000 05:30:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582430 | 245001587 | act--02 Installation | 02 Installation | Completed | Activity | 245001677 | 04/07/2018 12:30:00 | 04/07/2018 15:30:00 | 04/08/2018 08:00:00 | 04/08/2018 15:00:00
2582430 | 245001587 | act--03 Integration | 03 Integration | Completed | Activity | 245001734 | 04/08/2018 12:30:00 | 04/08/2018 21:00:00 | 04/09/2018 12:30:00 | 04/09/2018 15:00:00
2582430 | 245001587 | act--04 SSV | 04 SSV | Completed | Activity | 245001790 | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 | 04/11/2018 08:00:00 | 04/11/2018 15:00:00
2582430 | 245001587 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245001884 |  |  |  |  | 04/07/2018 06:30:00 | 04/07/2018 08:30:00 |  | 04/07/2018 09:30:00
2582431 | 245002190 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002589 |  |  |  |  | 05/04/2018 13:00:00 | 05/04/2018 15:00:00 |  | 05/04/2018 15:00:00
2582431 | 245002190 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002532 |  |  |  |  | 05/06/2018 12:30:00 | 05/06/2018 14:30:00 |  | 05/06/2018 15:00:00
2582431 | 245002190 | 0 | 07 Implementation Complete | Completed | Milestone | 245002642 |  |  |  |  | 01/01/2000 05:30:00 | 05/06/2018 15:00:00 |  | 05/06/2018 15:00:00
2582431 | 245002190 | act--02 Installation | 02 Installation | Completed | Activity | 245002284 | 05/01/2018 12:30:00 | 05/01/2018 15:30:00 | 05/02/2018 08:00:00 | 05/02/2018 15:00:00
2582431 | 245002190 | act--03 Integration | 03 Integration | Completed | Activity | 245002340 | 05/02/2018 12:30:00 | 05/02/2018 21:00:00 | 05/03/2018 12:30:00 | 05/03/2018 15:00:00
2582431 | 245002190 | act--04 SSV | 04 SSV | Completed | Activity | 245002403 | 05/04/2018 12:30:00 | 05/04/2018 14:30:00 | 05/05/2018 08:00:00 | 05/05/2018 15:00:00
2582431 | 245002190 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002473 |  |  |  |  | 05/01/2018 06:30:00 | 05/01/2018 08:30:00 |  | 05/01/2018 09:30:00
2582432 | 245002191 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002577 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582432 | 245002191 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002521 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 14:30:00 |  | 06/26/2018 15:00:00
2582432 | 245002191 | 0 | 07 Implementation Complete | Completed | Milestone | 245002637 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582432 | 245002191 | act--02 Installation | 02 Installation | Completed | Activity | 245002285 | 06/21/2018 12:30:00 | 06/21/2018 16:00:00 | 06/22/2018 08:00:00 | 06/22/2018 15:00:00
2582432 | 245002191 | act--03 Integration | 03 Integration | Completed | Activity | 245002324 | 04/05/2018 12:30:00 | 06/22/2018 21:00:00 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00
2582432 | 245002191 | act--04 SSV | 04 SSV | Completed | Activity | 245002394 | 04/07/2018 12:30:00 | 06/23/2018 21:00:00 | 06/24/2018 08:00:00 | 06/24/2018 15:00:00
2582432 | 245002191 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002454 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582433 | 245002188 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002588 |  |  |  |  | 05/02/2018 13:00:00 | 05/02/2018 15:00:00 |  | 05/02/2018 15:00:00
2582433 | 245002188 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002536 |  |  |  |  | 05/04/2018 12:30:00 | 05/04/2018 14:30:00 |  | 05/04/2018 15:00:00
2582433 | 245002188 | 0 | 07 Implementation Complete | Completed | Milestone | 245002646 |  |  |  |  | 01/01/2000 05:30:00 | 05/04/2018 15:00:00 |  | 05/04/2018 15:00:00
2582433 | 245002188 | act--02 Installation | 02 Installation | Completed | Activity | 245002292 | 04/29/2018 12:30:00 | 04/29/2018 15:30:00 | 04/30/2018 08:00:00 | 04/30/2018 15:00:00
2582433 | 245002188 | act--03 Integration | 03 Integration | Completed | Activity | 245002352 | 04/30/2018 12:30:00 | 04/30/2018 21:00:00 | 05/01/2018 12:30:00 | 05/01/2018 15:00:00
2582433 | 245002188 | act--04 SSV | 04 SSV | Completed | Activity | 245002407 | 05/02/2018 12:30:00 | 05/02/2018 14:30:00 | 05/03/2018 08:00:00 | 05/03/2018 15:00:00
2582433 | 245002188 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002478 |  |  |  |  | 04/29/2018 06:30:00 | 04/29/2018 08:30:00 |  | 04/29/2018 09:30:00
2582434 | 245002192 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002560 |  |  |  |  | 06/24/2018 13:00:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582434 | 245002192 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002497 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582434 | 245002192 | 0 | 07 Implementation Complete | Completed | Milestone | 245002614 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582434 | 245002192 | act--02 Installation | 02 Installation | Completed | Activity | 245002286 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582434 | 245002192 | act--03 Integration | 03 Integration | Completed | Activity | 245002326 | 06/22/2018 12:30:00 | 06/22/2018 23:00:00 | 06/23/2018 11:30:00 | 06/23/2018 15:30:00
2582434 | 245002192 | act--04 SSV | 04 SSV | Completed | Activity | 245002382 | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 | 06/25/2018 07:00:00 | 06/25/2018 15:30:00
2582434 | 245002192 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002437 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582435 | 245002195 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002559 |  |  |  |  | 03/25/2018 13:00:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582435 | 245002195 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002505 |  |  |  |  | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 |  | 03/27/2018 15:00:00
2582435 | 245002195 | 0 | 07 Implementation Complete | Completed | Milestone | 245002618 |  |  |  |  | 01/01/2000 05:30:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582435 | 245002195 | act--02 Installation | 02 Installation | Completed | Activity | 245002287 | 03/22/2018 12:30:00 | 03/22/2018 15:30:00 | 03/23/2018 08:00:00 | 03/23/2018 15:00:00
2582435 | 245002195 | act--03 Integration | 03 Integration | Completed | Activity | 245002341 | 03/23/2018 12:30:00 | 03/23/2018 21:00:00 | 03/24/2018 12:30:00 | 03/24/2018 15:00:00
2582435 | 245002195 | act--04 SSV | 04 SSV | Completed | Activity | 245002397 | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 | 03/26/2018 08:00:00 | 03/26/2018 15:00:00
2582435 | 245002195 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002451 |  |  |  |  | 03/22/2018 06:30:00 | 03/22/2018 08:30:00 |  | 03/22/2018 09:30:00
2582436 | 245002189 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002590 |  |  |  |  | 05/24/2018 13:00:00 | 05/24/2018 15:00:00 |  | 05/24/2018 15:00:00
2582436 | 245002189 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002533 |  |  |  |  | 05/26/2018 12:30:00 | 05/26/2018 14:30:00 |  | 05/26/2018 15:00:00
2582436 | 245002189 | 0 | 07 Implementation Complete | Completed | Milestone | 245002648 |  |  |  |  | 01/01/2000 05:30:00 | 05/26/2018 15:00:00 |  | 05/26/2018 15:00:00
2582436 | 245002189 | act--02 Installation | 02 Installation | Completed | Activity | 245002289 | 05/21/2018 12:30:00 | 05/21/2018 15:30:00 | 05/22/2018 08:00:00 | 05/22/2018 15:00:00
2582436 | 245002189 | act--03 Integration | 03 Integration | Completed | Activity | 245002345 | 05/22/2018 12:30:00 | 05/22/2018 21:00:00 | 05/23/2018 12:30:00 | 05/23/2018 15:00:00
2582436 | 245002189 | act--04 SSV | 04 SSV | Completed | Activity | 245002411 | 05/24/2018 12:30:00 | 05/24/2018 14:30:00 | 05/25/2018 08:00:00 | 05/25/2018 15:00:00
2582436 | 245002189 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002471 |  |  |  |  | 05/21/2018 06:30:00 | 05/21/2018 08:30:00 |  | 05/21/2018 09:30:00
2582437 | 245002198 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002582 |  |  |  |  | 03/29/2018 13:00:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582437 | 245002198 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002523 |  |  |  |  | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 |  | 03/31/2018 15:00:00
2582437 | 245002198 | 0 | 07 Implementation Complete | Completed | Milestone | 245002640 |  |  |  |  | 01/01/2000 05:30:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582437 | 245002198 | act--02 Installation | 02 Installation | Completed | Activity | 245002283 | 03/26/2018 12:30:00 | 03/26/2018 15:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582437 | 245002198 | act--03 Integration | 03 Integration | Completed | Activity | 245002336 | 03/27/2018 12:30:00 | 03/27/2018 21:00:00 | 03/28/2018 12:30:00 | 03/28/2018 15:00:00
2582437 | 245002198 | act--04 SSV | 04 SSV | Completed | Activity | 245002398 | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582437 | 245002198 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002459 |  |  |  |  | 03/26/2018 06:30:00 | 03/26/2018 08:30:00 |  | 03/26/2018 09:30:00
2582438 | 245002194 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002606 |  |  |  |  | 04/05/2018 13:00:00 | 04/05/2018 15:00:00 |  | 04/05/2018 15:00:00
2582438 | 245002194 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002546 |  |  |  |  | 04/07/2018 12:30:00 | 04/07/2018 14:30:00 |  | 04/07/2018 15:00:00
2582438 | 245002194 | 0 | 07 Implementation Complete | Completed | Milestone | 245002659 |  |  |  |  | 01/01/2000 05:30:00 | 04/07/2018 15:00:00 |  | 04/07/2018 15:00:00
2582438 | 245002194 | act--02 Installation | 02 Installation | Completed | Activity | 245002291 | 04/02/2018 12:30:00 | 04/02/2018 15:30:00 | 04/03/2018 08:00:00 | 04/03/2018 15:00:00
2582438 | 245002194 | act--03 Integration | 03 Integration | Completed | Activity | 245002354 | 04/03/2018 12:30:00 | 04/03/2018 21:00:00 | 04/04/2018 12:30:00 | 04/04/2018 15:00:00
2582438 | 245002194 | act--04 SSV | 04 SSV | Completed | Activity | 245002413 | 04/05/2018 12:30:00 | 04/05/2018 14:30:00 | 04/06/2018 08:00:00 | 04/06/2018 15:00:00
2582438 | 245002194 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002488 |  |  |  |  | 04/02/2018 06:30:00 | 04/02/2018 08:30:00 |  | 04/02/2018 09:30:00
2582439 | 245002193 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002611 |  |  |  |  | 04/06/2018 13:00:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582439 | 245002193 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002553 |  |  |  |  | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 |  | 04/08/2018 15:00:00
2582439 | 245002193 | 0 | 07 Implementation Complete | Completed | Milestone | 245002673 |  |  |  |  | 01/01/2000 05:30:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582439 | 245002193 | act--02 Installation | 02 Installation | Completed | Activity | 245002298 | 04/03/2018 12:30:00 | 04/03/2018 15:30:00 | 04/04/2018 08:00:00 | 04/04/2018 15:00:00
2582439 | 245002193 | act--03 Integration | 03 Integration | Completed | Activity | 245002364 | 04/04/2018 12:30:00 | 04/04/2018 21:00:00 | 04/05/2018 12:30:00 | 04/05/2018 15:00:00
2582439 | 245002193 | act--04 SSV | 04 SSV | Completed | Activity | 245002419 | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 | 04/07/2018 08:00:00 | 04/07/2018 15:00:00
2582439 | 245002193 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002496 |  |  |  |  | 04/03/2018 06:30:00 | 04/03/2018 08:30:00 |  | 04/03/2018 09:30:00
2582440 | 245002197 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002598 |  |  |  |  | 03/26/2018 13:00:00 | 03/26/2018 15:00:00 |  | 03/26/2018 15:00:00
2582440 | 245002197 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002541 |  |  |  |  | 03/28/2018 12:30:00 | 03/28/2018 14:30:00 |  | 03/28/2018 15:00:00
2582440 | 245002197 | 0 | 07 Implementation Complete | Completed | Milestone | 245002660 |  |  |  |  | 01/01/2000 05:30:00 | 03/28/2018 15:00:00 |  | 03/28/2018 15:00:00
2582440 | 245002197 | act--02 Installation | 02 Installation | Completed | Activity | 245002297 | 03/23/2018 12:30:00 | 03/23/2018 15:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582440 | 245002197 | act--03 Integration | 03 Integration | Completed | Activity | 245002356 | 03/24/2018 12:30:00 | 03/24/2018 21:00:00 | 03/25/2018 12:30:00 | 03/25/2018 15:00:00
2582440 | 245002197 | act--04 SSV | 04 SSV | Completed | Activity | 245002420 | 03/26/2018 12:30:00 | 03/26/2018 14:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582440 | 245002197 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002486 |  |  |  |  | 03/23/2018 06:30:00 | 03/23/2018 08:30:00 |  | 03/23/2018 09:30:00
2582441 | 245002196 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002616 |  |  |  |  | 03/27/2018 13:00:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582441 | 245002196 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002557 |  |  |  |  | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 |  | 03/29/2018 15:00:00
2582441 | 245002196 | 0 | 07 Implementation Complete | Completed | Milestone | 245002669 |  |  |  |  | 01/01/2000 05:30:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582441 | 245002196 | act--02 Installation | 02 Installation | Completed | Activity | 245002288 | 03/24/2018 12:30:00 | 03/24/2018 15:30:00 | 03/25/2018 08:00:00 | 03/25/2018 15:00:00
2582441 | 245002196 | act--03 Integration | 03 Integration | Completed | Activity | 245002344 | 03/25/2018 12:30:00 | 03/25/2018 21:00:00 | 03/26/2018 12:30:00 | 03/26/2018 15:00:00
2582441 | 245002196 | act--04 SSV | 04 SSV | Completed | Activity | 245002409 | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 | 03/28/2018 08:00:00 | 03/28/2018 15:00:00
2582441 | 245002196 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002500 |  |  |  |  | 03/24/2018 06:30:00 | 03/24/2018 08:30:00 |  | 03/24/2018 09:30:00
2582442 | 245002200 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002576 |  |  |  |  | 04/02/2018 13:00:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582442 | 245002200 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002518 |  |  |  |  | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 |  | 04/04/2018 15:00:00
2582442 | 245002200 | 0 | 07 Implementation Complete | Completed | Milestone | 245002627 |  |  |  |  | 01/01/2000 05:30:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582442 | 245002200 | act--02 Installation | 02 Installation | Completed | Activity | 245002293 | 03/30/2018 12:30:00 | 03/30/2018 15:30:00 | 03/31/2018 08:00:00 | 03/31/2018 15:00:00
2582442 | 245002200 | act--03 Integration | 03 Integration | Completed | Activity | 245002338 | 03/31/2018 12:30:00 | 03/31/2018 21:00:00 | 04/01/2018 12:30:00 | 04/01/2018 15:00:00
2582442 | 245002200 | act--04 SSV | 04 SSV | Completed | Activity | 245002387 | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 | 04/03/2018 08:00:00 | 04/03/2018 15:00:00
2582442 | 245002200 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002455 |  |  |  |  | 03/30/2018 06:30:00 | 03/30/2018 08:30:00 |  | 03/30/2018 09:30:00
2582443 | 245002202 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002569 |  |  |  |  | 04/30/2018 13:00:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582443 | 245002202 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002511 |  |  |  |  | 05/02/2018 12:30:00 | 05/02/2018 14:30:00 |  | 05/02/2018 15:00:00
2582443 | 245002202 | 0 | 07 Implementation Complete | Completed | Milestone | 245002625 |  |  |  |  | 01/01/2000 05:30:00 | 05/02/2018 15:00:00 |  | 05/02/2018 15:00:00
2582443 | 245002202 | act--02 Installation | 02 Installation | Completed | Activity | 245002290 | 04/27/2018 12:30:00 | 04/27/2018 15:30:00 | 04/28/2018 08:00:00 | 04/28/2018 15:00:00
2582443 | 245002202 | act--03 Integration | 03 Integration | Completed | Activity | 245002339 | 04/28/2018 12:30:00 | 04/28/2018 21:00:00 | 04/29/2018 12:30:00 | 04/29/2018 15:00:00
2582443 | 245002202 | act--04 SSV | 04 SSV | Completed | Activity | 245002389 | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 | 05/01/2018 08:00:00 | 05/01/2018 15:00:00
2582443 | 245002202 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002449 |  |  |  |  | 04/27/2018 06:30:00 | 04/27/2018 08:30:00 |  | 04/27/2018 09:30:00
2582444 | 245002199 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002587 |  |  |  |  | 03/29/2018 13:00:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582444 | 245002199 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002526 |  |  |  |  | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 |  | 03/31/2018 15:00:00
2582444 | 245002199 | 0 | 07 Implementation Complete | Completed | Milestone | 245002643 |  |  |  |  | 01/01/2000 05:30:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582444 | 245002199 | act--02 Installation | 02 Installation | Completed | Activity | 245002299 | 03/26/2018 12:30:00 | 03/26/2018 15:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582444 | 245002199 | act--03 Integration | 03 Integration | Completed | Activity | 245002347 | 03/27/2018 12:30:00 | 03/27/2018 21:00:00 | 03/28/2018 12:30:00 | 03/28/2018 15:00:00
2582444 | 245002199 | act--04 SSV | 04 SSV | Completed | Activity | 245002395 | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582444 | 245002199 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002457 |  |  |  |  | 03/26/2018 06:30:00 | 03/26/2018 08:30:00 |  | 03/26/2018 09:30:00
2582445 | 245002203 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002615 |  |  |  |  | 04/16/2018 13:00:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582445 | 245002203 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002558 |  |  |  |  | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 |  | 04/18/2018 15:00:00
2582445 | 245002203 | 0 | 07 Implementation Complete | Completed | Milestone | 245002677 |  |  |  |  | 01/01/2000 05:30:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582445 | 245002203 | act--02 Installation | 02 Installation | Completed | Activity | 245002304 | 04/13/2018 12:30:00 | 04/13/2018 15:30:00 | 04/14/2018 08:00:00 | 04/14/2018 15:00:00
2582445 | 245002203 | act--03 Integration | 03 Integration | Completed | Activity | 245002355 | 04/14/2018 12:30:00 | 04/14/2018 21:00:00 | 04/15/2018 12:30:00 | 04/15/2018 15:00:00
2582445 | 245002203 | act--04 SSV | 04 SSV | Completed | Activity | 245002418 | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 | 04/17/2018 08:00:00 | 04/17/2018 15:00:00
2582445 | 245002203 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002493 |  |  |  |  | 04/13/2018 06:30:00 | 04/13/2018 08:30:00 |  | 04/13/2018 09:30:00
2582446 | 245002201 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002601 |  |  |  |  | 03/23/2018 13:00:00 | 03/23/2018 15:00:00 |  | 03/23/2018 15:00:00
2582446 | 245002201 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002550 |  |  |  |  | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 |  | 03/25/2018 15:00:00
2582446 | 245002201 | 0 | 07 Implementation Complete | Completed | Milestone | 245002657 |  |  |  |  | 01/01/2000 05:30:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582446 | 245002201 | act--02 Installation | 02 Installation | Completed | Activity | 245002301 | 03/20/2018 12:30:00 | 03/20/2018 15:30:00 | 03/21/2018 08:00:00 | 03/21/2018 15:00:00
2582446 | 245002201 | act--03 Integration | 03 Integration | Completed | Activity | 245002358 | 03/21/2018 12:30:00 | 03/21/2018 21:00:00 | 03/22/2018 12:30:00 | 03/22/2018 15:00:00
2582446 | 245002201 | act--04 SSV | 04 SSV | Completed | Activity | 245002414 | 03/23/2018 12:30:00 | 03/23/2018 14:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582446 | 245002201 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002491 |  |  |  |  | 03/20/2018 06:30:00 | 03/20/2018 08:30:00 |  | 03/20/2018 09:30:00
2582447 | 245002211 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002608 |  |  |  |  | 04/04/2018 13:00:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582447 | 245002211 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002548 |  |  |  |  | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 |  | 04/06/2018 15:00:00
2582447 | 245002211 | 0 | 07 Implementation Complete | Completed | Milestone | 245002668 |  |  |  |  | 01/01/2000 05:30:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582447 | 245002211 | act--02 Installation | 02 Installation | Completed | Activity | 245002303 | 04/01/2018 12:30:00 | 04/01/2018 15:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582447 | 245002211 | act--03 Integration | 03 Integration | Completed | Activity | 245002361 | 04/02/2018 12:30:00 | 04/02/2018 21:00:00 | 04/03/2018 12:30:00 | 04/03/2018 15:00:00
2582447 | 245002211 | act--04 SSV | 04 SSV | Completed | Activity | 245002415 | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582447 | 245002211 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002502 |  |  |  |  | 04/01/2018 06:30:00 | 04/01/2018 08:30:00 |  | 04/01/2018 09:30:00
2582448 | 245002216 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002592 |  |  |  |  | 03/30/2018 13:00:00 | 03/30/2018 15:00:00 |  | 03/30/2018 15:00:00
2582448 | 245002216 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002534 |  |  |  |  | 04/01/2018 12:30:00 | 04/01/2018 14:30:00 |  | 04/01/2018 15:00:00
2582448 | 245002216 | 0 | 07 Implementation Complete | Completed | Milestone | 245002651 |  |  |  |  | 01/01/2000 05:30:00 | 04/01/2018 15:00:00 |  | 04/01/2018 15:00:00
2582448 | 245002216 | act--02 Installation | 02 Installation | Completed | Activity | 245002305 | 03/27/2018 12:30:00 | 03/27/2018 15:30:00 | 03/28/2018 08:00:00 | 03/28/2018 15:00:00
2582448 | 245002216 | act--03 Integration | 03 Integration | Completed | Activity | 245002359 | 03/28/2018 12:30:00 | 03/28/2018 21:00:00 | 03/29/2018 12:30:00 | 03/29/2018 15:00:00
2582448 | 245002216 | act--04 SSV | 04 SSV | Completed | Activity | 245002406 | 03/30/2018 12:30:00 | 03/30/2018 14:30:00 | 03/31/2018 08:00:00 | 03/31/2018 15:00:00
2582448 | 245002216 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002480 |  |  |  |  | 03/27/2018 06:30:00 | 03/27/2018 08:30:00 |  | 03/27/2018 09:30:00
2582449 | 245002215 | 0 | 05 NRO IM Accept | Completed | Milestone | 245002580 |  |  |  |  | 05/03/2018 13:00:00 | 05/03/2018 15:00:00 |  | 05/03/2018 15:00:00
2582449 | 245002215 | 0 | 06 NDO IM Accept | Completed | Milestone | 245002525 |  |  |  |  | 05/05/2018 12:30:00 | 05/05/2018 14:30:00 |  | 05/05/2018 15:00:00
2582449 | 245002215 | 0 | 07 Implementation Complete | Completed | Milestone | 245002635 |  |  |  |  | 01/01/2000 05:30:00 | 05/05/2018 15:00:00 |  | 05/05/2018 15:00:00
2582449 | 245002215 | act--02 Installation | 02 Installation | Completed | Activity | 245002295 | 04/30/2018 12:30:00 | 04/30/2018 15:30:00 | 05/01/2018 08:00:00 | 05/01/2018 15:00:00
2582449 | 245002215 | act--03 Integration | 03 Integration | Completed | Activity | 245002351 | 05/01/2018 12:30:00 | 05/01/2018 21:00:00 | 05/02/2018 12:30:00 | 05/02/2018 15:00:00
2582449 | 245002215 | act--04 SSV | 04 SSV | Completed | Activity | 245002405 | 05/03/2018 12:30:00 | 05/03/2018 14:30:00 | 05/04/2018 08:00:00 | 05/04/2018 15:00:00
2582449 | 245002215 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245002464 |  |  |  |  | 04/30/2018 06:30:00 | 04/30/2018 08:30:00 |  | 04/30/2018 09:30:00
2582450 | 245002817 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003219 |  |  |  |  | 04/01/2018 13:00:00 | 04/01/2018 15:00:00 |  | 04/01/2018 15:00:00
2582450 | 245002817 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003162 |  |  |  |  | 04/03/2018 12:30:00 | 04/03/2018 14:30:00 |  | 04/03/2018 15:00:00
2582450 | 245002817 | 0 | 07 Implementation Complete | Completed | Milestone | 245003273 |  |  |  |  | 01/01/2000 05:30:00 | 04/03/2018 15:00:00 |  | 04/03/2018 15:00:00
2582450 | 245002817 | act--02 Installation | 02 Installation | Completed | Activity | 245002915 | 03/29/2018 12:30:00 | 03/29/2018 15:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582450 | 245002817 | act--03 Integration | 03 Integration | Completed | Activity | 245002963 | 03/30/2018 12:30:00 | 03/30/2018 21:00:00 | 03/31/2018 12:30:00 | 03/31/2018 15:00:00
2582450 | 245002817 | act--04 SSV | 04 SSV | Completed | Activity | 245003031 | 04/01/2018 12:30:00 | 04/01/2018 14:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582450 | 245002817 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003098 |  |  |  |  | 03/29/2018 06:30:00 | 03/29/2018 08:30:00 |  | 03/29/2018 09:30:00
2582451 | 245002824 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003211 |  |  |  |  | 04/17/2018 13:00:00 | 04/17/2018 15:00:00 |  | 04/17/2018 15:00:00
2582451 | 245002824 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003157 |  |  |  |  | 04/19/2018 12:30:00 | 04/19/2018 14:30:00 |  | 04/19/2018 15:00:00
2582451 | 245002824 | 0 | 07 Implementation Complete | Completed | Milestone | 245003270 |  |  |  |  | 01/01/2000 05:30:00 | 04/19/2018 15:00:00 |  | 04/19/2018 15:00:00
2582451 | 245002824 | act--02 Installation | 02 Installation | Completed | Activity | 245002916 | 04/14/2018 12:30:00 | 04/14/2018 15:30:00 | 04/15/2018 08:00:00 | 04/15/2018 15:00:00
2582451 | 245002824 | act--03 Integration | 03 Integration | Completed | Activity | 245002974 | 04/15/2018 12:30:00 | 04/15/2018 21:00:00 | 04/16/2018 12:30:00 | 04/16/2018 15:00:00
2582451 | 245002824 | act--04 SSV | 04 SSV | Completed | Activity | 245003041 | 04/17/2018 12:30:00 | 04/17/2018 14:30:00 | 04/18/2018 08:00:00 | 04/18/2018 15:00:00
2582451 | 245002824 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003093 |  |  |  |  | 04/14/2018 06:30:00 | 04/14/2018 08:30:00 |  | 04/14/2018 09:30:00
2582452 | 245002821 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003260 |  |  |  |  | 04/05/2018 13:00:00 | 04/05/2018 15:00:00 |  | 04/05/2018 15:00:00
2582452 | 245002821 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003204 |  |  |  |  | 04/07/2018 12:30:00 | 04/07/2018 14:30:00 |  | 04/07/2018 15:00:00
2582452 | 245002821 | 0 | 07 Implementation Complete | Completed | Milestone | 245003315 |  |  |  |  | 01/01/2000 05:30:00 | 04/07/2018 15:00:00 |  | 04/07/2018 15:00:00
2582452 | 245002821 | act--02 Installation | 02 Installation | Completed | Activity | 245002913 | 04/02/2018 12:30:00 | 04/02/2018 15:30:00 | 04/03/2018 08:00:00 | 04/03/2018 15:00:00
2582452 | 245002821 | act--03 Integration | 03 Integration | Completed | Activity | 245002965 | 04/03/2018 12:30:00 | 04/03/2018 21:00:00 | 04/04/2018 12:30:00 | 04/04/2018 15:00:00
2582452 | 245002821 | act--04 SSV | 04 SSV | Completed | Activity | 245003048 | 04/05/2018 12:30:00 | 04/05/2018 14:30:00 | 04/06/2018 08:00:00 | 04/06/2018 15:00:00
2582452 | 245002821 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003138 |  |  |  |  | 04/02/2018 06:30:00 | 04/02/2018 08:30:00 |  | 04/02/2018 09:30:00
2582453 | 245002819 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003243 |  |  |  |  | 04/16/2018 13:00:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582453 | 245002819 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003187 |  |  |  |  | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 |  | 04/18/2018 15:00:00
2582453 | 245002819 | 0 | 07 Implementation Complete | Completed | Milestone | 245003303 |  |  |  |  | 01/01/2000 05:30:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582453 | 245002819 | act--02 Installation | 02 Installation | Completed | Activity | 245002929 | 04/13/2018 12:30:00 | 04/13/2018 15:30:00 | 04/14/2018 08:00:00 | 04/14/2018 15:00:00
2582453 | 245002819 | act--03 Integration | 03 Integration | Completed | Activity | 245002984 | 04/14/2018 12:30:00 | 04/14/2018 21:00:00 | 04/15/2018 12:30:00 | 04/15/2018 15:00:00
2582453 | 245002819 | act--04 SSV | 04 SSV | Completed | Activity | 245003036 | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 | 04/17/2018 08:00:00 | 04/17/2018 15:00:00
2582453 | 245002819 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003125 |  |  |  |  | 04/13/2018 06:30:00 | 04/13/2018 08:30:00 |  | 04/13/2018 09:30:00
2582454 | 245002820 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003255 |  |  |  |  | 04/20/2018 13:00:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582454 | 245002820 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003194 |  |  |  |  | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 |  | 04/22/2018 15:00:00
2582454 | 245002820 | 0 | 07 Implementation Complete | Completed | Milestone | 245003311 |  |  |  |  | 01/01/2000 05:30:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582454 | 245002820 | act--02 Installation | 02 Installation | Completed | Activity | 245002919 | 04/17/2018 12:30:00 | 04/17/2018 15:30:00 | 04/18/2018 08:00:00 | 04/18/2018 15:00:00
2582454 | 245002820 | act--03 Integration | 03 Integration | Completed | Activity | 245002973 | 04/18/2018 12:30:00 | 04/18/2018 21:00:00 | 04/19/2018 12:30:00 | 04/19/2018 15:00:00
2582454 | 245002820 | act--04 SSV | 04 SSV | Completed | Activity | 245003050 | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 | 04/21/2018 08:00:00 | 04/21/2018 15:00:00
2582454 | 245002820 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003141 |  |  |  |  | 04/17/2018 06:30:00 | 04/17/2018 08:30:00 |  | 04/17/2018 09:30:00
2582455 | 245002822 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003240 |  |  |  |  | 05/08/2018 13:00:00 | 05/08/2018 15:00:00 |  | 05/08/2018 15:00:00
2582455 | 245002822 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003180 |  |  |  |  | 05/10/2018 12:30:00 | 05/10/2018 14:30:00 |  | 05/10/2018 15:00:00
2582455 | 245002822 | 0 | 07 Implementation Complete | Completed | Milestone | 245003294 |  |  |  |  | 01/01/2000 05:30:00 | 05/10/2018 15:00:00 |  | 05/10/2018 15:00:00
2582455 | 245002822 | act--02 Installation | 02 Installation | Completed | Activity | 245002927 | 05/05/2018 12:30:00 | 05/05/2018 15:30:00 | 05/06/2018 08:00:00 | 05/06/2018 15:00:00
2582455 | 245002822 | act--03 Integration | 03 Integration | Completed | Activity | 245002985 | 05/06/2018 12:30:00 | 05/06/2018 21:00:00 | 05/07/2018 12:30:00 | 05/07/2018 15:00:00
2582455 | 245002822 | act--04 SSV | 04 SSV | Completed | Activity | 245003046 | 05/08/2018 12:30:00 | 05/08/2018 14:30:00 | 05/09/2018 08:00:00 | 05/09/2018 15:00:00
2582455 | 245002822 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003121 |  |  |  |  | 05/05/2018 06:30:00 | 05/05/2018 08:30:00 |  | 05/05/2018 09:30:00
2582456 | 245002818 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003263 |  |  |  |  | 04/11/2018 13:00:00 | 04/11/2018 15:00:00 |  | 04/11/2018 15:00:00
2582456 | 245002818 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003201 |  |  |  |  | 04/13/2018 12:30:00 | 04/13/2018 14:30:00 |  | 04/13/2018 15:00:00
2582456 | 245002818 | 0 | 07 Implementation Complete | Completed | Milestone | 245003320 |  |  |  |  | 01/01/2000 05:30:00 | 04/13/2018 15:00:00 |  | 04/13/2018 15:00:00
2582456 | 245002818 | act--02 Installation | 02 Installation | Completed | Activity | 245002918 | 04/08/2018 12:30:00 | 04/08/2018 15:30:00 | 04/09/2018 08:00:00 | 04/09/2018 15:00:00
2582456 | 245002818 | act--03 Integration | 03 Integration | Completed | Activity | 245002980 | 04/09/2018 12:30:00 | 04/09/2018 21:00:00 | 04/10/2018 12:30:00 | 04/10/2018 15:00:00
2582456 | 245002818 | act--04 SSV | 04 SSV | Completed | Activity | 245003049 | 04/11/2018 12:30:00 | 04/11/2018 14:30:00 | 04/12/2018 08:00:00 | 04/12/2018 15:00:00
2582456 | 245002818 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003142 |  |  |  |  | 04/08/2018 06:30:00 | 04/08/2018 08:30:00 |  | 04/08/2018 09:30:00
2582457 | 245002826 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003248 |  |  |  |  | 04/26/2018 13:00:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582457 | 245002826 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003186 |  |  |  |  | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 |  | 04/28/2018 15:00:00
2582457 | 245002826 | 0 | 07 Implementation Complete | Completed | Milestone | 245003307 |  |  |  |  | 01/01/2000 05:30:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582457 | 245002826 | act--02 Installation | 02 Installation | Completed | Activity | 245002924 | 04/23/2018 12:30:00 | 04/23/2018 15:30:00 | 04/24/2018 08:00:00 | 04/24/2018 15:00:00
2582457 | 245002826 | act--03 Integration | 03 Integration | Completed | Activity | 245002986 | 04/24/2018 12:30:00 | 04/24/2018 21:00:00 | 04/25/2018 12:30:00 | 04/25/2018 15:00:00
2582457 | 245002826 | act--04 SSV | 04 SSV | Completed | Activity | 245003051 | 04/26/2018 12:30:00 | 04/26/2018 14:30:00 | 04/27/2018 08:00:00 | 04/27/2018 15:00:00
2582457 | 245002826 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003124 |  |  |  |  | 04/23/2018 06:30:00 | 04/23/2018 08:30:00 |  | 04/23/2018 09:30:00
2582458 | 245002827 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003229 |  |  |  |  | 04/25/2018 13:00:00 | 04/25/2018 15:00:00 |  | 04/25/2018 15:00:00
2582458 | 245002827 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003165 |  |  |  |  | 04/27/2018 12:30:00 | 04/27/2018 14:30:00 |  | 04/27/2018 15:00:00
2582458 | 245002827 | 0 | 07 Implementation Complete | Completed | Milestone | 245003290 |  |  |  |  | 01/01/2000 05:30:00 | 04/27/2018 15:00:00 |  | 04/27/2018 15:00:00
2582458 | 245002827 | act--02 Installation | 02 Installation | Completed | Activity | 245002914 | 04/22/2018 12:30:00 | 04/22/2018 15:30:00 | 04/23/2018 08:00:00 | 04/23/2018 15:00:00
2582458 | 245002827 | act--03 Integration | 03 Integration | Completed | Activity | 245002960 | 04/23/2018 12:30:00 | 04/23/2018 21:00:00 | 04/24/2018 12:30:00 | 04/24/2018 15:00:00
2582458 | 245002827 | act--04 SSV | 04 SSV | Completed | Activity | 245003035 | 04/25/2018 12:30:00 | 04/25/2018 14:30:00 | 04/26/2018 08:00:00 | 04/26/2018 15:00:00
2582458 | 245002827 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003103 |  |  |  |  | 04/22/2018 06:30:00 | 04/22/2018 08:30:00 |  | 04/22/2018 09:30:00
2582459 | 245002828 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003237 |  |  |  |  | 04/29/2018 13:00:00 | 04/29/2018 15:00:00 |  | 04/29/2018 15:00:00
2582459 | 245002828 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003179 |  |  |  |  | 05/01/2018 12:30:00 | 05/01/2018 14:30:00 |  | 05/01/2018 15:00:00
2582459 | 245002828 | 0 | 07 Implementation Complete | Completed | Milestone | 245003298 |  |  |  |  | 01/01/2000 05:30:00 | 05/01/2018 15:00:00 |  | 05/01/2018 15:00:00
2582459 | 245002828 | act--02 Installation | 02 Installation | Completed | Activity | 245002920 | 04/26/2018 12:30:00 | 04/26/2018 15:30:00 | 04/27/2018 08:00:00 | 04/27/2018 15:00:00
2582459 | 245002828 | act--03 Integration | 03 Integration | Completed | Activity | 245002988 | 04/27/2018 12:30:00 | 04/27/2018 21:00:00 | 04/28/2018 12:30:00 | 04/28/2018 15:00:00
2582459 | 245002828 | act--04 SSV | 04 SSV | Completed | Activity | 245003044 | 04/29/2018 12:30:00 | 04/29/2018 14:30:00 | 04/30/2018 08:00:00 | 04/30/2018 15:00:00
2582459 | 245002828 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003127 |  |  |  |  | 04/26/2018 06:30:00 | 04/26/2018 08:30:00 |  | 04/26/2018 09:30:00
2582460 | 245002823 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003268 |  |  |  |  | 04/08/2018 13:00:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582460 | 245002823 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003209 |  |  |  |  | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 |  | 04/10/2018 15:00:00
2582460 | 245002823 | 0 | 07 Implementation Complete | Completed | Milestone | 245003331 |  |  |  |  | 01/01/2000 05:30:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582460 | 245002823 | act--02 Installation | 02 Installation | Completed | Activity | 245002921 | 04/05/2018 12:30:00 | 04/05/2018 15:30:00 | 04/06/2018 08:00:00 | 04/06/2018 15:00:00
2582460 | 245002823 | act--03 Integration | 03 Integration | Completed | Activity | 245002981 | 04/06/2018 12:30:00 | 04/06/2018 21:00:00 | 04/07/2018 12:30:00 | 04/07/2018 15:00:00
2582460 | 245002823 | act--04 SSV | 04 SSV | Completed | Activity | 245003058 | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 | 04/09/2018 08:00:00 | 04/09/2018 15:00:00
2582460 | 245002823 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003150 |  |  |  |  | 04/05/2018 06:30:00 | 04/05/2018 08:30:00 |  | 04/05/2018 09:30:00
2582461 | 245002825 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003221 |  |  |  |  | 05/16/2018 13:00:00 | 05/16/2018 15:00:00 |  | 05/16/2018 15:00:00
2582461 | 245002825 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003164 |  |  |  |  | 05/18/2018 12:30:00 | 05/18/2018 14:30:00 |  | 05/18/2018 15:00:00
2582461 | 245002825 | 0 | 07 Implementation Complete | Completed | Milestone | 245003278 |  |  |  |  | 01/01/2000 05:30:00 | 05/18/2018 15:00:00 |  | 05/18/2018 15:00:00
2582461 | 245002825 | act--02 Installation | 02 Installation | Completed | Activity | 245002922 | 05/13/2018 12:30:00 | 05/13/2018 15:30:00 | 05/14/2018 08:00:00 | 05/14/2018 15:00:00
2582461 | 245002825 | act--03 Integration | 03 Integration | Completed | Activity | 245002987 | 05/14/2018 12:30:00 | 05/14/2018 21:00:00 | 05/15/2018 12:30:00 | 05/15/2018 15:00:00
2582461 | 245002825 | act--04 SSV | 04 SSV | Completed | Activity | 245003056 | 05/16/2018 12:30:00 | 05/16/2018 14:30:00 | 05/17/2018 08:00:00 | 05/17/2018 15:00:00
2582461 | 245002825 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003104 |  |  |  |  | 05/13/2018 06:30:00 | 05/13/2018 08:30:00 |  | 05/13/2018 09:30:00
2582462 | 245002829 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003220 |  |  |  |  | 04/28/2018 13:00:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582462 | 245002829 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003163 |  |  |  |  | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 |  | 04/30/2018 15:00:00
2582462 | 245002829 | 0 | 07 Implementation Complete | Completed | Milestone | 245003275 |  |  |  |  | 01/01/2000 05:30:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582462 | 245002829 | act--02 Installation | 02 Installation | Completed | Activity | 245002928 | 04/25/2018 12:30:00 | 04/25/2018 15:30:00 | 04/26/2018 08:00:00 | 04/26/2018 15:00:00
2582462 | 245002829 | act--03 Integration | 03 Integration | Completed | Activity | 245002969 | 04/26/2018 12:30:00 | 04/26/2018 21:00:00 | 04/27/2018 12:30:00 | 04/27/2018 15:00:00
2582462 | 245002829 | act--04 SSV | 04 SSV | Completed | Activity | 245003029 | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 | 04/29/2018 08:00:00 | 04/29/2018 15:00:00
2582462 | 245002829 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003096 |  |  |  |  | 04/25/2018 06:30:00 | 04/25/2018 08:30:00 |  | 04/25/2018 09:30:00
2582463 | 245002831 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003241 |  |  |  |  | 04/27/2018 13:00:00 | 04/27/2018 15:00:00 |  | 04/27/2018 15:00:00
2582463 | 245002831 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003185 |  |  |  |  | 04/29/2018 12:30:00 | 04/29/2018 14:30:00 |  | 04/29/2018 15:00:00
2582463 | 245002831 | 0 | 07 Implementation Complete | Completed | Milestone | 245003289 |  |  |  |  | 01/01/2000 05:30:00 | 04/29/2018 15:00:00 |  | 04/29/2018 15:00:00
2582463 | 245002831 | act--02 Installation | 02 Installation | Completed | Activity | 245002931 | 04/24/2018 12:30:00 | 04/24/2018 15:30:00 | 04/25/2018 08:00:00 | 04/25/2018 15:00:00
2582463 | 245002831 | act--03 Integration | 03 Integration | Completed | Activity | 245002982 | 04/25/2018 12:30:00 | 04/25/2018 21:00:00 | 04/26/2018 12:30:00 | 04/26/2018 15:00:00
2582463 | 245002831 | act--04 SSV | 04 SSV | Completed | Activity | 245003054 | 04/27/2018 12:30:00 | 04/27/2018 14:30:00 | 04/28/2018 08:00:00 | 04/28/2018 15:00:00
2582463 | 245002831 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003120 |  |  |  |  | 04/24/2018 06:30:00 | 04/24/2018 08:30:00 |  | 04/24/2018 09:30:00
2582464 | 245002833 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003236 |  |  |  |  | 04/14/2018 13:00:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582464 | 245002833 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003178 |  |  |  |  | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 |  | 04/16/2018 15:00:00
2582464 | 245002833 | 0 | 07 Implementation Complete | Completed | Milestone | 245003281 |  |  |  |  | 01/01/2000 05:30:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582464 | 245002833 | act--02 Installation | 02 Installation | Completed | Activity | 245002932 | 04/11/2018 12:30:00 | 04/11/2018 15:30:00 | 04/12/2018 08:00:00 | 04/12/2018 15:00:00
2582464 | 245002833 | act--03 Integration | 03 Integration | Completed | Activity | 245002999 | 04/12/2018 12:30:00 | 04/12/2018 21:00:00 | 04/13/2018 12:30:00 | 04/13/2018 15:00:00
2582464 | 245002833 | act--04 SSV | 04 SSV | Completed | Activity | 245003053 | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 | 04/15/2018 08:00:00 | 04/15/2018 15:00:00
2582464 | 245002833 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003119 |  |  |  |  | 04/11/2018 06:30:00 | 04/11/2018 08:30:00 |  | 04/11/2018 09:30:00
2582465 | 245002836 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003225 |  |  |  |  | 04/20/2018 13:00:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582465 | 245002836 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003172 |  |  |  |  | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 |  | 04/22/2018 15:00:00
2582465 | 245002836 | 0 | 07 Implementation Complete | Completed | Milestone | 245003291 |  |  |  |  | 01/01/2000 05:30:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582465 | 245002836 | act--02 Installation | 02 Installation | Completed | Activity | 245002923 | 04/17/2018 12:30:00 | 04/17/2018 15:30:00 | 04/18/2018 08:00:00 | 04/18/2018 15:00:00
2582465 | 245002836 | act--03 Integration | 03 Integration | Completed | Activity | 245002989 | 04/18/2018 12:30:00 | 04/18/2018 21:00:00 | 04/19/2018 12:30:00 | 04/19/2018 15:00:00
2582465 | 245002836 | act--04 SSV | 04 SSV | Completed | Activity | 245003057 | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 | 04/21/2018 08:00:00 | 04/21/2018 15:00:00
2582465 | 245002836 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003111 |  |  |  |  | 04/17/2018 06:30:00 | 04/17/2018 08:30:00 |  | 04/17/2018 09:30:00
2582466 | 245002832 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003254 |  |  |  |  | 03/23/2018 13:00:00 | 03/23/2018 15:00:00 |  | 03/23/2018 15:00:00
2582466 | 245002832 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003197 |  |  |  |  | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 |  | 03/25/2018 15:00:00
2582466 | 245002832 | 0 | 07 Implementation Complete | Completed | Milestone | 245003312 |  |  |  |  | 01/01/2000 05:30:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582466 | 245002832 | act--02 Installation | 02 Installation | Completed | Activity | 245002933 | 03/20/2018 12:30:00 | 03/20/2018 15:30:00 | 03/21/2018 08:00:00 | 03/21/2018 15:00:00
2582466 | 245002832 | act--03 Integration | 03 Integration | Completed | Activity | 245002995 | 03/21/2018 12:30:00 | 03/21/2018 21:00:00 | 03/22/2018 12:30:00 | 03/22/2018 15:00:00
2582466 | 245002832 | act--04 SSV | 04 SSV | Completed | Activity | 245003059 | 03/23/2018 12:30:00 | 03/23/2018 14:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582466 | 245002832 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003137 |  |  |  |  | 03/20/2018 06:30:00 | 03/20/2018 08:30:00 |  | 03/20/2018 09:30:00
2582467 | 245002834 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003233 |  |  |  |  | 04/08/2018 13:00:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582467 | 245002834 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003175 |  |  |  |  | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 |  | 04/10/2018 15:00:00
2582467 | 245002834 | 0 | 07 Implementation Complete | Completed | Milestone | 245003293 |  |  |  |  | 01/01/2000 05:30:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582467 | 245002834 | act--02 Installation | 02 Installation | Completed | Activity | 245002934 | 04/05/2018 12:30:00 | 04/05/2018 15:30:00 | 04/06/2018 08:00:00 | 04/06/2018 15:00:00
2582467 | 245002834 | act--03 Integration | 03 Integration | Completed | Activity | 245002992 | 04/06/2018 12:30:00 | 04/06/2018 21:00:00 | 04/07/2018 12:30:00 | 04/07/2018 15:00:00
2582467 | 245002834 | act--04 SSV | 04 SSV | Completed | Activity | 245003047 | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 | 04/09/2018 08:00:00 | 04/09/2018 15:00:00
2582467 | 245002834 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003113 |  |  |  |  | 04/05/2018 06:30:00 | 04/05/2018 08:30:00 |  | 04/05/2018 09:30:00
2582468 | 245002846 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003269 |  |  |  |  | 04/18/2018 13:00:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582468 | 245002846 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003214 |  |  |  |  | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 |  | 04/20/2018 15:00:00
2582468 | 245002846 | 0 | 07 Implementation Complete | Completed | Milestone | 245003327 |  |  |  |  | 01/01/2000 05:30:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582468 | 245002846 | act--02 Installation | 02 Installation | Completed | Activity | 245002936 | 04/15/2018 12:30:00 | 04/15/2018 15:30:00 | 04/16/2018 08:00:00 | 04/16/2018 15:00:00
2582468 | 245002846 | act--03 Integration | 03 Integration | Completed | Activity | 245002998 | 04/16/2018 12:30:00 | 04/16/2018 21:00:00 | 04/17/2018 12:30:00 | 04/17/2018 15:00:00
2582468 | 245002846 | act--04 SSV | 04 SSV | Completed | Activity | 245003065 | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 | 04/19/2018 08:00:00 | 04/19/2018 15:00:00
2582468 | 245002846 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003156 |  |  |  |  | 04/15/2018 06:30:00 | 04/15/2018 08:30:00 |  | 04/15/2018 09:30:00
2582469 | 245003472 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003827 |  |  |  |  | 04/12/2018 13:00:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582469 | 245003472 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003769 |  |  |  |  | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 |  | 04/14/2018 15:00:00
2582469 | 245003472 | 0 | 07 Implementation Complete | Completed | Milestone | 245003879 |  |  |  |  | 01/01/2000 05:30:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582469 | 245003472 | act--02 Installation | 02 Installation | Completed | Activity | 245003566 | 04/09/2018 12:30:00 | 04/09/2018 15:30:00 | 04/10/2018 08:00:00 | 04/10/2018 15:00:00
2582469 | 245003472 | act--03 Integration | 03 Integration | Completed | Activity | 245003609 | 04/10/2018 12:30:00 | 04/10/2018 21:00:00 | 04/11/2018 12:30:00 | 04/11/2018 15:00:00
2582469 | 245003472 | act--04 SSV | 04 SSV | Completed | Activity | 245003668 | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 | 04/13/2018 08:00:00 | 04/13/2018 15:00:00
2582469 | 245003472 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003726 |  |  |  |  | 04/09/2018 06:30:00 | 04/09/2018 08:30:00 |  | 04/09/2018 09:30:00
2582470 | 245003471 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003858 |  |  |  |  | 03/31/2018 13:00:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582470 | 245003471 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003801 |  |  |  |  | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 |  | 04/02/2018 15:00:00
2582470 | 245003471 | 0 | 07 Implementation Complete | Completed | Milestone | 245003914 |  |  |  |  | 01/01/2000 05:30:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582470 | 245003471 | act--02 Installation | 02 Installation | Completed | Activity | 245003567 | 03/28/2018 12:30:00 | 03/28/2018 15:30:00 | 03/29/2018 08:00:00 | 03/29/2018 15:00:00
2582470 | 245003471 | act--03 Integration | 03 Integration | Completed | Activity | 245003618 | 03/29/2018 12:30:00 | 03/29/2018 21:00:00 | 03/30/2018 12:30:00 | 03/30/2018 15:00:00
2582470 | 245003471 | act--04 SSV | 04 SSV | Completed | Activity | 245003678 | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 | 04/01/2018 08:00:00 | 04/01/2018 15:00:00
2582470 | 245003471 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003738 |  |  |  |  | 03/28/2018 06:30:00 | 03/28/2018 08:30:00 |  | 03/28/2018 09:30:00
2582471 | 245003470 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003855 |  |  |  |  | 04/22/2018 13:00:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582471 | 245003470 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003794 |  |  |  |  | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 |  | 04/24/2018 15:00:00
2582471 | 245003470 | 0 | 07 Implementation Complete | Completed | Milestone | 245003913 |  |  |  |  | 01/01/2000 05:30:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582471 | 245003470 | act--02 Installation | 02 Installation | Completed | Activity | 245003568 | 04/19/2018 12:30:00 | 04/19/2018 15:30:00 | 04/20/2018 08:00:00 | 04/20/2018 15:00:00
2582471 | 245003470 | act--03 Integration | 03 Integration | Completed | Activity | 245003619 | 04/20/2018 12:30:00 | 04/20/2018 21:00:00 | 04/21/2018 12:30:00 | 04/21/2018 15:00:00
2582471 | 245003470 | act--04 SSV | 04 SSV | Completed | Activity | 245003669 | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 | 04/23/2018 08:00:00 | 04/23/2018 15:00:00
2582471 | 245003470 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003730 |  |  |  |  | 04/19/2018 06:30:00 | 04/19/2018 08:30:00 |  | 04/19/2018 09:30:00
2582472 | 245003474 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003848 |  |  |  |  | 04/26/2018 13:00:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582472 | 245003474 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003790 |  |  |  |  | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 |  | 04/28/2018 15:00:00
2582472 | 245003474 | 0 | 07 Implementation Complete | Completed | Milestone | 245003912 |  |  |  |  | 01/01/2000 05:30:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582472 | 245003474 | act--02 Installation | 02 Installation | Completed | Activity | 245003569 | 04/23/2018 12:30:00 | 04/23/2018 15:30:00 | 04/24/2018 08:00:00 | 04/24/2018 15:00:00
2582472 | 245003474 | act--03 Integration | 03 Integration | Completed | Activity | 245003623 | 06/02/2018 12:30:00 | 06/02/2018 15:00:00 | 04/25/2018 12:30:00 | 04/25/2018 15:00:00
2582472 | 245003474 | act--04 SSV | 04 SSV | Completed | Activity | 245003681 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 04/27/2018 08:00:00 | 04/27/2018 15:00:00
2582472 | 245003474 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003740 |  |  |  |  | 04/23/2018 06:30:00 | 04/23/2018 08:30:00 |  | 04/23/2018 09:30:00
2582473 | 245003476 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003882 |  |  |  |  | 05/18/2018 13:00:00 | 05/18/2018 15:00:00 |  | 05/18/2018 15:00:00
2582473 | 245003476 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003825 |  |  |  |  | 05/20/2018 12:30:00 | 05/20/2018 14:30:00 |  | 05/20/2018 15:00:00
2582473 | 245003476 | 0 | 07 Implementation Complete | Completed | Milestone | 245003933 |  |  |  |  | 01/01/2000 05:30:00 | 05/20/2018 15:00:00 |  | 05/20/2018 15:00:00
2582473 | 245003476 | act--02 Installation | 02 Installation | Completed | Activity | 245003570 | 05/15/2018 12:30:00 | 05/15/2018 15:30:00 | 05/16/2018 08:00:00 | 05/16/2018 15:00:00
2582473 | 245003476 | act--03 Integration | 03 Integration | Completed | Activity | 245003639 | 05/16/2018 12:30:00 | 05/16/2018 21:00:00 | 05/17/2018 12:30:00 | 05/17/2018 15:00:00
2582473 | 245003476 | act--04 SSV | 04 SSV | Completed | Activity | 245003702 | 05/18/2018 12:30:00 | 05/18/2018 14:30:00 | 05/19/2018 08:00:00 | 05/19/2018 15:00:00
2582473 | 245003476 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003776 |  |  |  |  | 05/15/2018 06:30:00 | 05/15/2018 08:30:00 |  | 05/15/2018 09:30:00
2582474 | 245003473 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003904 |  |  |  |  | 06/04/2018 13:00:00 | 06/04/2018 15:00:00 |  | 06/04/2018 15:00:00
2582474 | 245003473 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003850 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582474 | 245003473 | 0 | 07 Implementation Complete | Completed | Milestone | 245003961 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582474 | 245003473 | act--02 Installation | 02 Installation | Completed | Activity | 245003573 | 06/01/2018 12:30:00 | 06/01/2018 15:00:00 | 06/02/2018 07:00:00 | 06/02/2018 15:30:00
2582474 | 245003473 | act--03 Integration | 03 Integration | Completed | Activity | 245003647 | 06/02/2018 12:30:00 | 06/02/2018 23:00:00 | 06/03/2018 11:30:00 | 06/03/2018 15:30:00
2582474 | 245003473 | act--04 SSV | 04 SSV | Completed | Activity | 245003708 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582474 | 245003473 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003792 |  |  |  |  | 06/01/2018 06:30:00 | 06/01/2018 07:30:00 |  | 06/01/2018 08:30:00
2582475 | 245003477 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003888 |  |  |  |  | 04/24/2018 13:00:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582475 | 245003477 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003831 |  |  |  |  | 04/26/2018 12:30:00 | 04/26/2018 14:30:00 |  | 04/26/2018 15:00:00
2582475 | 245003477 | 0 | 07 Implementation Complete | Completed | Milestone | 245003950 |  |  |  |  | 01/01/2000 05:30:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582475 | 245003477 | act--02 Installation | 02 Installation | Completed | Activity | 245003572 | 04/21/2018 12:30:00 | 04/21/2018 15:30:00 | 04/22/2018 08:00:00 | 04/22/2018 15:00:00
2582475 | 245003477 | act--03 Integration | 03 Integration | Completed | Activity | 245003635 | 04/22/2018 12:30:00 | 04/22/2018 21:00:00 | 04/23/2018 12:30:00 | 04/23/2018 15:00:00
2582475 | 245003477 | act--04 SSV | 04 SSV | Completed | Activity | 245003700 | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 | 04/25/2018 08:00:00 | 04/25/2018 15:00:00
2582475 | 245003477 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003768 |  |  |  |  | 04/21/2018 06:30:00 | 04/21/2018 08:30:00 |  | 04/21/2018 09:30:00
2582476 | 245003478 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003894 |  |  |  |  | 03/24/2018 13:00:00 | 03/24/2018 15:00:00 |  | 03/24/2018 15:00:00
2582476 | 245003478 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003834 |  |  |  |  | 03/26/2018 12:30:00 | 03/26/2018 14:30:00 |  | 03/26/2018 15:00:00
2582476 | 245003478 | 0 | 07 Implementation Complete | Completed | Milestone | 245003953 |  |  |  |  | 01/01/2000 05:30:00 | 03/26/2018 15:00:00 |  | 03/26/2018 15:00:00
2582476 | 245003478 | act--02 Installation | 02 Installation | Completed | Activity | 245003571 | 03/21/2018 12:30:00 | 03/21/2018 15:30:00 | 03/22/2018 08:00:00 | 03/22/2018 15:00:00
2582476 | 245003478 | act--03 Integration | 03 Integration | Completed | Activity | 245003636 | 03/22/2018 12:30:00 | 03/22/2018 21:00:00 | 03/23/2018 12:30:00 | 03/23/2018 15:00:00
2582476 | 245003478 | act--04 SSV | 04 SSV | Completed | Activity | 245003698 | 03/24/2018 12:30:00 | 03/24/2018 14:30:00 | 03/25/2018 08:00:00 | 03/25/2018 15:00:00
2582476 | 245003478 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003770 |  |  |  |  | 03/21/2018 06:30:00 | 03/21/2018 08:30:00 |  | 03/21/2018 09:30:00
2582477 | 245003479 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003871 |  |  |  |  | 03/28/2018 13:00:00 | 03/28/2018 15:00:00 |  | 03/28/2018 15:00:00
2582477 | 245003479 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003818 |  |  |  |  | 03/30/2018 12:30:00 | 03/30/2018 14:30:00 |  | 03/30/2018 15:00:00
2582477 | 245003479 | 0 | 07 Implementation Complete | Completed | Milestone | 245003931 |  |  |  |  | 01/01/2000 05:30:00 | 03/30/2018 15:00:00 |  | 03/30/2018 15:00:00
2582477 | 245003479 | act--02 Installation | 02 Installation | Completed | Activity | 245003577 | 03/25/2018 12:30:00 | 03/25/2018 15:30:00 | 03/26/2018 08:00:00 | 03/26/2018 15:00:00
2582477 | 245003479 | act--03 Integration | 03 Integration | Completed | Activity | 245003631 | 03/26/2018 12:30:00 | 03/26/2018 21:00:00 | 03/27/2018 12:30:00 | 03/27/2018 15:00:00
2582477 | 245003479 | act--04 SSV | 04 SSV | Completed | Activity | 245003687 | 03/28/2018 12:30:00 | 03/28/2018 14:30:00 | 03/29/2018 08:00:00 | 03/29/2018 15:00:00
2582477 | 245003479 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003757 |  |  |  |  | 03/25/2018 06:30:00 | 03/25/2018 08:30:00 |  | 03/25/2018 09:30:00
2582478 | 245003475 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003891 |  |  |  |  | 05/17/2018 13:00:00 | 05/17/2018 15:00:00 |  | 05/17/2018 15:00:00
2582478 | 245003475 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003830 |  |  |  |  | 05/19/2018 12:30:00 | 05/19/2018 14:30:00 |  | 05/19/2018 15:00:00
2582478 | 245003475 | 0 | 07 Implementation Complete | Completed | Milestone | 245003952 |  |  |  |  | 01/01/2000 05:30:00 | 05/19/2018 15:00:00 |  | 05/19/2018 15:00:00
2582478 | 245003475 | act--02 Installation | 02 Installation | Completed | Activity | 245003575 | 05/14/2018 12:30:00 | 05/14/2018 15:30:00 | 05/15/2018 08:00:00 | 05/15/2018 15:00:00
2582478 | 245003475 | act--03 Integration | 03 Integration | Completed | Activity | 245003630 | 05/15/2018 12:30:00 | 05/15/2018 21:00:00 | 05/16/2018 12:30:00 | 05/16/2018 15:00:00
2582478 | 245003475 | act--04 SSV | 04 SSV | Completed | Activity | 245003697 | 05/17/2018 12:30:00 | 05/17/2018 14:30:00 | 05/18/2018 08:00:00 | 05/18/2018 15:00:00
2582478 | 245003475 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003774 |  |  |  |  | 05/14/2018 06:30:00 | 05/14/2018 08:30:00 |  | 05/14/2018 09:30:00
2582479 | 245003480 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003872 |  |  |  |  | 04/09/2018 13:00:00 | 04/09/2018 15:00:00 |  | 04/09/2018 15:00:00
2582479 | 245003480 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003813 |  |  |  |  | 04/11/2018 12:30:00 | 04/11/2018 14:30:00 |  | 04/11/2018 15:00:00
2582479 | 245003480 | 0 | 07 Implementation Complete | Completed | Milestone | 245003929 |  |  |  |  | 01/01/2000 05:30:00 | 04/11/2018 15:00:00 |  | 04/11/2018 15:00:00
2582479 | 245003480 | act--02 Installation | 02 Installation | Completed | Activity | 245003581 | 04/06/2018 12:30:00 | 04/06/2018 15:30:00 | 04/07/2018 08:00:00 | 04/07/2018 15:00:00
2582479 | 245003480 | act--03 Integration | 03 Integration | Completed | Activity | 245003638 | 04/07/2018 12:30:00 | 04/07/2018 21:00:00 | 04/08/2018 12:30:00 | 04/08/2018 15:00:00
2582479 | 245003480 | act--04 SSV | 04 SSV | Completed | Activity | 245003685 | 04/09/2018 12:30:00 | 04/09/2018 14:30:00 | 04/10/2018 08:00:00 | 04/10/2018 15:00:00
2582479 | 245003480 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003749 |  |  |  |  | 04/06/2018 06:30:00 | 04/06/2018 08:30:00 |  | 04/06/2018 09:30:00
2582480 | 245003481 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003875 |  |  |  |  | 04/02/2018 13:00:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582480 | 245003481 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003819 |  |  |  |  | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 |  | 04/04/2018 15:00:00
2582480 | 245003481 | 0 | 07 Implementation Complete | Completed | Milestone | 245003935 |  |  |  |  | 01/01/2000 05:30:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582480 | 245003481 | act--02 Installation | 02 Installation | Completed | Activity | 245003576 | 03/30/2018 12:30:00 | 03/30/2018 15:30:00 | 03/31/2018 08:00:00 | 03/31/2018 15:00:00
2582480 | 245003481 | act--03 Integration | 03 Integration | Completed | Activity | 245003633 | 03/31/2018 12:30:00 | 03/31/2018 21:00:00 | 04/01/2018 12:30:00 | 04/01/2018 15:00:00
2582480 | 245003481 | act--04 SSV | 04 SSV | Completed | Activity | 245003696 | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 | 04/03/2018 08:00:00 | 04/03/2018 15:00:00
2582480 | 245003481 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003765 |  |  |  |  | 03/30/2018 06:30:00 | 03/30/2018 08:30:00 |  | 03/30/2018 09:30:00
2582481 | 245003483 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003878 |  |  |  |  | 04/06/2018 13:00:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582481 | 245003483 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003823 |  |  |  |  | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 |  | 04/08/2018 15:00:00
2582481 | 245003483 | 0 | 07 Implementation Complete | Completed | Milestone | 245003932 |  |  |  |  | 01/01/2000 05:30:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582481 | 245003483 | act--02 Installation | 02 Installation | Completed | Activity | 245003578 | 04/03/2018 12:30:00 | 04/03/2018 15:30:00 | 04/04/2018 08:00:00 | 04/04/2018 15:00:00
2582481 | 245003483 | act--03 Integration | 03 Integration | Completed | Activity | 245003641 | 04/04/2018 12:30:00 | 04/04/2018 21:00:00 | 04/05/2018 12:30:00 | 04/05/2018 15:00:00
2582481 | 245003483 | act--04 SSV | 04 SSV | Completed | Activity | 245003690 | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 | 04/07/2018 08:00:00 | 04/07/2018 15:00:00
2582481 | 245003483 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003755 |  |  |  |  | 04/03/2018 06:30:00 | 04/03/2018 08:30:00 |  | 04/03/2018 09:30:00
2582482 | 245003484 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003901 |  |  |  |  | 05/01/2018 13:00:00 | 05/01/2018 15:00:00 |  | 05/01/2018 15:00:00
2582482 | 245003484 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003842 |  |  |  |  | 05/03/2018 12:30:00 | 05/03/2018 14:30:00 |  | 05/03/2018 15:00:00
2582482 | 245003484 | 0 | 07 Implementation Complete | Completed | Milestone | 245003954 |  |  |  |  | 01/01/2000 05:30:00 | 05/03/2018 15:00:00 |  | 05/03/2018 15:00:00
2582482 | 245003484 | act--02 Installation | 02 Installation | Completed | Activity | 245003580 | 04/28/2018 12:30:00 | 04/28/2018 15:30:00 | 04/29/2018 08:00:00 | 04/29/2018 15:00:00
2582482 | 245003484 | act--03 Integration | 03 Integration | Completed | Activity | 245003642 | 04/29/2018 12:30:00 | 04/29/2018 21:00:00 | 04/30/2018 12:30:00 | 04/30/2018 15:00:00
2582482 | 245003484 | act--04 SSV | 04 SSV | Completed | Activity | 245003701 | 05/01/2018 12:30:00 | 05/01/2018 14:30:00 | 05/02/2018 08:00:00 | 05/02/2018 15:00:00
2582482 | 245003484 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003779 |  |  |  |  | 04/28/2018 06:30:00 | 04/28/2018 08:30:00 |  | 04/28/2018 09:30:00
2582483 | 245003489 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003911 |  |  |  |  | 03/31/2018 13:00:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582483 | 245003489 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003854 |  |  |  |  | 04/02/2018 12:30:00 | 04/02/2018 14:30:00 |  | 04/02/2018 15:00:00
2582483 | 245003489 | 0 | 07 Implementation Complete | Completed | Milestone | 245003968 |  |  |  |  | 01/01/2000 05:30:00 | 04/02/2018 15:00:00 |  | 04/02/2018 15:00:00
2582483 | 245003489 | act--02 Installation | 02 Installation | Completed | Activity | 245003579 | 03/28/2018 12:30:00 | 03/28/2018 15:30:00 | 03/29/2018 08:00:00 | 03/29/2018 15:00:00
2582483 | 245003489 | act--03 Integration | 03 Integration | Completed | Activity | 245003650 | 03/29/2018 12:30:00 | 03/29/2018 21:00:00 | 03/30/2018 12:30:00 | 03/30/2018 15:00:00
2582483 | 245003489 | act--04 SSV | 04 SSV | Completed | Activity | 245003714 | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 | 04/01/2018 08:00:00 | 04/01/2018 15:00:00
2582483 | 245003489 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003798 |  |  |  |  | 03/28/2018 06:30:00 | 03/28/2018 08:30:00 |  | 03/28/2018 09:30:00
2582484 | 245003486 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003873 |  |  |  |  | 04/03/2018 13:00:00 | 04/03/2018 15:00:00 |  | 04/03/2018 15:00:00
2582484 | 245003486 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003817 |  |  |  |  | 04/05/2018 12:30:00 | 04/05/2018 14:30:00 |  | 04/05/2018 15:00:00
2582484 | 245003486 | 0 | 07 Implementation Complete | Completed | Milestone | 245003927 |  |  |  |  | 01/01/2000 05:30:00 | 04/05/2018 15:00:00 |  | 04/05/2018 15:00:00
2582484 | 245003486 | act--02 Installation | 02 Installation | Completed | Activity | 245003586 | 03/31/2018 12:30:00 | 03/31/2018 15:30:00 | 04/01/2018 08:00:00 | 04/01/2018 15:00:00
2582484 | 245003486 | act--03 Integration | 03 Integration | Completed | Activity | 245003637 | 04/01/2018 12:30:00 | 04/01/2018 21:00:00 | 04/02/2018 12:30:00 | 04/02/2018 15:00:00
2582484 | 245003486 | act--04 SSV | 04 SSV | Completed | Activity | 245003691 | 04/03/2018 12:30:00 | 04/03/2018 14:30:00 | 04/04/2018 08:00:00 | 04/04/2018 15:00:00
2582484 | 245003486 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003756 |  |  |  |  | 03/31/2018 06:30:00 | 03/31/2018 08:30:00 |  | 03/31/2018 09:30:00
2582485 | 245003488 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003921 |  |  |  |  | 05/05/2018 13:00:00 | 05/05/2018 15:00:00 |  | 05/05/2018 15:00:00
2582485 | 245003488 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003862 |  |  |  |  | 05/07/2018 12:30:00 | 05/07/2018 14:30:00 |  | 05/07/2018 15:00:00
2582485 | 245003488 | 0 | 07 Implementation Complete | Completed | Milestone | 245003972 |  |  |  |  | 01/01/2000 05:30:00 | 05/07/2018 15:00:00 |  | 05/07/2018 15:00:00
2582485 | 245003488 | act--02 Installation | 02 Installation | Completed | Activity | 245003584 | 05/02/2018 12:30:00 | 05/02/2018 15:30:00 | 05/03/2018 08:00:00 | 05/03/2018 15:00:00
2582485 | 245003488 | act--03 Integration | 03 Integration | Completed | Activity | 245003644 | 05/03/2018 12:30:00 | 05/03/2018 21:00:00 | 05/04/2018 12:30:00 | 05/04/2018 15:00:00
2582485 | 245003488 | act--04 SSV | 04 SSV | Completed | Activity | 245003707 | 05/05/2018 12:30:00 | 05/05/2018 14:30:00 | 05/06/2018 08:00:00 | 05/06/2018 15:00:00
2582485 | 245003488 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003805 |  |  |  |  | 05/02/2018 06:30:00 | 05/02/2018 08:30:00 |  | 05/02/2018 09:30:00
2582486 | 245003490 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003889 |  |  |  |  | 05/06/2018 13:00:00 | 05/06/2018 15:00:00 |  | 05/06/2018 15:00:00
2582486 | 245003490 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003833 |  |  |  |  | 05/08/2018 12:30:00 | 05/08/2018 14:30:00 |  | 05/08/2018 15:00:00
2582486 | 245003490 | 0 | 07 Implementation Complete | Completed | Milestone | 245003941 |  |  |  |  | 01/01/2000 05:30:00 | 05/08/2018 15:00:00 |  | 05/08/2018 15:00:00
2582486 | 245003490 | act--02 Installation | 02 Installation | Completed | Activity | 245003585 | 05/03/2018 12:30:00 | 05/03/2018 15:30:00 | 05/04/2018 08:00:00 | 05/04/2018 15:00:00
2582486 | 245003490 | act--03 Integration | 03 Integration | Completed | Activity | 245003640 | 05/04/2018 12:30:00 | 05/04/2018 21:00:00 | 05/05/2018 12:30:00 | 05/05/2018 15:00:00
2582486 | 245003490 | act--04 SSV | 04 SSV | Completed | Activity | 245003703 | 05/06/2018 12:30:00 | 05/06/2018 14:30:00 | 05/07/2018 08:00:00 | 05/07/2018 15:00:00
2582486 | 245003490 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003778 |  |  |  |  | 05/03/2018 06:30:00 | 05/03/2018 08:30:00 |  | 05/03/2018 09:30:00
2582487 | 245003495 | 0 | 05 NRO IM Accept | Completed | Milestone | 245003856 |  |  |  |  | 05/07/2018 13:00:00 | 05/07/2018 15:00:00 |  | 05/07/2018 15:00:00
2582487 | 245003495 | 0 | 06 NDO IM Accept | Completed | Milestone | 245003804 |  |  |  |  | 05/09/2018 12:30:00 | 05/09/2018 14:30:00 |  | 05/09/2018 15:00:00
2582487 | 245003495 | 0 | 07 Implementation Complete | Completed | Milestone | 245003910 |  |  |  |  | 01/01/2000 05:30:00 | 05/09/2018 15:00:00 |  | 05/09/2018 15:00:00
2582487 | 245003495 | act--02 Installation | 02 Installation | Completed | Activity | 245003587 | 05/04/2018 12:30:00 | 05/04/2018 15:30:00 | 05/05/2018 08:00:00 | 05/05/2018 15:00:00
2582487 | 245003495 | act--03 Integration | 03 Integration | Completed | Activity | 245003643 | 05/05/2018 12:30:00 | 05/05/2018 21:00:00 | 05/06/2018 12:30:00 | 05/06/2018 15:00:00
2582487 | 245003495 | act--04 SSV | 04 SSV | Completed | Activity | 245003692 | 05/07/2018 12:30:00 | 05/07/2018 14:30:00 | 05/08/2018 08:00:00 | 05/08/2018 15:00:00
2582487 | 245003495 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245003746 |  |  |  |  | 05/04/2018 06:30:00 | 05/04/2018 08:30:00 |  | 05/04/2018 09:30:00
2582488 | 245004104 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004520 |  |  |  |  | 04/10/2018 13:00:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582488 | 245004104 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004464 |  |  |  |  | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 |  | 04/12/2018 15:00:00
2582488 | 245004104 | 0 | 07 Implementation Complete | Completed | Milestone | 245004574 |  |  |  |  | 01/01/2000 05:30:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582488 | 245004104 | act--02 Installation | 02 Installation | Completed | Activity | 245004205 | 04/07/2018 12:30:00 | 04/07/2018 15:30:00 | 04/08/2018 08:00:00 | 04/08/2018 15:00:00
2582488 | 245004104 | act--03 Integration | 03 Integration | Completed | Activity | 245004254 | 04/08/2018 12:30:00 | 04/08/2018 21:00:00 | 04/09/2018 12:30:00 | 04/09/2018 15:00:00
2582488 | 245004104 | act--04 SSV | 04 SSV | Completed | Activity | 245004326 | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 | 04/11/2018 08:00:00 | 04/11/2018 15:00:00
2582488 | 245004104 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004410 |  |  |  |  | 04/07/2018 06:30:00 | 04/07/2018 08:30:00 |  | 04/07/2018 09:30:00
2582489 | 245004105 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004453 |  |  |  |  | 05/09/2018 13:00:00 | 05/09/2018 15:00:00 |  | 05/09/2018 15:00:00
2582489 | 245004105 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004393 |  |  |  |  | 05/11/2018 12:30:00 | 05/11/2018 14:30:00 |  | 05/11/2018 15:00:00
2582489 | 245004105 | 0 | 07 Implementation Complete | Completed | Milestone | 245004512 |  |  |  |  | 01/01/2000 05:30:00 | 05/11/2018 15:00:00 |  | 05/11/2018 15:00:00
2582489 | 245004105 | act--02 Installation | 02 Installation | Completed | Activity | 245004200 | 05/06/2018 12:30:00 | 05/06/2018 15:30:00 | 05/07/2018 08:00:00 | 05/07/2018 15:00:00
2582489 | 245004105 | act--03 Integration | 03 Integration | Completed | Activity | 245004242 | 05/07/2018 12:30:00 | 05/07/2018 21:00:00 | 05/08/2018 12:30:00 | 05/08/2018 15:00:00
2582489 | 245004105 | act--04 SSV | 04 SSV | Completed | Activity | 245004300 | 05/09/2018 12:30:00 | 05/09/2018 14:30:00 | 05/10/2018 08:00:00 | 05/10/2018 15:00:00
2582489 | 245004105 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004355 |  |  |  |  | 05/06/2018 06:30:00 | 05/06/2018 08:30:00 |  | 05/06/2018 09:30:00
2582490 | 245004106 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004458 |  |  |  |  | 05/10/2018 13:00:00 | 05/10/2018 15:00:00 |  | 05/10/2018 15:00:00
2582490 | 245004106 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004397 |  |  |  |  | 05/12/2018 12:30:00 | 05/12/2018 14:30:00 |  | 05/12/2018 15:00:00
2582490 | 245004106 | 0 | 07 Implementation Complete | Completed | Milestone | 245004518 |  |  |  |  | 01/01/2000 05:30:00 | 05/12/2018 15:00:00 |  | 05/12/2018 15:00:00
2582490 | 245004106 | act--02 Installation | 02 Installation | Completed | Activity | 245004199 | 05/07/2018 12:30:00 | 05/07/2018 15:30:00 | 05/08/2018 08:00:00 | 05/08/2018 15:00:00
2582490 | 245004106 | act--03 Integration | 03 Integration | Completed | Activity | 245004241 | 05/08/2018 12:30:00 | 05/08/2018 21:00:00 | 05/09/2018 12:30:00 | 05/09/2018 15:00:00
2582490 | 245004106 | act--04 SSV | 04 SSV | Completed | Activity | 245004298 | 05/10/2018 12:30:00 | 05/10/2018 14:30:00 | 05/11/2018 08:00:00 | 05/11/2018 15:00:00
2582490 | 245004106 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004352 |  |  |  |  | 05/07/2018 06:30:00 | 05/07/2018 08:30:00 |  | 05/07/2018 09:30:00
2582491 | 245004107 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004494 |  |  |  |  | 05/15/2018 13:00:00 | 05/15/2018 15:00:00 |  | 05/15/2018 15:00:00
2582491 | 245004107 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004439 |  |  |  |  | 05/17/2018 12:30:00 | 05/17/2018 14:30:00 |  | 05/17/2018 15:00:00
2582491 | 245004107 | 0 | 07 Implementation Complete | Completed | Milestone | 245004551 |  |  |  |  | 01/01/2000 05:30:00 | 05/17/2018 15:00:00 |  | 05/17/2018 15:00:00
2582491 | 245004107 | act--02 Installation | 02 Installation | Completed | Activity | 245004202 | 05/12/2018 12:30:00 | 05/12/2018 15:30:00 | 05/13/2018 08:00:00 | 05/13/2018 15:00:00
2582491 | 245004107 | act--03 Integration | 03 Integration | Completed | Activity | 245004251 | 05/13/2018 12:30:00 | 05/13/2018 21:00:00 | 05/14/2018 12:30:00 | 05/14/2018 15:00:00
2582491 | 245004107 | act--04 SSV | 04 SSV | Completed | Activity | 245004309 | 05/15/2018 12:30:00 | 05/15/2018 14:30:00 | 05/16/2018 08:00:00 | 05/16/2018 15:00:00
2582491 | 245004107 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004369 |  |  |  |  | 05/12/2018 06:30:00 | 05/12/2018 08:30:00 |  | 05/12/2018 09:30:00
2582492 | 245004113 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004508 |  |  |  |  | 04/21/2018 13:00:00 | 04/21/2018 15:00:00 |  | 04/21/2018 15:00:00
2582492 | 245004113 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004447 |  |  |  |  | 04/23/2018 12:30:00 | 04/23/2018 14:30:00 |  | 04/23/2018 15:00:00
2582492 | 245004113 | 0 | 07 Implementation Complete | Completed | Milestone | 245004571 |  |  |  |  | 01/01/2000 05:30:00 | 04/23/2018 15:00:00 |  | 04/23/2018 15:00:00
2582492 | 245004113 | act--02 Installation | 02 Installation | Completed | Activity | 245004201 | 04/18/2018 12:30:00 | 04/18/2018 15:30:00 | 04/19/2018 08:00:00 | 04/19/2018 15:00:00
2582492 | 245004113 | act--03 Integration | 03 Integration | Completed | Activity | 245004247 | 04/19/2018 12:30:00 | 04/19/2018 21:00:00 | 04/20/2018 12:30:00 | 04/20/2018 15:00:00
2582492 | 245004113 | act--04 SSV | 04 SSV | Completed | Activity | 245004311 | 04/21/2018 12:30:00 | 04/21/2018 14:30:00 | 04/22/2018 08:00:00 | 04/22/2018 15:00:00
2582492 | 245004113 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004383 |  |  |  |  | 04/18/2018 06:30:00 | 04/18/2018 08:30:00 |  | 04/18/2018 09:30:00
2582493 | 245004109 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004510 |  |  |  |  | 04/12/2018 13:00:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582493 | 245004109 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004461 |  |  |  |  | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 |  | 04/14/2018 15:00:00
2582493 | 245004109 | 0 | 07 Implementation Complete | Completed | Milestone | 245004566 |  |  |  |  | 01/01/2000 05:30:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582493 | 245004109 | act--02 Installation | 02 Installation | Completed | Activity | 245004206 | 04/09/2018 12:30:00 | 04/09/2018 15:30:00 | 04/10/2018 08:00:00 | 04/10/2018 15:00:00
2582493 | 245004109 | act--03 Integration | 03 Integration | Completed | Activity | 245004267 | 04/10/2018 12:30:00 | 04/10/2018 21:00:00 | 04/11/2018 12:30:00 | 04/11/2018 15:00:00
2582493 | 245004109 | act--04 SSV | 04 SSV | Completed | Activity | 245004328 | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 | 04/13/2018 08:00:00 | 04/13/2018 15:00:00
2582493 | 245004109 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004409 |  |  |  |  | 04/09/2018 06:30:00 | 04/09/2018 08:30:00 |  | 04/09/2018 09:30:00
2582494 | 245004115 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004519 |  |  |  |  | 04/13/2018 13:00:00 | 04/13/2018 15:00:00 |  | 04/13/2018 15:00:00
2582494 | 245004115 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004460 |  |  |  |  | 04/15/2018 12:30:00 | 04/15/2018 14:30:00 |  | 04/15/2018 15:00:00
2582494 | 245004115 | 0 | 07 Implementation Complete | Completed | Milestone | 245004575 |  |  |  |  | 01/01/2000 05:30:00 | 04/15/2018 15:00:00 |  | 04/15/2018 15:00:00
2582494 | 245004115 | act--02 Installation | 02 Installation | Completed | Activity | 245004209 | 04/10/2018 12:30:00 | 04/10/2018 15:30:00 | 04/11/2018 08:00:00 | 04/11/2018 15:00:00
2582494 | 245004115 | act--03 Integration | 03 Integration | Completed | Activity | 245004272 | 04/11/2018 12:30:00 | 04/11/2018 21:00:00 | 04/12/2018 12:30:00 | 04/12/2018 15:00:00
2582494 | 245004115 | act--04 SSV | 04 SSV | Completed | Activity | 245004324 | 04/13/2018 12:30:00 | 04/13/2018 14:30:00 | 04/14/2018 08:00:00 | 04/14/2018 15:00:00
2582494 | 245004115 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004401 |  |  |  |  | 04/10/2018 06:30:00 | 04/10/2018 08:30:00 |  | 04/10/2018 09:30:00
2582495 | 245004110 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004543 |  |  |  |  | 04/19/2018 13:00:00 | 04/19/2018 15:00:00 |  | 04/19/2018 15:00:00
2582495 | 245004110 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004487 |  |  |  |  | 04/21/2018 12:30:00 | 04/21/2018 14:30:00 |  | 04/21/2018 15:00:00
2582495 | 245004110 | 0 | 07 Implementation Complete | Completed | Milestone | 245004598 |  |  |  |  | 01/01/2000 05:30:00 | 04/21/2018 15:00:00 |  | 04/21/2018 15:00:00
2582495 | 245004110 | act--02 Installation | 02 Installation | Completed | Activity | 245004212 | 04/16/2018 12:30:00 | 04/16/2018 15:30:00 | 04/17/2018 08:00:00 | 04/17/2018 15:00:00
2582495 | 245004110 | act--03 Integration | 03 Integration | Completed | Activity | 245004273 | 04/17/2018 12:30:00 | 04/17/2018 21:00:00 | 04/18/2018 12:30:00 | 04/18/2018 15:00:00
2582495 | 245004110 | act--04 SSV | 04 SSV | Completed | Activity | 245004339 | 04/19/2018 12:30:00 | 04/19/2018 14:30:00 | 04/20/2018 08:00:00 | 04/20/2018 15:00:00
2582495 | 245004110 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004429 |  |  |  |  | 04/16/2018 06:30:00 | 04/16/2018 08:30:00 |  | 04/16/2018 09:30:00
2582496 | 245004108 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004538 |  |  |  |  | 04/07/2018 13:00:00 | 04/07/2018 15:00:00 |  | 04/07/2018 15:00:00
2582496 | 245004108 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004480 |  |  |  |  | 04/09/2018 12:30:00 | 04/09/2018 14:30:00 |  | 04/09/2018 15:00:00
2582496 | 245004108 | 0 | 07 Implementation Complete | Completed | Milestone | 245004597 |  |  |  |  | 01/01/2000 05:30:00 | 04/09/2018 15:00:00 |  | 04/09/2018 15:00:00
2582496 | 245004108 | act--02 Installation | 02 Installation | Completed | Activity | 245004221 | 04/04/2018 12:30:00 | 04/04/2018 15:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582496 | 245004108 | act--03 Integration | 03 Integration | Completed | Activity | 245004281 | 04/05/2018 12:30:00 | 04/05/2018 21:00:00 | 04/06/2018 12:30:00 | 04/06/2018 15:00:00
2582496 | 245004108 | act--04 SSV | 04 SSV | Completed | Activity | 245004332 | 04/07/2018 12:30:00 | 04/07/2018 14:30:00 | 04/08/2018 08:00:00 | 04/08/2018 15:00:00
2582496 | 245004108 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004423 |  |  |  |  | 04/04/2018 06:30:00 | 04/04/2018 08:30:00 |  | 04/04/2018 09:30:00
2582497 | 245004111 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004539 |  |  |  |  | 04/30/2018 13:00:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582497 | 245004111 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004473 |  |  |  |  | 05/02/2018 12:30:00 | 05/02/2018 14:30:00 |  | 05/02/2018 15:00:00
2582497 | 245004111 | 0 | 07 Implementation Complete | Completed | Milestone | 245004599 |  |  |  |  | 01/01/2000 05:30:00 | 05/02/2018 15:00:00 |  | 05/02/2018 15:00:00
2582497 | 245004111 | act--02 Installation | 02 Installation | Completed | Activity | 245004215 | 04/27/2018 12:30:00 | 04/27/2018 15:30:00 | 04/28/2018 08:00:00 | 04/28/2018 15:00:00
2582497 | 245004111 | act--03 Integration | 03 Integration | Completed | Activity | 245004270 | 04/28/2018 12:30:00 | 04/28/2018 21:00:00 | 04/29/2018 12:30:00 | 04/29/2018 15:00:00
2582497 | 245004111 | act--04 SSV | 04 SSV | Completed | Activity | 245004334 | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 | 05/01/2018 08:00:00 | 05/01/2018 15:00:00
2582497 | 245004111 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004413 |  |  |  |  | 04/27/2018 06:30:00 | 04/27/2018 08:30:00 |  | 04/27/2018 09:30:00
2582498 | 245004114 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004488 |  |  |  |  | 04/15/2018 13:00:00 | 04/15/2018 15:00:00 |  | 04/15/2018 15:00:00
2582498 | 245004114 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004434 |  |  |  |  | 04/17/2018 12:30:00 | 04/17/2018 14:30:00 |  | 04/17/2018 15:00:00
2582498 | 245004114 | 0 | 07 Implementation Complete | Completed | Milestone | 245004547 |  |  |  |  | 01/01/2000 05:30:00 | 04/17/2018 15:00:00 |  | 04/17/2018 15:00:00
2582498 | 245004114 | act--02 Installation | 02 Installation | Completed | Activity | 245004213 | 04/12/2018 12:30:00 | 04/12/2018 15:30:00 | 04/13/2018 08:00:00 | 04/13/2018 15:00:00
2582498 | 245004114 | act--03 Integration | 03 Integration | Completed | Activity | 245004264 | 04/13/2018 12:30:00 | 04/13/2018 21:00:00 | 04/14/2018 12:30:00 | 04/14/2018 15:00:00
2582498 | 245004114 | act--04 SSV | 04 SSV | Completed | Activity | 245004313 | 04/15/2018 12:30:00 | 04/15/2018 14:30:00 | 04/16/2018 08:00:00 | 04/16/2018 15:00:00
2582498 | 245004114 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004370 |  |  |  |  | 04/12/2018 06:30:00 | 04/12/2018 08:30:00 |  | 04/12/2018 09:30:00
2582499 | 245004118 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004506 |  |  |  |  | 03/25/2018 13:00:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582499 | 245004118 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004445 |  |  |  |  | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 |  | 03/27/2018 15:00:00
2582499 | 245004118 | 0 | 07 Implementation Complete | Completed | Milestone | 245004564 |  |  |  |  | 01/01/2000 05:30:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582499 | 245004118 | act--02 Installation | 02 Installation | Completed | Activity | 245004214 | 03/22/2018 12:30:00 | 03/22/2018 14:30:00 | 03/23/2018 08:00:00 | 03/23/2018 15:00:00
2582499 | 245004118 | act--03 Integration | 03 Integration | Completed | Activity | 245004266 | 03/23/2018 12:30:00 | 03/23/2018 21:00:00 | 03/24/2018 12:30:00 | 03/24/2018 15:00:00
2582499 | 245004118 | act--04 SSV | 04 SSV | Completed | Activity | 245004319 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 03/26/2018 08:00:00 | 03/26/2018 15:00:00
2582499 | 245004118 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004376 |  |  |  |  | 03/22/2018 06:30:00 | 03/22/2018 08:30:00 |  | 03/22/2018 09:30:00
2582500 | 245004116 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004511 |  |  |  |  | 05/12/2018 13:00:00 | 05/12/2018 15:00:00 |  | 05/12/2018 15:00:00
2582500 | 245004116 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004454 |  |  |  |  | 05/14/2018 12:30:00 | 05/14/2018 14:30:00 |  | 05/14/2018 15:00:00
2582500 | 245004116 | 0 | 07 Implementation Complete | Completed | Milestone | 245004565 |  |  |  |  | 01/01/2000 05:30:00 | 05/14/2018 15:00:00 |  | 05/14/2018 15:00:00
2582500 | 245004116 | act--02 Installation | 02 Installation | Completed | Activity | 245004203 | 05/09/2018 12:30:00 | 05/09/2018 15:30:00 | 05/10/2018 08:00:00 | 05/10/2018 15:00:00
2582500 | 245004116 | act--03 Integration | 03 Integration | Completed | Activity | 245004257 | 05/10/2018 12:30:00 | 05/10/2018 21:00:00 | 05/11/2018 12:30:00 | 05/11/2018 15:00:00
2582500 | 245004116 | act--04 SSV | 04 SSV | Completed | Activity | 245004323 | 05/12/2018 12:30:00 | 05/12/2018 14:30:00 | 05/13/2018 08:00:00 | 05/13/2018 15:00:00
2582500 | 245004116 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004391 |  |  |  |  | 05/09/2018 06:30:00 | 05/09/2018 08:30:00 |  | 05/09/2018 09:30:00
2582501 | 245004121 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004495 |  |  |  |  | 05/19/2018 13:00:00 | 05/19/2018 15:00:00 |  | 05/19/2018 15:00:00
2582501 | 245004121 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004438 |  |  |  |  | 05/21/2018 12:30:00 | 05/21/2018 14:30:00 |  | 05/21/2018 15:00:00
2582501 | 245004121 | 0 | 07 Implementation Complete | Completed | Milestone | 245004550 |  |  |  |  | 01/01/2000 05:30:00 | 05/21/2018 15:00:00 |  | 05/21/2018 15:00:00
2582501 | 245004121 | act--02 Installation | 02 Installation | Completed | Activity | 245004216 | 05/16/2018 12:30:00 | 05/16/2018 15:30:00 | 05/17/2018 08:00:00 | 05/17/2018 15:00:00
2582501 | 245004121 | act--03 Integration | 03 Integration | Completed | Activity | 245004269 | 05/17/2018 12:30:00 | 05/17/2018 21:00:00 | 05/18/2018 12:30:00 | 05/18/2018 15:00:00
2582501 | 245004121 | act--04 SSV | 04 SSV | Completed | Activity | 245004325 | 05/19/2018 12:30:00 | 05/19/2018 14:30:00 | 05/20/2018 08:00:00 | 05/20/2018 15:00:00
2582501 | 245004121 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004377 |  |  |  |  | 05/16/2018 06:30:00 | 05/16/2018 08:30:00 |  | 05/16/2018 09:30:00
2582502 | 245004122 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004501 |  |  |  |  | 04/04/2018 13:00:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582502 | 245004122 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004446 |  |  |  |  | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 |  | 04/06/2018 15:00:00
2582502 | 245004122 | 0 | 07 Implementation Complete | Completed | Milestone | 245004555 |  |  |  |  | 01/01/2000 05:30:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582502 | 245004122 | act--02 Installation | 02 Installation | Completed | Activity | 245004222 | 04/01/2018 12:30:00 | 04/01/2018 15:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582502 | 245004122 | act--03 Integration | 03 Integration | Completed | Activity | 245004275 | 04/02/2018 12:30:00 | 04/02/2018 21:00:00 | 04/03/2018 12:30:00 | 04/03/2018 15:00:00
2582502 | 245004122 | act--04 SSV | 04 SSV | Completed | Activity | 245004336 | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582502 | 245004122 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004379 |  |  |  |  | 04/01/2018 06:30:00 | 04/01/2018 08:30:00 |  | 04/01/2018 09:30:00
2582503 | 245004120 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004531 |  |  |  |  | 06/04/2018 13:00:00 | 06/04/2018 15:00:00 |  | 06/04/2018 15:00:00
2582503 | 245004120 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004469 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582503 | 245004120 | 0 | 07 Implementation Complete | Completed | Milestone | 245004587 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582503 | 245004120 | act--02 Installation | 02 Installation | Completed | Activity | 245004211 | 06/01/2018 12:30:00 | 06/01/2018 15:00:00 | 06/02/2018 07:00:00 | 06/02/2018 15:30:00
2582503 | 245004120 | act--03 Integration | 03 Integration | Completed | Activity | 245004268 | 06/02/2018 12:30:00 | 06/02/2018 23:00:00 | 06/03/2018 11:30:00 | 06/03/2018 15:30:00
2582503 | 245004120 | act--04 SSV | 04 SSV | Completed | Activity | 245004333 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582503 | 245004120 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004412 |  |  |  |  | 06/01/2018 06:30:00 | 06/01/2018 07:30:00 |  | 06/01/2018 08:30:00
2582504 | 245004124 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004545 |  |  |  |  | 04/22/2018 13:00:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582504 | 245004124 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004489 |  |  |  |  | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 |  | 04/24/2018 15:00:00
2582504 | 245004124 | 0 | 07 Implementation Complete | Completed | Milestone | 245004606 |  |  |  |  | 01/01/2000 05:30:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582504 | 245004124 | act--02 Installation | 02 Installation | Completed | Activity | 245004218 | 04/19/2018 12:30:00 | 04/19/2018 15:30:00 | 04/20/2018 08:00:00 | 04/20/2018 15:00:00
2582504 | 245004124 | act--03 Integration | 03 Integration | Completed | Activity | 245004280 | 04/20/2018 12:30:00 | 04/20/2018 21:00:00 | 04/21/2018 12:30:00 | 04/21/2018 15:00:00
2582504 | 245004124 | act--04 SSV | 04 SSV | Completed | Activity | 245004337 | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 | 04/23/2018 08:00:00 | 04/23/2018 15:00:00
2582504 | 245004124 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004431 |  |  |  |  | 04/19/2018 06:30:00 | 04/19/2018 08:30:00 |  | 04/19/2018 09:30:00
2582505 | 245004126 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004523 |  |  |  |  | 04/10/2018 13:00:00 | 04/10/2018 15:00:00 |  | 04/10/2018 15:00:00
2582505 | 245004126 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004471 |  |  |  |  | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 |  | 04/12/2018 15:00:00
2582505 | 245004126 | 0 | 07 Implementation Complete | Completed | Milestone | 245004578 |  |  |  |  | 01/01/2000 05:30:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582505 | 245004126 | act--02 Installation | 02 Installation | Completed | Activity | 245004217 | 04/07/2018 12:30:00 | 04/07/2018 15:30:00 | 04/08/2018 08:00:00 | 04/08/2018 15:00:00
2582505 | 245004126 | act--03 Integration | 03 Integration | Completed | Activity | 245004274 | 04/08/2018 12:30:00 | 04/08/2018 21:00:00 | 04/09/2018 12:30:00 | 04/09/2018 15:00:00
2582505 | 245004126 | act--04 SSV | 04 SSV | Completed | Activity | 245004330 | 04/10/2018 12:30:00 | 04/10/2018 14:30:00 | 04/11/2018 08:00:00 | 04/11/2018 15:00:00
2582505 | 245004126 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004417 |  |  |  |  | 04/07/2018 06:30:00 | 04/07/2018 08:30:00 |  | 04/07/2018 09:30:00
2582506 | 245004125 | 0 | 05 NRO IM Accept | Completed | Milestone | 245004532 |  |  |  |  | 04/06/2018 13:00:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582506 | 245004125 | 0 | 06 NDO IM Accept | Completed | Milestone | 245004470 |  |  |  |  | 04/08/2018 12:30:00 | 04/08/2018 14:30:00 |  | 04/08/2018 15:00:00
2582506 | 245004125 | 0 | 07 Implementation Complete | Completed | Milestone | 245004588 |  |  |  |  | 01/01/2000 05:30:00 | 04/08/2018 15:00:00 |  | 04/08/2018 15:00:00
2582506 | 245004125 | act--02 Installation | 02 Installation | Completed | Activity | 245004224 | 04/03/2018 12:30:00 | 04/03/2018 15:30:00 | 04/04/2018 08:00:00 | 04/04/2018 15:00:00
2582506 | 245004125 | act--03 Integration | 03 Integration | Completed | Activity | 245004278 | 04/04/2018 12:30:00 | 04/04/2018 21:00:00 | 04/05/2018 12:30:00 | 04/05/2018 15:00:00
2582506 | 245004125 | act--04 SSV | 04 SSV | Completed | Activity | 245004335 | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 | 04/07/2018 08:00:00 | 04/07/2018 15:00:00
2582506 | 245004125 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245004411 |  |  |  |  | 04/03/2018 06:30:00 | 04/03/2018 08:30:00 |  | 04/03/2018 09:30:00
2582507 | 245004753 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005102 |  |  |  |  | 05/23/2018 13:00:00 | 05/23/2018 15:00:00 |  | 05/23/2018 15:00:00
2582507 | 245004753 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005044 |  |  |  |  | 05/25/2018 12:30:00 | 05/25/2018 14:30:00 |  | 05/25/2018 15:00:00
2582507 | 245004753 | 0 | 07 Implementation Complete | Completed | Milestone | 245005155 |  |  |  |  | 01/01/2000 05:30:00 | 05/25/2018 15:00:00 |  | 05/25/2018 15:00:00
2582507 | 245004753 | act--02 Installation | 02 Installation | Completed | Activity | 245004847 | 05/20/2018 12:30:00 | 05/20/2018 15:30:00 | 05/21/2018 08:00:00 | 05/21/2018 15:00:00
2582507 | 245004753 | act--03 Integration | 03 Integration | Completed | Activity | 245004892 | 05/21/2018 12:30:00 | 05/21/2018 21:00:00 | 05/22/2018 12:30:00 | 05/22/2018 15:00:00
2582507 | 245004753 | act--04 SSV | 04 SSV | Completed | Activity | 245004946 | 05/23/2018 12:30:00 | 05/23/2018 14:30:00 | 05/24/2018 08:00:00 | 05/24/2018 15:00:00
2582507 | 245004753 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005007 |  |  |  |  | 05/20/2018 06:30:00 | 05/20/2018 08:30:00 |  | 05/20/2018 09:30:00
2582508 | 245004751 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005140 |  |  |  |  | 04/18/2018 13:00:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582508 | 245004751 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005083 |  |  |  |  | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 |  | 04/20/2018 15:00:00
2582508 | 245004751 | 0 | 07 Implementation Complete | Completed | Milestone | 245005198 |  |  |  |  | 01/01/2000 05:30:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582508 | 245004751 | act--02 Installation | 02 Installation | Completed | Activity | 245004846 | 04/15/2018 12:30:00 | 04/15/2018 15:30:00 | 04/16/2018 08:00:00 | 04/16/2018 15:00:00
2582508 | 245004751 | act--03 Integration | 03 Integration | Completed | Activity | 245004890 | 04/16/2018 12:30:00 | 04/16/2018 21:00:00 | 04/17/2018 12:30:00 | 04/17/2018 15:00:00
2582508 | 245004751 | act--04 SSV | 04 SSV | Completed | Activity | 245004950 | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 | 04/19/2018 08:00:00 | 04/19/2018 15:00:00
2582508 | 245004751 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005016 |  |  |  |  | 04/15/2018 06:30:00 | 04/15/2018 08:30:00 |  | 04/15/2018 09:30:00
2582509 | 245004752 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005137 |  |  |  |  | 04/24/2018 13:00:00 | 04/24/2018 15:00:00 |  | 04/24/2018 15:00:00
2582509 | 245004752 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005080 |  |  |  |  | 04/26/2018 12:30:00 | 04/26/2018 14:30:00 |  | 04/26/2018 15:00:00
2582509 | 245004752 | 0 | 07 Implementation Complete | Completed | Milestone | 245005195 |  |  |  |  | 01/01/2000 05:30:00 | 04/26/2018 15:00:00 |  | 04/26/2018 15:00:00
2582509 | 245004752 | act--02 Installation | 02 Installation | Completed | Activity | 245004849 | 04/21/2018 12:30:00 | 04/21/2018 15:30:00 | 04/22/2018 08:00:00 | 04/22/2018 15:00:00
2582509 | 245004752 | act--03 Integration | 03 Integration | Completed | Activity | 245004904 | 04/22/2018 12:30:00 | 04/22/2018 21:00:00 | 04/23/2018 12:30:00 | 04/23/2018 15:00:00
2582509 | 245004752 | act--04 SSV | 04 SSV | Completed | Activity | 245004961 | 04/24/2018 12:30:00 | 04/24/2018 14:30:00 | 04/25/2018 08:00:00 | 04/25/2018 15:00:00
2582509 | 245004752 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005017 |  |  |  |  | 04/21/2018 06:30:00 | 04/21/2018 08:30:00 |  | 04/21/2018 09:30:00
2582510 | 245004756 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005154 |  |  |  |  | 04/28/2018 13:00:00 | 04/28/2018 15:00:00 |  | 04/28/2018 15:00:00
2582510 | 245004756 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005097 |  |  |  |  | 04/30/2018 12:30:00 | 04/30/2018 14:30:00 |  | 04/30/2018 15:00:00
2582510 | 245004756 | 0 | 07 Implementation Complete | Completed | Milestone | 245005217 |  |  |  |  | 01/01/2000 05:30:00 | 04/30/2018 15:00:00 |  | 04/30/2018 15:00:00
2582510 | 245004756 | act--02 Installation | 02 Installation | Completed | Activity | 245004854 | 04/25/2018 12:30:00 | 04/25/2018 15:30:00 | 04/26/2018 08:00:00 | 04/26/2018 15:00:00
2582510 | 245004756 | act--03 Integration | 03 Integration | Completed | Activity | 245004910 | 04/26/2018 12:30:00 | 04/26/2018 21:00:00 | 04/27/2018 12:30:00 | 04/27/2018 15:00:00
2582510 | 245004756 | act--04 SSV | 04 SSV | Completed | Activity | 245004960 | 04/28/2018 12:30:00 | 04/28/2018 14:30:00 | 04/29/2018 08:00:00 | 04/29/2018 15:00:00
2582510 | 245004756 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005032 |  |  |  |  | 04/25/2018 06:30:00 | 04/25/2018 08:30:00 |  | 04/25/2018 09:30:00
2582511 | 245004755 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005157 |  |  |  |  | 05/14/2018 13:00:00 | 05/14/2018 15:00:00 |  | 05/14/2018 15:00:00
2582511 | 245004755 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005096 |  |  |  |  | 05/16/2018 12:30:00 | 05/16/2018 14:30:00 |  | 05/16/2018 15:00:00
2582511 | 245004755 | 0 | 07 Implementation Complete | Completed | Milestone | 245005214 |  |  |  |  | 01/01/2000 05:30:00 | 05/16/2018 15:00:00 |  | 05/16/2018 15:00:00
2582511 | 245004755 | act--02 Installation | 02 Installation | Completed | Activity | 245004848 | 05/11/2018 12:30:00 | 05/11/2018 15:30:00 | 05/12/2018 08:00:00 | 05/12/2018 15:00:00
2582511 | 245004755 | act--03 Integration | 03 Integration | Completed | Activity | 245004907 | 05/12/2018 12:30:00 | 05/12/2018 21:00:00 | 05/13/2018 12:30:00 | 05/13/2018 15:00:00
2582511 | 245004755 | act--04 SSV | 04 SSV | Completed | Activity | 245004964 | 05/14/2018 12:30:00 | 05/14/2018 14:30:00 | 05/15/2018 08:00:00 | 05/15/2018 15:00:00
2582511 | 245004755 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005035 |  |  |  |  | 05/11/2018 06:30:00 | 05/11/2018 08:30:00 |  | 05/11/2018 09:30:00
2582512 | 245004754 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005172 |  |  |  |  | 04/29/2018 13:00:00 | 04/29/2018 15:00:00 |  | 04/29/2018 15:00:00
2582512 | 245004754 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005124 |  |  |  |  | 05/01/2018 12:30:00 | 05/01/2018 14:30:00 |  | 05/01/2018 15:00:00
2582512 | 245004754 | 0 | 07 Implementation Complete | Completed | Milestone | 245005227 |  |  |  |  | 01/01/2000 05:30:00 | 05/01/2018 15:00:00 |  | 05/01/2018 15:00:00
2582512 | 245004754 | act--02 Installation | 02 Installation | Completed | Activity | 245004859 | 04/26/2018 12:30:00 | 04/26/2018 15:30:00 | 04/27/2018 08:00:00 | 04/27/2018 15:00:00
2582512 | 245004754 | act--03 Integration | 03 Integration | Completed | Activity | 245004925 | 04/27/2018 12:30:00 | 04/27/2018 21:00:00 | 04/28/2018 12:30:00 | 04/28/2018 15:00:00
2582512 | 245004754 | act--04 SSV | 04 SSV | Completed | Activity | 245004984 | 04/29/2018 12:30:00 | 04/29/2018 14:30:00 | 04/30/2018 08:00:00 | 04/30/2018 15:00:00
2582512 | 245004754 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005070 |  |  |  |  | 04/26/2018 06:30:00 | 04/26/2018 08:30:00 |  | 04/26/2018 09:30:00
2582513 | 245004761 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005141 |  |  |  |  | 05/02/2018 13:00:00 | 05/02/2018 15:00:00 |  | 05/02/2018 15:00:00
2582513 | 245004761 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005082 |  |  |  |  | 05/04/2018 12:30:00 | 05/04/2018 14:30:00 |  | 05/04/2018 15:00:00
2582513 | 245004761 | 0 | 07 Implementation Complete | Completed | Milestone | 245005202 |  |  |  |  | 01/01/2000 05:30:00 | 05/04/2018 15:00:00 |  | 05/04/2018 15:00:00
2582513 | 245004761 | act--02 Installation | 02 Installation | Completed | Activity | 245004850 | 04/29/2018 12:30:00 | 04/29/2018 15:30:00 | 04/30/2018 08:00:00 | 04/30/2018 15:00:00
2582513 | 245004761 | act--03 Integration | 03 Integration | Completed | Activity | 245004902 | 04/30/2018 12:30:00 | 04/30/2018 21:00:00 | 05/01/2018 12:30:00 | 05/01/2018 15:00:00
2582513 | 245004761 | act--04 SSV | 04 SSV | Completed | Activity | 245004955 | 05/02/2018 12:30:00 | 05/02/2018 14:30:00 | 05/03/2018 08:00:00 | 05/03/2018 15:00:00
2582513 | 245004761 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005021 |  |  |  |  | 04/29/2018 06:30:00 | 04/29/2018 08:30:00 |  | 04/29/2018 09:30:00
2582514 | 245004759 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005117 |  |  |  |  | 05/21/2018 13:00:00 | 05/21/2018 15:00:00 |  | 05/21/2018 15:00:00
2582514 | 245004759 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005052 |  |  |  |  | 05/23/2018 12:30:00 | 05/23/2018 14:30:00 |  | 05/23/2018 15:00:00
2582514 | 245004759 | 0 | 07 Implementation Complete | Completed | Milestone | 245005176 |  |  |  |  | 01/01/2000 05:30:00 | 05/23/2018 15:00:00 |  | 05/23/2018 15:00:00
2582514 | 245004759 | act--02 Installation | 02 Installation | Completed | Activity | 245004851 | 05/18/2018 12:30:00 | 05/18/2018 15:30:00 | 05/19/2018 08:00:00 | 05/19/2018 15:00:00
2582514 | 245004759 | act--03 Integration | 03 Integration | Completed | Activity | 245004894 | 05/19/2018 12:30:00 | 05/19/2018 21:00:00 | 05/20/2018 12:30:00 | 05/20/2018 15:00:00
2582514 | 245004759 | act--04 SSV | 04 SSV | Completed | Activity | 245004948 | 05/21/2018 12:30:00 | 05/21/2018 14:30:00 | 05/22/2018 08:00:00 | 05/22/2018 15:00:00
2582514 | 245004759 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005004 |  |  |  |  | 05/18/2018 06:30:00 | 05/18/2018 08:30:00 |  | 05/18/2018 09:30:00
2582515 | 245004757 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005152 |  |  |  |  | 04/23/2018 13:00:00 | 04/23/2018 15:00:00 |  | 04/23/2018 15:00:00
2582515 | 245004757 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005093 |  |  |  |  | 04/25/2018 12:30:00 | 04/25/2018 14:30:00 |  | 04/25/2018 15:00:00
2582515 | 245004757 | 0 | 07 Implementation Complete | Completed | Milestone | 245005212 |  |  |  |  | 01/01/2000 05:30:00 | 04/25/2018 15:00:00 |  | 04/25/2018 15:00:00
2582515 | 245004757 | act--02 Installation | 02 Installation | Completed | Activity | 245004852 | 04/20/2018 12:30:00 | 04/20/2018 15:30:00 | 04/21/2018 08:00:00 | 04/21/2018 15:00:00
2582515 | 245004757 | act--03 Integration | 03 Integration | Completed | Activity | 245004908 | 04/21/2018 12:30:00 | 04/21/2018 21:00:00 | 04/22/2018 12:30:00 | 04/22/2018 15:00:00
2582515 | 245004757 | act--04 SSV | 04 SSV | Completed | Activity | 245004967 | 04/23/2018 12:30:00 | 04/23/2018 14:30:00 | 04/24/2018 08:00:00 | 04/24/2018 15:00:00
2582515 | 245004757 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005031 |  |  |  |  | 04/20/2018 06:30:00 | 04/20/2018 08:30:00 |  | 04/20/2018 09:30:00
2582516 | 245004758 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005150 |  |  |  |  | 05/04/2018 13:00:00 | 05/04/2018 15:00:00 |  | 05/04/2018 15:00:00
2582516 | 245004758 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005095 |  |  |  |  | 05/06/2018 12:30:00 | 05/06/2018 14:30:00 |  | 05/06/2018 15:00:00
2582516 | 245004758 | 0 | 07 Implementation Complete | Completed | Milestone | 245005208 |  |  |  |  | 01/01/2000 05:30:00 | 05/06/2018 15:00:00 |  | 05/06/2018 15:00:00
2582516 | 245004758 | act--02 Installation | 02 Installation | Completed | Activity | 245004857 | 05/01/2018 12:30:00 | 05/01/2018 15:30:00 | 05/02/2018 08:00:00 | 05/02/2018 15:00:00
2582516 | 245004758 | act--03 Integration | 03 Integration | Completed | Activity | 245004916 | 05/02/2018 12:30:00 | 05/02/2018 21:00:00 | 05/03/2018 12:30:00 | 05/03/2018 15:00:00
2582516 | 245004758 | act--04 SSV | 04 SSV | Completed | Activity | 245004971 | 05/04/2018 12:30:00 | 05/04/2018 14:30:00 | 05/05/2018 08:00:00 | 05/05/2018 15:00:00
2582516 | 245004758 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005037 |  |  |  |  | 05/01/2018 06:30:00 | 05/01/2018 08:30:00 |  | 05/01/2018 09:30:00
2582517 | 245004762 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005129 |  |  |  |  | 05/13/2018 13:00:00 | 05/13/2018 15:00:00 |  | 05/13/2018 15:00:00
2582517 | 245004762 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005077 |  |  |  |  | 05/15/2018 12:30:00 | 05/15/2018 14:30:00 |  | 05/15/2018 15:00:00
2582517 | 245004762 | 0 | 07 Implementation Complete | Completed | Milestone | 245005185 |  |  |  |  | 01/01/2000 05:30:00 | 05/15/2018 15:00:00 |  | 05/15/2018 15:00:00
2582517 | 245004762 | act--02 Installation | 02 Installation | Completed | Activity | 245004853 | 05/10/2018 12:30:00 | 05/10/2018 15:30:00 | 05/11/2018 08:00:00 | 05/11/2018 15:00:00
2582517 | 245004762 | act--03 Integration | 03 Integration | Completed | Activity | 245004917 | 05/11/2018 12:30:00 | 05/11/2018 21:00:00 | 05/12/2018 12:30:00 | 05/12/2018 15:00:00
2582517 | 245004762 | act--04 SSV | 04 SSV | Completed | Activity | 245004959 | 05/13/2018 12:30:00 | 05/13/2018 14:30:00 | 05/14/2018 08:00:00 | 05/14/2018 15:00:00
2582517 | 245004762 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005018 |  |  |  |  | 05/10/2018 06:30:00 | 05/10/2018 08:30:00 |  | 05/10/2018 09:30:00
2582518 | 245004765 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005182 |  |  |  |  | 05/22/2018 13:00:00 | 05/22/2018 15:00:00 |  | 05/22/2018 15:00:00
2582518 | 245004765 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005118 |  |  |  |  | 05/24/2018 12:30:00 | 05/24/2018 14:30:00 |  | 05/24/2018 15:00:00
2582518 | 245004765 | 0 | 07 Implementation Complete | Completed | Milestone | 245005232 |  |  |  |  | 01/01/2000 05:30:00 | 05/24/2018 15:00:00 |  | 05/24/2018 15:00:00
2582518 | 245004765 | act--02 Installation | 02 Installation | Completed | Activity | 245004856 | 05/19/2018 12:30:00 | 05/19/2018 15:30:00 | 05/20/2018 08:00:00 | 05/20/2018 15:00:00
2582518 | 245004765 | act--03 Integration | 03 Integration | Completed | Activity | 245004912 | 05/20/2018 12:30:00 | 05/20/2018 21:00:00 | 05/21/2018 12:30:00 | 05/21/2018 15:00:00
2582518 | 245004765 | act--04 SSV | 04 SSV | Completed | Activity | 245004978 | 05/22/2018 12:30:00 | 05/22/2018 14:30:00 | 05/23/2018 08:00:00 | 05/23/2018 15:00:00
2582518 | 245004765 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005058 |  |  |  |  | 05/19/2018 06:30:00 | 05/19/2018 08:30:00 |  | 05/19/2018 09:30:00
2582519 | 245004760 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005173 |  |  |  |  | 05/11/2018 13:00:00 | 05/11/2018 15:00:00 |  | 05/11/2018 15:00:00
2582519 | 245004760 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005115 |  |  |  |  | 05/13/2018 12:30:00 | 05/13/2018 14:30:00 |  | 05/13/2018 15:00:00
2582519 | 245004760 | 0 | 07 Implementation Complete | Completed | Milestone | 245005226 |  |  |  |  | 01/01/2000 05:30:00 | 05/13/2018 15:00:00 |  | 05/13/2018 15:00:00
2582519 | 245004760 | act--02 Installation | 02 Installation | Completed | Activity | 245004862 | 05/08/2018 12:30:00 | 05/08/2018 15:30:00 | 05/09/2018 08:00:00 | 05/09/2018 15:00:00
2582519 | 245004760 | act--03 Integration | 03 Integration | Completed | Activity | 245004919 | 05/09/2018 12:30:00 | 05/09/2018 21:00:00 | 05/10/2018 12:30:00 | 05/10/2018 15:00:00
2582519 | 245004760 | act--04 SSV | 04 SSV | Completed | Activity | 245004980 | 05/11/2018 12:30:00 | 05/11/2018 14:30:00 | 05/12/2018 08:00:00 | 05/12/2018 15:00:00
2582519 | 245004760 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005056 |  |  |  |  | 05/08/2018 06:30:00 | 05/08/2018 08:30:00 |  | 05/08/2018 09:30:00
2582520 | 245004764 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005188 |  |  |  |  | 05/20/2018 13:00:00 | 05/20/2018 15:00:00 |  | 05/20/2018 15:00:00
2582520 | 245004764 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005133 |  |  |  |  | 05/22/2018 12:30:00 | 05/22/2018 14:30:00 |  | 05/22/2018 15:00:00
2582520 | 245004764 | 0 | 07 Implementation Complete | Completed | Milestone | 245005246 |  |  |  |  | 01/01/2000 05:30:00 | 05/22/2018 15:00:00 |  | 05/22/2018 15:00:00
2582520 | 245004764 | act--02 Installation | 02 Installation | Completed | Activity | 245004863 | 05/17/2018 12:30:00 | 05/17/2018 15:30:00 | 05/18/2018 08:00:00 | 05/18/2018 15:00:00
2582520 | 245004764 | act--03 Integration | 03 Integration | Completed | Activity | 245004926 | 05/18/2018 12:30:00 | 05/18/2018 21:00:00 | 05/19/2018 12:30:00 | 05/19/2018 15:00:00
2582520 | 245004764 | act--04 SSV | 04 SSV | Completed | Activity | 245004986 | 05/20/2018 12:30:00 | 05/20/2018 14:30:00 | 05/21/2018 08:00:00 | 05/21/2018 15:00:00
2582520 | 245004764 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005075 |  |  |  |  | 05/17/2018 06:30:00 | 05/17/2018 08:30:00 |  | 05/17/2018 09:30:00
2582521 | 245004768 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005156 |  |  |  |  | 04/13/2018 13:00:00 | 04/13/2018 15:00:00 |  | 04/13/2018 15:00:00
2582521 | 245004768 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005098 |  |  |  |  | 04/15/2018 12:30:00 | 04/15/2018 14:30:00 |  | 04/15/2018 15:00:00
2582521 | 245004768 | 0 | 07 Implementation Complete | Completed | Milestone | 245005216 |  |  |  |  | 01/01/2000 05:30:00 | 04/15/2018 15:00:00 |  | 04/15/2018 15:00:00
2582521 | 245004768 | act--02 Installation | 02 Installation | Completed | Activity | 245004861 | 04/10/2018 12:30:00 | 04/10/2018 15:30:00 | 04/11/2018 08:00:00 | 04/11/2018 15:00:00
2582521 | 245004768 | act--03 Integration | 03 Integration | Completed | Activity | 245004911 | 04/11/2018 12:30:00 | 04/11/2018 21:00:00 | 04/12/2018 12:30:00 | 04/12/2018 15:00:00
2582521 | 245004768 | act--04 SSV | 04 SSV | Completed | Activity | 245004972 | 04/13/2018 12:30:00 | 04/13/2018 14:30:00 | 04/14/2018 08:00:00 | 04/14/2018 15:00:00
2582521 | 245004768 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005042 |  |  |  |  | 04/10/2018 06:30:00 | 04/10/2018 08:30:00 |  | 04/10/2018 09:30:00
2582522 | 245004766 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005160 |  |  |  |  | 04/16/2018 13:00:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582522 | 245004766 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005107 |  |  |  |  | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 |  | 04/18/2018 15:00:00
2582522 | 245004766 | 0 | 07 Implementation Complete | Completed | Milestone | 245005211 |  |  |  |  | 01/01/2000 05:30:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582522 | 245004766 | act--02 Installation | 02 Installation | Completed | Activity | 245004866 | 04/13/2018 12:30:00 | 04/13/2018 15:30:00 | 04/14/2018 08:00:00 | 04/14/2018 15:00:00
2582522 | 245004766 | act--03 Integration | 03 Integration | Completed | Activity | 245004929 | 04/14/2018 12:30:00 | 04/14/2018 21:00:00 | 04/15/2018 12:30:00 | 04/15/2018 15:00:00
2582522 | 245004766 | act--04 SSV | 04 SSV | Completed | Activity | 245004988 | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 | 04/17/2018 08:00:00 | 04/17/2018 15:00:00
2582522 | 245004766 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005055 |  |  |  |  | 04/13/2018 06:30:00 | 04/13/2018 08:30:00 |  | 04/13/2018 09:30:00
2582523 | 245004770 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005175 |  |  |  |  | 04/15/2018 13:00:00 | 04/15/2018 15:00:00 |  | 04/15/2018 15:00:00
2582523 | 245004770 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005114 |  |  |  |  | 04/17/2018 12:30:00 | 04/17/2018 14:30:00 |  | 04/17/2018 15:00:00
2582523 | 245004770 | 0 | 07 Implementation Complete | Completed | Milestone | 245005235 |  |  |  |  | 01/01/2000 05:30:00 | 04/17/2018 15:00:00 |  | 04/17/2018 15:00:00
2582523 | 245004770 | act--02 Installation | 02 Installation | Completed | Activity | 245004865 | 04/12/2018 12:30:00 | 04/12/2018 15:30:00 | 04/13/2018 08:00:00 | 04/13/2018 15:00:00
2582523 | 245004770 | act--03 Integration | 03 Integration | Completed | Activity | 245004918 | 04/13/2018 12:30:00 | 04/13/2018 21:00:00 | 04/14/2018 12:30:00 | 04/14/2018 15:00:00
2582523 | 245004770 | act--04 SSV | 04 SSV | Completed | Activity | 245004973 | 04/15/2018 12:30:00 | 04/15/2018 14:30:00 | 04/16/2018 08:00:00 | 04/16/2018 15:00:00
2582523 | 245004770 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005054 |  |  |  |  | 04/12/2018 06:30:00 | 04/12/2018 08:30:00 |  | 04/12/2018 09:30:00
2582524 | 245004774 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005163 |  |  |  |  | 04/04/2018 13:00:00 | 04/04/2018 15:00:00 |  | 04/04/2018 15:00:00
2582524 | 245004774 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005110 |  |  |  |  | 04/06/2018 12:30:00 | 04/06/2018 14:30:00 |  | 04/06/2018 15:00:00
2582524 | 245004774 | 0 | 07 Implementation Complete | Completed | Milestone | 245005224 |  |  |  |  | 01/01/2000 05:30:00 | 04/06/2018 15:00:00 |  | 04/06/2018 15:00:00
2582524 | 245004774 | act--02 Installation | 02 Installation | Completed | Activity | 245004860 | 04/01/2018 12:30:00 | 04/01/2018 15:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582524 | 245004774 | act--03 Integration | 03 Integration | Completed | Activity | 245004921 | 04/02/2018 12:30:00 | 04/02/2018 21:00:00 | 04/03/2018 12:30:00 | 04/03/2018 15:00:00
2582524 | 245004774 | act--04 SSV | 04 SSV | Completed | Activity | 245004985 | 04/04/2018 12:30:00 | 04/04/2018 14:30:00 | 04/05/2018 08:00:00 | 04/05/2018 15:00:00
2582524 | 245004774 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005057 |  |  |  |  | 04/01/2018 06:30:00 | 04/01/2018 08:30:00 |  | 04/01/2018 09:30:00
2582525 | 245004775 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005187 |  |  |  |  | 04/17/2018 13:00:00 | 04/17/2018 15:00:00 |  | 04/17/2018 15:00:00
2582525 | 245004775 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005128 |  |  |  |  | 04/19/2018 12:30:00 | 04/19/2018 14:30:00 |  | 04/19/2018 15:00:00
2582525 | 245004775 | 0 | 07 Implementation Complete | Completed | Milestone | 245005243 |  |  |  |  | 01/01/2000 05:30:00 | 04/19/2018 15:00:00 |  | 04/19/2018 15:00:00
2582525 | 245004775 | act--02 Installation | 02 Installation | Completed | Activity | 245004864 | 04/14/2018 12:30:00 | 04/14/2018 15:30:00 | 04/15/2018 08:00:00 | 04/15/2018 15:00:00
2582525 | 245004775 | act--03 Integration | 03 Integration | Completed | Activity | 245004923 | 04/15/2018 12:30:00 | 04/15/2018 21:00:00 | 04/16/2018 12:30:00 | 04/16/2018 15:00:00
2582525 | 245004775 | act--04 SSV | 04 SSV | Completed | Activity | 245004977 | 04/17/2018 12:30:00 | 04/17/2018 14:30:00 | 04/18/2018 08:00:00 | 04/18/2018 15:00:00
2582525 | 245004775 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005074 |  |  |  |  | 04/14/2018 06:30:00 | 04/14/2018 08:30:00 |  | 04/14/2018 09:30:00
2582526 | 245005382 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005780 |  |  |  |  | 04/01/2018 13:00:00 | 04/01/2018 15:00:00 |  | 04/01/2018 15:00:00
2582526 | 245005382 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005728 |  |  |  |  | 04/03/2018 12:30:00 | 04/03/2018 14:30:00 |  | 04/03/2018 15:00:00
2582526 | 245005382 | 0 | 07 Implementation Complete | Completed | Milestone | 245005837 |  |  |  |  | 01/01/2000 05:30:00 | 04/03/2018 15:00:00 |  | 04/03/2018 15:00:00
2582526 | 245005382 | act--02 Installation | 02 Installation | Completed | Activity | 245005481 | 03/29/2018 12:30:00 | 03/29/2018 15:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582526 | 245005382 | act--03 Integration | 03 Integration | Completed | Activity | 245005539 | 03/30/2018 12:30:00 | 03/30/2018 21:00:00 | 03/31/2018 12:30:00 | 03/31/2018 15:00:00
2582526 | 245005382 | act--04 SSV | 04 SSV | Completed | Activity | 245005592 | 04/01/2018 12:30:00 | 04/01/2018 14:30:00 | 04/02/2018 08:00:00 | 04/02/2018 15:00:00
2582526 | 245005382 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005675 |  |  |  |  | 03/29/2018 06:30:00 | 03/29/2018 08:30:00 |  | 03/29/2018 09:30:00
2582527 | 245005384 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005795 |  |  |  |  | 03/26/2018 13:00:00 | 03/26/2018 15:00:00 |  | 03/26/2018 15:00:00
2582527 | 245005384 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005735 |  |  |  |  | 03/28/2018 12:30:00 | 03/28/2018 14:30:00 |  | 03/28/2018 15:00:00
2582527 | 245005384 | 0 | 07 Implementation Complete | Completed | Milestone | 245005859 |  |  |  |  | 01/01/2000 05:30:00 | 03/28/2018 15:00:00 |  | 03/28/2018 15:00:00
2582527 | 245005384 | act--02 Installation | 02 Installation | Completed | Activity | 245005479 | 03/23/2018 12:30:00 | 03/23/2018 15:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582527 | 245005384 | act--03 Integration | 03 Integration | Completed | Activity | 245005529 | 03/24/2018 12:30:00 | 03/24/2018 21:00:00 | 03/25/2018 12:30:00 | 03/25/2018 15:00:00
2582527 | 245005384 | act--04 SSV | 04 SSV | Completed | Activity | 245005596 | 03/26/2018 12:30:00 | 03/26/2018 14:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582527 | 245005384 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005672 |  |  |  |  | 03/23/2018 06:30:00 | 03/23/2018 08:30:00 |  | 03/23/2018 09:30:00
2582528 | 245005383 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005746 |  |  |  |  | 03/29/2018 13:00:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582528 | 245005383 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005686 |  |  |  |  | 03/31/2018 12:30:00 | 03/31/2018 14:30:00 |  | 03/31/2018 15:00:00
2582528 | 245005383 | 0 | 07 Implementation Complete | Completed | Milestone | 245005805 |  |  |  |  | 01/01/2000 05:30:00 | 03/31/2018 15:00:00 |  | 03/31/2018 15:00:00
2582528 | 245005383 | act--02 Installation | 02 Installation | Completed | Activity | 245005477 | 03/26/2018 12:30:00 | 03/26/2018 15:30:00 | 03/27/2018 08:00:00 | 03/27/2018 15:00:00
2582528 | 245005383 | act--03 Integration | 03 Integration | Completed | Activity | 245005516 | 03/27/2018 12:30:00 | 03/27/2018 21:00:00 | 03/28/2018 12:30:00 | 03/28/2018 15:00:00
2582528 | 245005383 | act--04 SSV | 04 SSV | Completed | Activity | 245005573 | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 | 03/30/2018 08:00:00 | 03/30/2018 15:00:00
2582528 | 245005383 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005627 |  |  |  |  | 03/26/2018 06:30:00 | 03/26/2018 08:30:00 |  | 03/26/2018 09:30:00
2582529 | 245005386 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005781 |  |  |  |  | 03/23/2018 13:00:00 | 03/23/2018 15:00:00 |  | 03/23/2018 15:00:00
2582529 | 245005386 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005727 |  |  |  |  | 03/25/2018 12:30:00 | 03/25/2018 14:30:00 |  | 03/25/2018 15:00:00
2582529 | 245005386 | 0 | 07 Implementation Complete | Completed | Milestone | 245005834 |  |  |  |  | 01/01/2000 05:30:00 | 03/25/2018 15:00:00 |  | 03/25/2018 15:00:00
2582529 | 245005386 | act--02 Installation | 02 Installation | Completed | Activity | 245005478 | 03/20/2018 12:30:00 | 03/20/2018 15:30:00 | 03/21/2018 08:00:00 | 03/21/2018 15:00:00
2582529 | 245005386 | act--03 Integration | 03 Integration | Completed | Activity | 245005531 | 03/21/2018 12:30:00 | 03/21/2018 21:00:00 | 03/22/2018 12:30:00 | 03/22/2018 15:00:00
2582529 | 245005386 | act--04 SSV | 04 SSV | Completed | Activity | 245005593 | 03/23/2018 12:30:00 | 03/23/2018 14:30:00 | 03/24/2018 08:00:00 | 03/24/2018 15:00:00
2582529 | 245005386 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005666 |  |  |  |  | 03/20/2018 06:30:00 | 03/20/2018 08:30:00 |  | 03/20/2018 09:30:00
2582530 | 245005388 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005770 |  |  |  |  | 04/21/2018 13:00:00 | 04/21/2018 15:00:00 |  | 04/21/2018 15:00:00
2582530 | 245005388 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005715 |  |  |  |  | 04/23/2018 12:30:00 | 04/23/2018 14:30:00 |  | 04/23/2018 15:00:00
2582530 | 245005388 | 0 | 07 Implementation Complete | Completed | Milestone | 245005831 |  |  |  |  | 01/01/2000 05:30:00 | 04/23/2018 15:00:00 |  | 04/23/2018 15:00:00
2582530 | 245005388 | act--02 Installation | 02 Installation | Completed | Activity | 245005483 | 04/18/2018 12:30:00 | 04/18/2018 15:30:00 | 04/19/2018 08:00:00 | 04/19/2018 15:00:00
2582530 | 245005388 | act--03 Integration | 03 Integration | Completed | Activity | 245005546 | 04/19/2018 12:30:00 | 04/19/2018 21:00:00 | 04/20/2018 12:30:00 | 04/20/2018 15:00:00
2582530 | 245005388 | act--04 SSV | 04 SSV | Completed | Activity | 245005590 | 04/21/2018 12:30:00 | 04/21/2018 14:30:00 | 04/22/2018 08:00:00 | 04/22/2018 15:00:00
2582530 | 245005388 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005654 |  |  |  |  | 04/18/2018 06:30:00 | 04/18/2018 08:30:00 |  | 04/18/2018 09:30:00
2582531 | 245005387 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005777 |  |  |  |  | 04/19/2018 13:00:00 | 04/19/2018 15:00:00 |  | 04/19/2018 15:00:00
2582531 | 245005387 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005721 |  |  |  |  | 04/21/2018 12:30:00 | 04/21/2018 14:30:00 |  | 04/21/2018 15:00:00
2582531 | 245005387 | 0 | 07 Implementation Complete | Completed | Milestone | 245005841 |  |  |  |  | 01/01/2000 05:30:00 | 04/21/2018 15:00:00 |  | 04/21/2018 15:00:00
2582531 | 245005387 | act--02 Installation | 02 Installation | Completed | Activity | 245005482 | 04/16/2018 12:30:00 | 04/16/2018 15:30:00 | 04/17/2018 08:00:00 | 04/17/2018 15:00:00
2582531 | 245005387 | act--03 Integration | 03 Integration | Completed | Activity | 245005540 | 04/17/2018 12:30:00 | 04/17/2018 21:00:00 | 04/18/2018 12:30:00 | 04/18/2018 15:00:00
2582531 | 245005387 | act--04 SSV | 04 SSV | Completed | Activity | 245005598 | 04/19/2018 12:30:00 | 04/19/2018 14:30:00 | 04/20/2018 08:00:00 | 04/20/2018 15:00:00
2582531 | 245005387 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005656 |  |  |  |  | 04/16/2018 06:30:00 | 04/16/2018 08:30:00 |  | 04/16/2018 09:30:00
2582532 | 245005385 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005772 |  |  |  |  | 04/12/2018 13:00:00 | 04/12/2018 15:00:00 |  | 04/12/2018 15:00:00
2582532 | 245005385 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005710 |  |  |  |  | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 |  | 04/14/2018 15:00:00
2582532 | 245005385 | 0 | 07 Implementation Complete | Completed | Milestone | 245005830 |  |  |  |  | 01/01/2000 05:30:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582532 | 245005385 | act--02 Installation | 02 Installation | Completed | Activity | 245005488 | 04/09/2018 12:30:00 | 04/09/2018 15:30:00 | 04/10/2018 08:00:00 | 04/10/2018 15:00:00
2582532 | 245005385 | act--03 Integration | 03 Integration | Completed | Activity | 245005528 | 04/10/2018 12:30:00 | 04/10/2018 21:00:00 | 04/11/2018 12:30:00 | 04/11/2018 15:00:00
2582532 | 245005385 | act--04 SSV | 04 SSV | Completed | Activity | 245005601 | 04/12/2018 12:30:00 | 04/12/2018 14:30:00 | 04/13/2018 08:00:00 | 04/13/2018 15:00:00
2582532 | 245005385 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005641 |  |  |  |  | 04/09/2018 06:30:00 | 04/09/2018 08:30:00 |  | 04/09/2018 09:30:00
2582533 | 245005389 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005758 |  |  |  |  | 04/18/2018 13:00:00 | 04/18/2018 15:00:00 |  | 04/18/2018 15:00:00
2582533 | 245005389 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005704 |  |  |  |  | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 |  | 04/20/2018 15:00:00
2582533 | 245005389 | 0 | 07 Implementation Complete | Completed | Milestone | 245005806 |  |  |  |  | 01/01/2000 05:30:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582533 | 245005389 | act--02 Installation | 02 Installation | Completed | Activity | 245005484 | 04/15/2018 12:30:00 | 04/15/2018 15:30:00 | 04/16/2018 08:00:00 | 04/16/2018 15:00:00
2582533 | 245005389 | act--03 Integration | 03 Integration | Completed | Activity | 245005534 | 04/16/2018 12:30:00 | 04/16/2018 21:00:00 | 04/17/2018 12:30:00 | 04/17/2018 15:00:00
2582533 | 245005389 | act--04 SSV | 04 SSV | Completed | Activity | 245005587 | 04/18/2018 12:30:00 | 04/18/2018 14:30:00 | 04/19/2018 08:00:00 | 04/19/2018 15:00:00
2582533 | 245005389 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005653 |  |  |  |  | 04/15/2018 06:30:00 | 04/15/2018 08:30:00 |  | 04/15/2018 09:30:00
2582534 | 245005390 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005774 |  |  |  |  | 06/07/2018 13:00:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582534 | 245005390 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005713 |  |  |  |  | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582534 | 245005390 | 0 | 07 Implementation Complete | Completed | Milestone | 245005828 |  |  |  |  | 01/01/2000 05:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582534 | 245005390 | act--02 Installation | 02 Installation | Completed | Activity | 245005491 | 06/04/2018 12:30:00 | 06/04/2018 16:00:00 | 06/05/2018 07:00:00 | 06/05/2018 15:30:00
2582534 | 245005390 | act--03 Integration | 03 Integration | Completed | Activity | 245005532 | 06/05/2018 12:30:00 | 06/05/2018 23:00:00 | 06/06/2018 11:30:00 | 06/06/2018 15:30:00
2582534 | 245005390 | act--04 SSV | 04 SSV | Completed | Activity | 245005586 | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582534 | 245005390 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005647 |  |  |  |  | 06/04/2018 06:30:00 | 06/04/2018 07:30:00 |  | 06/04/2018 08:30:00
2582535 | 245005393 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005796 |  |  |  |  | 06/10/2018 13:00:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582535 | 245005393 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005737 |  |  |  |  | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582535 | 245005393 | 0 | 07 Implementation Complete | Completed | Milestone | 245005855 |  |  |  |  | 01/01/2000 05:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582535 | 245005393 | act--02 Installation | 02 Installation | Completed | Activity | 245005486 | 06/07/2018 12:30:00 | 06/07/2018 16:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582535 | 245005393 | act--03 Integration | 03 Integration | Completed | Activity | 245005538 | 06/08/2018 12:30:00 | 06/08/2018 23:00:00 | 06/09/2018 11:30:00 | 06/09/2018 15:30:00
2582535 | 245005393 | act--04 SSV | 04 SSV | Completed | Activity | 245005605 | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582535 | 245005393 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005684 |  |  |  |  | 06/07/2018 06:30:00 | 06/07/2018 07:30:00 |  | 06/07/2018 08:30:00
2582536 | 245005392 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005791 |  |  |  |  | 06/09/2018 13:00:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582536 | 245005392 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005729 |  |  |  |  | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582536 | 245005392 | 0 | 07 Implementation Complete | Completed | Milestone | 245005851 |  |  |  |  | 01/01/2000 05:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582536 | 245005392 | act--02 Installation | 02 Installation | Completed | Activity | 245005490 | 06/06/2018 12:30:00 | 06/06/2018 16:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582536 | 245005392 | act--03 Integration | 03 Integration | Completed | Activity | 245005536 | 06/07/2018 12:30:00 | 06/07/2018 23:00:00 | 06/08/2018 11:30:00 | 06/08/2018 15:30:00
2582536 | 245005392 | act--04 SSV | 04 SSV | Completed | Activity | 245005591 | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582536 | 245005392 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005661 |  |  |  |  | 06/06/2018 06:30:00 | 06/06/2018 07:30:00 |  | 06/06/2018 08:30:00
2582537 | 245005391 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005810 |  |  |  |  | 06/05/2018 13:00:00 | 06/05/2018 15:00:00 |  | 06/05/2018 15:00:00
2582537 | 245005391 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005752 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582537 | 245005391 | 0 | 07 Implementation Complete | Completed | Milestone | 245005866 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582537 | 245005391 | act--02 Installation | 02 Installation | Completed | Activity | 245005493 | 06/02/2018 12:30:00 | 06/02/2018 16:00:00 | 06/03/2018 07:00:00 | 06/03/2018 15:30:00
2582537 | 245005391 | act--03 Integration | 03 Integration | Completed | Activity | 245005548 | 06/03/2018 12:30:00 | 06/03/2018 23:00:00 | 06/04/2018 11:30:00 | 06/04/2018 15:30:00
2582537 | 245005391 | act--04 SSV | 04 SSV | Completed | Activity | 245005620 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582537 | 245005391 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005697 |  |  |  |  | 06/02/2018 06:30:00 | 06/02/2018 07:30:00 |  | 06/02/2018 08:30:00
2582538 | 245005394 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005807 |  |  |  |  | 04/20/2018 13:00:00 | 04/20/2018 15:00:00 |  | 04/20/2018 15:00:00
2582538 | 245005394 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005749 |  |  |  |  | 04/22/2018 12:30:00 | 04/22/2018 14:30:00 |  | 04/22/2018 15:00:00
2582538 | 245005394 | 0 | 07 Implementation Complete | Completed | Milestone | 245005868 |  |  |  |  | 01/01/2000 05:30:00 | 04/22/2018 15:00:00 |  | 04/22/2018 15:00:00
2582538 | 245005394 | act--02 Installation | 02 Installation | Completed | Activity | 245005485 | 04/17/2018 12:30:00 | 04/17/2018 15:30:00 | 04/18/2018 08:00:00 | 04/18/2018 15:00:00
2582538 | 245005394 | act--03 Integration | 03 Integration | Completed | Activity | 245005547 | 04/18/2018 12:30:00 | 04/18/2018 21:00:00 | 04/19/2018 12:30:00 | 04/19/2018 15:00:00
2582538 | 245005394 | act--04 SSV | 04 SSV | Completed | Activity | 245005616 | 04/20/2018 12:30:00 | 04/20/2018 14:30:00 | 04/21/2018 08:00:00 | 04/21/2018 15:00:00
2582538 | 245005394 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005695 |  |  |  |  | 04/17/2018 06:30:00 | 04/17/2018 08:30:00 |  | 04/17/2018 09:30:00
2582539 | 245005397 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005803 |  |  |  |  | 06/04/2018 13:00:00 | 06/04/2018 15:00:00 |  | 06/04/2018 15:00:00
2582539 | 245005397 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005750 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582539 | 245005397 | 0 | 07 Implementation Complete | Completed | Milestone | 245005861 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582539 | 245005397 | act--02 Installation | 02 Installation | Completed | Activity | 245005495 | 06/01/2018 12:30:00 | 06/01/2018 16:00:00 | 06/02/2018 07:00:00 | 06/02/2018 15:30:00
2582539 | 245005397 | act--03 Integration | 03 Integration | Completed | Activity | 245005550 | 06/02/2018 12:30:00 | 06/02/2018 23:00:00 | 06/03/2018 11:30:00 | 06/03/2018 15:30:00
2582539 | 245005397 | act--04 SSV | 04 SSV | Completed | Activity | 245005604 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582539 | 245005397 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005694 |  |  |  |  | 06/01/2018 06:30:00 | 06/01/2018 07:30:00 |  | 06/01/2018 08:30:00
2582540 | 245005398 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005763 |  |  |  |  | 06/10/2018 13:00:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582540 | 245005398 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005707 |  |  |  |  | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582540 | 245005398 | 0 | 07 Implementation Complete | Completed | Milestone | 245005820 |  |  |  |  | 01/01/2000 05:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582540 | 245005398 | act--02 Installation | 02 Installation | Completed | Activity | 245005494 | 06/07/2018 12:30:00 | 06/07/2018 16:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582540 | 245005398 | act--03 Integration | 03 Integration | Completed | Activity | 245005549 | 06/08/2018 12:30:00 | 06/08/2018 23:00:00 | 06/09/2018 11:30:00 | 06/09/2018 15:30:00
2582540 | 245005398 | act--04 SSV | 04 SSV | Completed | Activity | 245005597 | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582540 | 245005398 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005640 |  |  |  |  | 06/07/2018 06:30:00 | 06/07/2018 07:30:00 |  | 06/07/2018 08:30:00
2582541 | 245005400 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005811 |  |  |  |  | 06/08/2018 13:00:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582541 | 245005400 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005759 |  |  |  |  | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582541 | 245005400 | 0 | 07 Implementation Complete | Completed | Milestone | 245005869 |  |  |  |  | 01/01/2000 05:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582541 | 245005400 | act--02 Installation | 02 Installation | Completed | Activity | 245005496 | 06/05/2018 12:30:00 | 06/05/2018 16:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582541 | 245005400 | act--03 Integration | 03 Integration | Completed | Activity | 245005558 | 06/06/2018 12:30:00 | 06/06/2018 23:00:00 | 06/07/2018 11:30:00 | 06/07/2018 15:30:00
2582541 | 245005400 | act--04 SSV | 04 SSV | Completed | Activity | 245005610 | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582541 | 245005400 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005700 |  |  |  |  | 06/05/2018 06:30:00 | 06/05/2018 07:30:00 |  | 06/05/2018 08:30:00
2582542 | 245005399 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005797 |  |  |  |  | 06/06/2018 13:00:00 | 06/06/2018 15:00:00 |  | 06/06/2018 15:00:00
2582542 | 245005399 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005738 |  |  |  |  | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582542 | 245005399 | 0 | 07 Implementation Complete | Completed | Milestone | 245005849 |  |  |  |  | 01/01/2000 05:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582542 | 245005399 | act--02 Installation | 02 Installation | Completed | Activity | 245005489 | 06/03/2018 12:30:00 | 06/03/2018 16:00:00 | 06/04/2018 07:00:00 | 06/04/2018 15:30:00
2582542 | 245005399 | act--03 Integration | 03 Integration | Completed | Activity | 245005544 | 06/04/2018 12:30:00 | 06/04/2018 23:00:00 | 06/05/2018 11:30:00 | 06/05/2018 15:30:00
2582542 | 245005399 | act--04 SSV | 04 SSV | Completed | Activity | 245005602 | 06/06/2018 12:30:00 | 06/06/2018 15:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582542 | 245005399 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005674 |  |  |  |  | 06/03/2018 06:30:00 | 06/03/2018 07:30:00 |  | 06/03/2018 08:30:00
2582543 | 245005406 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005779 |  |  |  |  | 06/07/2018 13:00:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582543 | 245005406 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005725 |  |  |  |  | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582543 | 245005406 | 0 | 07 Implementation Complete | Completed | Milestone | 245005835 |  |  |  |  | 01/01/2000 05:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582543 | 245005406 | act--02 Installation | 02 Installation | Completed | Activity | 245005498 | 06/04/2018 12:30:00 | 06/04/2018 16:00:00 | 06/05/2018 07:00:00 | 06/05/2018 15:30:00
2582543 | 245005406 | act--03 Integration | 03 Integration | Completed | Activity | 245005557 | 06/05/2018 12:30:00 | 06/05/2018 23:00:00 | 06/06/2018 11:30:00 | 06/06/2018 15:30:00
2582543 | 245005406 | act--04 SSV | 04 SSV | Completed | Activity | 245005607 | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582543 | 245005406 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005665 |  |  |  |  | 06/04/2018 06:30:00 | 06/04/2018 07:30:00 |  | 06/04/2018 08:30:00
2582544 | 245005412 | 0 | 05 NRO IM Accept | Completed | Milestone | 245005789 |  |  |  |  | 06/06/2018 13:00:00 | 06/06/2018 15:00:00 |  | 06/06/2018 15:00:00
2582544 | 245005412 | 0 | 06 NDO IM Accept | Completed | Milestone | 245005734 |  |  |  |  | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582544 | 245005412 | 0 | 07 Implementation Complete | Completed | Milestone | 245005838 |  |  |  |  | 01/01/2000 05:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582544 | 245005412 | act--02 Installation | 02 Installation | Completed | Activity | 245005497 | 06/03/2018 12:30:00 | 06/03/2018 16:00:00 | 06/04/2018 07:00:00 | 06/04/2018 15:30:00
2582544 | 245005412 | act--03 Integration | 03 Integration | Completed | Activity | 245005554 | 06/04/2018 12:30:00 | 06/04/2018 23:00:00 | 06/05/2018 11:30:00 | 06/05/2018 15:30:00
2582544 | 245005412 | act--04 SSV | 04 SSV | Completed | Activity | 245005609 | 06/06/2018 12:30:00 | 06/06/2018 15:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582544 | 245005412 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245005669 |  |  |  |  | 06/03/2018 06:30:00 | 06/03/2018 07:30:00 |  | 06/03/2018 08:30:00
2582545 | 245006013 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006387 |  |  |  |  | 06/06/2018 13:00:00 | 06/06/2018 15:00:00 |  | 06/06/2018 15:00:00
2582545 | 245006013 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006324 |  |  |  |  | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582545 | 245006013 | 0 | 07 Implementation Complete | Completed | Milestone | 245006445 |  |  |  |  | 01/01/2000 05:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582545 | 245006013 | act--02 Installation | 02 Installation | Completed | Activity | 245006110 | 06/03/2018 12:30:00 | 06/03/2018 16:00:00 | 06/04/2018 07:00:00 | 06/04/2018 15:30:00
2582545 | 245006013 | act--03 Integration | 03 Integration | Completed | Activity | 245006159 | 06/04/2018 12:30:00 | 06/04/2018 23:00:00 | 06/05/2018 11:30:00 | 06/05/2018 15:30:00
2582545 | 245006013 | act--04 SSV | 04 SSV | Completed | Activity | 245006216 | 06/06/2018 12:30:00 | 06/06/2018 15:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582545 | 245006013 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006268 |  |  |  |  | 06/03/2018 06:30:00 | 06/03/2018 07:30:00 |  | 06/03/2018 08:30:00
2582546 | 245006014 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006391 |  |  |  |  | 06/13/2018 13:00:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582546 | 245006014 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006334 |  |  |  |  | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582546 | 245006014 | 0 | 07 Implementation Complete | Completed | Milestone | 245006443 |  |  |  |  | 01/01/2000 05:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582546 | 245006014 | act--02 Installation | 02 Installation | Completed | Activity | 245006111 | 06/10/2018 12:30:00 | 06/10/2018 16:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582546 | 245006014 | act--03 Integration | 03 Integration | Completed | Activity | 245006155 | 06/11/2018 12:30:00 | 06/11/2018 23:00:00 | 06/12/2018 11:30:00 | 06/12/2018 15:30:00
2582546 | 245006014 | act--04 SSV | 04 SSV | Completed | Activity | 245006215 | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582546 | 245006014 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006275 |  |  |  |  | 06/10/2018 06:30:00 | 06/10/2018 07:30:00 |  | 06/10/2018 08:30:00
2582547 | 245006015 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006432 |  |  |  |  | 06/04/2018 13:00:00 | 06/04/2018 15:00:00 |  | 06/04/2018 15:00:00
2582547 | 245006015 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006374 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582547 | 245006015 | 0 | 07 Implementation Complete | Completed | Milestone | 245006497 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582547 | 245006015 | act--02 Installation | 02 Installation | Completed | Activity | 245006113 | 06/01/2018 12:30:00 | 06/01/2018 16:00:00 | 06/02/2018 07:00:00 | 06/02/2018 15:30:00
2582547 | 245006015 | act--03 Integration | 03 Integration | Completed | Activity | 245006171 | 06/02/2018 12:30:00 | 06/02/2018 23:00:00 | 06/03/2018 11:30:00 | 06/03/2018 15:30:00
2582547 | 245006015 | act--04 SSV | 04 SSV | Completed | Activity | 245006239 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582547 | 245006015 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006313 |  |  |  |  | 06/01/2018 06:30:00 | 06/01/2018 07:30:00 |  | 06/01/2018 08:30:00
2582548 | 245006018 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006405 |  |  |  |  | 06/06/2018 13:00:00 | 06/06/2018 15:00:00 |  | 06/06/2018 15:00:00
2582548 | 245006018 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006346 |  |  |  |  | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582548 | 245006018 | 0 | 07 Implementation Complete | Completed | Milestone | 245006462 |  |  |  |  | 01/01/2000 05:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582548 | 245006018 | act--02 Installation | 02 Installation | Completed | Activity | 245006112 | 06/03/2018 12:30:00 | 06/03/2018 16:00:00 | 06/04/2018 07:00:00 | 06/04/2018 15:30:00
2582548 | 245006018 | act--03 Integration | 03 Integration | Completed | Activity | 245006165 | 06/04/2018 12:30:00 | 06/04/2018 23:00:00 | 06/05/2018 11:30:00 | 06/05/2018 15:30:00
2582548 | 245006018 | act--04 SSV | 04 SSV | Completed | Activity | 245006224 | 06/06/2018 12:30:00 | 06/06/2018 15:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582548 | 245006018 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006285 |  |  |  |  | 06/03/2018 06:30:00 | 06/03/2018 07:30:00 |  | 06/03/2018 08:30:00
2582549 | 245006021 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006414 |  |  |  |  | 06/06/2018 13:00:00 | 06/06/2018 15:00:00 |  | 06/06/2018 15:00:00
2582549 | 245006021 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006355 |  |  |  |  | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582549 | 245006021 | 0 | 07 Implementation Complete | Completed | Milestone | 245006467 |  |  |  |  | 01/01/2000 05:30:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582549 | 245006021 | act--02 Installation | 02 Installation | Completed | Activity | 245006114 | 06/03/2018 12:30:00 | 06/03/2018 16:00:00 | 06/04/2018 07:00:00 | 06/04/2018 15:30:00
2582549 | 245006021 | act--03 Integration | 03 Integration | Completed | Activity | 245006169 | 06/04/2018 12:30:00 | 06/04/2018 23:00:00 | 06/05/2018 11:30:00 | 06/05/2018 15:30:00
2582549 | 245006021 | act--04 SSV | 04 SSV | Completed | Activity | 245006230 | 06/06/2018 12:30:00 | 06/06/2018 15:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582549 | 245006021 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006293 |  |  |  |  | 06/03/2018 06:30:00 | 06/03/2018 07:30:00 |  | 06/03/2018 08:30:00
2582550 | 245006019 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006420 |  |  |  |  | 06/04/2018 13:00:00 | 06/04/2018 15:00:00 |  | 06/04/2018 15:00:00
2582550 | 245006019 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006366 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582550 | 245006019 | 0 | 07 Implementation Complete | Completed | Milestone | 245006486 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582550 | 245006019 | act--02 Installation | 02 Installation | Completed | Activity | 245006116 | 06/01/2018 12:30:00 | 06/01/2018 16:00:00 | 06/02/2018 07:00:00 | 06/02/2018 15:30:00
2582550 | 245006019 | act--03 Integration | 03 Integration | Completed | Activity | 245006167 | 06/02/2018 12:30:00 | 06/02/2018 23:00:00 | 06/03/2018 11:30:00 | 06/03/2018 15:30:00
2582550 | 245006019 | act--04 SSV | 04 SSV | Completed | Activity | 245006229 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582550 | 245006019 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006302 |  |  |  |  | 06/01/2018 06:30:00 | 06/01/2018 07:30:00 |  | 06/01/2018 08:30:00
2582551 | 245006016 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006421 |  |  |  |  | 06/05/2018 13:00:00 | 06/05/2018 15:00:00 |  | 06/05/2018 15:00:00
2582551 | 245006016 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006372 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582551 | 245006016 | 0 | 07 Implementation Complete | Completed | Milestone | 245006473 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582551 | 245006016 | act--02 Installation | 02 Installation | Completed | Activity | 245006117 | 06/02/2018 12:30:00 | 06/02/2018 16:00:00 | 06/03/2018 07:00:00 | 06/03/2018 15:30:00
2582551 | 245006016 | act--03 Integration | 03 Integration | Completed | Activity | 245006182 | 06/03/2018 12:30:00 | 06/03/2018 23:00:00 | 06/04/2018 11:30:00 | 06/04/2018 15:30:00
2582551 | 245006016 | act--04 SSV | 04 SSV | Completed | Activity | 245006236 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582551 | 245006016 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006309 |  |  |  |  | 06/02/2018 06:30:00 | 06/02/2018 07:30:00 |  | 06/02/2018 08:30:00
2582552 | 245006017 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006460 |  |  |  |  | 06/07/2018 13:00:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582552 | 245006017 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006403 |  |  |  |  | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582552 | 245006017 | 0 | 07 Implementation Complete | Completed | Milestone | 245006518 |  |  |  |  | 01/01/2000 05:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582552 | 245006017 | act--02 Installation | 02 Installation | Completed | Activity | 245006115 | 06/04/2018 12:30:00 | 06/04/2018 16:00:00 | 06/05/2018 07:00:00 | 06/05/2018 15:30:00
2582552 | 245006017 | act--03 Integration | 03 Integration | Completed | Activity | 245006184 | 06/05/2018 12:30:00 | 06/05/2018 23:00:00 | 06/06/2018 11:30:00 | 06/06/2018 15:30:00
2582552 | 245006017 | act--04 SSV | 04 SSV | Completed | Activity | 245006245 | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582552 | 245006017 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006342 |  |  |  |  | 06/04/2018 06:30:00 | 06/04/2018 07:30:00 |  | 06/04/2018 08:30:00
2582553 | 245006022 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006409 |  |  |  |  | 06/05/2018 13:00:00 | 06/05/2018 15:00:00 |  | 06/05/2018 15:00:00
2582553 | 245006022 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006354 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582553 | 245006022 | 0 | 07 Implementation Complete | Completed | Milestone | 245006469 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582553 | 245006022 | act--02 Installation | 02 Installation | Completed | Activity | 245006122 | 06/02/2018 12:30:00 | 06/02/2018 16:00:00 | 06/03/2018 07:00:00 | 06/03/2018 15:30:00
2582553 | 245006022 | act--03 Integration | 03 Integration | Completed | Activity | 245006178 | 06/03/2018 12:30:00 | 06/03/2018 23:00:00 | 06/04/2018 11:30:00 | 06/04/2018 15:30:00
2582553 | 245006022 | act--04 SSV | 04 SSV | Completed | Activity | 245006232 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582553 | 245006022 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006300 |  |  |  |  | 06/02/2018 06:30:00 | 06/02/2018 07:30:00 |  | 06/02/2018 08:30:00
2582554 | 245006020 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006410 |  |  |  |  | 06/07/2018 13:00:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582554 | 245006020 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006352 |  |  |  |  | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582554 | 245006020 | 0 | 07 Implementation Complete | Completed | Milestone | 245006464 |  |  |  |  | 01/01/2000 05:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582554 | 245006020 | act--02 Installation | 02 Installation | Completed | Activity | 245006124 | 06/04/2018 12:30:00 | 06/04/2018 16:00:00 | 06/05/2018 07:00:00 | 06/05/2018 15:30:00
2582554 | 245006020 | act--03 Integration | 03 Integration | Completed | Activity | 245006174 | 06/05/2018 12:30:00 | 06/05/2018 23:00:00 | 06/06/2018 11:30:00 | 06/06/2018 15:30:00
2582554 | 245006020 | act--04 SSV | 04 SSV | Completed | Activity | 245006227 | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582554 | 245006020 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006287 |  |  |  |  | 06/04/2018 06:30:00 | 06/04/2018 07:30:00 |  | 06/04/2018 08:30:00
2582555 | 245006024 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006424 |  |  |  |  | 06/11/2018 13:00:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582555 | 245006024 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006362 |  |  |  |  | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582555 | 245006024 | 0 | 07 Implementation Complete | Completed | Milestone | 245006480 |  |  |  |  | 01/01/2000 05:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582555 | 245006024 | act--02 Installation | 02 Installation | Completed | Activity | 245006121 | 06/08/2018 12:30:00 | 06/08/2018 16:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582555 | 245006024 | act--03 Integration | 03 Integration | Completed | Activity | 245006177 | 06/09/2018 12:30:00 | 06/09/2018 23:00:00 | 06/10/2018 11:30:00 | 06/10/2018 15:30:00
2582555 | 245006024 | act--04 SSV | 04 SSV | Completed | Activity | 245006234 | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582555 | 245006024 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006301 |  |  |  |  | 06/08/2018 06:30:00 | 06/08/2018 07:30:00 |  | 06/08/2018 08:30:00
2582556 | 245006025 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006430 |  |  |  |  | 06/10/2018 13:00:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582556 | 245006025 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006364 |  |  |  |  | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582556 | 245006025 | 0 | 07 Implementation Complete | Completed | Milestone | 245006488 |  |  |  |  | 01/01/2000 05:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582556 | 245006025 | act--02 Installation | 02 Installation | Completed | Activity | 245006120 | 06/07/2018 12:30:00 | 06/07/2018 16:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582556 | 245006025 | act--03 Integration | 03 Integration | Completed | Activity | 245006180 | 06/08/2018 12:30:00 | 06/08/2018 23:00:00 | 06/09/2018 11:30:00 | 06/09/2018 15:30:00
2582556 | 245006025 | act--04 SSV | 04 SSV | Completed | Activity | 245006237 | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582556 | 245006025 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006303 |  |  |  |  | 06/07/2018 06:30:00 | 06/07/2018 07:30:00 |  | 06/07/2018 08:30:00
2582557 | 245006031 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006419 |  |  |  |  | 06/12/2018 13:00:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582557 | 245006031 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006363 |  |  |  |  | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582557 | 245006031 | 0 | 07 Implementation Complete | Completed | Milestone | 245006474 |  |  |  |  | 01/01/2000 05:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582557 | 245006031 | act--02 Installation | 02 Installation | Completed | Activity | 245006123 | 06/09/2018 12:30:00 | 06/09/2018 16:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582557 | 245006031 | act--03 Integration | 03 Integration | Completed | Activity | 245006189 | 06/10/2018 12:30:00 | 06/10/2018 23:00:00 | 06/11/2018 11:30:00 | 06/11/2018 15:30:00
2582557 | 245006031 | act--04 SSV | 04 SSV | Completed | Activity | 245006238 | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582557 | 245006031 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006306 |  |  |  |  | 06/09/2018 06:30:00 | 06/09/2018 07:30:00 |  | 06/09/2018 08:30:00
2582558 | 245006029 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006459 |  |  |  |  | 06/13/2018 13:00:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582558 | 245006029 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006400 |  |  |  |  | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582558 | 245006029 | 0 | 07 Implementation Complete | Completed | Milestone | 245006516 |  |  |  |  | 01/01/2000 05:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582558 | 245006029 | act--02 Installation | 02 Installation | Completed | Activity | 245006126 | 06/10/2018 12:30:00 | 06/10/2018 16:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582558 | 245006029 | act--03 Integration | 03 Integration | Completed | Activity | 245006194 | 06/11/2018 12:30:00 | 06/11/2018 23:00:00 | 06/12/2018 11:30:00 | 06/12/2018 15:30:00
2582558 | 245006029 | act--04 SSV | 04 SSV | Completed | Activity | 245006259 | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582558 | 245006029 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006347 |  |  |  |  | 06/10/2018 06:30:00 | 06/10/2018 07:30:00 |  | 06/10/2018 08:30:00
2582559 | 245006026 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006455 |  |  |  |  | 06/05/2018 13:00:00 | 06/05/2018 15:00:00 |  | 06/05/2018 15:00:00
2582559 | 245006026 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006394 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582559 | 245006026 | 0 | 07 Implementation Complete | Completed | Milestone | 245006513 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582559 | 245006026 | act--02 Installation | 02 Installation | Completed | Activity | 245006127 | 06/02/2018 12:30:00 | 06/02/2018 16:00:00 | 06/03/2018 07:00:00 | 06/03/2018 15:30:00
2582559 | 245006026 | act--03 Integration | 03 Integration | Completed | Activity | 245006190 | 06/03/2018 12:30:00 | 06/03/2018 23:00:00 | 06/04/2018 11:30:00 | 06/04/2018 15:30:00
2582559 | 245006026 | act--04 SSV | 04 SSV | Completed | Activity | 245006249 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582559 | 245006026 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006330 |  |  |  |  | 06/02/2018 06:30:00 | 06/02/2018 07:30:00 |  | 06/02/2018 08:30:00
2582560 | 245006032 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006435 |  |  |  |  | 06/11/2018 13:00:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582560 | 245006032 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006384 |  |  |  |  | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582560 | 245006032 | 0 | 07 Implementation Complete | Completed | Milestone | 245006496 |  |  |  |  | 01/01/2000 05:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582560 | 245006032 | act--02 Installation | 02 Installation | Completed | Activity | 245006129 | 06/08/2018 12:30:00 | 06/08/2018 16:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582560 | 245006032 | act--03 Integration | 03 Integration | Completed | Activity | 245006195 | 06/09/2018 12:30:00 | 06/09/2018 23:00:00 | 06/10/2018 11:30:00 | 06/10/2018 15:30:00
2582560 | 245006032 | act--04 SSV | 04 SSV | Completed | Activity | 245006247 | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582560 | 245006032 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006329 |  |  |  |  | 06/08/2018 06:30:00 | 06/08/2018 07:30:00 |  | 06/08/2018 08:30:00
2582561 | 245006030 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006433 |  |  |  |  | 06/09/2018 13:00:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582561 | 245006030 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006375 |  |  |  |  | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582561 | 245006030 | 0 | 07 Implementation Complete | Completed | Milestone | 245006495 |  |  |  |  | 01/01/2000 05:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582561 | 245006030 | act--02 Installation | 02 Installation | Completed | Activity | 245006128 | 06/06/2018 12:30:00 | 06/06/2018 16:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582561 | 245006030 | act--03 Integration | 03 Integration | Completed | Activity | 245006191 | 06/07/2018 12:30:00 | 06/07/2018 23:00:00 | 06/08/2018 11:30:00 | 06/08/2018 15:30:00
2582561 | 245006030 | act--04 SSV | 04 SSV | Completed | Activity | 245006251 | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582561 | 245006030 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006321 |  |  |  |  | 06/06/2018 06:30:00 | 06/06/2018 07:30:00 |  | 06/06/2018 08:30:00
2582562 | 245006037 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006397 |  |  |  |  | 06/09/2018 13:00:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582562 | 245006037 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006348 |  |  |  |  | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582562 | 245006037 | 0 | 07 Implementation Complete | Completed | Milestone | 245006453 |  |  |  |  | 01/01/2000 05:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582562 | 245006037 | act--02 Installation | 02 Installation | Completed | Activity | 245006125 | 06/06/2018 12:30:00 | 06/06/2018 16:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582562 | 245006037 | act--03 Integration | 03 Integration | Completed | Activity | 245006183 | 06/07/2018 12:30:00 | 06/07/2018 23:00:00 | 06/08/2018 11:30:00 | 06/08/2018 15:30:00
2582562 | 245006037 | act--04 SSV | 04 SSV | Completed | Activity | 245006228 | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582562 | 245006037 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006290 |  |  |  |  | 06/06/2018 06:30:00 | 06/06/2018 07:30:00 |  | 06/06/2018 08:30:00
2582563 | 245006034 | 0 | 05 NRO IM Accept | Completed | Milestone | 245006431 |  |  |  |  | 06/11/2018 13:00:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582563 | 245006034 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006378 |  |  |  |  | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582563 | 245006034 | 0 | 07 Implementation Complete | Completed | Milestone | 245006485 |  |  |  |  | 01/01/2000 05:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582563 | 245006034 | act--02 Installation | 02 Installation | Completed | Activity | 245006131 | 06/08/2018 12:30:00 | 06/08/2018 16:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582563 | 245006034 | act--03 Integration | 03 Integration | Completed | Activity | 245006186 | 06/09/2018 12:30:00 | 06/09/2018 23:00:00 | 06/10/2018 11:30:00 | 06/10/2018 15:30:00
2582563 | 245006034 | act--04 SSV | 04 SSV | Completed | Activity | 245006248 | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582563 | 245006034 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006318 |  |  |  |  | 06/08/2018 06:30:00 | 06/08/2018 07:30:00 |  | 06/08/2018 08:30:00
2582564 | 245006651 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007045 |  |  |  |  | 06/11/2018 13:00:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582564 | 245006651 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006990 |  |  |  |  | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582564 | 245006651 | 0 | 07 Implementation Complete | Completed | Milestone | 245007100 |  |  |  |  | 01/01/2000 05:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582564 | 245006651 | act--02 Installation | 02 Installation | Completed | Activity | 245006749 | 06/08/2018 12:30:00 | 06/08/2018 16:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582564 | 245006651 | act--03 Integration | 03 Integration | Completed | Activity | 245006798 | 06/09/2018 12:30:00 | 06/09/2018 23:00:00 | 06/10/2018 11:30:00 | 06/10/2018 15:30:00
2582564 | 245006651 | act--04 SSV | 04 SSV | Completed | Activity | 245006857 | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582564 | 245006651 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006927 |  |  |  |  | 06/08/2018 06:30:00 | 06/08/2018 07:30:00 |  | 06/08/2018 08:30:00
2582565 | 245006655 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007019 |  |  |  |  | 06/12/2018 13:00:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582565 | 245006655 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006956 |  |  |  |  | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582565 | 245006655 | 0 | 07 Implementation Complete | Completed | Milestone | 245007078 |  |  |  |  | 01/01/2000 05:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582565 | 245006655 | act--02 Installation | 02 Installation | Completed | Activity | 245006748 | 06/09/2018 12:30:00 | 06/09/2018 16:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582565 | 245006655 | act--03 Integration | 03 Integration | Completed | Activity | 245006791 | 06/10/2018 12:30:00 | 06/10/2018 23:00:00 | 06/11/2018 11:30:00 | 06/11/2018 15:30:00
2582565 | 245006655 | act--04 SSV | 04 SSV | Completed | Activity | 245006846 | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582565 | 245006655 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006904 |  |  |  |  | 06/09/2018 06:30:00 | 06/09/2018 07:30:00 |  | 06/09/2018 08:30:00
2582566 | 245006652 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007047 |  |  |  |  | 06/10/2018 13:00:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582566 | 245006652 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006988 |  |  |  |  | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582566 | 245006652 | 0 | 07 Implementation Complete | Completed | Milestone | 245007111 |  |  |  |  | 01/01/2000 05:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582566 | 245006652 | act--02 Installation | 02 Installation | Completed | Activity | 245006752 | 06/07/2018 12:30:00 | 06/07/2018 16:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582566 | 245006652 | act--03 Integration | 03 Integration | Completed | Activity | 245006812 | 06/08/2018 12:30:00 | 06/08/2018 23:00:00 | 06/09/2018 11:30:00 | 06/09/2018 15:30:00
2582566 | 245006652 | act--04 SSV | 04 SSV | Completed | Activity | 245006874 | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582566 | 245006652 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006929 |  |  |  |  | 06/07/2018 06:30:00 | 06/07/2018 07:30:00 |  | 06/07/2018 08:30:00
2582567 | 245006654 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007040 |  |  |  |  | 06/08/2018 13:00:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582567 | 245006654 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006983 |  |  |  |  | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582567 | 245006654 | 0 | 07 Implementation Complete | Completed | Milestone | 245007095 |  |  |  |  | 01/01/2000 05:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582567 | 245006654 | act--02 Installation | 02 Installation | Completed | Activity | 245006747 | 06/05/2018 12:30:00 | 06/05/2018 16:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582567 | 245006654 | act--03 Integration | 03 Integration | Completed | Activity | 245006797 | 06/06/2018 12:30:00 | 06/06/2018 23:00:00 | 06/07/2018 11:30:00 | 06/07/2018 15:30:00
2582567 | 245006654 | act--04 SSV | 04 SSV | Completed | Activity | 245006855 | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582567 | 245006654 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006921 |  |  |  |  | 06/05/2018 06:30:00 | 06/05/2018 07:30:00 |  | 06/05/2018 08:30:00
2582568 | 245006653 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007037 |  |  |  |  | 06/10/2018 13:00:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582568 | 245006653 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006980 |  |  |  |  | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582568 | 245006653 | 0 | 07 Implementation Complete | Completed | Milestone | 245007096 |  |  |  |  | 01/01/2000 05:30:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582568 | 245006653 | act--02 Installation | 02 Installation | Completed | Activity | 245006750 | 06/07/2018 12:30:00 | 06/07/2018 16:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582568 | 245006653 | act--03 Integration | 03 Integration | Completed | Activity | 245006808 | 06/08/2018 12:30:00 | 06/08/2018 23:00:00 | 06/09/2018 11:30:00 | 06/09/2018 15:30:00
2582568 | 245006653 | act--04 SSV | 04 SSV | Completed | Activity | 245006859 | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582568 | 245006653 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006918 |  |  |  |  | 06/07/2018 06:30:00 | 06/07/2018 07:30:00 |  | 06/07/2018 08:30:00
2582569 | 245006657 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007030 |  |  |  |  | 06/09/2018 13:00:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582569 | 245006657 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006973 |  |  |  |  | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582569 | 245006657 | 0 | 07 Implementation Complete | Completed | Milestone | 245007086 |  |  |  |  | 01/01/2000 05:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582569 | 245006657 | act--02 Installation | 02 Installation | Completed | Activity | 245006757 | 06/06/2018 12:30:00 | 06/06/2018 16:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582569 | 245006657 | act--03 Integration | 03 Integration | Completed | Activity | 245006800 | 06/07/2018 12:30:00 | 06/07/2018 23:00:00 | 06/08/2018 11:30:00 | 06/08/2018 15:30:00
2582569 | 245006657 | act--04 SSV | 04 SSV | Completed | Activity | 245006861 | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582569 | 245006657 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006913 |  |  |  |  | 06/06/2018 06:30:00 | 06/06/2018 07:30:00 |  | 06/06/2018 08:30:00
2582570 | 245006660 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007063 |  |  |  |  | 06/08/2018 13:00:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582570 | 245006660 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007003 |  |  |  |  | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582570 | 245006660 | 0 | 07 Implementation Complete | Completed | Milestone | 245007122 |  |  |  |  | 01/01/2000 05:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582570 | 245006660 | act--02 Installation | 02 Installation | Completed | Activity | 245006751 | 06/05/2018 12:30:00 | 06/05/2018 16:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582570 | 245006660 | act--03 Integration | 03 Integration | Completed | Activity | 245006809 | 06/06/2018 12:30:00 | 06/06/2018 23:00:00 | 06/07/2018 11:30:00 | 06/07/2018 15:30:00
2582570 | 245006660 | act--04 SSV | 04 SSV | Completed | Activity | 245006868 | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582570 | 245006660 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006951 |  |  |  |  | 06/05/2018 06:30:00 | 06/05/2018 07:30:00 |  | 06/05/2018 08:30:00
2582571 | 245006658 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007054 |  |  |  |  | 06/12/2018 13:00:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582571 | 245006658 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007004 |  |  |  |  | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582571 | 245006658 | 0 | 07 Implementation Complete | Completed | Milestone | 245007102 |  |  |  |  | 01/01/2000 05:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582571 | 245006658 | act--02 Installation | 02 Installation | Completed | Activity | 245006753 | 06/09/2018 12:30:00 | 06/09/2018 16:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582571 | 245006658 | act--03 Integration | 03 Integration | Completed | Activity | 245006810 | 06/10/2018 12:30:00 | 06/10/2018 23:00:00 | 06/11/2018 11:30:00 | 06/11/2018 15:30:00
2582571 | 245006658 | act--04 SSV | 04 SSV | Completed | Activity | 245006873 | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582571 | 245006658 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006939 |  |  |  |  | 06/09/2018 06:30:00 | 06/09/2018 07:30:00 |  | 06/09/2018 08:30:00
2582572 | 245006656 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007068 |  |  |  |  | 06/08/2018 13:00:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582572 | 245006656 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007018 |  |  |  |  | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582572 | 245006656 | 0 | 07 Implementation Complete | Completed | Milestone | 245007121 |  |  |  |  | 01/01/2000 05:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582572 | 245006656 | act--02 Installation | 02 Installation | Completed | Activity | 245006761 | 06/05/2018 12:30:00 | 06/05/2018 16:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582572 | 245006656 | act--03 Integration | 03 Integration | Completed | Activity | 245006823 | 06/06/2018 12:30:00 | 06/06/2018 23:00:00 | 06/07/2018 11:30:00 | 06/07/2018 15:30:00
2582572 | 245006656 | act--04 SSV | 04 SSV | Completed | Activity | 245006877 | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582572 | 245006656 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006963 |  |  |  |  | 06/05/2018 06:30:00 | 06/05/2018 07:30:00 |  | 06/05/2018 08:30:00
2582573 | 245006662 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007094 |  |  |  |  | 06/09/2018 13:00:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582573 | 245006662 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007039 |  |  |  |  | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582573 | 245006662 | 0 | 07 Implementation Complete | Completed | Milestone | 245007147 |  |  |  |  | 01/01/2000 05:30:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582573 | 245006662 | act--02 Installation | 02 Installation | Completed | Activity | 245006755 | 06/06/2018 12:30:00 | 06/06/2018 16:00:00 | 06/07/2018 07:00:00 | 06/07/2018 15:30:00
2582573 | 245006662 | act--03 Integration | 03 Integration | Completed | Activity | 245006826 | 06/07/2018 12:30:00 | 06/07/2018 23:00:00 | 06/08/2018 11:30:00 | 06/08/2018 15:30:00
2582573 | 245006662 | act--04 SSV | 04 SSV | Completed | Activity | 245006888 | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582573 | 245006662 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006977 |  |  |  |  | 06/06/2018 06:30:00 | 06/06/2018 07:30:00 |  | 06/06/2018 08:30:00
2582574 | 245006661 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007056 |  |  |  |  | 06/12/2018 13:00:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582574 | 245006661 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006995 |  |  |  |  | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582574 | 245006661 | 0 | 07 Implementation Complete | Completed | Milestone | 245007115 |  |  |  |  | 01/01/2000 05:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582574 | 245006661 | act--02 Installation | 02 Installation | Completed | Activity | 245006760 | 06/09/2018 12:30:00 | 06/09/2018 16:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582574 | 245006661 | act--03 Integration | 03 Integration | Completed | Activity | 245006818 | 06/10/2018 12:30:00 | 06/10/2018 23:00:00 | 06/11/2018 11:30:00 | 06/11/2018 15:30:00
2582574 | 245006661 | act--04 SSV | 04 SSV | Completed | Activity | 245006872 | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582574 | 245006661 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006942 |  |  |  |  | 06/09/2018 06:30:00 | 06/09/2018 07:30:00 |  | 06/09/2018 08:30:00
2582575 | 245006664 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007084 |  |  |  |  | 06/11/2018 13:00:00 | 06/11/2018 15:00:00 |  | 06/11/2018 15:00:00
2582575 | 245006664 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007025 |  |  |  |  | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582575 | 245006664 | 0 | 07 Implementation Complete | Completed | Milestone | 245007140 |  |  |  |  | 01/01/2000 05:30:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582575 | 245006664 | act--02 Installation | 02 Installation | Completed | Activity | 245006759 | 06/08/2018 12:30:00 | 06/08/2018 16:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582575 | 245006664 | act--03 Integration | 03 Integration | Completed | Activity | 245006824 | 06/09/2018 12:30:00 | 06/09/2018 23:00:00 | 06/10/2018 11:30:00 | 06/10/2018 15:30:00
2582575 | 245006664 | act--04 SSV | 04 SSV | Completed | Activity | 245006886 | 06/11/2018 12:30:00 | 06/11/2018 15:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582575 | 245006664 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006972 |  |  |  |  | 06/08/2018 06:30:00 | 06/08/2018 07:30:00 |  | 06/08/2018 08:30:00
2582576 | 245006663 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007049 |  |  |  |  | 06/13/2018 13:00:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582576 | 245006663 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006989 |  |  |  |  | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582576 | 245006663 | 0 | 07 Implementation Complete | Completed | Milestone | 245007118 |  |  |  |  | 01/01/2000 05:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582576 | 245006663 | act--02 Installation | 02 Installation | Completed | Activity | 245006754 | 06/10/2018 12:30:00 | 06/10/2018 16:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582576 | 245006663 | act--03 Integration | 03 Integration | Completed | Activity | 245006811 | 06/11/2018 12:30:00 | 06/11/2018 23:00:00 | 06/12/2018 11:30:00 | 06/12/2018 15:30:00
2582576 | 245006663 | act--04 SSV | 04 SSV | Completed | Activity | 245006869 | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582576 | 245006663 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006923 |  |  |  |  | 06/10/2018 06:30:00 | 06/10/2018 07:30:00 |  | 06/10/2018 08:30:00
2582577 | 245006665 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007091 |  |  |  |  | 06/07/2018 13:00:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582577 | 245006665 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007035 |  |  |  |  | 06/09/2018 12:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582577 | 245006665 | 0 | 07 Implementation Complete | Completed | Milestone | 245007146 |  |  |  |  | 01/01/2000 05:30:00 | 06/09/2018 15:00:00 |  | 06/09/2018 15:00:00
2582577 | 245006665 | act--02 Installation | 02 Installation | Completed | Activity | 245006763 | 06/04/2018 12:30:00 | 06/04/2018 16:00:00 | 06/05/2018 07:00:00 | 06/05/2018 15:30:00
2582577 | 245006665 | act--03 Integration | 03 Integration | Completed | Activity | 245006829 | 06/05/2018 12:30:00 | 06/05/2018 23:00:00 | 06/06/2018 11:30:00 | 06/06/2018 15:30:00
2582577 | 245006665 | act--04 SSV | 04 SSV | Completed | Activity | 245006891 | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 | 06/08/2018 07:00:00 | 06/08/2018 15:30:00
2582577 | 245006665 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006982 |  |  |  |  | 06/04/2018 06:30:00 | 06/04/2018 07:30:00 |  | 06/04/2018 08:30:00
2582578 | 245006667 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007066 |  |  |  |  | 06/05/2018 13:00:00 | 06/05/2018 15:00:00 |  | 06/05/2018 15:00:00
2582578 | 245006667 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007006 |  |  |  |  | 06/07/2018 12:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582578 | 245006667 | 0 | 07 Implementation Complete | Completed | Milestone | 245007130 |  |  |  |  | 01/01/2000 05:30:00 | 06/07/2018 15:00:00 |  | 06/07/2018 15:00:00
2582578 | 245006667 | act--02 Installation | 02 Installation | Completed | Activity | 245006770 | 06/02/2018 12:30:00 | 06/02/2018 16:00:00 | 06/03/2018 07:00:00 | 06/03/2018 15:30:00
2582578 | 245006667 | act--03 Integration | 03 Integration | Completed | Activity | 245006827 | 06/03/2018 12:30:00 | 06/03/2018 23:00:00 | 06/04/2018 11:30:00 | 06/04/2018 15:30:00
2582578 | 245006667 | act--04 SSV | 04 SSV | Completed | Activity | 245006882 | 06/05/2018 12:30:00 | 06/05/2018 15:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582578 | 245006667 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006948 |  |  |  |  | 06/02/2018 06:30:00 | 06/02/2018 07:30:00 |  | 06/02/2018 08:30:00
2582579 | 245006672 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007076 |  |  |  |  | 06/20/2018 13:00:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582579 | 245006672 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007015 |  |  |  |  | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582579 | 245006672 | 0 | 07 Implementation Complete | Completed | Milestone | 245007127 |  |  |  |  | 01/01/2000 05:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582579 | 245006672 | act--02 Installation | 02 Installation | Completed | Activity | 245006768 | 06/17/2018 12:30:00 | 06/17/2018 16:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582579 | 245006672 | act--03 Integration | 03 Integration | Completed | Activity | 245006822 | 06/18/2018 12:30:00 | 06/18/2018 23:00:00 | 06/19/2018 11:30:00 | 06/19/2018 15:30:00
2582579 | 245006672 | act--04 SSV | 04 SSV | Completed | Activity | 245006876 | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582579 | 245006672 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006950 |  |  |  |  | 06/17/2018 06:30:00 | 06/17/2018 07:30:00 |  | 06/17/2018 08:30:00
2582580 | 245006671 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007046 |  |  |  |  | 06/12/2018 13:00:00 | 06/12/2018 15:00:00 |  | 06/12/2018 15:00:00
2582580 | 245006671 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006991 |  |  |  |  | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582580 | 245006671 | 0 | 07 Implementation Complete | Completed | Milestone | 245007105 |  |  |  |  | 01/01/2000 05:30:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582580 | 245006671 | act--02 Installation | 02 Installation | Completed | Activity | 245006756 | 06/09/2018 12:30:00 | 06/09/2018 16:00:00 | 06/10/2018 07:00:00 | 06/10/2018 15:30:00
2582580 | 245006671 | act--03 Integration | 03 Integration | Completed | Activity | 245006820 | 06/10/2018 12:30:00 | 06/10/2018 23:00:00 | 06/11/2018 11:30:00 | 06/11/2018 15:30:00
2582580 | 245006671 | act--04 SSV | 04 SSV | Completed | Activity | 245006883 | 06/12/2018 12:30:00 | 06/12/2018 15:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582580 | 245006671 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006937 |  |  |  |  | 06/09/2018 06:30:00 | 06/09/2018 07:30:00 |  | 06/09/2018 08:30:00
2582581 | 245006670 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007058 |  |  |  |  | 06/08/2018 13:00:00 | 06/08/2018 15:00:00 |  | 06/08/2018 15:00:00
2582581 | 245006670 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007000 |  |  |  |  | 06/10/2018 12:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582581 | 245006670 | 0 | 07 Implementation Complete | Completed | Milestone | 245007120 |  |  |  |  | 01/01/2000 05:30:00 | 06/10/2018 15:00:00 |  | 06/10/2018 15:00:00
2582581 | 245006670 | act--02 Installation | 02 Installation | Completed | Activity | 245006767 | 06/05/2018 12:30:00 | 06/05/2018 16:00:00 | 06/06/2018 07:00:00 | 06/06/2018 15:30:00
2582581 | 245006670 | act--03 Integration | 03 Integration | Completed | Activity | 245006816 | 06/06/2018 12:30:00 | 06/06/2018 23:00:00 | 06/07/2018 11:30:00 | 06/07/2018 15:30:00
2582581 | 245006670 | act--04 SSV | 04 SSV | Completed | Activity | 245006885 | 06/08/2018 12:30:00 | 06/08/2018 15:00:00 | 06/09/2018 07:00:00 | 06/09/2018 15:30:00
2582581 | 245006670 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006938 |  |  |  |  | 06/05/2018 06:30:00 | 06/05/2018 07:30:00 |  | 06/05/2018 08:30:00
2582582 | 245006678 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007048 |  |  |  |  | 06/18/2018 13:00:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582582 | 245006678 | 0 | 06 NDO IM Accept | Completed | Milestone | 245006998 |  |  |  |  | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582582 | 245006678 | 0 | 07 Implementation Complete | Completed | Milestone | 245007107 |  |  |  |  | 01/01/2000 05:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582582 | 245006678 | act--02 Installation | 02 Installation | Completed | Activity | 245006766 | 06/15/2018 12:30:00 | 06/15/2018 16:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582582 | 245006678 | act--03 Integration | 03 Integration | Completed | Activity | 245006814 | 06/16/2018 12:30:00 | 06/16/2018 23:00:00 | 06/17/2018 11:30:00 | 06/17/2018 15:30:00
2582582 | 245006678 | act--04 SSV | 04 SSV | Completed | Activity | 245006875 | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582582 | 245006678 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245006952 |  |  |  |  | 06/15/2018 06:30:00 | 06/15/2018 07:30:00 |  | 06/15/2018 08:30:00
2582583 | 245007283 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007684 |  |  |  |  | 06/13/2018 13:00:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582583 | 245007283 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007622 |  |  |  |  | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582583 | 245007283 | 0 | 07 Implementation Complete | Completed | Milestone | 245007742 |  |  |  |  | 01/01/2000 05:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582583 | 245007283 | act--02 Installation | 02 Installation | Completed | Activity | 245007378 | 06/10/2018 12:30:00 | 06/10/2018 16:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582583 | 245007283 | act--03 Integration | 03 Integration | Completed | Activity | 245007430 | 06/11/2018 12:30:00 | 06/11/2018 23:00:00 | 06/12/2018 11:30:00 | 06/12/2018 15:30:00
2582583 | 245007283 | act--04 SSV | 04 SSV | Completed | Activity | 245007495 | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582583 | 245007283 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007565 |  |  |  |  | 06/10/2018 06:30:00 | 06/10/2018 07:30:00 |  | 06/10/2018 08:30:00
2582584 | 245007285 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007639 |  |  |  |  | 06/23/2018 13:00:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582584 | 245007285 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007582 |  |  |  |  | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582584 | 245007285 | 0 | 07 Implementation Complete | Completed | Milestone | 245007698 |  |  |  |  | 01/01/2000 05:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582584 | 245007285 | act--02 Installation | 02 Installation | Completed | Activity | 245007380 | 06/20/2018 12:30:00 | 06/20/2018 16:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582584 | 245007285 | act--03 Integration | 03 Integration | Completed | Activity | 245007420 | 06/21/2018 12:30:00 | 06/21/2018 23:00:00 | 06/22/2018 11:30:00 | 06/22/2018 15:30:00
2582584 | 245007285 | act--04 SSV | 04 SSV | Completed | Activity | 245007475 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582584 | 245007285 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007537 |  |  |  |  | 06/20/2018 06:30:00 | 06/20/2018 07:30:00 |  | 06/20/2018 08:30:00
2582585 | 245007284 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007669 |  |  |  |  | 06/23/2018 13:00:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582585 | 245007284 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007609 |  |  |  |  | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582585 | 245007284 | 0 | 07 Implementation Complete | Completed | Milestone | 245007723 |  |  |  |  | 01/01/2000 05:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582585 | 245007284 | act--02 Installation | 02 Installation | Completed | Activity | 245007379 | 06/20/2018 12:30:00 | 06/20/2018 16:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582585 | 245007284 | act--03 Integration | 03 Integration | Completed | Activity | 245007427 | 06/21/2018 12:30:00 | 06/21/2018 23:00:00 | 06/22/2018 11:30:00 | 06/22/2018 15:30:00
2582585 | 245007284 | act--04 SSV | 04 SSV | Completed | Activity | 245007485 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582585 | 245007284 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007547 |  |  |  |  | 06/20/2018 06:30:00 | 06/20/2018 07:30:00 |  | 06/20/2018 08:30:00
2582586 | 245007286 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007677 |  |  |  |  | 06/20/2018 13:00:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582586 | 245007286 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007625 |  |  |  |  | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582586 | 245007286 | 0 | 07 Implementation Complete | Completed | Milestone | 245007731 |  |  |  |  | 01/01/2000 05:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582586 | 245007286 | act--02 Installation | 02 Installation | Completed | Activity | 245007392 | 06/17/2018 12:30:00 | 06/17/2018 16:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582586 | 245007286 | act--03 Integration | 03 Integration | Completed | Activity | 245007452 | 06/18/2018 12:30:00 | 06/18/2018 23:00:00 | 06/19/2018 11:30:00 | 06/19/2018 15:30:00
2582586 | 245007286 | act--04 SSV | 04 SSV | Completed | Activity | 245007507 | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582586 | 245007286 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007569 |  |  |  |  | 06/17/2018 06:30:00 | 06/17/2018 07:30:00 |  | 06/17/2018 08:30:00
2582587 | 245007287 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007657 |  |  |  |  | 06/16/2018 13:00:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582587 | 245007287 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007603 |  |  |  |  | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582587 | 245007287 | 0 | 07 Implementation Complete | Completed | Milestone | 245007717 |  |  |  |  | 01/01/2000 05:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582587 | 245007287 | act--02 Installation | 02 Installation | Completed | Activity | 245007381 | 06/13/2018 12:30:00 | 06/13/2018 16:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582587 | 245007287 | act--03 Integration | 03 Integration | Completed | Activity | 245007438 | 06/14/2018 12:30:00 | 06/14/2018 23:00:00 | 06/15/2018 11:30:00 | 06/15/2018 15:30:00
2582587 | 245007287 | act--04 SSV | 04 SSV | Completed | Activity | 245007482 | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582587 | 245007287 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007541 |  |  |  |  | 06/13/2018 06:30:00 | 06/13/2018 07:30:00 |  | 06/13/2018 08:30:00
2582588 | 245007289 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007673 |  |  |  |  | 06/14/2018 13:00:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582588 | 245007289 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007614 |  |  |  |  | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582588 | 245007289 | 0 | 07 Implementation Complete | Completed | Milestone | 245007726 |  |  |  |  | 01/01/2000 05:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582588 | 245007289 | act--02 Installation | 02 Installation | Completed | Activity | 245007388 | 06/11/2018 12:30:00 | 06/11/2018 16:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582588 | 245007289 | act--03 Integration | 03 Integration | Completed | Activity | 245007448 | 06/12/2018 12:30:00 | 06/12/2018 23:00:00 | 06/13/2018 11:30:00 | 06/13/2018 15:30:00
2582588 | 245007289 | act--04 SSV | 04 SSV | Completed | Activity | 245007505 | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582588 | 245007289 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007558 |  |  |  |  | 06/11/2018 06:30:00 | 06/11/2018 07:30:00 |  | 06/11/2018 08:30:00
2582589 | 245007288 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007645 |  |  |  |  | 06/20/2018 13:00:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582589 | 245007288 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007589 |  |  |  |  | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582589 | 245007288 | 0 | 07 Implementation Complete | Completed | Milestone | 245007701 |  |  |  |  | 01/01/2000 05:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582589 | 245007288 | act--02 Installation | 02 Installation | Completed | Activity | 245007382 | 06/17/2018 12:30:00 | 06/17/2018 16:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582589 | 245007288 | act--03 Integration | 03 Integration | Completed | Activity | 245007425 | 06/18/2018 12:30:00 | 06/18/2018 23:00:00 | 06/19/2018 11:30:00 | 06/19/2018 15:30:00
2582589 | 245007288 | act--04 SSV | 04 SSV | Completed | Activity | 245007478 | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582589 | 245007288 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007536 |  |  |  |  | 06/17/2018 06:30:00 | 06/17/2018 07:30:00 |  | 06/17/2018 08:30:00
2582590 | 245007291 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007668 |  |  |  |  | 06/16/2018 13:00:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582590 | 245007291 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007611 |  |  |  |  | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582590 | 245007291 | 0 | 07 Implementation Complete | Completed | Milestone | 245007730 |  |  |  |  | 01/01/2000 05:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582590 | 245007291 | act--02 Installation | 02 Installation | Completed | Activity | 245007383 | 06/13/2018 12:30:00 | 06/13/2018 16:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582590 | 245007291 | act--03 Integration | 03 Integration | Completed | Activity | 245007439 | 06/14/2018 12:30:00 | 06/14/2018 23:00:00 | 06/15/2018 11:30:00 | 06/15/2018 15:30:00
2582590 | 245007291 | act--04 SSV | 04 SSV | Completed | Activity | 245007491 | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582590 | 245007291 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007550 |  |  |  |  | 06/13/2018 06:30:00 | 06/13/2018 07:30:00 |  | 06/13/2018 08:30:00
2582591 | 245007293 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007707 |  |  |  |  | 06/19/2018 13:00:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582591 | 245007293 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007651 |  |  |  |  | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582591 | 245007293 | 0 | 07 Implementation Complete | Completed | Milestone | 245007761 |  |  |  |  | 01/01/2000 05:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582591 | 245007293 | act--02 Installation | 02 Installation | Completed | Activity | 245007386 | 06/16/2018 12:30:00 | 06/16/2018 16:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582591 | 245007293 | act--03 Integration | 03 Integration | Completed | Activity | 245007441 | 06/17/2018 12:30:00 | 06/17/2018 23:00:00 | 06/18/2018 11:30:00 | 06/18/2018 15:30:00
2582591 | 245007293 | act--04 SSV | 04 SSV | Completed | Activity | 245007503 | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582591 | 245007293 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007588 |  |  |  |  | 06/16/2018 06:30:00 | 06/16/2018 07:30:00 |  | 06/16/2018 08:30:00
2582592 | 245007290 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007714 |  |  |  |  | 06/14/2018 13:00:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582592 | 245007290 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007655 |  |  |  |  | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582592 | 245007290 | 0 | 07 Implementation Complete | Completed | Milestone | 245007773 |  |  |  |  | 01/01/2000 05:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582592 | 245007290 | act--02 Installation | 02 Installation | Completed | Activity | 245007395 | 06/11/2018 12:30:00 | 06/11/2018 16:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582592 | 245007290 | act--03 Integration | 03 Integration | Completed | Activity | 245007454 | 06/12/2018 12:30:00 | 06/12/2018 23:00:00 | 06/13/2018 11:30:00 | 06/13/2018 15:30:00
2582592 | 245007290 | act--04 SSV | 04 SSV | Completed | Activity | 245007508 | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582592 | 245007290 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007595 |  |  |  |  | 06/11/2018 06:30:00 | 06/11/2018 07:30:00 |  | 06/11/2018 08:30:00
2582593 | 245007295 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007696 |  |  |  |  | 06/14/2018 13:00:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582593 | 245007295 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007633 |  |  |  |  | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582593 | 245007295 | 0 | 07 Implementation Complete | Completed | Milestone | 245007755 |  |  |  |  | 01/01/2000 05:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582593 | 245007295 | act--02 Installation | 02 Installation | Completed | Activity | 245007390 | 06/11/2018 12:30:00 | 06/11/2018 16:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582593 | 245007295 | act--03 Integration | 03 Integration | Completed | Activity | 245007442 | 06/12/2018 12:30:00 | 06/12/2018 23:00:00 | 06/13/2018 11:30:00 | 06/13/2018 15:30:00
2582593 | 245007295 | act--04 SSV | 04 SSV | Completed | Activity | 245007509 | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582593 | 245007295 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007573 |  |  |  |  | 06/11/2018 06:30:00 | 06/11/2018 07:30:00 |  | 06/11/2018 08:30:00
2582594 | 245007296 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007733 |  |  |  |  | 06/22/2018 13:00:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582594 | 245007296 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007670 |  |  |  |  | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582594 | 245007296 | 0 | 07 Implementation Complete | Completed | Milestone | 245007785 |  |  |  |  | 01/01/2000 05:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582594 | 245007296 | act--02 Installation | 02 Installation | Completed | Activity | 245007393 | 06/19/2018 12:30:00 | 06/19/2018 16:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582594 | 245007296 | act--03 Integration | 03 Integration | Completed | Activity | 245007451 | 06/20/2018 12:30:00 | 06/20/2018 23:00:00 | 06/21/2018 11:30:00 | 06/21/2018 15:30:00
2582594 | 245007296 | act--04 SSV | 04 SSV | Completed | Activity | 245007513 | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582594 | 245007296 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007613 |  |  |  |  | 06/19/2018 06:30:00 | 06/19/2018 07:30:00 |  | 06/19/2018 08:30:00
2582595 | 245007294 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007702 |  |  |  |  | 06/17/2018 13:00:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582595 | 245007294 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007640 |  |  |  |  | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582595 | 245007294 | 0 | 07 Implementation Complete | Completed | Milestone | 245007754 |  |  |  |  | 01/01/2000 05:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582595 | 245007294 | act--02 Installation | 02 Installation | Completed | Activity | 245007384 | 06/14/2018 12:30:00 | 06/14/2018 16:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582595 | 245007294 | act--03 Integration | 03 Integration | Completed | Activity | 245007443 | 06/15/2018 12:30:00 | 06/15/2018 23:00:00 | 06/16/2018 11:30:00 | 06/16/2018 15:30:00
2582595 | 245007294 | act--04 SSV | 04 SSV | Completed | Activity | 245007496 | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582595 | 245007294 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007577 |  |  |  |  | 06/14/2018 06:30:00 | 06/14/2018 07:30:00 |  | 06/14/2018 08:30:00
2582596 | 245007299 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007679 |  |  |  |  | 06/18/2018 13:00:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582596 | 245007299 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007618 |  |  |  |  | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582596 | 245007299 | 0 | 07 Implementation Complete | Completed | Milestone | 245007728 |  |  |  |  | 01/01/2000 05:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582596 | 245007299 | act--02 Installation | 02 Installation | Completed | Activity | 245007385 | 06/15/2018 12:30:00 | 06/15/2018 16:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582596 | 245007299 | act--03 Integration | 03 Integration | Completed | Activity | 245007429 | 06/16/2018 12:30:00 | 06/16/2018 23:00:00 | 06/17/2018 11:30:00 | 06/17/2018 15:30:00
2582596 | 245007299 | act--04 SSV | 04 SSV | Completed | Activity | 245007498 | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582596 | 245007299 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007564 |  |  |  |  | 06/15/2018 06:30:00 | 06/15/2018 07:30:00 |  | 06/15/2018 08:30:00
2582597 | 245007298 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007721 |  |  |  |  | 06/15/2018 13:00:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582597 | 245007298 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007667 |  |  |  |  | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582597 | 245007298 | 0 | 07 Implementation Complete | Completed | Milestone | 245007777 |  |  |  |  | 01/01/2000 05:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582597 | 245007298 | act--02 Installation | 02 Installation | Completed | Activity | 245007394 | 06/12/2018 12:30:00 | 06/12/2018 16:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582597 | 245007298 | act--03 Integration | 03 Integration | Completed | Activity | 245007463 | 06/13/2018 12:30:00 | 06/13/2018 23:00:00 | 06/14/2018 11:30:00 | 06/14/2018 15:30:00
2582597 | 245007298 | act--04 SSV | 04 SSV | Completed | Activity | 245007518 | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582597 | 245007298 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007610 |  |  |  |  | 06/12/2018 06:30:00 | 06/12/2018 07:30:00 |  | 06/12/2018 08:30:00
2582598 | 245007297 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007715 |  |  |  |  | 06/22/2018 13:00:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582598 | 245007297 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007662 |  |  |  |  | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582598 | 245007297 | 0 | 07 Implementation Complete | Completed | Milestone | 245007769 |  |  |  |  | 01/01/2000 05:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582598 | 245007297 | act--02 Installation | 02 Installation | Completed | Activity | 245007397 | 06/19/2018 12:30:00 | 06/19/2018 16:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582598 | 245007297 | act--03 Integration | 03 Integration | Completed | Activity | 245007459 | 06/20/2018 12:30:00 | 06/20/2018 23:00:00 | 06/21/2018 11:30:00 | 06/21/2018 15:30:00
2582598 | 245007297 | act--04 SSV | 04 SSV | Completed | Activity | 245007514 | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582598 | 245007297 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007608 |  |  |  |  | 06/19/2018 06:30:00 | 06/19/2018 07:30:00 |  | 06/19/2018 08:30:00
2582599 | 245007302 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007687 |  |  |  |  | 06/16/2018 13:00:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582599 | 245007302 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007634 |  |  |  |  | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582599 | 245007302 | 0 | 07 Implementation Complete | Completed | Milestone | 245007745 |  |  |  |  | 01/01/2000 05:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582599 | 245007302 | act--02 Installation | 02 Installation | Completed | Activity | 245007398 | 06/13/2018 12:30:00 | 06/13/2018 16:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582599 | 245007302 | act--03 Integration | 03 Integration | Completed | Activity | 245007445 | 06/14/2018 12:30:00 | 06/14/2018 23:00:00 | 06/15/2018 11:30:00 | 06/15/2018 15:30:00
2582599 | 245007302 | act--04 SSV | 04 SSV | Completed | Activity | 245007506 | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582599 | 245007302 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007576 |  |  |  |  | 06/13/2018 06:30:00 | 06/13/2018 07:30:00 |  | 06/13/2018 08:30:00
2582600 | 245007304 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007660 |  |  |  |  | 06/15/2018 13:00:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582600 | 245007304 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007602 |  |  |  |  | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582600 | 245007304 | 0 | 07 Implementation Complete | Completed | Milestone | 245007716 |  |  |  |  | 01/01/2000 05:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582600 | 245007304 | act--02 Installation | 02 Installation | Completed | Activity | 245007396 | 06/12/2018 12:30:00 | 06/12/2018 16:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582600 | 245007304 | act--03 Integration | 03 Integration | Completed | Activity | 245007447 | 06/13/2018 12:30:00 | 06/13/2018 23:00:00 | 06/14/2018 11:30:00 | 06/14/2018 15:30:00
2582600 | 245007304 | act--04 SSV | 04 SSV | Completed | Activity | 245007492 | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582600 | 245007304 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007556 |  |  |  |  | 06/12/2018 06:30:00 | 06/12/2018 07:30:00 |  | 06/12/2018 08:30:00
2582601 | 245007307 | 0 | 05 NRO IM Accept | Completed | Milestone | 245007711 |  |  |  |  | 06/15/2018 13:00:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582601 | 245007307 | 0 | 06 NDO IM Accept | Completed | Milestone | 245007656 |  |  |  |  | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582601 | 245007307 | 0 | 07 Implementation Complete | Completed | Milestone | 245007762 |  |  |  |  | 01/01/2000 05:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582601 | 245007307 | act--02 Installation | 02 Installation | Completed | Activity | 245007399 | 06/12/2018 12:30:00 | 06/12/2018 16:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582601 | 245007307 | act--03 Integration | 03 Integration | Completed | Activity | 245007456 | 06/13/2018 12:30:00 | 06/13/2018 23:00:00 | 06/14/2018 11:30:00 | 06/14/2018 15:30:00
2582601 | 245007307 | act--04 SSV | 04 SSV | Completed | Activity | 245007512 | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582601 | 245007307 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245007597 |  |  |  |  | 06/12/2018 06:30:00 | 06/12/2018 07:30:00 |  | 06/12/2018 08:30:00
2582602 | 245007915 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008333 |  |  |  |  | 06/16/2018 13:00:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582602 | 245007915 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008272 |  |  |  |  | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582602 | 245007915 | 0 | 07 Implementation Complete | Completed | Milestone | 245008392 |  |  |  |  | 01/01/2000 05:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582602 | 245007915 | act--02 Installation | 02 Installation | Completed | Activity | 245008016 | 06/13/2018 12:30:00 | 06/13/2018 16:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582602 | 245007915 | act--03 Integration | 03 Integration | Completed | Activity | 245008074 | 06/14/2018 12:30:00 | 06/14/2018 23:00:00 | 06/15/2018 11:30:00 | 06/15/2018 15:30:00
2582602 | 245007915 | act--04 SSV | 04 SSV | Completed | Activity | 245008136 | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582602 | 245007915 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008209 |  |  |  |  | 06/13/2018 06:30:00 | 06/13/2018 07:30:00 |  | 06/13/2018 08:30:00
2582603 | 245007917 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008289 |  |  |  |  | 06/15/2018 13:00:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582603 | 245007917 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008235 |  |  |  |  | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582603 | 245007917 | 0 | 07 Implementation Complete | Completed | Milestone | 245008351 |  |  |  |  | 01/01/2000 05:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582603 | 245007917 | act--02 Installation | 02 Installation | Completed | Activity | 245008018 | 06/12/2018 12:30:00 | 06/12/2018 16:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582603 | 245007917 | act--03 Integration | 03 Integration | Completed | Activity | 245008065 | 06/13/2018 12:30:00 | 06/13/2018 23:00:00 | 06/14/2018 11:30:00 | 06/14/2018 15:30:00
2582603 | 245007917 | act--04 SSV | 04 SSV | Completed | Activity | 245008120 | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582603 | 245007917 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008178 |  |  |  |  | 06/12/2018 06:30:00 | 06/12/2018 07:30:00 |  | 06/12/2018 08:30:00
2582604 | 245007916 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008318 |  |  |  |  | 06/17/2018 13:00:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582604 | 245007916 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008259 |  |  |  |  | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582604 | 245007916 | 0 | 07 Implementation Complete | Completed | Milestone | 245008376 |  |  |  |  | 01/01/2000 05:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582604 | 245007916 | act--02 Installation | 02 Installation | Completed | Activity | 245008020 | 06/14/2018 12:30:00 | 06/14/2018 16:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582604 | 245007916 | act--03 Integration | 03 Integration | Completed | Activity | 245008078 | 06/15/2018 12:30:00 | 06/15/2018 23:00:00 | 06/16/2018 11:30:00 | 06/16/2018 15:30:00
2582604 | 245007916 | act--04 SSV | 04 SSV | Completed | Activity | 245008128 | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582604 | 245007916 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008195 |  |  |  |  | 06/14/2018 06:30:00 | 06/14/2018 07:30:00 |  | 06/14/2018 08:30:00
2582605 | 245007920 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008312 |  |  |  |  | 06/17/2018 13:00:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582605 | 245007920 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008257 |  |  |  |  | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582605 | 245007920 | 0 | 07 Implementation Complete | Completed | Milestone | 245008370 |  |  |  |  | 01/01/2000 05:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582605 | 245007920 | act--02 Installation | 02 Installation | Completed | Activity | 245008023 | 06/14/2018 12:30:00 | 06/14/2018 16:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582605 | 245007920 | act--03 Integration | 03 Integration | Completed | Activity | 245008081 | 06/15/2018 12:30:00 | 06/15/2018 23:00:00 | 06/16/2018 11:30:00 | 06/16/2018 15:30:00
2582605 | 245007920 | act--04 SSV | 04 SSV | Completed | Activity | 245008130 | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582605 | 245007920 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008192 |  |  |  |  | 06/14/2018 06:30:00 | 06/14/2018 07:30:00 |  | 06/14/2018 08:30:00
2582606 | 245007918 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008357 |  |  |  |  | 06/17/2018 13:00:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582606 | 245007918 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008300 |  |  |  |  | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582606 | 245007918 | 0 | 07 Implementation Complete | Completed | Milestone | 245008414 |  |  |  |  | 01/01/2000 05:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582606 | 245007918 | act--02 Installation | 02 Installation | Completed | Activity | 245008026 | 06/14/2018 12:30:00 | 06/14/2018 16:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582606 | 245007918 | act--03 Integration | 03 Integration | Completed | Activity | 245008090 | 06/15/2018 12:30:00 | 06/15/2018 23:00:00 | 06/16/2018 11:30:00 | 06/16/2018 15:30:00
2582606 | 245007918 | act--04 SSV | 04 SSV | Completed | Activity | 245008143 | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582606 | 245007918 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008237 |  |  |  |  | 06/14/2018 06:30:00 | 06/14/2018 07:30:00 |  | 06/14/2018 08:30:00
2582607 | 245007919 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008328 |  |  |  |  | 06/18/2018 13:00:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582607 | 245007919 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008265 |  |  |  |  | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582607 | 245007919 | 0 | 07 Implementation Complete | Completed | Milestone | 245008389 |  |  |  |  | 01/01/2000 05:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582607 | 245007919 | act--02 Installation | 02 Installation | Completed | Activity | 245008017 | 06/15/2018 12:30:00 | 06/15/2018 16:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582607 | 245007919 | act--03 Integration | 03 Integration | Completed | Activity | 245008082 | 06/16/2018 12:30:00 | 06/16/2018 23:00:00 | 06/17/2018 11:30:00 | 06/17/2018 15:30:00
2582607 | 245007919 | act--04 SSV | 04 SSV | Completed | Activity | 245008153 | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582607 | 245007919 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008204 |  |  |  |  | 06/15/2018 06:30:00 | 06/15/2018 07:30:00 |  | 06/15/2018 08:30:00
2582608 | 245007924 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008309 |  |  |  |  | 06/21/2018 13:00:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582608 | 245007924 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008252 |  |  |  |  | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582608 | 245007924 | 0 | 07 Implementation Complete | Completed | Milestone | 245008367 |  |  |  |  | 01/01/2000 05:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582608 | 245007924 | act--02 Installation | 02 Installation | Completed | Activity | 245008021 | 06/18/2018 12:30:00 | 06/18/2018 16:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582608 | 245007924 | act--03 Integration | 03 Integration | Completed | Activity | 245008084 | 06/19/2018 12:30:00 | 06/19/2018 23:00:00 | 06/20/2018 11:30:00 | 06/20/2018 15:30:00
2582608 | 245007924 | act--04 SSV | 04 SSV | Completed | Activity | 245008138 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582608 | 245007924 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008194 |  |  |  |  | 06/18/2018 06:30:00 | 06/18/2018 07:30:00 |  | 06/18/2018 08:30:00
2582609 | 245007922 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008336 |  |  |  |  | 06/19/2018 13:00:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582609 | 245007922 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008281 |  |  |  |  | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582609 | 245007922 | 0 | 07 Implementation Complete | Completed | Milestone | 245008397 |  |  |  |  | 01/01/2000 05:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582609 | 245007922 | act--02 Installation | 02 Installation | Completed | Activity | 245008025 | 06/16/2018 12:30:00 | 06/16/2018 16:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582609 | 245007922 | act--03 Integration | 03 Integration | Completed | Activity | 245008096 | 06/17/2018 12:30:00 | 06/17/2018 23:00:00 | 06/18/2018 11:30:00 | 06/18/2018 15:30:00
2582609 | 245007922 | act--04 SSV | 04 SSV | Completed | Activity | 245008156 | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582609 | 245007922 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008226 |  |  |  |  | 06/16/2018 06:30:00 | 06/16/2018 07:30:00 |  | 06/16/2018 08:30:00
2582610 | 245007926 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008322 |  |  |  |  | 06/22/2018 13:00:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582610 | 245007926 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008269 |  |  |  |  | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582610 | 245007926 | 0 | 07 Implementation Complete | Completed | Milestone | 245008384 |  |  |  |  | 01/01/2000 05:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582610 | 245007926 | act--02 Installation | 02 Installation | Completed | Activity | 245008024 | 06/19/2018 12:30:00 | 06/19/2018 16:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582610 | 245007926 | act--03 Integration | 03 Integration | Completed | Activity | 245008089 | 06/20/2018 12:30:00 | 06/20/2018 23:00:00 | 06/21/2018 11:30:00 | 06/21/2018 15:30:00
2582610 | 245007926 | act--04 SSV | 04 SSV | Completed | Activity | 245008152 | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582610 | 245007926 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008217 |  |  |  |  | 06/19/2018 06:30:00 | 06/19/2018 07:30:00 |  | 06/19/2018 08:30:00
2582611 | 245007923 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008369 |  |  |  |  | 06/21/2018 13:00:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582611 | 245007923 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008310 |  |  |  |  | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582611 | 245007923 | 0 | 07 Implementation Complete | Completed | Milestone | 245008419 |  |  |  |  | 01/01/2000 05:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582611 | 245007923 | act--02 Installation | 02 Installation | Completed | Activity | 245008037 | 06/18/2018 12:30:00 | 06/18/2018 16:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582611 | 245007923 | act--03 Integration | 03 Integration | Completed | Activity | 245008091 | 06/19/2018 12:30:00 | 06/19/2018 23:00:00 | 06/20/2018 11:30:00 | 06/20/2018 15:30:00
2582611 | 245007923 | act--04 SSV | 04 SSV | Completed | Activity | 245008158 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582611 | 245007923 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008249 |  |  |  |  | 06/18/2018 06:30:00 | 06/18/2018 07:30:00 |  | 06/18/2018 08:30:00
2582612 | 245007928 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008360 |  |  |  |  | 06/15/2018 13:00:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582612 | 245007928 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008304 |  |  |  |  | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582612 | 245007928 | 0 | 07 Implementation Complete | Completed | Milestone | 245008413 |  |  |  |  | 01/01/2000 05:30:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582612 | 245007928 | act--02 Installation | 02 Installation | Completed | Activity | 245008027 | 06/12/2018 12:30:00 | 06/12/2018 16:00:00 | 06/13/2018 07:00:00 | 06/13/2018 15:30:00
2582612 | 245007928 | act--03 Integration | 03 Integration | Completed | Activity | 245008098 | 06/13/2018 12:30:00 | 06/13/2018 23:00:00 | 06/14/2018 11:30:00 | 06/14/2018 15:30:00
2582612 | 245007928 | act--04 SSV | 04 SSV | Completed | Activity | 245008161 | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582612 | 245007928 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008250 |  |  |  |  | 06/12/2018 06:30:00 | 06/12/2018 07:30:00 |  | 06/12/2018 08:30:00
2582613 | 245007925 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008325 |  |  |  |  | 06/21/2018 13:00:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582613 | 245007925 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008277 |  |  |  |  | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582613 | 245007925 | 0 | 07 Implementation Complete | Completed | Milestone | 245008377 |  |  |  |  | 01/01/2000 05:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582613 | 245007925 | act--02 Installation | 02 Installation | Completed | Activity | 245008034 | 06/18/2018 12:30:00 | 06/18/2018 16:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582613 | 245007925 | act--03 Integration | 03 Integration | Completed | Activity | 245008097 | 06/19/2018 12:30:00 | 06/19/2018 23:00:00 | 06/20/2018 11:30:00 | 06/20/2018 15:30:00
2582613 | 245007925 | act--04 SSV | 04 SSV | Completed | Activity | 245008157 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582613 | 245007925 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008232 |  |  |  |  | 06/18/2018 06:30:00 | 06/18/2018 07:30:00 |  | 06/18/2018 08:30:00
2582614 | 245007929 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008338 |  |  |  |  | 06/20/2018 13:00:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582614 | 245007929 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008274 |  |  |  |  | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582614 | 245007929 | 0 | 07 Implementation Complete | Completed | Milestone | 245008394 |  |  |  |  | 01/01/2000 05:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582614 | 245007929 | act--02 Installation | 02 Installation | Completed | Activity | 245008031 | 06/17/2018 12:30:00 | 06/17/2018 16:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582614 | 245007929 | act--03 Integration | 03 Integration | Completed | Activity | 245008092 | 06/18/2018 12:30:00 | 06/18/2018 23:00:00 | 06/19/2018 11:30:00 | 06/19/2018 15:30:00
2582614 | 245007929 | act--04 SSV | 04 SSV | Completed | Activity | 245008146 | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582614 | 245007929 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008210 |  |  |  |  | 06/17/2018 06:30:00 | 06/17/2018 07:30:00 |  | 06/17/2018 08:30:00
2582615 | 245007921 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008324 |  |  |  |  | 06/21/2018 13:00:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582615 | 245007921 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008267 |  |  |  |  | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582615 | 245007921 | 0 | 07 Implementation Complete | Completed | Milestone | 245008387 |  |  |  |  | 01/01/2000 05:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582615 | 245007921 | act--02 Installation | 02 Installation | Completed | Activity | 245008032 | 06/18/2018 12:30:00 | 06/18/2018 16:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582615 | 245007921 | act--03 Integration | 03 Integration | Completed | Activity | 245008093 | 06/19/2018 12:30:00 | 06/19/2018 23:00:00 | 06/20/2018 11:30:00 | 06/20/2018 15:30:00
2582615 | 245007921 | act--04 SSV | 04 SSV | Completed | Activity | 245008151 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582615 | 245007921 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008203 |  |  |  |  | 06/18/2018 06:30:00 | 06/18/2018 07:30:00 |  | 06/18/2018 08:30:00
2582616 | 245007932 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008362 |  |  |  |  | 06/21/2018 13:00:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582616 | 245007932 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008306 |  |  |  |  | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582616 | 245007932 | 0 | 07 Implementation Complete | Completed | Milestone | 245008417 |  |  |  |  | 01/01/2000 05:30:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582616 | 245007932 | act--02 Installation | 02 Installation | Completed | Activity | 245008038 | 06/18/2018 12:30:00 | 06/18/2018 16:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582616 | 245007932 | act--03 Integration | 03 Integration | Completed | Activity | 245008104 | 06/19/2018 12:30:00 | 06/19/2018 23:00:00 | 06/20/2018 11:30:00 | 06/20/2018 15:30:00
2582616 | 245007932 | act--04 SSV | 04 SSV | Completed | Activity | 245008162 | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582616 | 245007932 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008245 |  |  |  |  | 06/18/2018 06:30:00 | 06/18/2018 07:30:00 |  | 06/18/2018 08:30:00
2582617 | 245007930 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008343 |  |  |  |  | 06/26/2018 13:00:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582617 | 245007930 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008280 |  |  |  |  | 06/28/2018 12:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582617 | 245007930 | 0 | 07 Implementation Complete | Completed | Milestone | 245008383 |  |  |  |  | 01/01/2000 05:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582617 | 245007930 | act--02 Installation | 02 Installation | Completed | Activity | 245008028 | 06/23/2018 12:30:00 | 06/23/2018 16:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582617 | 245007930 | act--03 Integration | 03 Integration | Completed | Activity | 245008088 | 06/24/2018 12:30:00 | 06/24/2018 23:00:00 | 06/25/2018 11:30:00 | 06/25/2018 15:30:00
2582617 | 245007930 | act--04 SSV | 04 SSV | Completed | Activity | 245008150 | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 | 06/27/2018 07:00:00 | 06/27/2018 15:30:00
2582617 | 245007930 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008221 |  |  |  |  | 06/23/2018 06:30:00 | 06/23/2018 07:30:00 |  | 06/23/2018 08:30:00
2582618 | 245007931 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008303 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582618 | 245007931 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008251 |  |  |  |  | 06/27/2018 12:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582618 | 245007931 | 0 | 07 Implementation Complete | Completed | Milestone | 245008361 |  |  |  |  | 01/01/2000 05:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582618 | 245007931 | act--02 Installation | 02 Installation | Completed | Activity | 245008033 | 06/22/2018 12:30:00 | 06/22/2018 16:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582618 | 245007931 | act--03 Integration | 03 Integration | Completed | Activity | 245008095 | 06/23/2018 12:30:00 | 06/23/2018 23:00:00 | 06/24/2018 11:30:00 | 06/24/2018 15:30:00
2582618 | 245007931 | act--04 SSV | 04 SSV | Completed | Activity | 245008137 | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 | 06/26/2018 07:00:00 | 06/26/2018 15:30:00
2582618 | 245007931 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008197 |  |  |  |  | 06/22/2018 06:30:00 | 06/22/2018 07:30:00 |  | 06/22/2018 08:30:00
2582619 | 245007937 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008346 |  |  |  |  | 06/26/2018 13:00:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582619 | 245007937 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008278 |  |  |  |  | 06/28/2018 12:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582619 | 245007937 | 0 | 07 Implementation Complete | Completed | Milestone | 245008408 |  |  |  |  | 01/01/2000 05:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582619 | 245007937 | act--02 Installation | 02 Installation | Completed | Activity | 245008039 | 06/23/2018 12:30:00 | 06/23/2018 16:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582619 | 245007937 | act--03 Integration | 03 Integration | Completed | Activity | 245008101 | 06/24/2018 12:30:00 | 06/24/2018 23:00:00 | 06/25/2018 11:30:00 | 06/25/2018 15:30:00
2582619 | 245007937 | act--04 SSV | 04 SSV | Completed | Activity | 245008148 | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 | 06/27/2018 07:00:00 | 06/27/2018 15:30:00
2582619 | 245007937 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008216 |  |  |  |  | 06/23/2018 06:30:00 | 06/23/2018 07:30:00 |  | 06/23/2018 08:30:00
2582620 | 245007938 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008330 |  |  |  |  | 06/22/2018 13:00:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582620 | 245007938 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008273 |  |  |  |  | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582620 | 245007938 | 0 | 07 Implementation Complete | Completed | Milestone | 245008379 |  |  |  |  | 01/01/2000 05:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582620 | 245007938 | act--02 Installation | 02 Installation | Completed | Activity | 245008040 | 06/19/2018 12:30:00 | 06/19/2018 16:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582620 | 245007938 | act--03 Integration | 03 Integration | Completed | Activity | 245008094 | 06/20/2018 12:30:00 | 06/20/2018 23:00:00 | 06/21/2018 11:30:00 | 06/21/2018 15:30:00
2582620 | 245007938 | act--04 SSV | 04 SSV | Completed | Activity | 245008147 | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582620 | 245007938 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008208 |  |  |  |  | 06/19/2018 06:30:00 | 06/19/2018 07:30:00 |  | 06/19/2018 08:30:00
2582621 | 245008559 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008962 |  |  |  |  | 06/24/2018 13:00:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582621 | 245008559 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008908 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582621 | 245008559 | 0 | 07 Implementation Complete | Completed | Milestone | 245009019 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582621 | 245008559 | act--02 Installation | 02 Installation | Completed | Activity | 245008657 | 06/21/2018 12:30:00 | 06/21/2018 16:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582621 | 245008559 | act--03 Integration | 03 Integration | Completed | Activity | 245008725 | 06/22/2018 12:30:00 | 06/22/2018 23:00:00 | 06/23/2018 11:30:00 | 06/23/2018 15:30:00
2582621 | 245008559 | act--04 SSV | 04 SSV | Completed | Activity | 245008778 | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 | 06/25/2018 07:00:00 | 06/25/2018 15:30:00
2582621 | 245008559 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008854 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582622 | 245008562 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008941 |  |  |  |  | 06/23/2018 13:00:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582622 | 245008562 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008884 |  |  |  |  | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582622 | 245008562 | 0 | 07 Implementation Complete | Completed | Milestone | 245009003 |  |  |  |  | 01/01/2000 05:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582622 | 245008562 | act--02 Installation | 02 Installation | Completed | Activity | 245008654 | 06/20/2018 12:30:00 | 06/20/2018 16:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582622 | 245008562 | act--03 Integration | 03 Integration | Completed | Activity | 245008694 | 06/21/2018 12:30:00 | 06/21/2018 23:00:00 | 06/22/2018 11:30:00 | 06/22/2018 15:30:00
2582622 | 245008562 | act--04 SSV | 04 SSV | Completed | Activity | 245008757 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582622 | 245008562 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008819 |  |  |  |  | 06/20/2018 06:30:00 | 06/20/2018 07:30:00 |  | 06/20/2018 08:30:00
2582623 | 245008560 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008949 |  |  |  |  | 06/24/2018 13:00:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582623 | 245008560 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008899 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582623 | 245008560 | 0 | 07 Implementation Complete | Completed | Milestone | 245008997 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582623 | 245008560 | act--02 Installation | 02 Installation | Completed | Activity | 245008656 | 06/21/2018 12:30:00 | 06/21/2018 16:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582623 | 245008560 | act--03 Integration | 03 Integration | Completed | Activity | 245008711 | 06/22/2018 12:30:00 | 06/22/2018 23:00:00 | 06/23/2018 11:30:00 | 06/23/2018 15:30:00
2582623 | 245008560 | act--04 SSV | 04 SSV | Completed | Activity | 245008772 | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 | 06/25/2018 07:00:00 | 06/25/2018 15:30:00
2582623 | 245008560 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008830 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582624 | 245008561 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008948 |  |  |  |  | 06/14/2018 13:00:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582624 | 245008561 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008896 |  |  |  |  | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582624 | 245008561 | 0 | 07 Implementation Complete | Completed | Milestone | 245009002 |  |  |  |  | 01/01/2000 05:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582624 | 245008561 | act--02 Installation | 02 Installation | Completed | Activity | 245008655 | 06/11/2018 12:30:00 | 06/11/2018 16:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582624 | 245008561 | act--03 Integration | 03 Integration | Completed | Activity | 245008699 | 06/12/2018 12:30:00 | 06/12/2018 23:00:00 | 06/13/2018 11:30:00 | 06/13/2018 15:30:00
2582624 | 245008561 | act--04 SSV | 04 SSV | Completed | Activity | 245008767 | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582624 | 245008561 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008837 |  |  |  |  | 06/11/2018 06:30:00 | 06/11/2018 07:30:00 |  | 06/11/2018 08:30:00
2582625 | 245008563 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008943 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582625 | 245008563 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008886 |  |  |  |  | 06/27/2018 12:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582625 | 245008563 | 0 | 07 Implementation Complete | Completed | Milestone | 245009008 |  |  |  |  | 01/01/2000 05:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582625 | 245008563 | act--02 Installation | 02 Installation | Completed | Activity | 245008658 | 06/22/2018 12:30:00 | 06/22/2018 16:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582625 | 245008563 | act--03 Integration | 03 Integration | Completed | Activity | 245008714 | 06/23/2018 12:30:00 | 06/23/2018 23:00:00 | 06/24/2018 11:30:00 | 06/24/2018 15:30:00
2582625 | 245008563 | act--04 SSV | 04 SSV | Completed | Activity | 245008768 | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 | 06/26/2018 07:00:00 | 06/26/2018 15:30:00
2582625 | 245008563 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008829 |  |  |  |  | 06/22/2018 06:30:00 | 06/22/2018 07:30:00 |  | 06/22/2018 08:30:00
2582626 | 245008564 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008971 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582626 | 245008564 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008914 |  |  |  |  | 06/27/2018 12:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582626 | 245008564 | 0 | 07 Implementation Complete | Completed | Milestone | 245009023 |  |  |  |  | 01/01/2000 05:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582626 | 245008564 | act--02 Installation | 02 Installation | Completed | Activity | 245008660 | 06/22/2018 12:30:00 | 06/22/2018 16:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582626 | 245008564 | act--03 Integration | 03 Integration | Completed | Activity | 245008717 | 06/23/2018 12:30:00 | 06/23/2018 23:00:00 | 06/24/2018 11:30:00 | 06/24/2018 15:30:00
2582626 | 245008564 | act--04 SSV | 04 SSV | Completed | Activity | 245008774 | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 | 06/26/2018 07:00:00 | 06/26/2018 15:30:00
2582626 | 245008564 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008852 |  |  |  |  | 06/22/2018 06:30:00 | 06/22/2018 07:30:00 |  | 06/22/2018 08:30:00
2582627 | 245008565 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008967 |  |  |  |  | 06/24/2018 13:00:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582627 | 245008565 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008902 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582627 | 245008565 | 0 | 07 Implementation Complete | Completed | Milestone | 245009031 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582627 | 245008565 | act--02 Installation | 02 Installation | Completed | Activity | 245008665 | 06/21/2018 12:30:00 | 06/21/2018 16:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582627 | 245008565 | act--03 Integration | 03 Integration | Completed | Activity | 245008718 | 06/22/2018 12:30:00 | 06/22/2018 23:00:00 | 06/23/2018 11:30:00 | 06/23/2018 15:30:00
2582627 | 245008565 | act--04 SSV | 04 SSV | Completed | Activity | 245008781 | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 | 06/25/2018 07:00:00 | 06/25/2018 15:30:00
2582627 | 245008565 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008848 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582628 | 245008566 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008928 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582628 | 245008566 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008871 |  |  |  |  | 06/27/2018 12:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582628 | 245008566 | 0 | 07 Implementation Complete | Completed | Milestone | 245008969 |  |  |  |  | 01/01/2000 05:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582628 | 245008566 | act--02 Installation | 02 Installation | Completed | Activity | 245008662 | 06/22/2018 12:30:00 | 06/22/2018 16:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582628 | 245008566 | act--03 Integration | 03 Integration | Completed | Activity | 245008715 | 06/23/2018 12:30:00 | 06/23/2018 23:00:00 | 06/24/2018 11:30:00 | 06/24/2018 15:30:00
2582628 | 245008566 | act--04 SSV | 04 SSV | Completed | Activity | 245008764 | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 | 06/26/2018 07:00:00 | 06/26/2018 15:30:00
2582628 | 245008566 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008822 |  |  |  |  | 06/22/2018 06:30:00 | 06/22/2018 07:30:00 |  | 06/22/2018 08:30:00
2582629 | 245008567 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008984 |  |  |  |  | 06/26/2018 13:00:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582629 | 245008567 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008924 |  |  |  |  | 06/28/2018 12:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582629 | 245008567 | 0 | 07 Implementation Complete | Completed | Milestone | 245009049 |  |  |  |  | 01/01/2000 05:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582629 | 245008567 | act--02 Installation | 02 Installation | Completed | Activity | 245008670 | 06/23/2018 12:30:00 | 06/23/2018 16:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582629 | 245008567 | act--03 Integration | 03 Integration | Completed | Activity | 245008728 | 06/24/2018 12:30:00 | 06/24/2018 23:00:00 | 06/25/2018 11:30:00 | 06/25/2018 15:30:00
2582629 | 245008567 | act--04 SSV | 04 SSV | Completed | Activity | 245008784 | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 | 06/27/2018 07:00:00 | 06/27/2018 15:30:00
2582629 | 245008567 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008858 |  |  |  |  | 06/23/2018 06:30:00 | 06/23/2018 07:30:00 |  | 06/23/2018 08:30:00
2582630 | 245008571 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008989 |  |  |  |  | 06/20/2018 13:00:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582630 | 245008571 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008922 |  |  |  |  | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582630 | 245008571 | 0 | 07 Implementation Complete | Completed | Milestone | 245009047 |  |  |  |  | 01/01/2000 05:30:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582630 | 245008571 | act--02 Installation | 02 Installation | Completed | Activity | 245008664 | 06/17/2018 12:30:00 | 06/17/2018 16:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582630 | 245008571 | act--03 Integration | 03 Integration | Completed | Activity | 245008723 | 06/18/2018 12:30:00 | 06/18/2018 23:00:00 | 06/19/2018 11:30:00 | 06/19/2018 15:30:00
2582630 | 245008571 | act--04 SSV | 04 SSV | Completed | Activity | 245008787 | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582630 | 245008571 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008860 |  |  |  |  | 06/17/2018 06:30:00 | 06/17/2018 07:30:00 |  | 06/17/2018 08:30:00
2582631 | 245008570 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008974 |  |  |  |  | 06/25/2018 13:00:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582631 | 245008570 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008925 |  |  |  |  | 06/27/2018 12:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582631 | 245008570 | 0 | 07 Implementation Complete | Completed | Milestone | 245009027 |  |  |  |  | 01/01/2000 05:30:00 | 06/27/2018 15:00:00 |  | 06/27/2018 15:00:00
2582631 | 245008570 | act--02 Installation | 02 Installation | Completed | Activity | 245008673 | 06/22/2018 12:30:00 | 06/22/2018 16:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582631 | 245008570 | act--03 Integration | 03 Integration | Completed | Activity | 245008724 | 06/23/2018 12:30:00 | 06/23/2018 23:00:00 | 06/24/2018 11:30:00 | 06/24/2018 15:30:00
2582631 | 245008570 | act--04 SSV | 04 SSV | Completed | Activity | 245008780 | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 | 06/26/2018 07:00:00 | 06/26/2018 15:30:00
2582631 | 245008570 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008857 |  |  |  |  | 06/22/2018 06:30:00 | 06/22/2018 07:30:00 |  | 06/22/2018 08:30:00
2582632 | 245008576 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008944 |  |  |  |  | 06/24/2018 13:00:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582632 | 245008576 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008883 |  |  |  |  | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582632 | 245008576 | 0 | 07 Implementation Complete | Completed | Milestone | 245009010 |  |  |  |  | 01/01/2000 05:30:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582632 | 245008576 | act--02 Installation | 02 Installation | Completed | Activity | 245008663 | 06/21/2018 12:30:00 | 06/21/2018 16:00:00 | 06/22/2018 07:00:00 | 06/22/2018 15:30:00
2582632 | 245008576 | act--03 Integration | 03 Integration | Completed | Activity | 245008726 | 06/22/2018 12:30:00 | 06/22/2018 23:00:00 | 06/23/2018 11:30:00 | 06/23/2018 15:30:00
2582632 | 245008576 | act--04 SSV | 04 SSV | Completed | Activity | 245008775 | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 | 06/25/2018 07:00:00 | 06/25/2018 15:30:00
2582632 | 245008576 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008828 |  |  |  |  | 06/21/2018 06:30:00 | 06/21/2018 07:30:00 |  | 06/21/2018 08:30:00
2582633 | 245008573 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008999 |  |  |  |  | 06/16/2018 13:00:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582633 | 245008573 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008940 |  |  |  |  | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582633 | 245008573 | 0 | 07 Implementation Complete | Completed | Milestone | 245009054 |  |  |  |  | 01/01/2000 05:30:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582633 | 245008573 | act--02 Installation | 02 Installation | Completed | Activity | 245008669 | 06/13/2018 12:30:00 | 06/13/2018 16:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582633 | 245008573 | act--03 Integration | 03 Integration | Completed | Activity | 245008730 | 06/14/2018 12:30:00 | 06/14/2018 23:00:00 | 06/15/2018 11:30:00 | 06/15/2018 15:30:00
2582633 | 245008573 | act--04 SSV | 04 SSV | Completed | Activity | 245008788 | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582633 | 245008573 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008873 |  |  |  |  | 06/13/2018 06:30:00 | 06/13/2018 07:30:00 |  | 06/13/2018 08:30:00
2582634 | 245008575 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008947 |  |  |  |  | 06/18/2018 13:00:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582634 | 245008575 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008900 |  |  |  |  | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582634 | 245008575 | 0 | 07 Implementation Complete | Completed | Milestone | 245008995 |  |  |  |  | 01/01/2000 05:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582634 | 245008575 | act--02 Installation | 02 Installation | Completed | Activity | 245008671 | 06/15/2018 12:30:00 | 06/15/2018 16:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582634 | 245008575 | act--03 Integration | 03 Integration | Completed | Activity | 245008720 | 06/16/2018 12:30:00 | 06/16/2018 23:00:00 | 06/17/2018 11:30:00 | 06/17/2018 15:30:00
2582634 | 245008575 | act--04 SSV | 04 SSV | Completed | Activity | 245008776 | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582634 | 245008575 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008856 |  |  |  |  | 06/15/2018 06:30:00 | 06/15/2018 07:30:00 |  | 06/15/2018 08:30:00
2582635 | 245008577 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008917 |  |  |  |  | 06/18/2018 13:00:00 | 06/18/2018 15:00:00 |  | 06/18/2018 15:00:00
2582635 | 245008577 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008866 |  |  |  |  | 06/20/2018 12:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582635 | 245008577 | 0 | 07 Implementation Complete | Completed | Milestone | 245008981 |  |  |  |  | 01/01/2000 05:30:00 | 06/20/2018 15:00:00 |  | 06/20/2018 15:00:00
2582635 | 245008577 | act--02 Installation | 02 Installation | Completed | Activity | 245008661 | 06/15/2018 12:30:00 | 06/15/2018 16:00:00 | 06/16/2018 07:00:00 | 06/16/2018 15:30:00
2582635 | 245008577 | act--03 Integration | 03 Integration | Completed | Activity | 245008719 | 06/16/2018 12:30:00 | 06/16/2018 23:00:00 | 06/17/2018 11:30:00 | 06/17/2018 15:30:00
2582635 | 245008577 | act--04 SSV | 04 SSV | Completed | Activity | 245008759 | 06/18/2018 12:30:00 | 06/18/2018 15:00:00 | 06/19/2018 07:00:00 | 06/19/2018 15:30:00
2582635 | 245008577 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008808 |  |  |  |  | 06/15/2018 06:30:00 | 06/15/2018 07:30:00 |  | 06/15/2018 08:30:00
2582636 | 245008578 | 0 | 05 NRO IM Accept | Completed | Milestone | 245009034 |  |  |  |  | 06/23/2018 13:00:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582636 | 245008578 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008968 |  |  |  |  | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582636 | 245008578 | 0 | 07 Implementation Complete | Completed | Milestone | 245009096 |  |  |  |  | 01/01/2000 05:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582636 | 245008578 | act--02 Installation | 02 Installation | Completed | Activity | 245008675 | 06/20/2018 12:30:00 | 06/20/2018 16:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582636 | 245008578 | act--03 Integration | 03 Integration | Completed | Activity | 245008739 | 06/21/2018 12:30:00 | 06/21/2018 23:00:00 | 06/22/2018 11:30:00 | 06/22/2018 15:30:00
2582636 | 245008578 | act--04 SSV | 04 SSV | Completed | Activity | 245008802 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582636 | 245008578 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008909 |  |  |  |  | 06/20/2018 06:30:00 | 06/20/2018 07:30:00 |  | 06/20/2018 08:30:00
2582637 | 245008579 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008976 |  |  |  |  | 06/22/2018 13:00:00 | 06/22/2018 15:00:00 |  | 06/22/2018 15:00:00
2582637 | 245008579 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008906 |  |  |  |  | 06/24/2018 12:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582637 | 245008579 | 0 | 07 Implementation Complete | Completed | Milestone | 245009022 |  |  |  |  | 01/01/2000 05:30:00 | 06/24/2018 15:00:00 |  | 06/24/2018 15:00:00
2582637 | 245008579 | act--02 Installation | 02 Installation | Completed | Activity | 245008672 | 06/19/2018 12:30:00 | 06/19/2018 16:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582637 | 245008579 | act--03 Integration | 03 Integration | Completed | Activity | 245008721 | 06/20/2018 12:30:00 | 06/20/2018 23:00:00 | 06/21/2018 11:30:00 | 06/21/2018 15:30:00
2582637 | 245008579 | act--04 SSV | 04 SSV | Completed | Activity | 245008782 | 06/22/2018 12:30:00 | 06/22/2018 15:00:00 | 06/23/2018 07:00:00 | 06/23/2018 15:30:00
2582637 | 245008579 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008842 |  |  |  |  | 06/19/2018 06:30:00 | 06/19/2018 07:30:00 |  | 06/19/2018 08:30:00
2582638 | 245008580 | 0 | 05 NRO IM Accept | Completed | Milestone | 245008903 |  |  |  |  | 06/14/2018 13:00:00 | 06/14/2018 15:00:00 |  | 06/14/2018 15:00:00
2582638 | 245008580 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008861 |  |  |  |  | 06/16/2018 12:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582638 | 245008580 | 0 | 07 Implementation Complete | Completed | Milestone | 245008966 |  |  |  |  | 01/01/2000 05:30:00 | 06/16/2018 15:00:00 |  | 06/16/2018 15:00:00
2582638 | 245008580 | act--02 Installation | 02 Installation | Completed | Activity | 245008667 | 06/11/2018 12:30:00 | 06/11/2018 16:00:00 | 06/12/2018 07:00:00 | 06/12/2018 15:30:00
2582638 | 245008580 | act--03 Integration | 03 Integration | Completed | Activity | 245008716 | 06/12/2018 12:30:00 | 06/12/2018 23:00:00 | 06/13/2018 11:30:00 | 06/13/2018 15:30:00
2582638 | 245008580 | act--04 SSV | 04 SSV | Completed | Activity | 245008760 | 06/14/2018 12:30:00 | 06/14/2018 15:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582638 | 245008580 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008816 |  |  |  |  | 06/11/2018 06:30:00 | 06/11/2018 07:30:00 |  | 06/11/2018 08:30:00
2582639 | 245008584 | 0 | 05 NRO IM Accept | Completed | Milestone | 245009006 |  |  |  |  | 06/19/2018 13:00:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582639 | 245008584 | 0 | 06 NDO IM Accept | Completed | Milestone | 245008945 |  |  |  |  | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582639 | 245008584 | 0 | 07 Implementation Complete | Completed | Milestone | 245009063 |  |  |  |  | 01/01/2000 05:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582639 | 245008584 | act--02 Installation | 02 Installation | Completed | Activity | 245008674 | 06/16/2018 12:30:00 | 06/16/2018 16:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582639 | 245008584 | act--03 Integration | 03 Integration | Completed | Activity | 245008733 | 06/17/2018 12:30:00 | 06/17/2018 23:00:00 | 06/18/2018 11:30:00 | 06/18/2018 15:30:00
2582639 | 245008584 | act--04 SSV | 04 SSV | Completed | Activity | 245008799 | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582639 | 245008584 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245008891 |  |  |  |  | 06/16/2018 06:30:00 | 06/16/2018 07:30:00 |  | 06/16/2018 08:30:00
2582640 | 245009203 | 0 | 05 NRO IM Accept | Completed | Milestone | 245009266 |  |  |  |  | 06/17/2018 13:00:00 | 06/17/2018 15:00:00 |  | 06/17/2018 15:00:00
2582640 | 245009203 | 0 | 06 NDO IM Accept | Completed | Milestone | 245009257 |  |  |  |  | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582640 | 245009203 | 0 | 07 Implementation Complete | Completed | Milestone | 245009275 |  |  |  |  | 01/01/2000 05:30:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582640 | 245009203 | act--02 Installation | 02 Installation | Completed | Activity | 245009218 | 06/14/2018 12:30:00 | 06/14/2018 16:00:00 | 06/15/2018 07:00:00 | 06/15/2018 15:30:00
2582640 | 245009203 | act--03 Integration | 03 Integration | Completed | Activity | 245009227 | 06/15/2018 12:30:00 | 06/15/2018 23:00:00 | 06/16/2018 11:30:00 | 06/16/2018 15:30:00
2582640 | 245009203 | act--04 SSV | 04 SSV | Completed | Activity | 245009234 | 06/17/2018 12:30:00 | 06/17/2018 15:00:00 | 06/18/2018 07:00:00 | 06/18/2018 15:30:00
2582640 | 245009203 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245009246 |  |  |  |  | 06/14/2018 06:30:00 | 06/14/2018 07:30:00 |  | 06/14/2018 08:30:00
2582641 | 245009204 | 0 | 05 NRO IM Accept | Completed | Milestone | 245009270 |  |  |  |  | 06/13/2018 13:00:00 | 06/13/2018 15:00:00 |  | 06/13/2018 15:00:00
2582641 | 245009204 | 0 | 06 NDO IM Accept | Completed | Milestone | 245009261 |  |  |  |  | 06/15/2018 12:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582641 | 245009204 | 0 | 07 Implementation Complete | Completed | Milestone | 245009280 |  |  |  |  | 01/01/2000 05:30:00 | 06/15/2018 15:00:00 |  | 06/15/2018 15:00:00
2582641 | 245009204 | act--02 Installation | 02 Installation | Completed | Activity | 245009219 | 06/10/2018 12:30:00 | 06/10/2018 16:00:00 | 06/11/2018 07:00:00 | 06/11/2018 15:30:00
2582641 | 245009204 | act--03 Integration | 03 Integration | Completed | Activity | 245009228 | 06/11/2018 12:30:00 | 06/11/2018 23:00:00 | 06/12/2018 11:30:00 | 06/12/2018 15:30:00
2582641 | 245009204 | act--04 SSV | 04 SSV | Completed | Activity | 245009241 | 06/13/2018 12:30:00 | 06/13/2018 15:00:00 | 06/14/2018 07:00:00 | 06/14/2018 15:30:00
2582641 | 245009204 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245009253 |  |  |  |  | 06/10/2018 06:30:00 | 06/10/2018 07:30:00 |  | 06/10/2018 08:30:00
2582642 | 245009205 | 0 | 05 NRO IM Accept | Completed | Milestone | 245009269 |  |  |  |  | 06/26/2018 13:00:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582642 | 245009205 | 0 | 06 NDO IM Accept | Completed | Milestone | 245009260 |  |  |  |  | 06/28/2018 12:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582642 | 245009205 | 0 | 07 Implementation Complete | Completed | Milestone | 245009278 |  |  |  |  | 01/01/2000 05:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582642 | 245009205 | act--02 Installation | 02 Installation | Completed | Activity | 245009220 | 06/23/2018 12:30:00 | 06/23/2018 16:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582642 | 245009205 | act--03 Integration | 03 Integration | Completed | Activity | 245009229 | 06/24/2018 12:30:00 | 06/24/2018 23:00:00 | 06/25/2018 11:30:00 | 06/25/2018 15:30:00
2582642 | 245009205 | act--04 SSV | 04 SSV | Completed | Activity | 245009240 | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 | 06/27/2018 07:00:00 | 06/27/2018 15:30:00
2582642 | 245009205 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245009251 |  |  |  |  | 06/23/2018 06:30:00 | 06/23/2018 07:30:00 |  | 06/23/2018 08:30:00
2582643 | 245012012 | 0 | 05 NRO IM Accept | Completed | Milestone | 245012110 |  |  |  |  | 06/19/2018 13:00:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582643 | 245012012 | 0 | 06 NDO IM Accept | Completed | Milestone | 245012098 |  |  |  |  | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582643 | 245012012 | 0 | 07 Implementation Complete | Completed | Milestone | 245012122 |  |  |  |  | 01/01/2000 05:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582643 | 245012012 | act--02 Installation | 02 Installation | Completed | Activity | 245012035 | 06/16/2018 12:30:00 | 06/16/2018 16:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582643 | 245012012 | act--03 Integration | 03 Integration | Completed | Activity | 245012047 | 06/17/2018 12:30:00 | 06/17/2018 23:00:00 | 06/18/2018 11:30:00 | 06/18/2018 15:30:00
2582643 | 245012012 | act--04 SSV | 04 SSV | Completed | Activity | 245012075 | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582643 | 245012012 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245012086 |  |  |  |  | 06/16/2018 06:30:00 | 06/16/2018 07:30:00 |  | 06/16/2018 08:30:00
2582644 | 245012013 | 0 | 05 NRO IM Accept | Completed | Milestone | 245012112 |  |  |  |  | 06/26/2018 13:00:00 | 06/26/2018 15:00:00 |  | 06/26/2018 15:00:00
2582644 | 245012013 | 0 | 06 NDO IM Accept | Completed | Milestone | 245012100 |  |  |  |  | 06/28/2018 12:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582644 | 245012013 | 0 | 07 Implementation Complete | Completed | Milestone | 245012123 |  |  |  |  | 01/01/2000 05:30:00 | 06/28/2018 15:00:00 |  | 06/28/2018 15:00:00
2582644 | 245012013 | act--02 Installation | 02 Installation | Completed | Activity | 245012037 | 06/23/2018 12:30:00 | 06/23/2018 16:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582644 | 245012013 | act--03 Integration | 03 Integration | Completed | Activity | 245012048 | 06/24/2018 12:30:00 | 06/24/2018 23:00:00 | 06/25/2018 11:30:00 | 06/25/2018 15:30:00
2582644 | 245012013 | act--04 SSV | 04 SSV | Completed | Activity | 245012074 | 06/26/2018 12:30:00 | 06/26/2018 15:00:00 | 06/27/2018 07:00:00 | 06/27/2018 15:30:00
2582644 | 245012013 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245012089 |  |  |  |  | 06/23/2018 06:30:00 | 06/23/2018 07:30:00 |  | 06/23/2018 08:30:00
2582645 | 245012014 | 0 | 05 NRO IM Accept | Completed | Milestone | 245012109 |  |  |  |  | 06/19/2018 13:00:00 | 06/19/2018 15:00:00 |  | 06/19/2018 15:00:00
2582645 | 245012014 | 0 | 06 NDO IM Accept | Completed | Milestone | 245012097 |  |  |  |  | 06/21/2018 12:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582645 | 245012014 | 0 | 07 Implementation Complete | Completed | Milestone | 245012120 |  |  |  |  | 01/01/2000 05:30:00 | 06/21/2018 15:00:00 |  | 06/21/2018 15:00:00
2582645 | 245012014 | act--02 Installation | 02 Installation | Completed | Activity | 245012034 | 06/16/2018 12:30:00 | 06/16/2018 16:00:00 | 06/17/2018 07:00:00 | 06/17/2018 15:30:00
2582645 | 245012014 | act--03 Integration | 03 Integration | Completed | Activity | 245012049 | 06/17/2018 12:30:00 | 06/17/2018 23:00:00 | 06/18/2018 11:30:00 | 06/18/2018 15:30:00
2582645 | 245012014 | act--04 SSV | 04 SSV | Completed | Activity | 245012073 | 06/19/2018 12:30:00 | 06/19/2018 15:00:00 | 06/20/2018 07:00:00 | 06/20/2018 15:30:00
2582645 | 245012014 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245012085 |  |  |  |  | 06/16/2018 06:30:00 | 06/16/2018 07:30:00 |  | 06/16/2018 08:30:00
2582646 | 245012015 | 0 | 05 NRO IM Accept | Completed | Milestone | 245012108 |  |  |  |  | 04/14/2018 13:00:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582646 | 245012015 | 0 | 06 NDO IM Accept | Completed | Milestone | 245012096 |  |  |  |  | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 |  | 04/16/2018 15:00:00
2582646 | 245012015 | 0 | 07 Implementation Complete | Completed | Milestone | 245012121 |  |  |  |  | 01/01/2000 05:30:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582646 | 245012015 | act--02 Installation | 02 Installation | Completed | Activity | 245012036 | 04/11/2018 12:30:00 | 04/11/2018 15:30:00 | 04/12/2018 08:00:00 | 04/12/2018 15:00:00
2582646 | 245012015 | act--03 Integration | 03 Integration | Completed | Activity | 245012046 | 04/12/2018 12:30:00 | 04/12/2018 21:00:00 | 04/13/2018 12:30:00 | 04/13/2018 15:00:00
2582646 | 245012015 | act--04 SSV | 04 SSV | Completed | Activity | 245012072 | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 | 04/15/2018 08:00:00 | 04/15/2018 15:00:00
2582646 | 245012015 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245012084 |  |  |  |  | 04/11/2018 06:30:00 | 04/11/2018 08:30:00 |  | 04/11/2018 09:30:00
2582647 | 245014982 | 0 | 05 NRO IM Accept | Completed | Milestone | 245015086 |  |  |  |  | 03/27/2018 13:00:00 | 03/27/2018 15:00:00 |  | 03/27/2018 15:00:00
2582647 | 245014982 | 0 | 06 NDO IM Accept | Completed | Milestone | 245015074 |  |  |  |  | 03/29/2018 12:30:00 | 03/29/2018 14:30:00 |  | 03/29/2018 15:00:00
2582647 | 245014982 | 0 | 07 Implementation Complete | Completed | Milestone | 245015098 |  |  |  |  | 01/01/2000 05:30:00 | 03/29/2018 15:00:00 |  | 03/29/2018 15:00:00
2582647 | 245014982 | act--02 Installation | 02 Installation | Completed | Activity | 245015004 | 03/24/2018 12:30:00 | 03/24/2018 15:30:00 | 03/25/2018 08:00:00 | 03/25/2018 15:00:00
2582647 | 245014982 | act--03 Integration | 03 Integration | Completed | Activity | 245015021 | 03/25/2018 12:30:00 | 03/25/2018 21:00:00 | 03/26/2018 12:30:00 | 03/26/2018 15:00:00
2582647 | 245014982 | act--04 SSV | 04 SSV | Completed | Activity | 245015047 | 03/27/2018 12:30:00 | 03/27/2018 14:30:00 | 03/28/2018 08:00:00 | 03/28/2018 15:00:00
2582647 | 245014982 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245015061 |  |  |  |  | 03/24/2018 06:30:00 | 03/24/2018 08:30:00 |  | 03/24/2018 09:30:00
2582648 | 245014984 | 0 | 05 NRO IM Accept | Completed | Milestone | 245015089 |  |  |  |  | 06/23/2018 13:00:00 | 06/23/2018 15:00:00 |  | 06/23/2018 15:00:00
2582648 | 245014984 | 0 | 06 NDO IM Accept | Completed | Milestone | 245015076 |  |  |  |  | 06/25/2018 12:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582648 | 245014984 | 0 | 07 Implementation Complete | Completed | Milestone | 245015103 |  |  |  |  | 01/01/2000 05:30:00 | 06/25/2018 15:00:00 |  | 06/25/2018 15:00:00
2582648 | 245014984 | act--02 Installation | 02 Installation | Completed | Activity | 245015002 | 06/20/2018 12:30:00 | 06/20/2018 16:00:00 | 06/21/2018 07:00:00 | 06/21/2018 15:30:00
2582648 | 245014984 | act--03 Integration | 03 Integration | Completed | Activity | 245015022 | 06/21/2018 12:30:00 | 06/21/2018 23:00:00 | 06/22/2018 11:30:00 | 06/22/2018 15:30:00
2582648 | 245014984 | act--04 SSV | 04 SSV | Completed | Activity | 245015049 | 06/23/2018 12:30:00 | 06/23/2018 15:00:00 | 06/24/2018 07:00:00 | 06/24/2018 15:30:00
2582648 | 245014984 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245015064 |  |  |  |  | 06/20/2018 06:30:00 | 06/20/2018 07:30:00 |  | 06/20/2018 08:30:00
2582649 | 245014985 | 0 | 05 NRO IM Accept | Completed | Milestone | 245015090 |  |  |  |  | 04/14/2018 13:00:00 | 04/14/2018 15:00:00 |  | 04/14/2018 15:00:00
2582649 | 245014985 | 0 | 06 NDO IM Accept | Completed | Milestone | 245015077 |  |  |  |  | 04/16/2018 12:30:00 | 04/16/2018 14:30:00 |  | 04/16/2018 15:00:00
2582649 | 245014985 | 0 | 07 Implementation Complete | Completed | Milestone | 245015102 |  |  |  |  | 01/01/2000 05:30:00 | 04/16/2018 15:00:00 |  | 04/16/2018 15:00:00
2582649 | 245014985 | act--02 Installation | 02 Installation | Completed | Activity | 245015003 | 04/11/2018 12:30:00 | 04/11/2018 15:30:00 | 04/12/2018 08:00:00 | 04/12/2018 15:00:00
2582649 | 245014985 | act--03 Integration | 03 Integration | Completed | Activity | 245015020 | 04/12/2018 12:30:00 | 04/12/2018 21:00:00 | 04/13/2018 12:30:00 | 04/13/2018 15:00:00
2582649 | 245014985 | act--04 SSV | 04 SSV | Completed | Activity | 245015048 | 04/14/2018 12:30:00 | 04/14/2018 14:30:00 | 04/15/2018 08:00:00 | 04/15/2018 15:00:00
2582649 | 245014985 | ms--01 Implementation Start | 01 Implementation Start | Completed | Milestone | 245015066 |  |  |  |  | 04/11/2018 06:30:00 | 04/11/2018 08:30:00 |  | 04/11/2018 09:30:00

## UDF ITEM
WP ID | Workplan--SystemRecordID | PLO name | PLO--SystemRecordID | UDF Name | UDF - System Record ID | UDF Category Name | UDF CategorySystem Record ID | UDF item Name | UDF Item--SystemRecordID | UDF Value