## PRJ WP Site
Project--ID | Project--ProjectName | Project--SystemRecordID | Project--ProjectPlanStartDate | Project--ProjectPlanEndDate | Project--ProjectExecutionCountry | Project--Customer | Project--Status | Workplan--Country | Workplan--WorkPlanID | Workplan--FASID | Workplan--SystemRecordID | Workplan--WorkPlanStatus | Workplan--ProjectName | Workplan--Prefix | Workplan--Suffix | Workplan--CustomerDeliverableID | Workplan--RelatedNetworkElement | Workplan--CustomerScopeID | Workplan--WorkPlanType | Sites--ID | Sites--Name | Sites--RecordName | Sites--SystemRecordID | Sites--Customer | Sites--SiteType | Sites--City | Sites--Country | Sites--Status | Sites--StreetAddress | Sites--LatitudeDecimal | Sites--LatitudeDMS | Sites--LongitudeDecimal | Sites--LongitudeDMS
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-09 | 2019-09-01 | China | China Telecom Guangdong | Issued | China | 3550483 |  | 675858528 | Started | 50125271-清溪聚福路口_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975026-清溪聚福路口_NO\DGQX_NO_D7975026-清溪聚福路口_NO |  | Radio Site | DGQX_NO_D7975026 | 清溪聚福路口_NO_1 | DGQX_NO_D7975026-清溪聚福路口_NO | 611751526 |  |  | Dongguan | China | Draft | 清溪聚福路口_NO | 22.8348 | 22'50'5' | 114.1548 | 114'9'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-12 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550484 |  | 675858527 | Started | 50125271-石排新局_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGSP_NO_D7975008-石排新局_NO\DGSP_NO_D7975008-石排新局_NO |  | Radio Site | DGSP_NO_D7975008 | 石排新局_NO_1 | DGSP_NO_D7975008-石排新局_NO | 611751525 |  |  | Dongguan | China | Draft | 石排新局_NO | 23.0954 | 23'5'44' | 113.9335 | 113'56'0'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-18 | 2021-04-26 | China | China Telecom Guangdong | Issued | China | 3550485 |  | 675858534 | Started | 50125271-石排汇正大厦_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGSP_NO_D7975119-石排汇正大厦_NO\DGSP_NO_D7975119-石排汇正大厦_NO |  | Radio Site | DGSP_NO_D7975119 | 石排汇正大厦_NO_1 | DGSP_NO_D7975119-石排汇正大厦_NO | 611751670 |  |  | Dongguan | China | Draft | 石排汇正大厦_NO | 23.078 | 23'4'41' | 113.9369 | 113'56'12'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-26 | 2020-03-26 | China | China Telecom Guangdong | Issued | China | 3550486 |  | 675858535 | Started | 50125271-常平山水雅居_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975121-常平山水雅居_NO\DGCP_NO_D7975121-常平山水雅居_NO |  | Radio Site | DGCP_NO_D7975121 | 常平山水雅居_NO_1 | DGCP_NO_D7975121-常平山水雅居_NO | 611751668 |  |  | Dongguan | China | Draft | 常平山水雅居_NO | 22.9823 | 22'58'56' | 114.0191 | 114'1'8'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-19 | 2020-03-26 | China | China Telecom Guangdong | Issued | China | 3550487 |  | 675858538 | Started | 50125271-清溪重木村_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975050-清溪重木村_NO\DGQX_NO_D7975050-清溪重木村_NO |  | Radio Site | DGQX_NO_D7975050 | 清溪重木村_NO_1 | DGQX_NO_D7975050-清溪重木村_NO | 611751617 |  |  | Dongguan | China | Draft | 清溪重木村_NO | 22.8489 | 22'50'56' | 114.1686 | 114'10'7'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-20 | 2019-12-24 | China | China Telecom Guangdong | Issued | China | 3550488 |  | 675858602 | Started | 50125271-凤岗小布_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975017-凤岗小布_NO\DGFG_NO_D7975017-凤岗小布_NO |  | Radio Site | DGFG_NO_D7975017 | 凤岗小布_NO_1 | DGFG_NO_D7975017-凤岗小布_NO | 611751532 |  |  | Dongguan | China | Draft | 凤岗小布_NO | 22.7275 | 22'43'39' | 114.1748 | 114'10'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-02 | 2021-04-28 | China | China Telecom Guangdong | Issued | China | 3550489 |  | 675858614 | Started | 50125271-企石电信大楼_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7975155-企石电信大楼_NO\DGQS_NO_D7975155-企石电信大楼_NO |  | Radio Site | DGQS_NO_D7975155 | 企石电信大楼_NO_1 | DGQS_NO_D7975155-企石电信大楼_NO | 611751986 |  |  | Dongguan | China | Draft | 企石电信大楼_NO | 23.0655 | 23'3'56' | 114.0041 | 114'0'14'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-11 | 2020-03-06 | China | China Telecom Guangdong | Issued | China | 3550490 |  | 675858616 | Started | 50125271-常平恒隆_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975093-常平恒隆_NO\DGCP_NO_D7975093-常平恒隆_NO |  | Radio Site | DGCP_NO_D7975093 | 常平恒隆_NO_1 | DGCP_NO_D7975093-常平恒隆_NO | 611751684 |  |  | Dongguan | China | Draft | 常平恒隆_NO | 22.9785 | 22'58'43' | 113.9942 | 113'59'39'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-11 | 2020-03-11 | China | China Telecom Guangdong | Issued | China | 3550491 |  | 675858613 | Started | 50125271-常平商业大街_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975065-常平商业大街_NO\DGCP_NO_D7975065-常平商业大街_NO |  | Radio Site | DGCP_NO_D7975065 | 常平商业大街_NO_1 | DGCP_NO_D7975065-常平商业大街_NO | 611752358 |  |  | Dongguan | China | Draft | 常平商业大街_NO | 22.9796 | 22'58'47' | 113.9905 | 113'59'25'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-17 | 2020-03-11 | China | China Telecom Guangdong | Issued | China | 3550492 |  | 675858621 | Started | 50125271-常平金美新堂_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975062-常平金美新堂_NO\DGCP_NO_D7975062-常平金美新堂_NO |  | Radio Site | DGCP_NO_D7975062 | 常平金美新堂_NO_1 | DGCP_NO_D7975062-常平金美新堂_NO | 611752319 |  |  | Dongguan | China | Draft | 常平金美新堂_NO | 22.9627 | 22'57'46' | 113.9748 | 113'58'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-19 | 2019-11-27 | China | China Telecom Guangdong | Issued | China | 3550493 |  | 675858625 | Started | 50125271-清溪康怡花园_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975023-清溪康怡花园_NO\DGQX_NO_D7975023-清溪康怡花园_NO |  | Radio Site | DGQX_NO_D7975023 | 清溪康怡花园_NO_1 | DGQX_NO_D7975023-清溪康怡花园_NO | 611751533 |  |  | Dongguan | China | Draft | 清溪康怡花园_NO | 22.8433 | 22'50'36' | 114.1497 | 114'8'59'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-10 | 2019-12-14 | China | China Telecom Guangdong | Issued | China | 3550494 |  | 675858629 | Started | 50125271-常平电信大楼_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975046-常平电信大楼_NO\DGCP_NO_D7975046-常平电信大楼_NO |  | Radio Site | DGCP_NO_D7975046 | 常平电信大楼_NO_1 | DGCP_NO_D7975046-常平电信大楼_NO | 611751625 |  |  | Dongguan | China | Draft | 常平电信大楼_NO | 22.9674 | 22'58'3' | 113.9879 | 113'59'16'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-15 | 2021-04-28 | China | China Telecom Guangdong | Issued | China | 3550495 |  | 675858639 | Started | 50125271-企石上桥路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7975156-企石上桥路_NO\DGQS_NO_D7975156-企石上桥路_NO |  | Radio Site | DGQS_NO_D7975156 | 企石上桥路_NO_1 | DGQS_NO_D7975156-企石上桥路_NO | 611752400 |  |  | Dongguan | China | Draft | 企石上桥路_NO | 23.0599 | 23'3'36' | 114.0049 | 114'0'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-12 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550496 |  | 675858641 | Started | 50125271-东坑电信_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGDK_NO_D7975100-东坑电信_NO\DGDK_NO_D7975100-东坑电信_NO |  | Radio Site | DGDK_NO_D7975100 | 东坑电信_NO_1 | DGDK_NO_D7975100-东坑电信_NO | 611752367 |  |  | Dongguan | China | Draft | 东坑电信_NO | 23.0016 | 23'0'6' | 113.9331 | 113'55'59'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-05 | 2020-01-14 | China | China Telecom Guangdong | Issued | China | 3550497 |  | 675858896 | Started | 50125271-塘厦莆心湖光纤站_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975068-塘厦莆心湖光纤站_NO\DGTX_NO_D7975068-塘厦莆心湖光纤站_NO |  | Radio Site | DGTX_NO_D7975068 | 塘厦莆心湖光纤站_NO_1 | DGTX_NO_D7975068-塘厦莆心湖光纤站_NO | 611751681 |  |  | Dongguan | China | Draft | 塘厦莆心湖光纤站_NO | 22.7961 | 22'47'46' | 114.0821 | 114'4'55'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-14 | 2019-12-29 | China | China Telecom Guangdong | Issued | China | 3550498 |  | 675858905 | Started | 50125271-塘厦椰山路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975144-塘厦椰山路_NO\DGTX_NO_D7975144-塘厦椰山路_NO |  | Radio Site | DGTX_NO_D7975144 | 塘厦椰山路_NO_1 | DGTX_NO_D7975144-塘厦椰山路_NO | 611751844 |  |  | Dongguan | China | Draft | 塘厦椰山路_NO | 22.8092 | 22'48'33' | 114.0794 | 114'4'45'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-25 | China | China Telecom Guangdong | Issued | China | 3550499 |  | 675858915 | Started | 50125271-GO_坪山比亚迪D12栋-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761928-GO_坪山比亚迪D12栋\GO_S_FE_D7761928-GO_坪山比亚迪D12栋 |  | Radio Site | GO_S_FE_D7761928 | GO_坪山比亚迪D12栋_1 | GO_S_FE_D7761928-GO_坪山比亚迪D12栋 | 675841841 |  |  | Shenzhen | China | Draft |  | 22.6779 | 22'40'41' | 114.3539 | 114'21'14'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2019-12-28 | China | China Telecom Guangdong | Issued | China | 3550500 |  | 675858922 | Started | 50125271-凤岗康佳_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975020-凤岗康佳_NO\DGFG_NO_D7975020-凤岗康佳_NO |  | Radio Site | DGFG_NO_D7975020 | 凤岗康佳_NO_1 | DGFG_NO_D7975020-凤岗康佳_NO | 611752304 |  |  | Dongguan | China | Draft | 凤岗康佳_NO | 22.7417 | 22'44'30' | 114.139 | 114'8'20'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-06 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550501 |  | 675858924 | Started | 50125271-企石剧院_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7974919-企石剧院_NO\DGQS_NO_D7974919-企石剧院_NO |  | Radio Site | DGQS_NO_D7974919 | 企石剧院_NO_1 | DGQS_NO_D7974919-企石剧院_NO | 611751199 |  |  | Dongguan | China | Draft | 企石剧院_NO | 23.0754 | 23'4'31' | 114.0199 | 114'1'11'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-01-06 | China | China Telecom Guangdong | Issued | China | 3550502 |  | 675858923 | Started | 50125271-GO_坪山文化路56号东-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761940-GO_坪山文化路56号东\GO_S_FE_D7761940-GO_坪山文化路56号东 |  | Radio Site | GO_S_FE_D7761940 | GO_坪山文化路56号东_1 | GO_S_FE_D7761940-GO_坪山文化路56号东 | 675841817 |  |  | Shenzhen | China | Draft |  | 22.691 | 22'41'28' | 114.3448 | 114'20'41'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-04-14 | China | China Telecom Guangdong | Issued | China | 3550503 |  | 675858920 | Started | 50125271-GO_坪山新嘉工业园-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761935-GO_坪山新嘉工业园\GO_S_FE_D7761935-GO_坪山新嘉工业园 |  | Radio Site | GO_S_FE_D7761935 | GO_坪山新嘉工业园_1 | GO_S_FE_D7761935-GO_坪山新嘉工业园 | 675841827 |  |  | Shenzhen | China | Draft |  | 22.6685 | 22'40'7' | 114.3264 | 114'19'35'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-17 | 2021-01-06 | China | China Telecom Guangdong | Issued | China | 3550504 |  | 675858918 | Started | 50125271-GO_坪山山吓路七巷6号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761948-GO_坪山山吓路七巷6号\GO_S_FE_D7761948-GO_坪山山吓路七巷6号 |  | Radio Site | GO_S_FE_D7761948 | GO_坪山山吓路七巷6号_1 | GO_S_FE_D7761948-GO_坪山山吓路七巷6号 | 675841851 |  |  | Shenzhen | China | Draft |  | 22.7009 | 22'42'3' | 114.3406 | 114'20'26'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-23 | 2020-10-12 | China | China Telecom Guangdong | Issued | China | 3550505 |  | 675858921 | Started | 50125271-塘厦行政中心_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975072-塘厦行政中心_NO\DGTX_NO_D7975072-塘厦行政中心_NO |  | Radio Site | DGTX_NO_D7975072 | 塘厦行政中心_NO_1 | DGTX_NO_D7975072-塘厦行政中心_NO | 611751679 |  |  | Dongguan | China | Draft | 塘厦行政中心_NO | 22.8103 | 22'48'37' | 114.0687 | 114'4'7'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-05 | 2020-03-30 | China | China Telecom Guangdong | Issued | China | 3550506 |  | 675858919 | Started | 50125271-清溪市场_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975032-清溪市场_NO\DGQX_NO_D7975032-清溪市场_NO |  | Radio Site | DGQX_NO_D7975032 | 清溪市场_NO_1 | DGQX_NO_D7975032-清溪市场_NO | 611751469 |  |  | Dongguan | China | Draft | 清溪市场_NO | 22.8378 | 22'50'16' | 114.1581 | 114'9'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-21 | 2020-03-30 | China | China Telecom Guangdong | Issued | China | 3550507 |  | 675858965 | Started | 50125271-凤岗官井头_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975009-凤岗官井头_NO\DGFG_NO_D7975009-凤岗官井头_NO |  | Radio Site | DGFG_NO_D7975009 | 凤岗官井头_NO_1 | DGFG_NO_D7975009-凤岗官井头_NO | 611751476 |  |  | Dongguan | China | Draft | 凤岗官井头_NO | 22.7212 | 22'43'16' | 114.1795 | 114'10'46'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-01-13 | China | China Telecom Guangdong | Issued | China | 3550508 |  | 675858968 | Started | 50125271-GO_坪山深孚酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761925-GO_坪山深孚酒店\GO_S_FE_D7761925-GO_坪山深孚酒店 |  | Radio Site | GO_S_FE_D7761925 | GO_坪山深孚酒店_1 | GO_S_FE_D7761925-GO_坪山深孚酒店 | 675841852 |  |  | Shenzhen | China | Draft |  | 22.6888 | 22'41'20' | 114.3568 | 114'21'24'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-21 | 2019-12-20 | China | China Telecom Guangdong | Issued | China | 3550509 |  | 675858966 | Started | 50125271-凤岗卧龙村_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975010-凤岗卧龙村_NO\DGFG_NO_D7975010-凤岗卧龙村_NO |  | Radio Site | DGFG_NO_D7975010 | 凤岗卧龙村_NO_1 | DGFG_NO_D7975010-凤岗卧龙村_NO | 611751513 |  |  | Dongguan | China | Draft | 凤岗卧龙村_NO | 22.7623 | 22'45'44' | 114.1414 | 114'8'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-29 | China | China Telecom Guangdong | Issued | China | 3550510 |  | 675858967 | Started | 50125271-GO_坪山石井工业园-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761938-GO_坪山石井工业园\GO_S_FE_D7761938-GO_坪山石井工业园 |  | Radio Site | GO_S_FE_D7761938 | GO_坪山石井工业园_1 | GO_S_FE_D7761938-GO_坪山石井工业园 | 675841849 |  |  | Shenzhen | China | Draft |  | 22.6881 | 22'41'17' | 114.3736 | 114'22'25'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-26 | China | China Telecom Guangdong | Issued | China | 3550511 |  | 675858973 | Started | 50125271-GO_坪山新区管委会大楼-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761926-GO_坪山新区管委会大楼\GO_S_FE_D7761926-GO_坪山新区管委会大楼 |  | Radio Site | GO_S_FE_D7761926 | GO_坪山新区管委会大楼_1 | GO_S_FE_D7761926-GO_坪山新区管委会大楼 | 675841805 |  |  | Shenzhen | China | Draft |  | 22.7119 | 22'42'43' | 114.3461 | 114'20'46'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-04 | 2020-03-07 | China | China Telecom Guangdong | Issued | China | 3550512 |  | 675859053 | Started | 50125271-塘厦浦心湖_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975066-塘厦浦心湖_NO\DGTX_NO_D7975066-塘厦浦心湖_NO |  | Radio Site | DGTX_NO_D7975066 | 塘厦浦心湖_NO_1 | DGTX_NO_D7975066-塘厦浦心湖_NO | 611751671 |  |  | Dongguan | China | Draft | 塘厦浦心湖_NO | 22.8013 | 22'48'5' | 114.0798 | 114'4'47'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-25 | China | China Telecom Guangdong | Issued | China | 3550513 |  | 675859052 | Started | 50125271-GO_坪山比亚迪-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761920-GO_坪山比亚迪\GO_S_FE_D7761920-GO_坪山比亚迪 |  | Radio Site | GO_S_FE_D7761920 | GO_坪山比亚迪_1 | GO_S_FE_D7761920-GO_坪山比亚迪 | 675841833 |  |  | Shenzhen | China | Draft |  | 22.681 | 22'40'52' | 114.3656 | 114'21'56'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-27 | 2020-03-07 | China | China Telecom Guangdong | Issued | China | 3550514 |  | 675859081 | Started | 50125271-凤岗华心宿舍_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975048-凤岗华心宿舍_NO\DGFG_NO_D7975048-凤岗华心宿舍_NO |  | Radio Site | DGFG_NO_D7975048 | 凤岗华心宿舍_NO_1 | DGFG_NO_D7975048-凤岗华心宿舍_NO | 611751697 |  |  | Dongguan | China | Draft | 凤岗华心宿舍_NO | 22.7219 | 22'43'19' | 114.1761 | 114'10'33'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2020-11-08 | China | China Telecom Guangdong | Issued | China | 3550515 |  | 675859082 | Started | 50125271-GO_坪山黄沙坑-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761932-GO_坪山黄沙坑\GO_S_FE_D7761932-GO_坪山黄沙坑 |  | Radio Site | GO_S_FE_D7761932 | GO_坪山黄沙坑_1 | GO_S_FE_D7761932-GO_坪山黄沙坑 | 675841850 |  |  | Shenzhen | China | Draft |  | 22.6793 | 22'40'45' | 114.3352 | 114'20'6'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-02 | 2020-11-08 | China | China Telecom Guangdong | Issued | China | 3550516 |  | 675859083 | Started | 50125271-清溪万胜洲际酒店_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975047-清溪万胜洲际酒店_NO\DGQX_NO_D7975047-清溪万胜洲际酒店_NO |  | Radio Site | DGQX_NO_D7975047 | 清溪万胜洲际酒店_NO_1 | DGQX_NO_D7975047-清溪万胜洲际酒店_NO | 611751690 |  |  | Dongguan | China | Draft | 清溪万胜洲际酒店_NO | 22.8461 | 22'50'46' | 114.1664 | 114'9'59'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-24 | 2021-03-23 | China | China Telecom Guangdong | Issued | China | 3550517 |  | 675859080 | Started | 50125271-GO_盐田林场宿舍-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761946-GO_盐田林场宿舍\GO_S_FE_D7761946-GO_盐田林场宿舍 |  | Radio Site | GO_S_FE_D7761946 | GO_盐田林场宿舍_1 | GO_S_FE_D7761946-GO_盐田林场宿舍 | 675841844 |  |  | Shenzhen | China | Draft |  | 22.5636 | 22'33'49' | 114.232 | 114'13'55'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-15 | 2019-12-26 | China | China Telecom Guangdong | Issued | China | 3550518 |  | 675859085 | Started | 50125271-塘厦四村_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975053-塘厦四村_NO\DGTX_NO_D7975053-塘厦四村_NO |  | Radio Site | DGTX_NO_D7975053 | 塘厦四村_NO_1 | DGTX_NO_D7975053-塘厦四村_NO | 611751680 |  |  | Dongguan | China | Draft | 塘厦四村_NO | 22.8038 | 22'48'14' | 114.072 | 114'4'19'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-19 | 2019-12-26 | China | China Telecom Guangdong | Issued | China | 3550519 |  | 675859087 | Started | 50125271-塘厦杨梅苑_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975064-塘厦杨梅苑_NO\DGTX_NO_D7975064-塘厦杨梅苑_NO |  | Radio Site | DGTX_NO_D7975064 | 塘厦杨梅苑_NO_1 | DGTX_NO_D7975064-塘厦杨梅苑_NO | 611752290 |  |  | Dongguan | China | Draft | 塘厦杨梅苑_NO | 22.8044 | 22'48'16' | 114.063 | 114'3'46'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-06 | 2020-01-01 | China | China Telecom Guangdong | Issued | China | 3550520 |  | 675859086 | Started | 50125271-塘厦田心_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975090-塘厦田心_NO\DGTX_NO_D7975090-塘厦田心_NO |  | Radio Site | DGTX_NO_D7975090 | 塘厦田心_NO_1 | DGTX_NO_D7975090-塘厦田心_NO | 611752307 |  |  | Dongguan | China | Draft | 塘厦田心_NO | 22.8018 | 22'48'6' | 114.0584 | 114'3'30'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-20 | 2019-12-31 | China | China Telecom Guangdong | Issued | China | 3550521 |  | 675859117 | Started | 50125271-清溪鹿鸣路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975016-清溪鹿鸣路_NO\DGQX_NO_D7975016-清溪鹿鸣路_NO |  | Radio Site | DGQX_NO_D7975016 | 清溪鹿鸣路_NO_1 | DGQX_NO_D7975016-清溪鹿鸣路_NO | 611752314 |  |  | Dongguan | China | Draft | 清溪鹿鸣路_NO | 22.8357 | 22'50'9' | 114.1617 | 114'9'41'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-17 | 2020-09-27 | China | China Telecom Guangdong | Issued | China | 3550522 |  | 675859140 | Started | 50125271-GO_坑梓大窝村16号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761960-GO_坑梓大窝村16号\GO_S_FE_D7761960-GO_坑梓大窝村16号 |  | Radio Site | GO_S_FE_D7761960 | GO_坑梓大窝村16号_1 | GO_S_FE_D7761960-GO_坑梓大窝村16号 | 675841882 |  |  | Shenzhen | China | Draft |  | 22.7644 | 22'45'52' | 114.3632 | 114'21'47'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-28 | 2020-09-27 | China | China Telecom Guangdong | Issued | China | 3550523 |  | 675859145 | Started | 50125271-常平工贸_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975133-常平工贸_NO\DGCP_NO_D7975133-常平工贸_NO |  | Radio Site | DGCP_NO_D7975133 | 常平工贸_NO_1 | DGCP_NO_D7975133-常平工贸_NO | 611752364 |  |  | Dongguan | China | Draft | 常平工贸_NO | 22.9757 | 22'58'32' | 113.9876 | 113'59'15'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-30 | 2020-01-12 | China | China Telecom Guangdong | Issued | China | 3550524 |  | 675859167 | Started | 50125271-常平桔园三街_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975092-常平桔园三街_NO\DGCP_NO_D7975092-常平桔园三街_NO |  | Radio Site | DGCP_NO_D7975092 | 常平桔园三街_NO_1 | DGCP_NO_D7975092-常平桔园三街_NO | 611752353 |  |  | Dongguan | China | Draft | 常平桔园三街_NO | 22.9655 | 22'57'56' | 113.9839 | 113'59'1'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-06 | 2020-10-20 | China | China Telecom Guangdong | Issued | China | 3550525 |  | 675859168 | Started | 50125271-GO_坑梓吉康路口-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762000-GO_坑梓吉康路口\GO_S_FE_D7762000-GO_坑梓吉康路口 |  | Radio Site | GO_S_FE_D7762000 | GO_坑梓吉康路口_1 | GO_S_FE_D7762000-GO_坑梓吉康路口 | 675841902 |  |  | Shenzhen | China | Draft |  | 22.7351 | 22'44'6' | 114.3533 | 114'21'11'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2020-10-22 | China | China Telecom Guangdong | Issued | China | 3550526 |  | 675859166 | Started | 50125271-GO_坪山大万村1号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761933-GO_坪山大万村1号\GO_S_FE_D7761933-GO_坪山大万村1号 |  | Radio Site | GO_S_FE_D7761933 | GO_坪山大万村1号_1 | GO_S_FE_D7761933-GO_坪山大万村1号 | 675841854 |  |  | Shenzhen | China | Draft |  | 22.6862 | 22'41'10' | 114.3372 | 114'20'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-21 | 2020-10-21 | China | China Telecom Guangdong | Issued | China | 3550527 |  | 675859169 | Started | 50125271-GO_坑梓青排新村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761978-GO_坑梓青排新村\GO_S_FE_D7761978-GO_坑梓青排新村 |  | Radio Site | GO_S_FE_D7761978 | GO_坑梓青排新村_1 | GO_S_FE_D7761978-GO_坑梓青排新村 | 675841908 |  |  | Shenzhen | China | Draft |  | 22.7559 | 22'45'21' | 114.3947 | 114'23'40'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-09 | 2020-09-27 | China | China Telecom Guangdong | Issued | China | 3550528 |  | 675859175 | Started | 50125271-塘厦四村塘龙中路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975063-塘厦四村塘龙中路_NO\DGTX_NO_D7975063-塘厦四村塘龙中路_NO |  | Radio Site | DGTX_NO_D7975063 | 塘厦四村塘龙中路_NO_1 | DGTX_NO_D7975063-塘厦四村塘龙中路_NO | 611751636 |  |  | Dongguan | China | Draft | 塘厦四村塘龙中路_NO | 22.8026 | 22'48'10' | 114.0675 | 114'4'2'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-06 | 2020-01-03 | China | China Telecom Guangdong | Issued | China | 3550529 |  | 675859174 | Started | 50125271-常平金河二路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7823548-常平金河二路_NO\DGCP_NO_D7823548-常平金河二路_NO |  | Radio Site | DGCP_NO_D7823548 | 常平金河二路_NO_1 | DGCP_NO_D7823548-常平金河二路_NO | 675841853 |  |  | Dongguan | China | Draft |  | 22.9669 | 22'58'1' | 113.9803 | 113'58'49'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-19 | 2021-04-26 | China | China Telecom Guangdong | Issued | China | 3550530 |  | 675859183 | Started | 50125271-石排利丰_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGSP_NO_D7975117-石排利丰_NO\DGSP_NO_D7975117-石排利丰_NO |  | Radio Site | DGSP_NO_D7975117 | 石排利丰_NO_1 | DGSP_NO_D7975117-石排利丰_NO | 611752359 |  |  | Dongguan | China | Draft | 石排利丰_NO | 23.0854 | 23'5'7' | 113.9381 | 113'56'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-04 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550531 |  | 675859192 | Started | 50125271-石龙美能达_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGSL_NO_D7975118-石龙美能达_NO\DGSL_NO_D7975118-石龙美能达_NO |  | Radio Site | DGSL_NO_D7975118 | 石龙美能达_NO_1 | DGSL_NO_D7975118-石龙美能达_NO | 611751692 |  |  | Dongguan | China | Draft | 石龙美能达_NO | 23.1219 | 23'7'19' | 113.8746 | 113'52'28'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2020-10-14 | China | China Telecom Guangdong | Issued | China | 3550532 |  | 675859293 | Started | 50125271-GO_坪山帝王酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761937-GO_坪山帝王酒店\GO_S_FE_D7761937-GO_坪山帝王酒店 |  | Radio Site | GO_S_FE_D7761937 | GO_坪山帝王酒店_1 | GO_S_FE_D7761937-GO_坪山帝王酒店 | 675841825 |  |  | Shenzhen | China | Draft |  | 22.6874 | 22'41'14' | 114.3461 | 114'20'45'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-07 | 2020-10-14 | China | China Telecom Guangdong | Issued | China | 3550533 |  | 675859294 | Started | 50125271-GO_坪山赤坳工业区南侧-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761929-GO_坪山赤坳工业区南侧\GO_S_FE_D7761929-GO_坪山赤坳工业区南侧 |  | Radio Site | GO_S_FE_D7761929 | GO_坪山赤坳工业区南侧_1 | GO_S_FE_D7761929-GO_坪山赤坳工业区南侧 | 675841855 |  |  | Shenzhen | China | Draft |  | 22.6691 | 22'40'9' | 114.3564 | 114'21'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-20 | 2020-10-09 | China | China Telecom Guangdong | Issued | China | 3550534 |  | 675859295 | Started | 50125271-凤岗狮岭山_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975037-凤岗狮岭山_NO\DGFG_NO_D7975037-凤岗狮岭山_NO |  | Radio Site | DGFG_NO_D7975037 | 凤岗狮岭山_NO_1 | DGFG_NO_D7975037-凤岗狮岭山_NO | 611751490 |  |  | Dongguan | China | Draft | 凤岗狮岭山_NO | 22.7315 | 22'43'54' | 114.1711 | 114'10'16'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-06 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550535 |  | 675859304 | Started | 50125271-企石旧石围_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7974952-企石旧石围_NO\DGQS_NO_D7974952-企石旧石围_NO |  | Radio Site | DGQS_NO_D7974952 | 企石旧石围_NO_1 | DGQS_NO_D7974952-企石旧石围_NO | 611752249 |  |  | Dongguan | China | Draft | 企石旧石围_NO | 23.0758 | 23'4'33' | 114.0279 | 114'1'40'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-29 | 2021-03-27 | China | China Telecom Guangdong | Issued | China | 3550536 |  | 675859351 | Started | 50125271-GO_坪山龙商大酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761944-GO_坪山龙商大酒店\GO_S_FE_D7761944-GO_坪山龙商大酒店 |  | Radio Site | GO_S_FE_D7761944 | GO_坪山龙商大酒店_1 | GO_S_FE_D7761944-GO_坪山龙商大酒店 | 675841836 |  |  | Shenzhen | China | Draft |  | 22.7018 | 22'42'6' | 114.3283 | 114'19'41'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-26 | 2020-10-10 | China | China Telecom Guangdong | Issued | China | 3550537 |  | 675859352 | Started | 50125271-GO_坪山福安东五巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761965-GO_坪山福安东五巷\GO_S_FE_D7761965-GO_坪山福安东五巷 |  | Radio Site | GO_S_FE_D7761965 | GO_坪山福安东五巷_1 | GO_S_FE_D7761965-GO_坪山福安东五巷 | 675841895 |  |  | Shenzhen | China | Draft |  | 22.6934 | 22'41'36' | 114.3319 | 114'19'54'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-28 | 2020-10-09 | China | China Telecom Guangdong | Issued | China | 3550538 |  | 675859364 | Started | 50125271-常平吴屋村_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975095-常平吴屋村_NO\DGCP_NO_D7975095-常平吴屋村_NO |  | Radio Site | DGCP_NO_D7975095 | 常平吴屋村_NO_1 | DGCP_NO_D7975095-常平吴屋村_NO | 611752357 |  |  | Dongguan | China | Draft | 常平吴屋村_NO | 22.9711 | 22'58'16' | 114.0066 | 114'0'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-15 | 2020-03-11 | China | China Telecom Guangdong | Issued | China | 3550539 |  | 675859367 | Started | 50125271-塘厦塘龙中路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975145-塘厦塘龙中路_NO\DGTX_NO_D7975145-塘厦塘龙中路_NO |  | Radio Site | DGTX_NO_D7975145 | 塘厦塘龙中路_NO_1 | DGTX_NO_D7975145-塘厦塘龙中路_NO | 611752392 |  |  | Dongguan | China | Draft | 塘厦塘龙中路_NO | 22.8051 | 22'48'18' | 114.0773 | 114'4'38'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-11 | 2021-04-28 | China | China Telecom Guangdong | Issued | China | 3550540 |  | 675859369 | Started | 50125271-东坑计生所_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGDK_NO_D7975124-东坑计生所_NO\DGDK_NO_D7975124-东坑计生所_NO |  | Radio Site | DGDK_NO_D7975124 | 东坑计生所_NO_1 | DGDK_NO_D7975124-东坑计生所_NO | 611751720 |  |  | Dongguan | China | Draft | 东坑计生所_NO | 22.9937 | 22'59'37' | 113.9427 | 113'56'33'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-22 | 2020-04-03 | China | China Telecom Guangdong | Issued | China | 3550541 |  | 675859379 | Started | 50125271-塘厦湖景路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975044-塘厦湖景路_NO\DGTX_NO_D7975044-塘厦湖景路_NO |  | Radio Site | DGTX_NO_D7975044 | 塘厦湖景路_NO_1 | DGTX_NO_D7975044-塘厦湖景路_NO | 611751627 |  |  | Dongguan | China | Draft | 塘厦湖景路_NO | 22.8229 | 22'49'22' | 114.068 | 114'4'4'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-13 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550542 |  | 675859390 | Started | 50125271-企石绿兰岗北_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7975157-企石绿兰岗北_NO\DGQS_NO_D7975157-企石绿兰岗北_NO |  | Radio Site | DGQS_NO_D7975157 | 企石绿兰岗北_NO_1 | DGQS_NO_D7975157-企石绿兰岗北_NO | 611752399 |  |  | Dongguan | China | Draft | 企石绿兰岗北_NO | 23.0658 | 23'3'57' | 114.0083 | 114'0'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-21 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550543 |  | 675859391 | Started | 50125271-GO_坪山燕子岭生活区7号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761980-GO_坪山燕子岭生活区7号\GO_S_FE_D7761980-GO_坪山燕子岭生活区7号 |  | Radio Site | GO_S_FE_D7761980 | GO_坪山燕子岭生活区7号_1 | GO_S_FE_D7761980-GO_坪山燕子岭生活区7号 | 675841890 |  |  | Shenzhen | China | Draft |  | 22.704 | 22'42'15' | 114.3653 | 114'21'55'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-19 | 2020-09-28 | China | China Telecom Guangdong | Issued | China | 3550544 |  | 675859395 | Started | 50125271-凤岗布心基工业区_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975031-凤岗布心基工业区_NO\DGFG_NO_D7975031-凤岗布心基工业区_NO |  | Radio Site | DGFG_NO_D7975031 | 凤岗布心基工业区_NO_1 | DGFG_NO_D7975031-凤岗布心基工业区_NO | 611752317 |  |  | Dongguan | China | Draft | 凤岗布心基工业区_NO | 22.7319 | 22'43'55' | 114.19 | 114'11'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-09 | 2019-12-03 | China | China Telecom Guangdong | Issued | China | 3550545 |  | 675859396 | Started | 50125271-常平嘉美豪苑搬迁_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975094-常平嘉美豪苑搬迁_NO\DGCP_NO_D7975094-常平嘉美豪苑搬迁_NO |  | Radio Site | DGCP_NO_D7975094 | 常平嘉美豪苑搬迁_NO_1 | DGCP_NO_D7975094-常平嘉美豪苑搬迁_NO | 611751689 |  |  | Dongguan | China | Draft | 常平嘉美豪苑搬迁_NO | 22.9764 | 22'58'35' | 114.0021 | 114'0'7'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-12 | 2020-10-20 | China | China Telecom Guangdong | Issued | China | 3550546 |  | 675859403 | Started | 50125271-GO_坪山龙兴四巷4号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761998-GO_坪山龙兴四巷4号\GO_S_FE_D7761998-GO_坪山龙兴四巷4号 |  | Radio Site | GO_S_FE_D7761998 | GO_坪山龙兴四巷4号_1 | GO_S_FE_D7761998-GO_坪山龙兴四巷4号 | 675841891 |  |  | Shenzhen | China | Draft |  | 22.6942 | 22'41'39' | 114.3614 | 114'21'41'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-01 | 2020-10-20 | China | China Telecom Guangdong | Issued | China | 3550547 |  | 675859409 | Started | 50125271-GO_坪山香江商务酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761942-GO_坪山香江商务酒店\GO_S_FE_D7761942-GO_坪山香江商务酒店 |  | Radio Site | GO_S_FE_D7761942 | GO_坪山香江商务酒店_1 | GO_S_FE_D7761942-GO_坪山香江商务酒店 | 675841820 |  |  | Shenzhen | China | Draft |  | 22.6853 | 22'41'7' | 114.3509 | 114'21'3'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-25 | China | China Telecom Guangdong | Issued | China | 3550548 |  | 675859418 | Started | 50125271-GO_坪山比亚迪D21栋-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761922-GO_坪山比亚迪D21栋\GO_S_FE_D7761922-GO_坪山比亚迪D21栋 |  | Radio Site | GO_S_FE_D7761922 | GO_坪山比亚迪D21栋_1 | GO_S_FE_D7761922-GO_坪山比亚迪D21栋 | 675841823 |  |  | Shenzhen | China | Draft |  | 22.6804 | 22'40'50' | 114.3609 | 114'21'39'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-20 | 2020-10-07 | China | China Telecom Guangdong | Issued | China | 3550549 |  | 675859420 | Started | 50125271-凤岗小布村北_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975035-凤岗小布村北_NO\DGFG_NO_D7975035-凤岗小布村北_NO |  | Radio Site | DGFG_NO_D7975035 | 凤岗小布村北_NO_1 | DGFG_NO_D7975035-凤岗小布村北_NO | 611751488 |  |  | Dongguan | China | Draft | 凤岗小布村北_NO | 22.7313 | 22'43'53' | 114.1804 | 114'10'49'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-16 | 2021-05-28 | China | China Telecom Guangdong | Issued | China | 3550550 |  | 675859432 | Started | 50125271-石龙西湖_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGSL_NO_D7975116-石龙西湖_NO\DGSL_NO_D7975116-石龙西湖_NO |  | Radio Site | DGSL_NO_D7975116 | 石龙西湖_NO_1 | DGSL_NO_D7975116-石龙西湖_NO | 611751686 |  |  | Dongguan | China | Draft | 石龙西湖_NO | 23.102 | 23'6'7' | 113.8549 | 113'51'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-19 | 2019-12-17 | China | China Telecom Guangdong | Issued | China | 3550551 |  | 675859433 | Started | 50125271-清溪松岗二街_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975012-清溪松岗二街_NO\DGQX_NO_D7975012-清溪松岗二街_NO |  | Radio Site | DGQX_NO_D7975012 | 清溪松岗二街_NO_1 | DGQX_NO_D7975012-清溪松岗二街_NO | 611751468 |  |  | Dongguan | China | Draft | 清溪松岗二街_NO | 22.8478 | 22'50'52' | 114.1515 | 114'9'5'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-11 | 2021-03-27 | China | China Telecom Guangdong | Issued | China | 3550552 |  | 675859464 | Started | 50125271-GO_坑梓金沙五岭街-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761994-GO_坑梓金沙五岭街\GO_S_FE_D7761994-GO_坑梓金沙五岭街 |  | Radio Site | GO_S_FE_D7761994 | GO_坑梓金沙五岭街_1 | GO_S_FE_D7761994-GO_坑梓金沙五岭街 | 675841878 |  |  | Shenzhen | China | Draft |  | 22.7569 | 22'45'25' | 114.3911 | 114'23'28'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2020-10-07 | China | China Telecom Guangdong | Issued | China | 3550553 |  | 675859501 | Started | 50125271-GO_坪山江岭路口-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761943-GO_坪山江岭路口\GO_S_FE_D7761943-GO_坪山江岭路口 |  | Radio Site | GO_S_FE_D7761943 | GO_坪山江岭路口_1 | GO_S_FE_D7761943-GO_坪山江岭路口 | 675841835 |  |  | Shenzhen | China | Draft |  | 22.6806 | 22'40'50' | 114.3445 | 114'20'40'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-24 | 2020-10-07 | China | China Telecom Guangdong | Issued | China | 3550554 |  | 675859502 | Started | 50125271-凤岗竹塘_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975036-凤岗竹塘_NO\DGFG_NO_D7975036-凤岗竹塘_NO |  | Radio Site | DGFG_NO_D7975036 | 凤岗竹塘_NO_1 | DGFG_NO_D7975036-凤岗竹塘_NO | 611751487 |  |  | Dongguan | China | Draft | 凤岗竹塘_NO | 22.7627 | 22'45'46' | 114.1315 | 114'7'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-01 | 2021-02-01 | China | China Telecom Guangdong | Issued | China | 3550555 |  | 675859503 | Started | 50125271-GO_坪山翠景兰竹交界-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761981-GO_坪山翠景兰竹交界\GO_S_FE_D7761981-GO_坪山翠景兰竹交界 |  | Radio Site | GO_S_FE_D7761981 | GO_坪山翠景兰竹交界_1 | GO_S_FE_D7761981-GO_坪山翠景兰竹交界 | 675841876 |  |  | Shenzhen | China | Draft |  | 22.7177 | 22'43'4' | 114.3842 | 114'23'3'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-25 | China | China Telecom Guangdong | Issued | China | 3550557 |  | 675859512 | Started | 50125271-GO_坪山比亚迪D16栋-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761921-GO_坪山比亚迪D16栋\GO_S_FE_D7761921-GO_坪山比亚迪D16栋 |  | Radio Site | GO_S_FE_D7761921 | GO_坪山比亚迪D16栋_1 | GO_S_FE_D7761921-GO_坪山比亚迪D16栋 | 675841857 |  |  | Shenzhen | China | Draft |  | 22.6845 | 22'41'4' | 114.3717 | 114'22'18'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-06 | 2021-07-30 | China | China Telecom Guangdong | Issued | China | 3550559 |  | 675859570 | Started | 50125271-企石新南2_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQS_NO_D7974921-企石新南2_NO\DGQS_NO_D7974921-企石新南2_NO |  | Radio Site | DGQS_NO_D7974921 | 企石新南2_NO_1 | DGQS_NO_D7974921-企石新南2_NO | 611752316 |  |  | Dongguan | China | Draft | 企石新南2_NO | 23.0613 | 23'3'41' | 113.9973 | 113'59'50'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-31 | 2020-09-26 | China | China Telecom Guangdong | Issued | China | 3550560 |  | 675859581 | Started | 50125271-GO_大鹏金沙大道-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761989-GO_大鹏金沙大道\GO_S_FE_D7761989-GO_大鹏金沙大道 |  | Radio Site | GO_S_FE_D7761989 | GO_大鹏金沙大道_1 | GO_S_FE_D7761989-GO_大鹏金沙大道 | 675841909 |  |  | Shenzhen | China | Draft |  | 22.586 | 22'35'9' | 114.4594 | 114'27'33'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-05 | 2020-09-26 | China | China Telecom Guangdong | Issued | China | 3550561 |  | 675859587 | Started | 50125271-桥头迳联祥兴路_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQT_NO_D7975136-桥头迳联祥兴路_NO\DGQT_NO_D7975136-桥头迳联祥兴路_NO |  | Radio Site | DGQT_NO_D7975136 | 桥头迳联祥兴路_NO_1 | DGQT_NO_D7975136-桥头迳联祥兴路_NO | 611751789 |  |  | Dongguan | China | Draft | 桥头迳联祥兴路_NO | 23.0033 | 23'0'12' | 114.0982 | 114'5'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-11 | 2019-12-26 | China | China Telecom Guangdong | Issued | China | 3550562 |  | 675859586 | Started | 50125271-凤岗第二社区卫生服务站_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975071-凤岗第二社区卫生服务站_NO\DGFG_NO_D7975071-凤岗第二社区卫生服务站_NO |  | Radio Site | DGFG_NO_D7975071 | 凤岗第二社区卫生服务站_NO_1 | DGFG_NO_D7975071-凤岗第二社区卫生服务站_NO | 611751673 |  |  | Dongguan | China | Draft | 凤岗第二社区卫生服务站_NO | 22.7505 | 22'45'2' | 114.1458 | 114'8'44'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-20 | 2020-03-10 | China | China Telecom Guangdong | Issued | China | 3550563 |  | 675859583 | Started | 50125271-塘厦湖畔山庄_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975146-塘厦湖畔山庄_NO\DGTX_NO_D7975146-塘厦湖畔山庄_NO |  | Radio Site | DGTX_NO_D7975146 | 塘厦湖畔山庄_NO_1 | DGTX_NO_D7975146-塘厦湖畔山庄_NO | 611751828 |  |  | Dongguan | China | Draft | 塘厦湖畔山庄_NO | 22.8193 | 22'49'10' | 114.0751 | 114'4'30'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-12 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550564 |  | 675859582 | Started | 50125271-GO_坪山坪环工业城-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761972-GO_坪山坪环工业城\GO_S_FE_D7761972-GO_坪山坪环工业城 |  | Radio Site | GO_S_FE_D7761972 | GO_坪山坪环工业城_1 | GO_S_FE_D7761972-GO_坪山坪环工业城 | 675841903 |  |  | Shenzhen | China | Draft |  | 22.6819 | 22'40'55' | 114.3423 | 114'20'32'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-01-15 | China | China Telecom Guangdong | Issued | China | 3550565 |  | 675859585 | Started | 50125271-GO_坪山新屋村新区-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761927-GO_坪山新屋村新区\GO_S_FE_D7761927-GO_坪山新屋村新区 |  | Radio Site | GO_S_FE_D7761927 | GO_坪山新屋村新区_1 | GO_S_FE_D7761927-GO_坪山新屋村新区 | 675841856 |  |  | Shenzhen | China | Draft |  | 22.6899 | 22'41'24' | 114.3625 | 114'21'45'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-30 | 2021-03-27 | China | China Telecom Guangdong | Issued | China | 3550566 |  | 675859584 | Started | 50125271-GO_坪山沙新路5号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761945-GO_坪山沙新路5号\GO_S_FE_D7761945-GO_坪山沙新路5号 |  | Radio Site | GO_S_FE_D7761945 | GO_坪山沙新路5号_1 | GO_S_FE_D7761945-GO_坪山沙新路5号 | 675841848 |  |  | Shenzhen | China | Draft |  | 22.6899 | 22'41'24' | 114.3598 | 114'21'35'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-29 | 2019-12-25 | China | China Telecom Guangdong | Issued | China | 3550568 |  | 675859641 | Started | 50125271-常平埔新街_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975045-常平埔新街_NO\DGCP_NO_D7975045-常平埔新街_NO |  | Radio Site | DGCP_NO_D7975045 | 常平埔新街_NO_1 | DGCP_NO_D7975045-常平埔新街_NO | 611752292 |  |  | Dongguan | China | Draft | 常平埔新街_NO | 22.9618 | 22'57'42' | 113.9856 | 113'59'8'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-19 | 2021-01-16 | China | China Telecom Guangdong | Issued | China | 3550569 |  | 675859683 | Started | 50125271-GO_坪山洋岭路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761970-GO_坪山洋岭路\GO_S_FE_D7761970-GO_坪山洋岭路 |  | Radio Site | GO_S_FE_D7761970 | GO_坪山洋岭路_1 | GO_S_FE_D7761970-GO_坪山洋岭路 | 675841877 |  |  | Shenzhen | China | Draft |  | 22.6873 | 22'41'14' | 114.3347 | 114'20'4'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-02 | 2021-04-01 | China | China Telecom Guangdong | Issued | China | 3550570 |  | 675859687 | Started | 50125271-GO_坪山碧三路2-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761950-GO_坪山碧三路2\GO_S_FE_D7761950-GO_坪山碧三路2 |  | Radio Site | GO_S_FE_D7761950 | GO_坪山碧三路2_1 | GO_S_FE_D7761950-GO_坪山碧三路2 | 675841912 |  |  | Shenzhen | China | Draft |  | 22.6507 | 22'39'3' | 114.278 | 114'16'40'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-26 | 2021-01-16 | China | China Telecom Guangdong | Issued | China | 3550571 |  | 675859725 | Started | 50125271-GO_坪山浪尾新区-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762013-GO_坪山浪尾新区\GO_S_FE_D7762013-GO_坪山浪尾新区 |  | Radio Site | GO_S_FE_D7762013 | GO_坪山浪尾新区_1 | GO_S_FE_D7762013-GO_坪山浪尾新区 | 675841894 |  |  | Shenzhen | China | Draft |  | 22.6942 | 22'41'39' | 114.3182 | 114'19'5'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-02 | 2020-11-12 | China | China Telecom Guangdong | Issued | China | 3550572 |  | 675859727 | Started | 50125271-GO_坪山六联股份有限公司-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761953-GO_坪山六联股份有限公司\GO_S_FE_D7761953-GO_坪山六联股份有限公司 |  | Radio Site | GO_S_FE_D7761953 | GO_坪山六联股份有限公司_1 | GO_S_FE_D7761953-GO_坪山六联股份有限公司 | 675841834 |  |  | Shenzhen | China | Draft |  | 22.6929 | 22'41'35' | 114.3376 | 114'20'15'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-15 | 2021-03-25 | China | China Telecom Guangdong | Issued | China | 3550573 |  | 675859786 | Started | 50125271-GO_坪山比亚迪二期宿舍-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761991-GO_坪山比亚迪二期宿舍\GO_S_FE_D7761991-GO_坪山比亚迪二期宿舍 |  | Radio Site | GO_S_FE_D7761991 | GO_坪山比亚迪二期宿舍_1 | GO_S_FE_D7761991-GO_坪山比亚迪二期宿舍 | 675841918 |  |  | Shenzhen | China | Draft |  | 22.6728 | 22'40'22' | 114.353 | 114'21'10'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-27 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550574 |  | 675859787 | Started | 50125271-GO_坪山兔岗岭-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761949-GO_坪山兔岗岭\GO_S_FE_D7761949-GO_坪山兔岗岭 |  | Radio Site | GO_S_FE_D7761949 | GO_坪山兔岗岭_1 | GO_S_FE_D7761949-GO_坪山兔岗岭 | 675841826 |  |  | Shenzhen | China | Draft |  | 22.7109 | 22'42'39' | 114.4082 | 114'24'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2020-10-14 | China | China Telecom Guangdong | Issued | China | 3550575 |  | 675859811 | Started | 50125271-GO_坪山大万村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761936-GO_坪山大万村\GO_S_FE_D7761936-GO_坪山大万村 |  | Radio Site | GO_S_FE_D7761936 | GO_坪山大万村_1 | GO_S_FE_D7761936-GO_坪山大万村 | 675841819 |  |  | Shenzhen | China | Draft |  | 22.6841 | 22'41'3' | 114.3388 | 114'20'19'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-08 | 2020-10-14 | China | China Telecom Guangdong | Issued | China | 3550576 |  | 675859812 | Started | 50125271-清溪新局_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975086-清溪新局_NO\DGQX_NO_D7975086-清溪新局_NO |  | Radio Site | DGQX_NO_D7975086 | 清溪新局_NO_1 | DGQX_NO_D7975086-清溪新局_NO | 611752360 |  |  | Dongguan | China | Draft | 清溪新局_NO | 22.8279 | 22'49'40' | 114.1537 | 114'9'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-15 | 2021-03-11 | China | China Telecom Guangdong | Issued | China | 3550577 |  | 675859907 | Started | 50125271-GO_坪山龙岗大工业C-01-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761924-GO_坪山龙岗大工业C-01\GO_S_FE_D7761924-GO_坪山龙岗大工业C-01 |  | Radio Site | GO_S_FE_D7761924 | GO_坪山龙岗大工业C-01_1 | GO_S_FE_D7761924-GO_坪山龙岗大工业C-01 | 675841828 |  |  | Shenzhen | China | Draft |  | 22.7101 | 22'42'36' | 114.3519 | 114'21'6'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-26 | 2020-11-12 | China | China Telecom Guangdong | Issued | China | 3550578 |  | 675859910 | Started | 50125271-GO_坪山浪尾路113号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761971-GO_坪山浪尾路113号\GO_S_FE_D7761971-GO_坪山浪尾路113号 |  | Radio Site | GO_S_FE_D7761971 | GO_坪山浪尾路113号_1 | GO_S_FE_D7761971-GO_坪山浪尾路113号 | 675841910 |  |  | Shenzhen | China | Draft |  | 22.6937 | 22'41'37' | 114.3202 | 114'19'12'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-07 | 2020-11-12 | China | China Telecom Guangdong | Issued | China | 3550579 |  | 675859913 | Started | 50125271-清溪振兴路西_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975059-清溪振兴路西_NO\DGQX_NO_D7975059-清溪振兴路西_NO |  | Radio Site | DGQX_NO_D7975059 | 清溪振兴路西_NO_1 | DGQX_NO_D7975059-清溪振兴路西_NO | 611751626 |  |  | Dongguan | China | Draft | 清溪振兴路西_NO | 22.8437 | 22'50'37' | 114.1587 | 114'9'31'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-30 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550580 |  | 675859918 | Started | 50125271-GO_大鹏第六工业区-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761990-GO_大鹏第六工业区\GO_S_FE_D7761990-GO_大鹏第六工业区 |  | Radio Site | GO_S_FE_D7761990 | GO_大鹏第六工业区_1 | GO_S_FE_D7761990-GO_大鹏第六工业区 | 675841879 |  |  | Shenzhen | China | Draft |  | 22.5875 | 22'35'15' | 114.4787 | 114'28'43'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-23 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550581 |  | 675859929 | Started | 50125271-常平半岛豪庭_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGCP_NO_D7975096-常平半岛豪庭_NO\DGCP_NO_D7975096-常平半岛豪庭_NO |  | Radio Site | DGCP_NO_D7975096 | 常平半岛豪庭_NO_1 | DGCP_NO_D7975096-常平半岛豪庭_NO | 611752326 |  |  | Dongguan | China | Draft | 常平半岛豪庭_NO | 22.968 | 22'58'5' | 114.0035 | 114'0'12'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-22 | 2021-03-23 | China | China Telecom Guangdong | Issued | China | 3550582 |  | 675859960 | Started | 50125271-GO_横坪公路3-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761984-GO_横坪公路3\GO_S_FE_D7761984-GO_横坪公路3 |  | Radio Site | GO_S_FE_D7761984 | GO_横坪公路3_1 | GO_S_FE_D7761984-GO_横坪公路3 | 675841911 |  |  | Shenzhen | China | Draft |  | 22.6622 | 22'39'44' | 114.2871 | 114'17'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-19 | 2019-12-24 | China | China Telecom Guangdong | Issued | China | 3550583 |  | 675859961 | Started | 50125271-清溪昌明酒店_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGQX_NO_D7975034-清溪昌明酒店_NO\DGQX_NO_D7975034-清溪昌明酒店_NO |  | Radio Site | DGQX_NO_D7975034 | 清溪昌明酒店_NO_1 | DGQX_NO_D7975034-清溪昌明酒店_NO | 611751527 |  |  | Dongguan | China | Draft | 清溪昌明酒店_NO | 22.8367 | 22'50'12' | 114.1522 | 114'9'7'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-08-20 | 2020-03-12 | China | China Telecom Guangdong | Issued | China | 3550584 |  | 675860036 | Started | 50125271-凤岗永盛大街_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGFG_NO_D7975025-凤岗永盛大街_NO\DGFG_NO_D7975025-凤岗永盛大街_NO |  | Radio Site | DGFG_NO_D7975025 | 凤岗永盛大街_NO_1 | DGFG_NO_D7975025-凤岗永盛大街_NO | 611752274 |  |  | Dongguan | China | Draft | 凤岗永盛大街_NO | 22.7446 | 22'44'40' | 114.1254 | 114'7'31'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-09-26 | 2020-03-12 | China | China Telecom Guangdong | Issued | China | 3550585 |  | 675860034 | Started | 50125271-塘厦康舒电子厂_NO-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\DGTX_NO_D7975067-塘厦康舒电子厂_NO\DGTX_NO_D7975067-塘厦康舒电子厂_NO |  | Radio Site | DGTX_NO_D7975067 | 塘厦康舒电子厂_NO_1 | DGTX_NO_D7975067-塘厦康舒电子厂_NO | 611752301 |  |  | Dongguan | China | Draft | 塘厦康舒电子厂_NO | 22.8272 | 22'49'38' | 114.0826 | 114'4'57'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-30 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550586 |  | 675860410 | Started | 50125271-GO_坪山文化公园-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762006-GO_坪山文化公园\GO_S_FE_D7762006-GO_坪山文化公园 |  | Radio Site | GO_S_FE_D7762006 | GO_坪山文化公园_1 | GO_S_FE_D7762006-GO_坪山文化公园 | 675841922 |  |  | Shenzhen | China | Draft |  | 22.7074 | 22'42'27' | 114.3325 | 114'19'56'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-01 | 2020-09-24 | China | China Telecom Guangdong | Issued | China | 3550587 |  | 675860435 | Started | 50125271-GO_坪山碧三路5-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761951-GO_坪山碧三路5\GO_S_FE_D7761951-GO_坪山碧三路5 |  | Radio Site | GO_S_FE_D7761951 | GO_坪山碧三路5_1 | GO_S_FE_D7761951-GO_坪山碧三路5 | 675841924 |  |  | Shenzhen | China | Draft |  | 22.6425 | 22'38'33' | 114.2811 | 114'16'51'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-28 | 2020-10-12 | China | China Telecom Guangdong | Issued | China | 3550588 |  | 675860438 | Started | 50125271-GO_坪山坪马线公路5-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761956-GO_坪山坪马线公路5\GO_S_FE_D7761956-GO_坪山坪马线公路5 |  | Radio Site | GO_S_FE_D7761956 | GO_坪山坪马线公路5_1 | GO_S_FE_D7761956-GO_坪山坪马线公路5 | 675841925 |  |  | Shenzhen | China | Draft |  | 22.6353 | 22'38'7' | 114.3179 | 114'19'4'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-15 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550589 |  | 675860789 | Started | 50125271-GO_坪山坪马线公路6-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761957-GO_坪山坪马线公路6\GO_S_FE_D7761957-GO_坪山坪马线公路6 |  | Radio Site | GO_S_FE_D7761957 | GO_坪山坪马线公路6_1 | GO_S_FE_D7761957-GO_坪山坪马线公路6 | 675841926 |  |  | Shenzhen | China | Draft |  | 22.6437 | 22'38'37' | 114.3525 | 114'21'8'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-30 | 2021-02-02 | China | China Telecom Guangdong | Issued | China | 3550590 |  | 675860893 | Started | 50125271-GO_坪山三洋湖路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762028-GO_坪山三洋湖路\GO_S_FE_D7762028-GO_坪山三洋湖路 |  | Radio Site | GO_S_FE_D7762028 | GO_坪山三洋湖路_1 | GO_S_FE_D7762028-GO_坪山三洋湖路 | 675841948 |  |  | Shenzhen | China | Draft |  | 22.6924 | 22'41'33' | 114.3482 | 114'20'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-20 | 2021-03-29 | China | China Telecom Guangdong | Issued | China | 3550591 |  | 675860889 | Started | 50125271-GO_坝核路2-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762017-GO_坝核路2\GO_S_FE_D7762017-GO_坝核路2 |  | Radio Site | GO_S_FE_D7762017 | GO_坝核路2_1 | GO_S_FE_D7762017-GO_坝核路2 | 675841943 |  |  | Shenzhen | China | Draft |  | 22.6451 | 22'38'42' | 114.5036 | 114'30'12'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-15 | 2021-03-26 | China | China Telecom Guangdong | Issued | China | 3550592 |  | 675860891 | Started | 50125271-GO_坪山青松-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762026-GO_坪山青松\GO_S_FE_D7762026-GO_坪山青松 |  | Radio Site | GO_S_FE_D7762026 | GO_坪山青松_1 | GO_S_FE_D7762026-GO_坪山青松 | 675841942 |  |  | Shenzhen | China | Draft |  | 22.7257 | 22'43'33' | 114.394 | 114'23'38'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-01 | 2020-10-12 | China | China Telecom Guangdong | Issued | China | 3550594 |  | 675860898 | Started | 50125271-GO_南澳海港路改-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761992-GO_南澳海港路改\GO_S_FE_D7761992-GO_南澳海港路改 |  | Radio Site | GO_S_FE_D7761992 | GO_南澳海港路改_1 | GO_S_FE_D7761992-GO_南澳海港路改 | 675841927 |  |  | Shenzhen | China | Draft |  | 22.5345 | 22'32'4' | 114.487 | 114'29'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-06-04 | 2020-10-12 | China | China Telecom Guangdong | Issued | China | 3550595 |  | 675860888 | Started | 50125271-GO_坪山坪马线公路1-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761987-GO_坪山坪马线公路1\GO_S_FE_D7761987-GO_坪山坪马线公路1 |  | Radio Site | GO_S_FE_D7761987 | GO_坪山坪马线公路1_1 | GO_S_FE_D7761987-GO_坪山坪马线公路1 | 675841950 |  |  | Shenzhen | China | Draft |  | 22.6506 | 22'39'2' | 114.3381 | 114'20'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-29 | 2021-01-16 | China | China Telecom Guangdong | Issued | China | 3550596 |  | 675860890 | Started | 50125271-GO_坪山竹坑老围村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762010-GO_坪山竹坑老围村\GO_S_FE_D7762010-GO_坪山竹坑老围村 |  | Radio Site | GO_S_FE_D7762010 | GO_坪山竹坑老围村_1 | GO_S_FE_D7762010-GO_坪山竹坑老围村 | 675841919 |  |  | Shenzhen | China | Draft |  | 22.7118 | 22'42'42' | 114.3848 | 114'23'5'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-31 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550599 |  | 675860887 | Started | 50125271-GO_坪山绿基实业-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761983-GO_坪山绿基实业\GO_S_FE_D7761983-GO_坪山绿基实业 |  | Radio Site | GO_S_FE_D7761983 | GO_坪山绿基实业_1 | GO_S_FE_D7761983-GO_坪山绿基实业 | 675841923 |  |  | Shenzhen | China | Draft |  | 22.7147 | 22'42'53' | 114.3707 | 114'22'14'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-30 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550600 |  | 675860894 | Started | 50125271-GO_坪山竹坑村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762025-GO_坪山竹坑村\GO_S_FE_D7762025-GO_坪山竹坑村 |  | Radio Site | GO_S_FE_D7762025 | GO_坪山竹坑村_1 | GO_S_FE_D7762025-GO_坪山竹坑村 | 675841931 |  |  | Shenzhen | China | Draft |  | 22.7147 | 22'42'53' | 114.3886 | 114'23'18'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-09 | 2020-09-28 | China | China Telecom Guangdong | Issued | China | 3550601 |  | 675860895 | Started | 50125271-GO_坪山沙龙路33号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761973-GO_坪山沙龙路33号\GO_S_FE_D7761973-GO_坪山沙龙路33号 |  | Radio Site | GO_S_FE_D7761973 | GO_坪山沙龙路33号_1 | GO_S_FE_D7761973-GO_坪山沙龙路33号 | 675841921 |  |  | Shenzhen | China | Draft |  | 22.6931 | 22'41'35' | 114.356 | 114'21'21'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-19 | 2021-03-21 | China | China Telecom Guangdong | Issued | China | 3550603 |  | 675860926 | Started | 50125271-GO_坪山坪葵路138号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761985-GO_坪山坪葵路138号\GO_S_FE_D7761985-GO_坪山坪葵路138号 |  | Radio Site | GO_S_FE_D7761985 | GO_坪山坪葵路138号_1 | GO_S_FE_D7761985-GO_坪山坪葵路138号 | 675841951 |  |  | Shenzhen | China | Draft |  | 22.6796 | 22'40'47' | 114.3854 | 114'23'7'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-17 | 2020-11-13 | China | China Telecom Guangdong | Issued | China | 3550604 |  | 675861107 | Started | 50125271-GO_坑梓牛湖村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761959-GO_坑梓牛湖村\GO_S_FE_D7761959-GO_坑梓牛湖村 |  | Radio Site | GO_S_FE_D7761959 | GO_坑梓牛湖村_1 | GO_S_FE_D7761959-GO_坑梓牛湖村 | 675841958 |  |  | Shenzhen | China | Draft |  | 22.7518 | 22'45'7' | 114.3565 | 114'21'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-07 | 2021-04-01 | China | China Telecom Guangdong | Issued | China | 3550605 |  | 675861109 | Started | 50125271-GO_坪山金碧路548号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762023-GO_坪山金碧路548号\GO_S_FE_D7762023-GO_坪山金碧路548号 |  | Radio Site | GO_S_FE_D7762023 | GO_坪山金碧路548号_1 | GO_S_FE_D7762023-GO_坪山金碧路548号 | 675841957 |  |  | Shenzhen | China | Draft |  | 22.6703 | 22'40'13' | 114.2784 | 114'16'42'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-02 | 2021-01-05 | China | China Telecom Guangdong | Issued | China | 3550607 |  | 675861246 | Started | 50125271-GO_坪山御和园-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762012-GO_坪山御和园\GO_S_FE_D7762012-GO_坪山御和园 |  | Radio Site | GO_S_FE_D7762012 | GO_坪山御和园_1 | GO_S_FE_D7762012-GO_坪山御和园 | 675841962 |  |  | Shenzhen | China | Draft |  | 22.6796 | 22'40'47' | 114.3193 | 114'19'9'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-19 | 2021-04-13 | China | China Telecom Guangdong | Issued | China | 3550608 |  | 675861264 | Started | 50125271-GO_坪山金茂园大酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761966-GO_坪山金茂园大酒店\GO_S_FE_D7761966-GO_坪山金茂园大酒店 |  | Radio Site | GO_S_FE_D7761966 | GO_坪山金茂园大酒店_1 | GO_S_FE_D7761966-GO_坪山金茂园大酒店 | 675841966 |  |  | Shenzhen | China | Draft |  | 22.7033 | 22'42'12' | 114.3511 | 114'21'4'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-21 | 2021-03-30 | China | China Telecom Guangdong | Issued | China | 3550609 |  | 675861269 | Started | 50125271-GO_坪山沙陂路18-1号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762005-GO_坪山沙陂路18-1号\GO_S_FE_D7762005-GO_坪山沙陂路18-1号 |  | Radio Site | GO_S_FE_D7762005 | GO_坪山沙陂路18-1号_1 | GO_S_FE_D7762005-GO_坪山沙陂路18-1号 | 675841960 |  |  | Shenzhen | China | Draft |  | 22.6666 | 22'39'60' | 114.2868 | 114'17'12'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-02 | 2021-03-28 | China | China Telecom Guangdong | Issued | China | 3550610 |  | 675861273 | Started | 50125271-GO_坪山沙陂路58-1号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762011-GO_坪山沙陂路58-1号\GO_S_FE_D7762011-GO_坪山沙陂路58-1号 |  | Radio Site | GO_S_FE_D7762011 | GO_坪山沙陂路58-1号_1 | GO_S_FE_D7762011-GO_坪山沙陂路58-1号 | 675841961 |  |  | Shenzhen | China | Draft |  | 22.6668 | 22'40'0' | 114.2899 | 114'17'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-15 | 2021-01-05 | China | China Telecom Guangdong | Issued | China | 3550611 |  | 675861295 | Started | 50125271-GO_坪山金碧路258-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762018-GO_坪山金碧路258\GO_S_FE_D7762018-GO_坪山金碧路258 |  | Radio Site | GO_S_FE_D7762018 | GO_坪山金碧路258_1 | GO_S_FE_D7762018-GO_坪山金碧路258 | 675841981 |  |  | Shenzhen | China | Draft |  | 22.6834 | 22'41'0' | 114.3082 | 114'18'29'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-17 | 2020-10-12 | China | China Telecom Guangdong | Issued | China | 3550612 |  | 675861296 | Started | 50125271-GO_坪山坪马线公路4-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761955-GO_坪山坪马线公路4\GO_S_FE_D7761955-GO_坪山坪马线公路4 |  | Radio Site | GO_S_FE_D7761955 | GO_坪山坪马线公路4_1 | GO_S_FE_D7761955-GO_坪山坪马线公路4 | 675841970 |  |  | Shenzhen | China | Draft |  | 22.6385 | 22'38'19' | 114.3171 | 114'19'1'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-20 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550613 |  | 675861292 | Started | 50125271-GO_坪山坪兴三巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762015-GO_坪山坪兴三巷\GO_S_FE_D7762015-GO_坪山坪兴三巷 |  | Radio Site | GO_S_FE_D7762015 | GO_坪山坪兴三巷_1 | GO_S_FE_D7762015-GO_坪山坪兴三巷 | 675841978 |  |  | Shenzhen | China | Draft |  | 22.6776 | 22'40'39' | 114.3358 | 114'20'8'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-02 | 2021-03-28 | China | China Telecom Guangdong | Issued | China | 3550614 |  | 675861290 | Started | 50125271-GO_大鹏王母一工业区-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761986-GO_大鹏王母一工业区\GO_S_FE_D7761986-GO_大鹏王母一工业区 |  | Radio Site | GO_S_FE_D7761986 | GO_大鹏王母一工业区_1 | GO_S_FE_D7761986-GO_大鹏王母一工业区 | 675841979 |  |  | Shenzhen | China | Draft |  | 22.6003 | 22'36'1' | 114.4653 | 114'27'54'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-26 | 2021-04-14 | China | China Telecom Guangdong | Issued | China | 3550616 |  | 675861294 | Started | 50125271-GO_坪山沙新路四巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761979-GO_坪山沙新路四巷\GO_S_FE_D7761979-GO_坪山沙新路四巷 |  | Radio Site | GO_S_FE_D7761979 | GO_坪山沙新路四巷_1 | GO_S_FE_D7761979-GO_坪山沙新路四巷 | 675841980 |  |  | Shenzhen | China | Draft |  | 22.692 | 22'41'31' | 114.3596 | 114'21'34'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-28 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550617 |  | 675861331 | Started | 50125271-GO_坪山金碧路419-3号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762009-GO_坪山金碧路419-3号\GO_S_FE_D7762009-GO_坪山金碧路419-3号 |  | Radio Site | GO_S_FE_D7762009 | GO_坪山金碧路419-3号_1 | GO_S_FE_D7762009-GO_坪山金碧路419-3号 | 675841988 |  |  | Shenzhen | China | Draft |  | 22.6745 | 22'40'28' | 114.2899 | 114'17'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-09 | 2020-10-09 | China | China Telecom Guangdong | Issued | China | 3550618 |  | 675861340 | Started | 50125271-GO_坪山建业路东三巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762046-GO_坪山建业路东三巷\GO_S_FE_D7762046-GO_坪山建业路东三巷 |  | Radio Site | GO_S_FE_D7762046 | GO_坪山建业路东三巷_1 | GO_S_FE_D7762046-GO_坪山建业路东三巷 | 675841989 |  |  | Shenzhen | China | Draft |  | 22.7029 | 22'42'10' | 114.3204 | 114'19'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-26 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550619 |  | 675861361 | Started | 50125271-GO_坪山新屋村26号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761969-GO_坪山新屋村26号\GO_S_FE_D7761969-GO_坪山新屋村26号 |  | Radio Site | GO_S_FE_D7761969 | GO_坪山新屋村26号_1 | GO_S_FE_D7761969-GO_坪山新屋村26号 | 675841991 |  |  | Shenzhen | China | Draft |  | 22.6779 | 22'40'41' | 114.3099 | 114'18'35'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-30 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550620 |  | 675861366 | Started | 50125271-GO_坪山飞西鹅地-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761952-GO_坪山飞西鹅地\GO_S_FE_D7761952-GO_坪山飞西鹅地 |  | Radio Site | GO_S_FE_D7761952 | GO_坪山飞西鹅地_1 | GO_S_FE_D7761952-GO_坪山飞西鹅地 | 675841990 |  |  | Shenzhen | China | Draft |  | 22.7001 | 22'42'0' | 114.3332 | 114'19'59'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-14 | 2021-01-14 | China | China Telecom Guangdong | Issued | China | 3550621 |  | 675861382 | Started | 50125271-GO_坑梓秀新新村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762051-GO_坑梓秀新新村\GO_S_FE_D7762051-GO_坑梓秀新新村 |  | Radio Site | GO_S_FE_D7762051 | GO_坑梓秀新新村_1 | GO_S_FE_D7762051-GO_坑梓秀新新村 | 675841993 |  |  | Shenzhen | China | Draft |  | 22.7573 | 22'45'26' | 114.3724 | 114'22'20'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-30 | 2020-09-27 | China | China Telecom Guangdong | Issued | China | 3550622 |  | 675861414 | Started | 50125271-GO_坪山金碧路519号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761999-GO_坪山金碧路519号\GO_S_FE_D7761999-GO_坪山金碧路519号 |  | Radio Site | GO_S_FE_D7761999 | GO_坪山金碧路519号_1 | GO_S_FE_D7761999-GO_坪山金碧路519号 | 675841992 |  |  | Shenzhen | China | Draft |  | 22.6709 | 22'40'15' | 114.2811 | 114'16'51'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-29 | 2021-03-30 | China | China Telecom Guangdong | Issued | China | 3550623 |  | 675861423 | Started | 50125271-GO_坑梓龙湾路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762050-GO_坑梓龙湾路\GO_S_FE_D7762050-GO_坑梓龙湾路 |  | Radio Site | GO_S_FE_D7762050 | GO_坑梓龙湾路_1 | GO_S_FE_D7762050-GO_坑梓龙湾路 | 675842001 |  |  | Shenzhen | China | Draft |  | 22.7571 | 22'45'26' | 114.3671 | 114'22'1'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-24 | 2021-03-29 | China | China Telecom Guangdong | Issued | China | 3550625 |  | 675861439 | Started | 50125271-GO_坪山华瀚科技-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761988-GO_坪山华瀚科技\GO_S_FE_D7761988-GO_坪山华瀚科技 |  | Radio Site | GO_S_FE_D7761988 | GO_坪山华瀚科技_1 | GO_S_FE_D7761988-GO_坪山华瀚科技 | 675842002 |  |  | Shenzhen | China | Draft |  | 22.7026 | 22'42'9' | 114.3482 | 114'20'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-19 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550626 |  | 675861451 | Started | 50125271-GO_坪山矮岭三巷8号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762027-GO_坪山矮岭三巷8号\GO_S_FE_D7762027-GO_坪山矮岭三巷8号 |  | Radio Site | GO_S_FE_D7762027 | GO_坪山矮岭三巷8号_1 | GO_S_FE_D7762027-GO_坪山矮岭三巷8号 | 675842003 |  |  | Shenzhen | China | Draft |  | 22.6954 | 22'41'44' | 114.3953 | 114'23'43'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-01 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550627 |  | 675861456 | Started | 50125271-GO_坪山坪葵路243号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762030-GO_坪山坪葵路243号\GO_S_FE_D7762030-GO_坪山坪葵路243号 |  | Radio Site | GO_S_FE_D7762030 | GO_坪山坪葵路243号_1 | GO_S_FE_D7762030-GO_坪山坪葵路243号 | 675842011 |  |  | Shenzhen | China | Draft |  | 22.6853 | 22'41'7' | 114.38 | 114'22'48'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-20 | 2021-03-26 | China | China Telecom Guangdong | Issued | China | 3550628 |  | 675861457 | Started | 50125271-GO_坪山深圳监狱办公楼-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762002-GO_坪山深圳监狱办公楼\GO_S_FE_D7762002-GO_坪山深圳监狱办公楼 |  | Radio Site | GO_S_FE_D7762002 | GO_坪山深圳监狱办公楼_1 | GO_S_FE_D7762002-GO_坪山深圳监狱办公楼 | 675842004 |  |  | Shenzhen | China | Draft |  | 22.6897 | 22'41'23' | 114.3956 | 114'23'44'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-03 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550629 |  | 675861547 | Started | 50125271-GO_坪山石井望牛岗-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761958-GO_坪山石井望牛岗\GO_S_FE_D7761958-GO_坪山石井望牛岗 |  | Radio Site | GO_S_FE_D7761958 | GO_坪山石井望牛岗_1 | GO_S_FE_D7761958-GO_坪山石井望牛岗 | 675842017 |  |  | Shenzhen | China | Draft |  | 22.7089 | 22'42'32' | 114.3715 | 114'22'17'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-30 | 2021-02-02 | China | China Telecom Guangdong | Issued | China | 3550630 |  | 675861552 | Started | 50125271-GO_坪山黄一村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762054-GO_坪山黄一村\GO_S_FE_D7762054-GO_坪山黄一村 |  | Radio Site | GO_S_FE_D7762054 | GO_坪山黄一村_1 | GO_S_FE_D7762054-GO_坪山黄一村 | 675842026 |  |  | Shenzhen | China | Draft |  | 22.663 | 22'39'47' | 114.314 | 114'18'50'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-05-15 | 2020-09-23 | China | China Telecom Guangdong | Issued | China | 3550634 |  | 675861571 | Started | 50125271-GO_坝核路4-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762008-GO_坝核路4\GO_S_FE_D7762008-GO_坝核路4 |  | Radio Site | GO_S_FE_D7762008 | GO_坝核路4_1 | GO_S_FE_D7762008-GO_坝核路4 | 675842013 |  |  | Shenzhen | China | Draft |  | 22.648 | 22'38'53' | 114.5199 | 114'31'11'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-24 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550635 |  | 675861572 | Started | 50125271-GO_坪山华美六巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761975-GO_坪山华美六巷\GO_S_FE_D7761975-GO_坪山华美六巷 |  | Radio Site | GO_S_FE_D7761975 | GO_坪山华美六巷_1 | GO_S_FE_D7761975-GO_坪山华美六巷 | 675842025 |  |  | Shenzhen | China | Draft |  | 22.6923 | 22'41'32' | 114.3287 | 114'19'43'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-24 | 2020-10-13 | China | China Telecom Guangdong | Issued | China | 3550636 |  | 675861574 | Started | 50125271-GO_坪山汤坑新村十二巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762001-GO_坪山汤坑新村十二巷\GO_S_FE_D7762001-GO_坪山汤坑新村十二巷 |  | Radio Site | GO_S_FE_D7762001 | GO_坪山汤坑新村十二巷_1 | GO_S_FE_D7762001-GO_坪山汤坑新村十二巷 | 675842014 |  |  | Shenzhen | China | Draft |  | 22.6711 | 22'40'16' | 114.3067 | 114'18'24'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-30 | 2021-04-16 | China | China Telecom Guangdong | Issued | China | 3550637 |  | 675861569 | Started | 50125271-GO_坪山兰亭科技公司-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761977-GO_坪山兰亭科技公司\GO_S_FE_D7761977-GO_坪山兰亭科技公司 |  | Radio Site | GO_S_FE_D7761977 | GO_坪山兰亭科技公司_1 | GO_S_FE_D7761977-GO_坪山兰亭科技公司 | 675842016 |  |  | Shenzhen | China | Draft |  | 22.721 | 22'43'15' | 114.3953 | 114'23'43'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-26 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550638 |  | 675861657 | Started | 50125271-GO_坪山中兴东七巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761961-GO_坪山中兴东七巷\GO_S_FE_D7761961-GO_坪山中兴东七巷 |  | Radio Site | GO_S_FE_D7761961 | GO_坪山中兴东七巷_1 | GO_S_FE_D7761961-GO_坪山中兴东七巷 | 675842032 |  |  | Shenzhen | China | Draft |  | 22.6886 | 22'41'19' | 114.3419 | 114'20'30'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-24 | 2021-01-14 | China | China Telecom Guangdong | Issued | China | 3550639 |  | 675861656 | Started | 50125271-GO_坑梓金沙工业-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762021-GO_坑梓金沙工业\GO_S_FE_D7762021-GO_坑梓金沙工业 |  | Radio Site | GO_S_FE_D7762021 | GO_坑梓金沙工业_1 | GO_S_FE_D7762021-GO_坑梓金沙工业 | 675842028 |  |  | Shenzhen | China | Draft |  | 22.7531 | 22'45'11' | 114.3951 | 114'23'42'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-12 | 2021-01-14 | China | China Telecom Guangdong | Issued | China | 3550640 |  | 675861663 | Started | 50125271-GO_坪山昌盛南-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762043-GO_坪山昌盛南\GO_S_FE_D7762043-GO_坪山昌盛南 |  | Radio Site | GO_S_FE_D7762043 | GO_坪山昌盛南_1 | GO_S_FE_D7762043-GO_坪山昌盛南 | 675842029 |  |  | Shenzhen | China | Draft |  | 22.6956 | 22'41'44' | 114.3303 | 114'19'49'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-21 | 2020-09-25 | China | China Telecom Guangdong | Issued | China | 3550642 |  | 675861709 | Started | 50125271-GO_坪山立新西路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762053-GO_坪山立新西路\GO_S_FE_D7762053-GO_坪山立新西路 |  | Radio Site | GO_S_FE_D7762053 | GO_坪山立新西路_1 | GO_S_FE_D7762053-GO_坪山立新西路 | 675842039 |  |  | Shenzhen | China | Draft |  | 22.6936 | 22'41'37' | 114.3453 | 114'20'43'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-01-02 | 2020-09-28 | China | China Telecom Guangdong | Issued | China | 3550643 |  | 675861708 | Started | 50125271-GO_坪山金牛路东-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762004-GO_坪山金牛路东\GO_S_FE_D7762004-GO_坪山金牛路东 |  | Radio Site | GO_S_FE_D7762004 | GO_坪山金牛路东_1 | GO_S_FE_D7762004-GO_坪山金牛路东 | 675842036 |  |  | Shenzhen | China | Draft |  | 22.7107 | 22'42'39' | 114.3815 | 114'22'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-29 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550644 |  | 675861710 | Started | 50125271-GO_坪山浪尾路39号东-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761967-GO_坪山浪尾路39号东\GO_S_FE_D7761967-GO_坪山浪尾路39号东 |  | Radio Site | GO_S_FE_D7761967 | GO_坪山浪尾路39号东_1 | GO_S_FE_D7761967-GO_坪山浪尾路39号东 | 675842037 |  |  | Shenzhen | China | Draft |  | 22.6927 | 22'41'34' | 114.3255 | 114'19'31'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-06-23 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550645 |  | 675861793 | Started | 50125271-GO_坪山青兰一路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762048-GO_坪山青兰一路\GO_S_FE_D7762048-GO_坪山青兰一路 |  | Radio Site | GO_S_FE_D7762048 | GO_坪山青兰一路_1 | GO_S_FE_D7762048-GO_坪山青兰一路 | 675842040 |  |  | Shenzhen | China | Draft |  | 22.7252 | 22'43'31' | 114.3888 | 114'23'19'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-29 | 2021-03-21 | China | China Telecom Guangdong | Issued | China | 3550646 |  | 675861797 | Started | 50125271-GO_坪山艾迪斯-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762057-GO_坪山艾迪斯\GO_S_FE_D7762057-GO_坪山艾迪斯 |  | Radio Site | GO_S_FE_D7762057 | GO_坪山艾迪斯_1 | GO_S_FE_D7762057-GO_坪山艾迪斯 | 675842041 |  |  | Shenzhen | China | Draft |  | 22.6884 | 22'41'18' | 114.3137 | 114'18'49'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-02 | 2021-04-17 | China | China Telecom Guangdong | Issued | China | 3550647 |  | 675861802 | Started | 50125271-GO_横坪公路4-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762033-GO_横坪公路4\GO_S_FE_D7762033-GO_横坪公路4 |  | Radio Site | GO_S_FE_D7762033 | GO_横坪公路4_1 | GO_S_FE_D7762033-GO_横坪公路4 | 675842042 |  |  | Shenzhen | China | Draft |  | 22.6894 | 22'41'22' | 114.3859 | 114'23'9'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-15 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550648 |  | 675861816 | Started | 50125271-GO_坪山竹青路三巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762062-GO_坪山竹青路三巷\GO_S_FE_D7762062-GO_坪山竹青路三巷 |  | Radio Site | GO_S_FE_D7762062 | GO_坪山竹青路三巷_1 | GO_S_FE_D7762062-GO_坪山竹青路三巷 | 675842043 |  |  | Shenzhen | China | Draft |  | 22.6931 | 22'41'35' | 114.3737 | 114'22'25'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-17 | 2020-10-19 | China | China Telecom Guangdong | Issued | China | 3550650 |  | 675861913 | Started | 50125271-GO_坪山汤坑二路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762041-GO_坪山汤坑二路\GO_S_FE_D7762041-GO_坪山汤坑二路 |  | Radio Site | GO_S_FE_D7762041 | GO_坪山汤坑二路_1 | GO_S_FE_D7762041-GO_坪山汤坑二路 | 675842052 |  |  | Shenzhen | China | Draft |  | 22.6672 | 22'40'2' | 114.3024 | 114'18'8'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-26 | 2020-09-29 | China | China Telecom Guangdong | Issued | China | 3550651 |  | 675861925 | Started | 50125271-GO_坪山宝捷讯宿舍-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762061-GO_坪山宝捷讯宿舍\GO_S_FE_D7762061-GO_坪山宝捷讯宿舍 |  | Radio Site | GO_S_FE_D7762061 | GO_坪山宝捷讯宿舍_1 | GO_S_FE_D7762061-GO_坪山宝捷讯宿舍 | 675842058 |  |  | Shenzhen | China | Draft |  | 22.6942 | 22'41'39' | 114.2899 | 114'17'23'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-22 | 2021-03-28 | China | China Telecom Guangdong | Issued | China | 3550652 |  | 675861957 | Started | 50125271-GO_坪山创景路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762056-GO_坪山创景路\GO_S_FE_D7762056-GO_坪山创景路 |  | Radio Site | GO_S_FE_D7762056 | GO_坪山创景路_1 | GO_S_FE_D7762056-GO_坪山创景路 | 675842059 |  |  | Shenzhen | China | Draft |  | 22.7063 | 22'42'23' | 114.3935 | 114'23'36'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-03-17 | 2021-04-13 | China | China Telecom Guangdong | Issued | China | 3550653 |  | 675861958 | Started | 50125271-GO_坪山洋母帐六巷-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762065-GO_坪山洋母帐六巷\GO_S_FE_D7762065-GO_坪山洋母帐六巷 |  | Radio Site | GO_S_FE_D7762065 | GO_坪山洋母帐六巷_1 | GO_S_FE_D7762065-GO_坪山洋母帐六巷 | 675842060 |  |  | Shenzhen | China | Draft |  | 22.6899 | 22'41'24' | 114.3309 | 114'19'51'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-11-25 | 2021-04-17 | China | China Telecom Guangdong | Issued | China | 3550654 |  | 675862917 | Started | 50125271-GO_坪山宝龙六路5号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761963-GO_坪山宝龙六路5号\GO_S_FE_D7761963-GO_坪山宝龙六路5号 |  | Radio Site | GO_S_FE_D7761963 | GO_坪山宝龙六路5号_1 | GO_S_FE_D7761963-GO_坪山宝龙六路5号 | 675842061 |  |  | Shenzhen | China | Draft |  | 22.6958 | 22'41'45' | 114.3009 | 114'18'3'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-10-31 | 2020-09-27 | China | China Telecom Guangdong | Issued | China | 3550655 |  | 675862922 | Started | 50125271-GO_坪山新龙路18号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7761964-GO_坪山新龙路18号\GO_S_FE_D7761964-GO_坪山新龙路18号 |  | Radio Site | GO_S_FE_D7761964 | GO_坪山新龙路18号_1 | GO_S_FE_D7761964-GO_坪山新龙路18号 | 675842062 |  |  | Shenzhen | China | Draft |  | 22.6826 | 22'40'57' | 114.3151 | 114'18'54'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2019-12-28 | 2020-09-28 | China | China Telecom Guangdong | Issued | China | 3550656 |  | 675863025 | Started | 50125271-GO_坪山金田路128号南-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762058-GO_坪山金田路128号南\GO_S_FE_D7762058-GO_坪山金田路128号南 |  | Radio Site | GO_S_FE_D7762058 | GO_坪山金田路128号南_1 | GO_S_FE_D7762058-GO_坪山金田路128号南 | 675842065 |  |  | Shenzhen | China | Draft |  | 22.6945 | 22'41'40' | 114.3844 | 114'23'3'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-04-09 | 2021-03-31 | China | China Telecom Guangdong | Issued | China | 3550657 |  | 675863031 | Started | 50125271-GO_葵涌大湾一舍度假酒店-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762060-GO_葵涌大湾一舍度假酒店\GO_S_FE_D7762060-GO_葵涌大湾一舍度假酒店 |  | Radio Site | GO_S_FE_D7762060 | GO_葵涌大湾一舍度假酒店_1 | GO_S_FE_D7762060-GO_葵涌大湾一舍度假酒店 | 675842064 |  |  | Shenzhen | China | Draft |  | 22.5957 | 22'35'45' | 114.4307 | 114'25'50'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-09 | 2020-09-30 | China | China Telecom Guangdong | Issued | China | 3550658 |  | 675863037 | Started | 50125271-GO_坪山高级中学北-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762035-GO_坪山高级中学北\GO_S_FE_D7762035-GO_坪山高级中学北 |  | Radio Site | GO_S_FE_D7762035 | GO_坪山高级中学北_1 | GO_S_FE_D7762035-GO_坪山高级中学北 | 675842063 |  |  | Shenzhen | China | Draft |  | 22.688 | 22'41'17' | 114.323 | 114'19'22'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2020-07-13 | 2020-10-20 | China | China Telecom Guangdong | Issued | China | 3550659 |  | 675863039 | Started | 50125271-GO_坪山飞东新村-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GO_S_FE_D7762063-GO_坪山飞东新村\GO_S_FE_D7762063-GO_坪山飞东新村 |  | Radio Site | GO_S_FE_D7762063 | GO_坪山飞东新村_1 | GO_S_FE_D7762063-GO_坪山飞东新村 | 675842067 |  |  | Shenzhen | China | Draft |  | 22.7017 | 22'42'6' | 114.3379 | 114'20'16'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-15 | China | China Telecom Guangdong | Issued | China | 3819436 |  | 745819936 | Started | 50125271-GO_坪山坪马线公路2-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_01-GO_坪山坪马线公路2\GD_NO_CP0_01-GO_坪山坪马线公路2 |  | Radio Site | GD_NO_CP0_01 | GO_坪山坪马线公路2_1 | GD_NO_CP0_01-GO_坪山坪马线公路2 | 745806238 |  |  | Shenzhen | China | Draft |  | 22.645 | 22'38'42' | 114.3395 | 114'20'22'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-01 | China | China Telecom Guangdong | Issued | China | 3819437 |  | 745819942 | Started | 50125271-GO_坪山大虹路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_08-GO_坪山大虹路\GD_NO_CP0_08-GO_坪山大虹路 |  | Radio Site | GD_NO_CP0_08 | GO_坪山大虹路_1 | GD_NO_CP0_08-GO_坪山大虹路 | 745806255 |  |  | Shenzhen | China | Draft |  | 22.6903 | 22'41'25' | 114.3339 | 114'20'2'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-24 | China | China Telecom Guangdong | Issued | China | 3819438 |  | 745819966 | Started | 50125271-GO_坑梓东联村3号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_07-GO_坑梓东联村3号\GD_NO_CP0_07-GO_坑梓东联村3号 |  | Radio Site | GD_NO_CP0_07 | GO_坑梓东联村3号_1 | GD_NO_CP0_07-GO_坑梓东联村3号 | 745806239 |  |  | Shenzhen | China | Draft |  | 22.7411 | 22'44'28' | 114.3842 | 114'23'3'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-18 | China | China Telecom Guangdong | Issued | China | 3819439 |  | 745819946 | Started | 50125271-GO_坪山谷仓吓路57号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_03-GO_坪山谷仓吓路57号\GD_NO_CP0_03-GO_坪山谷仓吓路57号 |  | Radio Site | GD_NO_CP0_03 | GO_坪山谷仓吓路57号_1 | GD_NO_CP0_03-GO_坪山谷仓吓路57号 | 745806249 |  |  | Shenzhen | China | Draft |  | 22.6847 | 22'41'5' | 114.3612 | 114'21'40'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-18 | China | China Telecom Guangdong | Issued | China | 3819440 |  | 745819947 | Started | 50125271-GO_葵涌污水处理厂-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_14-GO_葵涌污水处理厂\GD_NO_CP0_14-GO_葵涌污水处理厂 |  | Radio Site | GD_NO_CP0_14 | GO_葵涌污水处理厂_1 | GD_NO_CP0_14-GO_葵涌污水处理厂 | 745806215 |  |  | Shenzhen | China | Draft |  | 22.6142 | 22'36'51' | 114.4151 | 114'24'54'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-18 | China | China Telecom Guangdong | Issued | China | 3819442 |  | 745819938 | Started | 50125271-GO_坪山马鞍岭西区-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_13-GO_坪山马鞍岭西区\GD_NO_CP0_13-GO_坪山马鞍岭西区 |  | Radio Site | GD_NO_CP0_13 | GO_坪山马鞍岭西区_1 | GD_NO_CP0_13-GO_坪山马鞍岭西区 | 745806195 |  |  | Shenzhen | China | Draft |  | 22.7049 | 22'42'18' | 114.3978 | 114'23'51'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-17 | China | China Telecom Guangdong | Issued | China | 3819448 |  | 745820009 | Started | 50125271-GO_坪山澳昌路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_12-GO_坪山澳昌路\GD_NO_CP0_12-GO_坪山澳昌路 |  | Radio Site | GD_NO_CP0_12 | GO_坪山澳昌路_1 | GD_NO_CP0_12-GO_坪山澳昌路 | 745806205 |  |  | Shenzhen | China | Draft |  | 22.685 | 22'41'6' | 114.3139 | 114'18'50'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-02 | China | China Telecom Guangdong | Issued | China | 3819451 |  | 745819965 | Started | 50125271-GO_坪山坪慧路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_16-GO_坪山坪慧路\GD_NO_CP0_16-GO_坪山坪慧路 |  | Radio Site | GD_NO_CP0_16 | GO_坪山坪慧路_1 | GD_NO_CP0_16-GO_坪山坪慧路 | 745806243 |  |  | Shenzhen | China | Draft |  | 22.7038 | 22'42'14' | 114.3435 | 114'20'36'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-03 | China | China Telecom Guangdong | Issued | China | 3819456 |  | 745819987 | Started | 50125271-GO_坪山坪环工业城87栋-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_09-GO_坪山坪环工业城87栋\GD_NO_CP0_09-GO_坪山坪环工业城87栋 |  | Radio Site | GD_NO_CP0_09 | GO_坪山坪环工业城87栋_1 | GD_NO_CP0_09-GO_坪山坪环工业城87栋 | 745806185 |  |  | Shenzhen | China | Draft |  | 22.6794 | 22'40'46' | 114.34 | 114'20'24'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-11 | China | China Telecom Guangdong | Issued | China | 3819457 |  | 745819959 | Started | 50125271-GO_坪山金地三巷3号-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_15-GO_坪山金地三巷3号\GD_NO_CP0_15-GO_坪山金地三巷3号 |  | Radio Site | GD_NO_CP0_15 | GO_坪山金地三巷3号_1 | GD_NO_CP0_15-GO_坪山金地三巷3号 | 745806235 |  |  | Shenzhen | China | Draft |  | 22.6885 | 22'41'18' | 114.3337 | 114'20'1'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-03 | China | China Telecom Guangdong | Issued | China | 3819461 |  | 745820022 | Started | 50125271-GO_大鹏永进达F3栋改-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_02-GO_大鹏永进达F3栋改\GD_NO_CP0_02-GO_大鹏永进达F3栋改 |  | Radio Site | GD_NO_CP0_02 | GO_大鹏永进达F3栋改_1 | GD_NO_CP0_02-GO_大鹏永进达F3栋改 | 745806236 |  |  | Shenzhen | China | Draft |  | 22.5991 | 22'35'57' | 114.4933 | 114'29'36'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-03 | China | China Telecom Guangdong | Issued | China | 3819463 |  | 745819990 | Started | 50125271-GO_坪山龙坪路-SV_MACRO | 50125271 | SV_MACRO | 50128903 | \Locations\GD_NO_CP0_05-GO_坪山龙坪路\GD_NO_CP0_05-GO_坪山龙坪路 |  | Radio Site | GD_NO_CP0_05 | GO_坪山龙坪路_1 | GD_NO_CP0_05-GO_坪山龙坪路 | 745806250 |  |  | Shenzhen | China | Draft |  | 22.693 | 22'41'35' | 114.3538 | 114'21'13'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-04-03 | China | China Telecom Guangdong | Issued | China | 3819464 |  | 745820037 | Started | 50125271-GO_坪山老围四巷5号-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\GD_NO_CP0_11-GO_坪山老围四巷5号\GD_NO_CP0_11-GO_坪山老围四巷5号 |  | Radio Site | GD_NO_CP0_11 | GO_坪山老围四巷5号_1 | GD_NO_CP0_11-GO_坪山老围四巷5号 | 745806247 |  |  | Shenzhen | China | Draft |  | 22.6872 | 22'41'14' | 114.3314 | 114'19'53'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-18 | China | China Telecom Guangdong | Issued | China | 3819468 |  | 745820027 | Started | 50125271-GO_坪山肯发科技-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\GD_NO_CP0_06-GO_坪山肯发科技\GD_NO_CP0_06-GO_坪山肯发科技 |  | Radio Site | GD_NO_CP0_06 | GO_坪山肯发科技_1 | GD_NO_CP0_06-GO_坪山肯发科技 | 745806201 |  |  | Shenzhen | China | Draft |  | 22.7174 | 22'43'3' | 114.3667 | 114'22'0'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-18 | China | China Telecom Guangdong | Issued | China | 3819471 |  | 745820062 | Started | 50125271-GO_坪山马峦工业园21栋-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\GD_NO_CP0_10-GO_坪山马峦工业园21栋\GD_NO_CP0_10-GO_坪山马峦工业园21栋 |  | Radio Site | GD_NO_CP0_10 | GO_坪山马峦工业园21栋_1 | GD_NO_CP0_10-GO_坪山马峦工业园21栋 | 745806240 |  |  | Shenzhen | China | Draft |  | 22.6675 | 22'40'3' | 114.298 | 114'17'52'
1010960 | CN_CT_COMGZ_G_D_5G_CP0_CC_50125271 | 675858325 | 2000-01-01 | 2021-03-01 | China | China Telecom Guangdong | Issued | China | 3819480 |  | 745820083 | Started | 50125271-GO_坪山沙湖村-SV_MACRO | 50125271 | SV_MACRO |  | \Locations\GD_NO_CP0_04-GO_坪山沙湖村\GD_NO_CP0_04-GO_坪山沙湖村 |  | Radio Site | GD_NO_CP0_04 | GO_坪山沙湖村_1 | GD_NO_CP0_04-GO_坪山沙湖村 | 745806234 |  |  | Shenzhen | China | Draft |  | 22.6807 | 22'40'51' | 114.312 | 114'18'43'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244886 |  | 883892937 | Started | 50139878-GS_MZDP_京华花园室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_23-GS_MZDP_京华花园室分\GD_CP4_23-GS_MZDP_京华花园室分 |  | Radio Site | GD_CP4_23 | GS_MZDP_京华花园室分_1 | GD_CP4_23-GS_MZDP_京华花园室分 | 883876077 |  |  | Meizhou | China | Draft |  | 42.1235 | 42'7'24' | 136.7824 | 136'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244887 |  | 883892938 | Started | 50139878-GS_MZDP_绣山水城室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_09-GS_MZDP_绣山水城室分\GD_CP4_09-GS_MZDP_绣山水城室分 |  | Radio Site | GD_CP4_09 | GS_MZDP_绣山水城室分_1 | GD_CP4_09-GS_MZDP_绣山水城室分 | 883876175 |  |  | Meizhou | China | Draft |  | 28.1235 | 28'7'24' | 122.7824 | 122'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244888 |  | 883892949 | Started | 50139878-GS_MZDP_龙湾国际室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_20-GS_MZDP_龙湾国际室分\GD_CP4_20-GS_MZDP_龙湾国际室分 |  | Radio Site | GD_CP4_20 | GS_MZDP_龙湾国际室分_1 | GD_CP4_20-GS_MZDP_龙湾国际室分 | 883876198 |  |  | Meizhou | China | Draft |  | 39.1235 | 39'7'24' | 133.7824 | 133'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244889 |  | 883892948 | Started | 50139878-GS_MZDP_翰林华府二期室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_01-GS_MZDP_翰林华府二期室分\GD_CP4_01-GS_MZDP_翰林华府二期室分 |  | Radio Site | GD_CP4_01 | GS_MZDP_翰林华府二期室分_1 | GD_CP4_01-GS_MZDP_翰林华府二期室分 | 883876176 |  |  | Meizhou | China | Draft |  | 20.1235 | 20'7'24' | 114.7824 | 114'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244890 |  | 883892950 | Started | 50139878-GS_MZDP_翰林华府室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_22-GS_MZDP_翰林华府室分\GD_CP4_22-GS_MZDP_翰林华府室分 |  | Radio Site | GD_CP4_22 | GS_MZDP_翰林华府室分_1 | GD_CP4_22-GS_MZDP_翰林华府室分 | 883876163 |  |  | Meizhou | China | Draft |  | 41.1235 | 41'7'24' | 135.7824 | 135'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244891 |  | 883892962 | Started | 50139878-GS_MZDP_龙湾国际室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_14-GS_MZDP_龙湾国际室分\GD_CP4_14-GS_MZDP_龙湾国际室分 |  | Radio Site | GD_CP4_14 | GS_MZDP_龙湾国际室分_2 | GD_CP4_14-GS_MZDP_龙湾国际室分 | 883876168 |  |  | Meizhou | China | Draft |  | 33.1235 | 33'7'24' | 127.7824 | 127'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244892 |  | 883892961 | Started | 50139878-GS_MZDP_海棠四季室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_11-GS_MZDP_海棠四季室分\GD_CP4_11-GS_MZDP_海棠四季室分 |  | Radio Site | GD_CP4_11 | GS_MZDP_海棠四季室分_1 | GD_CP4_11-GS_MZDP_海棠四季室分 | 883876197 |  |  | Meizhou | China | Draft |  | 30.1235 | 30'7'24' | 124.7824 | 124'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244893 |  | 883892969 | Started | 50139878-GS_MZDP_东城上品室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_17-GS_MZDP_东城上品室分\GD_CP4_17-GS_MZDP_东城上品室分 |  | Radio Site | GD_CP4_17 | GS_MZDP_东城上品室分_1 | GD_CP4_17-GS_MZDP_东城上品室分 | 883876074 |  |  | Meizhou | China | Draft |  | 36.1235 | 36'7'24' | 130.7824 | 130'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244894 |  | 883892968 | Started | 50139878-GS_MZDP_幸福城室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_06-GS_MZDP_幸福城室分\GD_CP4_06-GS_MZDP_幸福城室分 |  | Radio Site | GD_CP4_06 | GS_MZDP_幸福城室分_1 | GD_CP4_06-GS_MZDP_幸福城室分 | 883876083 |  |  | Meizhou | China | Draft |  | 25.1235 | 25'7'24' | 119.7824 | 119'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244895 |  | 883892972 | Started | 50139878-GS_MZJL_碧桂园三期室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_21-GS_MZJL_碧桂园三期室分\GD_CP4_21-GS_MZJL_碧桂园三期室分 |  | Radio Site | GD_CP4_21 | GS_MZJL_碧桂园三期室分_1 | GD_CP4_21-GS_MZJL_碧桂园三期室分 | 883876177 |  |  | Meizhou | China | Draft |  | 40.1235 | 40'7'24' | 134.7824 | 134'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244896 |  | 883892978 | Started | 50139878-GS_MZJL_新世纪二期室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_03-GS_MZJL_新世纪二期室分\GD_CP4_03-GS_MZJL_新世纪二期室分 |  | Radio Site | GD_CP4_03 | GS_MZJL_新世纪二期室分_1 | GD_CP4_03-GS_MZJL_新世纪二期室分 | 883876084 |  |  | Meizhou | China | Draft |  | 22.1235 | 22'7'24' | 116.7824 | 116'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244897 |  | 883892980 | Started | 50139878-GS_MZJL_迎宾馆室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_05-GS_MZJL_迎宾馆室分\GD_CP4_05-GS_MZJL_迎宾馆室分 |  | Radio Site | GD_CP4_05 | GS_MZJL_迎宾馆室分_1 | GD_CP4_05-GS_MZJL_迎宾馆室分 | 883876216 |  |  | Meizhou | China | Draft |  | 24.1235 | 24'7'24' | 118.7824 | 118'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244898 |  | 883892990 | Started | 50139878-GS_MZJL_香榭丽湾小区室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_24-GS_MZJL_香榭丽湾小区室分\GD_CP4_24-GS_MZJL_香榭丽湾小区室分 |  | Radio Site | GD_CP4_24 | GS_MZJL_香榭丽湾小区室分_1 | GD_CP4_24-GS_MZJL_香榭丽湾小区室分 | 883876215 |  |  | Meizhou | China | Draft |  | 43.1235 | 43'7'24' | 137.7824 | 137'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244899 |  | 883892994 | Started | 50139878-GS_MZJL_新公安大楼室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_33-GS_MZJL_新公安大楼室分\GD_CP4_33-GS_MZJL_新公安大楼室分 |  | Radio Site | GD_CP4_33 | GS_MZJL_新公安大楼室分_1 | GD_CP4_33-GS_MZJL_新公安大楼室分 | 883876180 |  |  | Meizhou | China | Draft |  | 52.1235 | 52'7'24' | 146.7824 | 146'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244900 |  | 883892996 | Started | 50139878-GS_MZJL_喜多多超市室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_15-GS_MZJL_喜多多超市室分\GD_CP4_15-GS_MZJL_喜多多超市室分 |  | Radio Site | GD_CP4_15 | GS_MZJL_喜多多超市室分_1 | GD_CP4_15-GS_MZJL_喜多多超市室分 | 883876165 |  |  | Meizhou | China | Draft |  | 34.1235 | 34'7'24' | 128.7824 | 128'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244901 |  | 883893020 | Started | 50139878-GO_JYPN_普宁中华新城_RRU_N21_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_37-GO_JYPN_普宁中华新城_RRU_N21_2\GD_CP4_37-GO_JYPN_普宁中华新城_RRU_N21_2 |  | Radio Site | GD_CP4_37 | GO_JYPN_普宁中华新城_RRU_N21_2_1 | GD_CP4_37-GO_JYPN_普宁中华新城_RRU_N21_2 | 883876189 |  |  | Jieyang | China | Draft |  | 56.1235 | 56'7'24' | 150.7824 | 150'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244902 |  | 883893033 | Started | 50139878-GO_JYPN_普宁御景城一期_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_35-GO_JYPN_普宁御景城一期_RRU_N21\GD_CP4_35-GO_JYPN_普宁御景城一期_RRU_N21 |  | Radio Site | GD_CP4_35 | GO_JYPN_普宁御景城一期_RRU_N21_1 | GD_CP4_35-GO_JYPN_普宁御景城一期_RRU_N21 | 883876193 |  |  | Jieyang | China | Draft |  | 54.1235 | 54'7'24' | 148.7824 | 148'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244903 |  | 883893037 | Started | 50139878-GO_JYPN_普宁万泰城二期_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_31-GO_JYPN_普宁万泰城二期_RRU_N21\GD_CP4_31-GO_JYPN_普宁万泰城二期_RRU_N21 |  | Radio Site | GD_CP4_31 | GO_JYPN_普宁万泰城二期_RRU_N21_1 | GD_CP4_31-GO_JYPN_普宁万泰城二期_RRU_N21 | 883876182 |  |  | Jieyang | China | Draft |  | 50.1235 | 50'7'24' | 144.7824 | 144'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244904 |  | 883893036 | Started | 50139878-GO_JYPN_普宁万泰城一期_RRU_N21_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_30-GO_JYPN_普宁万泰城一期_RRU_N21_2\GD_CP4_30-GO_JYPN_普宁万泰城一期_RRU_N21_2 |  | Radio Site | GD_CP4_30 | GO_JYPN_普宁万泰城一期_RRU_N21_2_1 | GD_CP4_30-GO_JYPN_普宁万泰城一期_RRU_N21_2 | 883876191 |  |  | Jieyang | China | Draft |  | 49.1235 | 49'7'24' | 143.7824 | 143'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244905 |  | 883893035 | Started | 50139878-GO_JYPN_普宁江南新城怡景湾_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_49-GO_JYPN_普宁江南新城怡景湾_RRU_N21\GD_CP4_49-GO_JYPN_普宁江南新城怡景湾_RRU_N21 |  | Radio Site | GD_CP4_49 | GO_JYPN_普宁江南新城怡景湾_RRU_N21_1 | GD_CP4_49-GO_JYPN_普宁江南新城怡景湾_RRU_N21 | 883876328 |  |  | Jieyang | China | Draft |  | 68.1235 | 68'7'24' | 162.7824 | 162'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244906 |  | 883893043 | Started | 50139878-GO_JYPN_普宁平安里_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_10-GO_JYPN_普宁平安里_RRU_N21\GD_CP4_10-GO_JYPN_普宁平安里_RRU_N21 |  | Radio Site | GD_CP4_10 | GO_JYPN_普宁平安里_RRU_N21_1 | GD_CP4_10-GO_JYPN_普宁平安里_RRU_N21 | 883876063 |  |  | Jieyang | China | Draft |  | 29.1235 | 29'7'24' | 123.7824 | 123'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244907 |  | 883893038 | Started | 50139878-GO_JYPN_普宁小商品城_RRU_N21_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_13-GO_JYPN_普宁小商品城_RRU_N21_2\GD_CP4_13-GO_JYPN_普宁小商品城_RRU_N21_2 |  | Radio Site | GD_CP4_13 | GO_JYPN_普宁小商品城_RRU_N21_2_1 | GD_CP4_13-GO_JYPN_普宁小商品城_RRU_N21_2 | 883876174 |  |  | Jieyang | China | Draft |  | 32.1235 | 32'7'24' | 126.7824 | 126'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244908 |  | 883893301 | Started | 50139878-GO_JYPN_普宁小商品城_RRU_N21_3-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_40-GO_JYPN_普宁小商品城_RRU_N21_3\GD_CP4_40-GO_JYPN_普宁小商品城_RRU_N21_3 |  | Radio Site | GD_CP4_40 | GO_JYPN_普宁小商品城_RRU_N21_3_1 | GD_CP4_40-GO_JYPN_普宁小商品城_RRU_N21_3 | 883876291 |  |  | Jieyang | China | Draft |  | 59.1235 | 59'7'24' | 153.7824 | 153'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244909 |  | 883893314 | Started | 50139878-GO_JYPN_普宁中信华府_RRU_N21_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_61-GO_JYPN_普宁中信华府_RRU_N21_2\GD_CP4_61-GO_JYPN_普宁中信华府_RRU_N21_2 |  | Radio Site | GD_CP4_61 | GO_JYPN_普宁中信华府_RRU_N21_2_1 | GD_CP4_61-GO_JYPN_普宁中信华府_RRU_N21_2 | 883876322 |  |  | Jieyang | China | Draft |  | 80.1235 | 80'7'24' | 174.7824 | 174'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244910 |  | 883893322 | Started | 50139878-GO_JYPN_普宁佳顺花园_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_32-GO_JYPN_普宁佳顺花园_RRU_N21\GD_CP4_32-GO_JYPN_普宁佳顺花园_RRU_N21 |  | Radio Site | GD_CP4_32 | GO_JYPN_普宁佳顺花园_RRU_N21_1 | GD_CP4_32-GO_JYPN_普宁佳顺花园_RRU_N21 | 883876200 |  |  | Jieyang | China | Draft |  | 51.1235 | 51'7'24' | 145.7824 | 145'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244911 |  | 883893364 | Started | 50139878-GO_JYPN_普宁御景城三期_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_26-GO_JYPN_普宁御景城三期_RRU_N21\GD_CP4_26-GO_JYPN_普宁御景城三期_RRU_N21 |  | Radio Site | GD_CP4_26 | GO_JYPN_普宁御景城三期_RRU_N21_1 | GD_CP4_26-GO_JYPN_普宁御景城三期_RRU_N21 | 883876166 |  |  | Jieyang | China | Draft |  | 23.3133 | 23'18'48' | 116.1594 | 116'9'33'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244912 |  | 883893366 | Started | 50139878-GO_JYPN_普宁幸福里_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_47-GO_JYPN_普宁幸福里_RRU_N21\GD_CP4_47-GO_JYPN_普宁幸福里_RRU_N21 |  | Radio Site | GD_CP4_47 | GO_JYPN_普宁幸福里_RRU_N21_1 | GD_CP4_47-GO_JYPN_普宁幸福里_RRU_N21 | 883876317 |  |  | Jieyang | China | Draft |  | 23.3001 | 23'18'0' | 116.1655 | 116'9'55'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244913 |  | 883893365 | Started | 50139878-GO_JYPN_普宁御景城二期_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_62-GO_JYPN_普宁御景城二期_RRU_N21\GD_CP4_62-GO_JYPN_普宁御景城二期_RRU_N21 |  | Radio Site | GD_CP4_62 | GO_JYPN_普宁御景城二期_RRU_N21_1 | GD_CP4_62-GO_JYPN_普宁御景城二期_RRU_N21 | 883876330 |  |  | Jieyang | China | Draft |  | 23.3132 | 23'18'48' | 116.0349 | 116'2'5'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244914 |  | 883893435 | Started | 50139878-GO_JYPN_普宁君林天下_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_54-GO_JYPN_普宁君林天下_RRU_N21\GD_CP4_54-GO_JYPN_普宁君林天下_RRU_N21 |  | Radio Site | GD_CP4_54 | GO_JYPN_普宁君林天下_RRU_N21_1 | GD_CP4_54-GO_JYPN_普宁君林天下_RRU_N21 | 883876274 |  |  | Jieyang | China | Draft |  | 23.3077 | 23'18'28' | 116.1456 | 116'8'44'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244915 |  | 883893454 | Started | 50139878-GO_JYPN_普宁新华城_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_60-GO_JYPN_普宁新华城_RRU_N21\GD_CP4_60-GO_JYPN_普宁新华城_RRU_N21 |  | Radio Site | GD_CP4_60 | GO_JYPN_普宁新华城_RRU_N21_1 | GD_CP4_60-GO_JYPN_普宁新华城_RRU_N21 | 883876333 |  |  | Jieyang | China | Draft |  | 23.3172 | 23'19'2' | 116.1529 | 116'9'10'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244916 |  | 883893490 | Started | 50139878-GO_JYPN_普宁滨湖花园_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_19-GO_JYPN_普宁滨湖花园_RRU_N21\GD_CP4_19-GO_JYPN_普宁滨湖花园_RRU_N21 |  | Radio Site | GD_CP4_19 | GO_JYPN_普宁滨湖花园_RRU_N21_1 | GD_CP4_19-GO_JYPN_普宁滨湖花园_RRU_N21 | 883876192 |  |  | Jieyang | China | Draft |  | 23.3117 | 23'18'42' | 116.1415 | 116'8'29'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244917 |  | 883893493 | Started | 50139878-GO_JYPN_普宁江景新城_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_44-GO_JYPN_普宁江景新城_RRU_N21\GD_CP4_44-GO_JYPN_普宁江景新城_RRU_N21 |  | Radio Site | GD_CP4_44 | GO_JYPN_普宁江景新城_RRU_N21_1 | GD_CP4_44-GO_JYPN_普宁江景新城_RRU_N21 | 883876312 |  |  | Jieyang | China | Draft |  | 23.2971 | 23'17'50' | 116.146 | 116'8'45'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244918 |  | 883893495 | Started | 50139878-GO_JYPN_普宁福盛花园_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_02-GO_JYPN_普宁福盛花园_RRU_N21\GD_CP4_02-GO_JYPN_普宁福盛花园_RRU_N21 |  | Radio Site | GD_CP4_02 | GO_JYPN_普宁福盛花园_RRU_N21_1 | GD_CP4_02-GO_JYPN_普宁福盛花园_RRU_N21 | 883876181 |  |  | Jieyang | China | Draft |  | 23.3025 | 23'18'9' | 116.144 | 116'8'38'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244919 |  | 883893494 | Started | 50139878-GO_JYPN_普宁桂荣茗园_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_52-GO_JYPN_普宁桂荣茗园_RRU_N21\GD_CP4_52-GO_JYPN_普宁桂荣茗园_RRU_N21 |  | Radio Site | GD_CP4_52 | GO_JYPN_普宁桂荣茗园_RRU_N21_1 | GD_CP4_52-GO_JYPN_普宁桂荣茗园_RRU_N21 | 883876320 |  |  | Jieyang | China | Draft |  | 23.3047 | 23'18'17' | 116.1516 | 116'9'5'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244920 |  | 883893497 | Started | 50139878-GO_JYPN_普宁丹桂苑_RRU_N21-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_42-GO_JYPN_普宁丹桂苑_RRU_N21\GD_CP4_42-GO_JYPN_普宁丹桂苑_RRU_N21 |  | Radio Site | GD_CP4_42 | GO_JYPN_普宁丹桂苑_RRU_N21_1 | GD_CP4_42-GO_JYPN_普宁丹桂苑_RRU_N21 | 883876271 |  |  | Jieyang | China | Draft |  | 23.3044 | 23'18'16' | 116.1516 | 116'9'5'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244921 |  | 883893491 | Released | 50139878-石排琼莊酒楼5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_34-石排琼莊酒楼5G_1\GD_CP4_34-石排琼莊酒楼5G_1 |  | Radio Site | GD_CP4_34 | 石排琼莊酒楼5G_1_1 | GD_CP4_34-石排琼莊酒楼5G_1 | 883876190 |  |  | Dongguan | China | Draft |  | 53.1235 | 53'7'24' | 147.7824 | 147'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244922 |  | 883893489 | Released | 50139878-石排休闲沐足阁5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_43-石排休闲沐足阁5G_1\GD_CP4_43-石排休闲沐足阁5G_1 |  | Radio Site | GD_CP4_43 | 石排休闲沐足阁5G_1_1 | GD_CP4_43-石排休闲沐足阁5G_1 | 883876281 |  |  | Dongguan | China | Draft |  | 62.1235 | 62'7'24' | 156.7824 | 156'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244923 |  | 883893509 | Released | 50139878-石排濠美服饰有限公司5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_39-石排濠美服饰有限公司5G_1\GD_CP4_39-石排濠美服饰有限公司5G_1 |  | Radio Site | GD_CP4_39 | 石排濠美服饰有限公司5G_1_1 | GD_CP4_39-石排濠美服饰有限公司5G_1 | 883876282 |  |  | Dongguan | China | Draft |  | 58.1235 | 58'7'24' | 152.7824 | 152'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244924 |  | 883893496 | Released | 50139878-石排旭业光电科技5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_07-石排旭业光电科技5G_1\GD_CP4_07-石排旭业光电科技5G_1 |  | Radio Site | GD_CP4_07 | 石排旭业光电科技5G_1_1 | GD_CP4_07-石排旭业光电科技5G_1 | 883876088 |  |  | Dongguan | China | Draft |  | 26.1235 | 26'7'24' | 120.7824 | 120'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244925 |  | 883893513 | Started | 50139878-茶山保利东岸5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_57-茶山保利东岸5G_1\GD_CP4_57-茶山保利东岸5G_1 |  | Radio Site | GD_CP4_57 | 茶山保利东岸5G_1_1 | GD_CP4_57-茶山保利东岸5G_1 | 883876321 |  |  | Dongguan | China | Draft |  | 76.1235 | 76'7'24' | 170.7824 | 170'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244926 |  | 883893492 | Started | 50139878-茶山保利东岸5G_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_28-茶山保利东岸5G_2\GD_CP4_28-茶山保利东岸5G_2 |  | Radio Site | GD_CP4_28 | 茶山保利东岸5G_2_1 | GD_CP4_28-茶山保利东岸5G_2 | 883876173 |  |  | Dongguan | China | Draft |  | 47.1235 | 47'7'24' | 141.7824 | 141'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244927 |  | 883893500 | Started | 50139878-茶山保利东岸5G_3-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_25-茶山保利东岸5G_3\GD_CP4_25-茶山保利东岸5G_3 |  | Radio Site | GD_CP4_25 | 茶山保利东岸5G_3_1 | GD_CP4_25-茶山保利东岸5G_3 | 883876194 |  |  | Dongguan | China | Draft |  | 44.1235 | 44'7'24' | 138.7824 | 138'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244928 |  | 883893515 | Started | 50139878-茶山芋丰名苑5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_65-茶山芋丰名苑5G_1\GD_CP4_65-茶山芋丰名苑5G_1 |  | Radio Site | GD_CP4_65 | 茶山芋丰名苑5G_1_1 | GD_CP4_65-茶山芋丰名苑5G_1 | 883876325 |  |  | Dongguan | China | Draft |  | 84.1235 | 84'7'24' | 178.7824 | 178'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244929 |  | 883893518 | Started | 50139878-石龙嘉宏锦峯5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_36-石龙嘉宏锦峯5G_1\GD_CP4_36-石龙嘉宏锦峯5G_1 |  | Radio Site | GD_CP4_36 | 石龙嘉宏锦峯5G_1_1 | GD_CP4_36-石龙嘉宏锦峯5G_1 | 883876199 |  |  | Dongguan | China | Draft |  | 55.1235 | 55'7'24' | 149.7824 | 149'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244930 |  | 883893528 | Started | 50139878-石龙嘉宏锦峯5G_2-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_50-石龙嘉宏锦峯5G_2\GD_CP4_50-石龙嘉宏锦峯5G_2 |  | Radio Site | GD_CP4_50 | 石龙嘉宏锦峯5G_2_1 | GD_CP4_50-石龙嘉宏锦峯5G_2 | 883876326 |  |  | Dongguan | China | Draft |  | 69.1235 | 69'7'24' | 163.7824 | 163'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244931 |  | 883893510 | Released | 50139878-石龙广安电气检测中心5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_04-石龙广安电气检测中心5G_1\GD_CP4_04-石龙广安电气检测中心5G_1 |  | Radio Site | GD_CP4_04 | 石龙广安电气检测中心5G_1_1 | GD_CP4_04-石龙广安电气检测中心5G_1 | 883876164 |  |  | Dongguan | China | Draft |  | 23.1235 | 23'7'24' | 117.7824 | 117'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244932 |  | 883893511 | Released | 50139878-石龙人民医院新院（大修）5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_48-石龙人民医院新院（大修）5G_1\GD_CP4_48-石龙人民医院新院（大修）5G_1 |  | Radio Site | GD_CP4_48 | 石龙人民医院新院（大修）5G_1_1 | GD_CP4_48-石龙人民医院新院（大修）5G_1 | 883876272 |  |  | Dongguan | China | Draft |  | 67.1235 | 67'7'24' | 161.7824 | 161'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244933 |  | 883893508 | Started | 50139878-茶山翔国光电科技有限公司5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_16-茶山翔国光电科技有限公司5G_1\GD_CP4_16-茶山翔国光电科技有限公司5G_1 |  | Radio Site | GD_CP4_16 | 茶山翔国光电科技有限公司5G_1_1 | GD_CP4_16-茶山翔国光电科技有限公司5G_1 | 883876201 |  |  | Dongguan | China | Draft |  | 35.1235 | 35'7'24' | 129.7824 | 129'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244934 |  | 883893512 | Started | 50139878-茶山东莞联桥电子有限公司5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_41-茶山东莞联桥电子有限公司5G_1\GD_CP4_41-茶山东莞联桥电子有限公司5G_1 |  | Radio Site | GD_CP4_41 | 茶山东莞联桥电子有限公司5G_1_1 | GD_CP4_41-茶山东莞联桥电子有限公司5G_1 | 883876273 |  |  | Dongguan | China | Draft |  | 60.1235 | 60'7'24' | 154.7824 | 154'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244935 |  | 883893541 | Released | 50139878-石龙公安分局副楼5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_51-石龙公安分局副楼5G_1\GD_CP4_51-石龙公安分局副楼5G_1 |  | Radio Site | GD_CP4_51 | 石龙公安分局副楼5G_1_1 | GD_CP4_51-石龙公安分局副楼5G_1 | 883876313 |  |  | Dongguan | China | Draft |  | 70.1235 | 70'7'24' | 164.7824 | 164'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244936 |  | 883893539 | Started | 50139878-石龙京瓷光学厂房5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_53-石龙京瓷光学厂房5G_1\GD_CP4_53-石龙京瓷光学厂房5G_1 |  | Radio Site | GD_CP4_53 | 石龙京瓷光学厂房5G_1_1 | GD_CP4_53-石龙京瓷光学厂房5G_1 | 883876318 |  |  | Dongguan | China | Draft |  | 72.1235 | 72'7'24' | 166.7824 | 166'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244937 |  | 883893565 | Released | 50139878-茶山庆丰家园5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_29-茶山庆丰家园5G_1\GD_CP4_29-茶山庆丰家园5G_1 |  | Radio Site | GD_CP4_29 | 茶山庆丰家园5G_1_1 | GD_CP4_29-茶山庆丰家园5G_1 | 883876202 |  |  | Dongguan | China | Draft |  | 48.1235 | 48'7'24' | 142.7824 | 142'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244938 |  | 883893562 | Started | 50139878-茶山立本工业5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_27-茶山立本工业5G_1\GD_CP4_27-茶山立本工业5G_1 |  | Radio Site | GD_CP4_27 | 茶山立本工业5G_1_1 | GD_CP4_27-茶山立本工业5G_1 | 883876091 |  |  | Dongguan | China | Draft |  | 46.1235 | 46'7'24' | 140.7824 | 140'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244939 |  | 883893561 | Started | 50139878-茶山庆丰家园二期5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_45-茶山庆丰家园二期5G_1\GD_CP4_45-茶山庆丰家园二期5G_1 |  | Radio Site | GD_CP4_45 | 茶山庆丰家园二期5G_1_1 | GD_CP4_45-茶山庆丰家园二期5G_1 | 883876327 |  |  | Dongguan | China | Draft |  | 64.1235 | 64'7'24' | 158.7824 | 158'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244940 |  | 883893574 | Started | 50139878-茶山广东百顺纸品有限公司5G_1-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_18-茶山广东百顺纸品有限公司5G_1\GD_CP4_18-茶山广东百顺纸品有限公司5G_1 |  | Radio Site | GD_CP4_18 | 茶山广东百顺纸品有限公司5G_1_1 | GD_CP4_18-茶山广东百顺纸品有限公司5G_1 | 883876196 |  |  | Dongguan | China | Draft |  | 37.1235 | 37'7'24' | 131.7824 | 131'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244941 |  | 883893576 | Created | 50139878-CP4_dummy08-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_08-CP4_dummy08\GD_CP4_08-CP4_dummy08 |  | Radio Site | GD_CP4_08 | CP4_dummy08_1 | GD_CP4_08-CP4_dummy08 | 883876090 |  |  | Chaozhou | China | Draft |  | 27 | 27'0'0' | 122 | 122'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244942 |  | 883893577 | Created | 50139878-CP4_dummy46-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_46-CP4_dummy46\GD_CP4_46-CP4_dummy46 |  | Radio Site | GD_CP4_46 | CP4_dummy46_1 | GD_CP4_46-CP4_dummy46 | 883876319 |  |  | Chaozhou | China | Draft |  | 65 | 65'0'0' | 160 | 160'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244943 |  | 883893578 | Created | 50139878-CP4_dummy38-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_38-CP4_dummy38\GD_CP4_38-CP4_dummy38 |  | Radio Site | GD_CP4_38 | CP4_dummy38_1 | GD_CP4_38-CP4_dummy38 | 883876292 |  |  | Chaozhou | China | Draft |  | 57 | 57'0'0' | 152 | 152'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244944 |  | 883893567 | Created | 50139878-CP4_dummy12-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_12-CP4_dummy12\GD_CP4_12-CP4_dummy12 |  | Radio Site | GD_CP4_12 | CP4_dummy12_1 | GD_CP4_12-CP4_dummy12 | 883876167 |  |  | Chaozhou | China | Draft |  | 31 | 31'0'0' | 126 | 126'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244945 |  | 883893779 | Created | 50139878-CP4_dummy64-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_64-CP4_dummy64\GD_CP4_64-CP4_dummy64 |  | Radio Site | GD_CP4_64 | CP4_dummy64_1 | GD_CP4_64-CP4_dummy64 | 883876335 |  |  | Chaozhou | China | Draft |  | 83 | 83'0'0' | 178 | 178'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244946 |  | 883893776 | Created | 50139878-CP4_dummy55-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_55-CP4_dummy55\GD_CP4_55-CP4_dummy55 |  | Radio Site | GD_CP4_55 | CP4_dummy55_1 | GD_CP4_55-CP4_dummy55 | 883876334 |  |  | Chaozhou | China | Draft |  | 74 | 74'0'0' | 169 | 169'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244947 |  | 883893807 | Created | 50139878-CP4_dummy66-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_66-CP4_dummy66\GD_CP4_66-CP4_dummy66 |  | Radio Site | GD_CP4_66 | CP4_dummy66_1 | GD_CP4_66-CP4_dummy66 | 883876336 |  |  | Chaozhou | China | Draft |  | 85 | 85'0'0' | 180 | 180'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244948 |  | 883893822 | Created | 50139878-CP4_dummy58-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_58-CP4_dummy58\GD_CP4_58-CP4_dummy58 |  | Radio Site | GD_CP4_58 | CP4_dummy58_1 | GD_CP4_58-CP4_dummy58 | 883876337 |  |  | Chaozhou | China | Draft |  | 77 | 77'0'0' | 172 | 172'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244949 |  | 883893848 | Created | 50139878-CP4_dummy63-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_63-CP4_dummy63\GD_CP4_63-CP4_dummy63 |  | Radio Site | GD_CP4_63 | CP4_dummy63_1 | GD_CP4_63-CP4_dummy63 | 883876338 |  |  | Chaozhou | China | Draft |  | 82 | 82'0'0' | 177 | 177'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244950 |  | 883893875 | Created | 50139878-CP4_dummy59-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_59-CP4_dummy59\GD_CP4_59-CP4_dummy59 |  | Radio Site | GD_CP4_59 | CP4_dummy59_1 | GD_CP4_59-CP4_dummy59 | 883876352 |  |  | Chaozhou | China | Draft |  | 78 | 78'0'0' | 173 | 173'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244951 |  | 883893876 | Created | 50139878-CP4_dummy56-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_56-CP4_dummy56\GD_CP4_56-CP4_dummy56 |  | Radio Site | GD_CP4_56 | CP4_dummy56_1 | GD_CP4_56-CP4_dummy56 | 883876339 |  |  | Chaozhou | China | Draft |  | 75 | 75'0'0' | 170 | 170'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244952 |  | 883894063 | Created | 50139878-CP4_dummy71-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_71-CP4_dummy71\GD_CP4_71-CP4_dummy71 |  | Radio Site | GD_CP4_71 | CP4_dummy71_1 | GD_CP4_71-CP4_dummy71 | 883876357 |  |  | Chaozhou | China | Draft |  | 90 | 90'0'0' | 185 | 185'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244953 |  | 883894072 | Created | 50139878-CP4_dummy70-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_70-CP4_dummy70\GD_CP4_70-CP4_dummy70 |  | Radio Site | GD_CP4_70 | CP4_dummy70_1 | GD_CP4_70-CP4_dummy70 | 883876355 |  |  | Chaozhou | China | Draft |  | 89 | 89'0'0' | 184 | 184'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244954 |  | 883894124 | Created | 50139878-CP4_dummy72-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_72-CP4_dummy72\GD_CP4_72-CP4_dummy72 |  | Radio Site | GD_CP4_72 | CP4_dummy72_1 | GD_CP4_72-CP4_dummy72 | 883876359 |  |  | Chaozhou | China | Draft |  | 91 | 91'0'0' | 186 | 186'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244955 |  | 883894140 | Created | 50139878-CP4_dummy73-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_73-CP4_dummy73\GD_CP4_73-CP4_dummy73 |  | Radio Site | GD_CP4_73 | CP4_dummy73_1 | GD_CP4_73-CP4_dummy73 | 883876360 |  |  | Chaozhou | China | Draft |  | 92 | 92'0'0' | 187 | 187'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244956 |  | 883894141 | Created | 50139878-CP4_dummy68-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_68-CP4_dummy68\GD_CP4_68-CP4_dummy68 |  | Radio Site | GD_CP4_68 | CP4_dummy68_1 | GD_CP4_68-CP4_dummy68 | 883876365 |  |  | Chaozhou | China | Draft |  | 87 | 87'0'0' | 182 | 182'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244957 |  | 883894147 | Created | 50139878-CP4_dummy74-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_74-CP4_dummy74\GD_CP4_74-CP4_dummy74 |  | Radio Site | GD_CP4_74 | CP4_dummy74_1 | GD_CP4_74-CP4_dummy74 | 883876363 |  |  | Chaozhou | China | Draft |  | 93 | 93'0'0' | 188 | 188'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244958 |  | 883894127 | Created | 50139878-CP4_dummy67-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_67-CP4_dummy67\GD_CP4_67-CP4_dummy67 |  | Radio Site | GD_CP4_67 | CP4_dummy67_1 | GD_CP4_67-CP4_dummy67 | 883876358 |  |  | Chaozhou | China | Draft |  | 86 | 86'0'0' | 181 | 181'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244959 |  | 883894138 | Created | 50139878-CP4_dummy69-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_69-CP4_dummy69\GD_CP4_69-CP4_dummy69 |  | Radio Site | GD_CP4_69 | CP4_dummy69_1 | GD_CP4_69-CP4_dummy69 | 883876366 |  |  | Chaozhou | China | Draft |  | 88 | 88'0'0' | 183 | 183'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244960 |  | 883894163 | Created | 50139878-CP4_dummy77-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_77-CP4_dummy77\GD_CP4_77-CP4_dummy77 |  | Radio Site | GD_CP4_77 | CP4_dummy77_1 | GD_CP4_77-CP4_dummy77 | 883876395 |  |  | Chaozhou | China | Draft |  | 96 | 96'0'0' | 191 | 191'0'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244961 |  | 883894256 | Started | 50139878-GS_MZDP_县酒厂室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_78-GS_MZDP_县酒厂室分\GD_CP4_78-GS_MZDP_县酒厂室分 |  | Radio Site | GD_CP4_78 | GS_MZDP_县酒厂室分_1 | GD_CP4_78-GS_MZDP_县酒厂室分 | 883876396 |  |  | Meizhou | China | Draft |  | 97.1235 | 97'7'24' | 191.7824 | 191'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244962 |  | 883894300 | Started | 50139878-GS_MZDP_奥园6-8栋室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_76-GS_MZDP_奥园6-8栋室分\GD_CP4_76-GS_MZDP_奥园6-8栋室分 |  | Radio Site | GD_CP4_76 | GS_MZDP_奥园6-8栋室分_1 | GD_CP4_76-GS_MZDP_奥园6-8栋室分 | 883876398 |  |  | Meizhou | China | Draft |  | 95.1235 | 95'7'24' | 189.7824 | 189'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244963 |  | 883894295 | Started | 50139878-GS_MZDP_时代广场室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_75-GS_MZDP_时代广场室分\GD_CP4_75-GS_MZDP_时代广场室分 |  | Radio Site | GD_CP4_75 | GS_MZDP_时代广场室分_1 | GD_CP4_75-GS_MZDP_时代广场室分 | 883876402 |  |  | Meizhou | China | Draft |  | 94.1235 | 94'7'24' | 188.7824 | 188'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244964 |  | 883894333 | Started | 50139878-GS_MZDP_碧桂园室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_81-GS_MZDP_碧桂园室分\GD_CP4_81-GS_MZDP_碧桂园室分 |  | Radio Site | GD_CP4_81 | GS_MZDP_碧桂园室分_1 | GD_CP4_81-GS_MZDP_碧桂园室分 | 883876426 |  |  | Meizhou | China | Draft |  | 100.1235 | 100'7'24' | 194.7824 | 194'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244965 |  | 883894408 | Started | 50139878-GS_MZDP_富兴豪庭室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_82-GS_MZDP_富兴豪庭室分\GD_CP4_82-GS_MZDP_富兴豪庭室分 |  | Radio Site | GD_CP4_82 | GS_MZDP_富兴豪庭室分_1 | GD_CP4_82-GS_MZDP_富兴豪庭室分 | 883876427 |  |  | Meizhou | China | Draft |  | 101.1235 | 101'7'24' | 195.7824 | 195'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244966 |  | 883894472 | Started | 50139878-GS_MZDP_中华广场室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_85-GS_MZDP_中华广场室分\GD_CP4_85-GS_MZDP_中华广场室分 |  | Radio Site | GD_CP4_85 | GS_MZDP_中华广场室分_1 | GD_CP4_85-GS_MZDP_中华广场室分 | 883876428 |  |  | Meizhou | China | Draft |  | 104.1235 | 104'7'24' | 198.7824 | 198'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244967 |  | 883895401 | Started | 50139878-GS_MZJL_安宁电信营业厅室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_79-GS_MZJL_安宁电信营业厅室分\GD_CP4_79-GS_MZJL_安宁电信营业厅室分 |  | Radio Site | GD_CP4_79 | GS_MZJL_安宁电信营业厅室分_1 | GD_CP4_79-GS_MZJL_安宁电信营业厅室分 | 883876429 |  |  | Meizhou | China | Draft |  | 98.1235 | 98'7'24' | 192.7824 | 192'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244968 |  | 883895463 | Started | 50139878-GS_MZJL_碧桂园二期室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_84-GS_MZJL_碧桂园二期室分\GD_CP4_84-GS_MZJL_碧桂园二期室分 |  | Radio Site | GD_CP4_84 | GS_MZJL_碧桂园二期室分_1 | GD_CP4_84-GS_MZJL_碧桂园二期室分 | 883876432 |  |  | Meizhou | China | Draft |  | 103.1235 | 103'7'24' | 197.7824 | 197'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244969 |  | 883895464 | Started | 50139878-GS_MZJL_碧翠园室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_80-GS_MZJL_碧翠园室分\GD_CP4_80-GS_MZJL_碧翠园室分 |  | Radio Site | GD_CP4_80 | GS_MZJL_碧翠园室分_1 | GD_CP4_80-GS_MZJL_碧翠园室分 | 883876434 |  |  | Meizhou | China | Draft |  | 99.1235 | 99'7'24' | 193.7824 | 193'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4244970 |  | 883895527 | Started | 50139878-GS_MZJL_奥园广场室分-SV_MACRO | 50139878 | SV_MACRO |  | \Locations\GD_CP4_83-GS_MZJL_奥园广场室分\GD_CP4_83-GS_MZJL_奥园广场室分 |  | Radio Site | GD_CP4_83 | GS_MZJL_奥园广场室分_1 | GD_CP4_83-GS_MZJL_奥园广场室分 | 883876435 |  |  | Meizhou | China | Draft |  | 102.1235 | 102'7'24' | 196.7824 | 196'46'56'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512561 |  | 930107132 | Created | 50139878-CT_addKR_015-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_15-CT_addKR_015\CT_addKR_15-CT_addKR_015 |  | Radio Site | CT_addKR_15 | CT_addKR_015_1 | CT_addKR_15-CT_addKR_015 | 930103386 |  |  | Meizhou | China | Draft |  | 35.4564 | 35'27'23' | 1127.2 | 1127'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512562 |  | 930107131 | Created | 50139878-CT_addKR_001-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_01-CT_addKR_001\CT_addKR_01-CT_addKR_001 |  | Radio Site | CT_addKR_01 | CT_addKR_001_1 | CT_addKR_01-CT_addKR_001 | 930103255 |  |  | Jieyang | China | Draft |  | 21.4564 | 21'27'23' | 1113.2 | 1113'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512563 |  | 930107135 | Created | 50139878-CT_addKR_006-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_06-CT_addKR_006\CT_addKR_06-CT_addKR_006 |  | Radio Site | CT_addKR_06 | CT_addKR_006_1 | CT_addKR_06-CT_addKR_006 | 930103259 |  |  | Chaozhou | China | Draft |  | 26.4564 | 26'27'23' | 1118.2 | 1118'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512564 |  | 930107143 | Created | 50139878-CT_addKR_009-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_09-CT_addKR_009\CT_addKR_09-CT_addKR_009 |  | Radio Site | CT_addKR_09 | CT_addKR_009_1 | CT_addKR_09-CT_addKR_009 | 930103256 |  |  | Chaozhou | China | Draft |  | 29.4564 | 29'27'23' | 1121.2 | 1121'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512565 |  | 930107144 | Created | 50139878-CT_addKR_013-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_13-CT_addKR_013\CT_addKR_13-CT_addKR_013 |  | Radio Site | CT_addKR_13 | CT_addKR_013_1 | CT_addKR_13-CT_addKR_013 | 930103238 |  |  | Meizhou | China | Draft |  | 33.4564 | 33'27'23' | 1125.2 | 1125'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512566 |  | 930107145 | Created | 50139878-CT_addKR_002-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_02-CT_addKR_002\CT_addKR_02-CT_addKR_002 |  | Radio Site | CT_addKR_02 | CT_addKR_002_1 | CT_addKR_02-CT_addKR_002 | 930103239 |  |  | Jieyang | China | Draft |  | 22.4564 | 22'27'23' | 1114.2 | 1114'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512567 |  | 930107146 | Created | 50139878-CT_addKR_003-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_03-CT_addKR_003\CT_addKR_03-CT_addKR_003 |  | Radio Site | CT_addKR_03 | CT_addKR_003_1 | CT_addKR_03-CT_addKR_003 | 930103247 |  |  | Jieyang | China | Draft |  | 23.4564 | 23'27'23' | 1115.2 | 1115'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512568 |  | 930107149 | Created | 50139878-CT_addKR_005-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_05-CT_addKR_005\CT_addKR_05-CT_addKR_005 |  | Radio Site | CT_addKR_05 | CT_addKR_005_1 | CT_addKR_05-CT_addKR_005 | 930103253 |  |  | Chaozhou | China | Draft |  | 25.4564 | 25'27'23' | 1117.2 | 1117'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512569 |  | 930107193 | Created | 50139878-CT_addKR_008-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_08-CT_addKR_008\CT_addKR_08-CT_addKR_008 |  | Radio Site | CT_addKR_08 | CT_addKR_008_1 | CT_addKR_08-CT_addKR_008 | 930103254 |  |  | Chaozhou | China | Draft |  | 28.4564 | 28'27'23' | 1120.2 | 1120'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512570 |  | 930107195 | Created | 50139878-CT_addKR_004-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_04-CT_addKR_004\CT_addKR_04-CT_addKR_004 |  | Radio Site | CT_addKR_04 | CT_addKR_004_1 | CT_addKR_04-CT_addKR_004 | 930103257 |  |  | Chaozhou | China | Draft |  | 24.4564 | 24'27'23' | 1116.2 | 1116'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512571 |  | 930107213 | Created | 50139878-CT_addKR_014-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_14-CT_addKR_014\CT_addKR_14-CT_addKR_014 |  | Radio Site | CT_addKR_14 | CT_addKR_014_1 | CT_addKR_14-CT_addKR_014 | 930103252 |  |  | Meizhou | China | Draft |  | 34.4564 | 34'27'23' | 1126.2 | 1126'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512572 |  | 930107216 | Created | 50139878-CT_addKR_010-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_10-CT_addKR_010\CT_addKR_10-CT_addKR_010 |  | Radio Site | CT_addKR_10 | CT_addKR_010_1 | CT_addKR_10-CT_addKR_010 | 930103246 |  |  | Meizhou | China | Draft |  | 30.4564 | 30'27'23' | 1122.2 | 1122'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512573 |  | 930107214 | Created | 50139878-CT_addKR_012-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_12-CT_addKR_012\CT_addKR_12-CT_addKR_012 |  | Radio Site | CT_addKR_12 | CT_addKR_012_1 | CT_addKR_12-CT_addKR_012 | 930103251 |  |  | Meizhou | China | Draft |  | 32.4564 | 32'27'23' | 1124.2 | 1124'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512574 |  | 930107215 | Created | 50139878-CT_addKR_007-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_07-CT_addKR_007\CT_addKR_07-CT_addKR_007 |  | Radio Site | CT_addKR_07 | CT_addKR_007_1 | CT_addKR_07-CT_addKR_007 | 930103243 |  |  | Chaozhou | China | Draft |  | 27.4564 | 27'27'23' | 1119.2 | 1119'12'0'
1018468 | CN_CT_COMGZ_G_D_5G_CP4_ES_50139878 | 883892735 | 2022-05-09 09:24 |  | China | China Telecom Guangdong | Issued | China | 4512575 |  | 930107217 | Created | 50139878-CT_addKR_011-SV_EXPANSION | 50139878 | SV_EXPANSION |  | \Locations\CT_addKR_11-CT_addKR_011\CT_addKR_11-CT_addKR_011 |  | Radio Site | CT_addKR_11 | CT_addKR_011_1 | CT_addKR_11-CT_addKR_011 | 930103242 |  |  | Meizhou | China | Draft |  | 31.4564 | 31'27'23' | 1123.2 | 1123'12'0'

## PLO dates
WP ID | Workplan--SystemRecordID | Customised PLO name | PLO--Name | PLO--Status | Object type | PLO--SystemRecordID | act--BaselineEndDate | act--ForecastEndDate | act--ActualStartDate | act--ActualEndDate | ms--BaselineEndDate | ms--ForecastEndDate | ms--ActualStartDate | ms--ActualEndDate
3550483 | 675858528 | act--02 Integration | 02 Integration | Completed | Activity | 675858612 | 08/09/2019 15:00:00 | 08/09/2019 15:00:00 | 08/09/2019 13:30:00 | 08/09/2019 15:00:00
3550483 | 675858528 | act--04 SSV | 04 SSV | Completed | Activity | 675858653 | 08/28/2019 15:30:00 | 08/26/2019 15:30:00 | 08/26/2019 07:45:36 | 08/26/2019 14:54:35
3550483 | 675858528 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675858707 | 09/01/2019 06:30:00 | 09/01/2019 06:30:00 | 12/27/2021 14:26:29 | 12/27/2021 14:26:28
3550483 | 675858528 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858586 |  |  |  |  | 08/09/2019 11:30:00 | 08/09/2019 11:30:00 |  | 08/09/2019 11:30:00
3550483 | 675858528 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858572 |  |  |  |  | 08/09/2019 05:30:00 | 08/09/2019 05:30:00 |  | 08/09/2019 05:30:00
3550483 | 675858528 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858539 |  |  |  |  | 08/09/2019 16:30:00 | 08/09/2019 16:30:00 |  | 08/09/2019 16:30:00
3550483 | 675858528 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858550 |  |  |  |  | 09/01/2019 06:30:00 | 09/01/2019 06:30:00 |  | 09/01/2019 07:00:00
3550483 | 675858528 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062121 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550483 | 675858528 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062575 |  |  |  |  | 09/01/2019 06:30:00 | 07/30/2021 05:30:00
3550484 | 675858527 | act--02 Integration | 02 Integration | Completed | Activity | 675858604 | 09/12/2019 15:10:00 | 09/12/2019 15:10:00 | 09/12/2019 13:40:00 | 09/12/2019 15:10:00
3550484 | 675858527 | act--04 SSV | 04 SSV | Completed | Activity | 675858650 | 12/12/2019 15:30:00 | 12/13/2019 15:30:00 | 12/11/2019 07:34:15 | 12/11/2019 13:09:57
3550484 | 675858527 | act--06 Tuning | 06 Tuning | Completed | Activity | 675858713 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550484 | 675858527 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858578 |  |  |  |  | 09/12/2019 11:40:00 | 09/12/2019 11:40:00 |  | 09/12/2019 11:40:00
3550484 | 675858527 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858563 |  |  |  |  | 09/12/2019 05:40:00 | 09/12/2019 05:40:00 |  | 09/12/2019 05:40:00
3550484 | 675858527 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858531 |  |  |  |  | 09/12/2019 16:40:00 | 09/12/2019 16:40:00 |  | 09/12/2019 16:40:00
3550484 | 675858527 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858548 |  |  |  |  | 12/12/2019 06:30:00 | 12/12/2019 06:30:00 |  | 12/12/2019 06:43:33
3550484 | 675858527 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061942 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550484 | 675858527 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062395 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550485 | 675858534 | act--02 Integration | 02 Integration | Completed | Activity | 675858661 | 01/18/2020 15:00:00 | 01/18/2020 15:00:00 | 01/18/2020 13:30:00 | 01/18/2020 15:00:00
3550485 | 675858534 | act--04 SSV | 04 SSV | Completed | Activity | 675858731 | 03/10/2020 15:30:00 | 03/11/2020 15:30:00 | 03/09/2020 06:40:55 | 03/09/2020 13:18:50
3550485 | 675858534 | act--06 Tuning | 06 Tuning | Completed | Activity | 675858895 | 04/26/2021 05:30:01 | 04/26/2021 05:30:01 | 04/01/2021 06:00:00 | 04/26/2021 06:00:01
3550485 | 675858534 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858623 |  |  |  |  | 01/18/2020 11:30:00 | 01/18/2020 11:30:00 |  | 01/18/2020 11:30:00
3550485 | 675858534 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858606 |  |  |  |  | 01/18/2020 05:30:00 | 01/18/2020 05:30:00 |  | 01/18/2020 05:30:00
3550485 | 675858534 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858552 |  |  |  |  | 01/18/2020 16:30:00 | 01/18/2020 16:30:00 |  | 01/18/2020 16:30:00
3550485 | 675858534 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858580 |  |  |  |  | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 |  | 03/10/2020 06:38:42
3550485 | 675858534 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062961 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550485 | 675858534 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063137 |  |  |  |  | 04/26/2021 05:30:01 | 07/30/2021 07:00:00
3550486 | 675858535 | act--02 Integration | 02 Integration | Completed | Activity | 675858671 | 10/26/2019 15:10:00 | 10/26/2019 15:10:00 | 10/26/2019 13:40:00 | 10/26/2019 15:10:00
3550486 | 675858535 | act--04 SSV | 04 SSV | Completed | Activity | 675858734 | 03/27/2020 15:30:00 | 03/27/2020 15:30:00 | 03/25/2020 08:32:40 | 03/25/2020 13:48:38
3550486 | 675858535 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675858884 | 03/26/2020 06:30:00 | 03/26/2020 06:30:00 | 12/27/2021 14:20:44 | 12/27/2021 14:20:43
3550486 | 675858535 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858619 |  |  |  |  | 10/26/2019 11:40:00 | 10/26/2019 11:40:00 |  | 10/26/2019 11:40:00
3550486 | 675858535 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858601 |  |  |  |  | 10/26/2019 05:40:00 | 10/26/2019 05:40:00 |  | 10/26/2019 05:40:00
3550486 | 675858535 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858555 |  |  |  |  | 10/26/2019 16:40:00 | 10/26/2019 16:40:00 |  | 10/26/2019 16:40:00
3550486 | 675858535 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858579 |  |  |  |  | 03/26/2020 06:30:00 | 03/26/2020 06:30:00 |  | 03/26/2020 08:50:15
3550486 | 675858535 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061018 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550486 | 675858535 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061277 |  |  |  |  | 03/26/2020 06:30:00 | 07/30/2021 05:30:00
3550487 | 675858538 | act--02 Integration | 02 Integration | Completed | Activity | 675858665 | 10/19/2019 15:00:00 | 10/19/2019 15:00:00 | 10/19/2019 13:30:00 | 10/19/2019 15:00:00
3550487 | 675858538 | act--04 SSV | 04 SSV | Completed | Activity | 675858735 | 12/23/2019 15:30:00 | 12/25/2019 15:30:00 | 12/23/2019 08:36:03 | 12/23/2019 13:24:31
3550487 | 675858538 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675858885 | 03/26/2020 06:30:00 | 03/26/2020 06:30:00 | 12/27/2021 14:26:35 | 12/27/2021 14:26:34
3550487 | 675858538 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858632 |  |  |  |  | 10/19/2019 11:30:00 | 10/19/2019 11:30:00 |  | 10/19/2019 11:30:00
3550487 | 675858538 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858610 |  |  |  |  | 10/19/2019 05:30:00 | 10/19/2019 05:30:00 |  | 10/19/2019 05:30:00
3550487 | 675858538 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858559 |  |  |  |  | 10/19/2019 16:30:00 | 10/19/2019 16:30:00 |  | 10/19/2019 16:30:00
3550487 | 675858538 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858584 |  |  |  |  | 03/26/2020 06:30:00 | 03/26/2020 06:30:00 |  | 03/25/2020 17:44:07
3550487 | 675858538 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062119 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550487 | 675858538 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062713 |  |  |  |  | 03/26/2020 06:30:00 | 07/30/2021 05:30:00
3550488 | 675858602 | act--02 Integration | 02 Integration | Completed | Activity | 675858904 | 08/20/2019 15:20:00 | 08/20/2019 15:20:00 | 08/20/2019 13:50:00 | 08/20/2019 15:20:00
3550488 | 675858602 | act--04 SSV | 04 SSV | Completed | Activity | 675859005 | 08/27/2019 15:30:00 | 08/26/2019 15:30:00 | 08/25/2019 06:55:47 | 08/25/2019 15:09:37
3550488 | 675858602 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859110 | 12/24/2019 06:30:00 | 12/24/2019 06:30:00 | 12/27/2021 14:00:51 | 12/27/2021 14:00:50
3550488 | 675858602 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858796 |  |  |  |  | 08/20/2019 11:50:00 | 08/20/2019 11:50:00 |  | 08/20/2019 11:50:00
3550488 | 675858602 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858739 |  |  |  |  | 08/20/2019 05:50:00 | 08/20/2019 05:50:00 |  | 08/20/2019 05:50:00
3550488 | 675858602 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858646 |  |  |  |  | 08/20/2019 16:50:00 | 08/20/2019 16:50:00 |  | 08/20/2019 16:50:00
3550488 | 675858602 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858680 |  |  |  |  | 12/24/2019 06:30:00 | 12/24/2019 06:30:00 |  | 12/23/2019 17:35:56
3550488 | 675858602 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062682 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550488 | 675858602 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063149 |  |  |  |  | 12/24/2019 06:30:00 | 12/27/2021 14:00:50
3550489 | 675858614 | act--02 Integration | 02 Integration | Completed | Activity | 675858941 | 01/02/2020 15:20:00 | 01/02/2020 15:20:00 | 01/02/2020 13:50:00 | 01/02/2020 15:20:00
3550489 | 675858614 | act--04 SSV | 04 SSV | Completed | Activity | 675859041 | 03/06/2020 15:30:00 | 03/06/2020 15:30:00 | 03/05/2020 06:54:40 | 03/05/2020 14:15:59
3550489 | 675858614 | act--06 Tuning | 06 Tuning | Completed | Activity | 675859136 | 04/28/2021 05:30:01 | 04/28/2021 05:30:01 | 04/01/2021 06:00:00 | 04/28/2021 06:00:01
3550489 | 675858614 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858842 |  |  |  |  | 01/02/2020 11:50:00 | 01/02/2020 11:50:00 |  | 01/02/2020 11:50:00
3550489 | 675858614 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858765 |  |  |  |  | 01/02/2020 05:50:00 | 01/02/2020 05:50:00 |  | 01/02/2020 05:50:00
3550489 | 675858614 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858658 |  |  |  |  | 01/02/2020 16:50:00 | 01/02/2020 16:50:00 |  | 01/02/2020 16:50:00
3550489 | 675858614 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858703 |  |  |  |  | 03/06/2020 06:30:00 | 03/06/2020 06:30:00 |  | 03/06/2020 07:43:34
3550489 | 675858614 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062975 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550489 | 675858614 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063134 |  |  |  |  | 04/28/2021 05:30:01 | 07/30/2021 07:00:00
3550490 | 675858616 | act--02 Integration | 02 Integration | Completed | Activity | 675858944 | 11/11/2019 15:20:00 | 11/11/2019 15:20:00 | 11/11/2019 13:50:00 | 11/11/2019 15:20:00
3550490 | 675858616 | act--04 SSV | 04 SSV | Completed | Activity | 675859042 | 11/29/2019 15:30:00 | 11/27/2019 15:30:00 | 11/27/2019 07:46:09 | 11/27/2019 13:20:44
3550490 | 675858616 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859149 | 03/06/2020 06:30:00 | 03/06/2020 06:30:00 | 12/27/2021 14:00:48 | 12/27/2021 14:00:47
3550490 | 675858616 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858857 |  |  |  |  | 11/11/2019 11:50:00 | 11/11/2019 11:50:00 |  | 11/11/2019 11:50:00
3550490 | 675858616 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858776 |  |  |  |  | 11/11/2019 05:50:00 | 11/11/2019 05:50:00 |  | 11/11/2019 05:50:00
3550490 | 675858616 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858666 |  |  |  |  | 11/11/2019 16:50:00 | 11/11/2019 16:50:00 |  | 11/11/2019 16:50:00
3550490 | 675858616 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858718 |  |  |  |  | 03/06/2020 06:30:00 | 03/06/2020 06:30:00 |  | 03/05/2020 17:38:46
3550490 | 675858616 | ms--07 PAC | 07 PAC | Completed | Milestone | 718059442 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550490 | 675858616 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718059759 |  |  |  |  | 03/06/2020 06:30:00 | 12/27/2021 14:00:47
3550491 | 675858613 | act--02 Integration | 02 Integration | Completed | Activity | 675858942 | 12/11/2019 15:00:00 | 12/11/2019 15:00:00 | 12/11/2019 13:30:00 | 12/11/2019 15:00:00
3550491 | 675858613 | act--04 SSV | 04 SSV | Completed | Activity | 675859040 | 03/10/2020 15:30:00 | 03/10/2020 15:30:00 | 03/10/2020 07:51:58 | 03/10/2020 14:35:21
3550491 | 675858613 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859138 | 03/11/2020 06:30:00 | 03/11/2020 06:30:00 | 12/27/2021 14:13:05 | 12/27/2021 14:13:01
3550491 | 675858613 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858863 |  |  |  |  | 12/11/2019 11:30:00 | 12/11/2019 11:30:00 |  | 12/11/2019 11:30:00
3550491 | 675858613 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858779 |  |  |  |  | 12/11/2019 05:30:00 | 12/11/2019 05:30:00 |  | 12/11/2019 05:30:00
3550491 | 675858613 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858663 |  |  |  |  | 12/11/2019 16:30:00 | 12/11/2019 16:30:00 |  | 12/11/2019 16:30:00
3550491 | 675858613 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858710 |  |  |  |  | 03/11/2020 06:30:00 | 03/11/2020 06:30:00 |  | 03/11/2020 07:29:25
3550491 | 675858613 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061784 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550491 | 675858613 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062077 |  |  |  |  | 03/11/2020 06:30:00 | 07/30/2021 05:30:00
3550492 | 675858621 | act--02 Integration | 02 Integration | Completed | Activity | 675859043 | 10/17/2019 15:00:00 | 10/17/2019 15:00:00 | 10/17/2019 13:30:00 | 10/17/2019 15:00:00
3550492 | 675858621 | act--04 SSV | 04 SSV | Completed | Activity | 675859144 | 11/27/2019 15:30:00 | 11/28/2019 15:30:00 | 11/26/2019 08:14:40 | 11/26/2019 13:29:48
3550492 | 675858621 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859319 | 03/11/2020 06:30:00 | 03/11/2020 06:30:00 | 12/27/2021 14:20:45 | 12/27/2021 14:20:42
3550492 | 675858621 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858960 |  |  |  |  | 10/17/2019 11:30:00 | 10/17/2019 11:30:00 |  | 10/17/2019 11:30:00
3550492 | 675858621 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858909 |  |  |  |  | 10/17/2019 05:30:00 | 10/17/2019 05:30:00 |  | 10/17/2019 05:30:00
3550492 | 675858621 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858721 |  |  |  |  | 10/17/2019 16:30:00 | 10/17/2019 16:30:00 |  | 10/17/2019 16:30:00
3550492 | 675858621 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858815 |  |  |  |  | 03/11/2020 06:30:00 | 03/11/2020 06:30:00 |  | 03/10/2020 17:09:57
3550492 | 675858621 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062036 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550492 | 675858621 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062583 |  |  |  |  | 03/11/2020 06:30:00 | 07/30/2021 05:30:00
3550493 | 675858625 | act--02 Integration | 02 Integration | Completed | Activity | 675859031 | 08/19/2019 15:00:00 | 08/19/2019 15:00:00 | 08/19/2019 13:30:00 | 08/19/2019 15:00:00
3550493 | 675858625 | act--04 SSV | 04 SSV | Completed | Activity | 675859137 | 08/29/2019 15:30:00 | 08/28/2019 15:30:00 | 08/27/2019 07:57:14 | 08/27/2019 15:12:39
3550493 | 675858625 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859331 | 11/27/2019 06:30:00 | 11/27/2019 06:30:00 | 12/27/2021 14:20:50 | 12/27/2021 14:20:50
3550493 | 675858625 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858951 |  |  |  |  | 08/19/2019 11:30:00 | 08/19/2019 11:30:00 |  | 08/19/2019 11:30:00
3550493 | 675858625 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858899 |  |  |  |  | 08/19/2019 05:30:00 | 08/19/2019 05:30:00 |  | 08/19/2019 05:30:00
3550493 | 675858625 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858711 |  |  |  |  | 08/19/2019 16:30:00 | 08/19/2019 16:30:00 |  | 08/19/2019 16:30:00
3550493 | 675858625 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858783 |  |  |  |  | 11/27/2019 06:30:00 | 11/27/2019 06:30:00 |  | 11/26/2019 17:45:08
3550493 | 675858625 | ms--07 PAC | 07 PAC | Completed | Milestone | 718063056 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550493 | 675858625 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063200 |  |  |  |  | 11/27/2019 06:30:00 | 07/30/2021 05:30:00
3550494 | 675858629 | act--02 Integration | 02 Integration | Completed | Activity | 675859019 | 10/10/2019 15:20:00 | 10/10/2019 15:20:00 | 10/10/2019 13:50:00 | 10/10/2019 15:20:00
3550494 | 675858629 | act--04 SSV | 04 SSV | Completed | Activity | 675859139 | 12/13/2019 15:30:00 | 12/14/2019 15:30:00 | 12/13/2019 07:26:33 | 12/13/2019 13:56:23
3550494 | 675858629 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859312 | 12/14/2019 06:30:00 | 12/14/2019 06:30:00 | 12/27/2021 14:26:09 | 12/27/2021 14:26:07
3550494 | 675858629 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858933 |  |  |  |  | 10/10/2019 11:50:00 | 10/10/2019 11:50:00 |  | 10/10/2019 11:50:00
3550494 | 675858629 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858881 |  |  |  |  | 10/10/2019 05:50:00 | 10/10/2019 05:50:00 |  | 10/10/2019 05:50:00
3550494 | 675858629 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858691 |  |  |  |  | 10/10/2019 16:50:00 | 10/10/2019 16:50:00 |  | 10/10/2019 16:50:00
3550494 | 675858629 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858764 |  |  |  |  | 12/14/2019 06:30:00 | 12/14/2019 06:30:00 |  | 12/14/2019 08:49:10
3550494 | 675858629 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061312 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550494 | 675858629 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061589 |  |  |  |  | 12/14/2019 06:30:00 | 07/30/2021 05:30:00
3550495 | 675858639 | act--02 Integration | 02 Integration | Completed | Activity | 675859023 | 01/15/2020 15:00:00 | 01/15/2020 15:00:00 | 01/15/2020 13:30:00 | 01/15/2020 15:00:00
3550495 | 675858639 | act--04 SSV | 04 SSV | Completed | Activity | 675859134 | 03/05/2020 15:30:00 | 03/06/2020 15:30:00 | 03/05/2020 07:17:15 | 03/05/2020 13:34:08
3550495 | 675858639 | act--06 Tuning | 06 Tuning | Completed | Activity | 675859290 | 04/28/2021 05:30:01 | 04/28/2021 05:30:01 | 04/01/2021 06:00:00 | 04/28/2021 06:00:01
3550495 | 675858639 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858935 |  |  |  |  | 01/15/2020 11:30:00 | 01/15/2020 11:30:00 |  | 01/15/2020 11:30:00
3550495 | 675858639 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858887 |  |  |  |  | 01/15/2020 05:30:00 | 01/15/2020 05:30:00 |  | 01/15/2020 05:30:00
3550495 | 675858639 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858697 |  |  |  |  | 01/15/2020 16:30:00 | 01/15/2020 16:30:00 |  | 01/15/2020 16:30:00
3550495 | 675858639 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858756 |  |  |  |  | 03/06/2020 06:30:00 | 03/06/2020 06:30:00 |  | 03/06/2020 08:45:58
3550495 | 675858639 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061315 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550495 | 675858639 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061569 |  |  |  |  | 04/28/2021 05:30:01 | 07/30/2021 07:00:00
3550496 | 675858641 | act--02 Integration | 02 Integration | Completed | Activity | 675859016 | 09/12/2019 15:00:00 | 09/12/2019 15:00:00 | 09/12/2019 13:30:00 | 09/12/2019 15:00:00
3550496 | 675858641 | act--04 SSV | 04 SSV | Completed | Activity | 675859135 | 01/13/2020 15:30:00 | 01/15/2020 15:30:00 | 01/13/2020 08:38:43 | 01/13/2020 14:28:47
3550496 | 675858641 | act--06 Tuning | 06 Tuning | Completed | Activity | 675859297 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550496 | 675858641 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675858934 |  |  |  |  | 09/12/2019 11:30:00 | 09/12/2019 11:30:00 |  | 09/12/2019 11:30:00
3550496 | 675858641 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675858888 |  |  |  |  | 09/12/2019 05:30:00 | 09/12/2019 05:30:00 |  | 09/12/2019 05:30:00
3550496 | 675858641 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675858709 |  |  |  |  | 09/12/2019 16:30:00 | 09/12/2019 16:30:00 |  | 09/12/2019 16:30:00
3550496 | 675858641 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675858775 |  |  |  |  | 03/06/2020 06:30:00 | 03/06/2020 06:30:00 |  | 03/05/2020 16:43:17
3550496 | 675858641 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062872 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550496 | 675858641 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063105 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550497 | 675858896 | act--02 Integration | 02 Integration | Completed | Activity | 675859621 | 09/05/2019 15:30:00 | 09/05/2019 15:30:00 | 09/05/2019 14:00:00 | 09/05/2019 15:30:00
3550497 | 675858896 | act--04 SSV | 04 SSV | Completed | Activity | 675859830 | 10/26/2019 15:30:00 | 10/26/2019 15:30:00 | 10/25/2019 07:54:29 | 10/25/2019 14:31:13
3550497 | 675858896 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860052 | 01/14/2020 06:30:00 | 01/14/2020 06:30:00 | 12/27/2021 14:01:01 | 12/27/2021 14:01:00
3550497 | 675858896 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859444 |  |  |  |  | 09/05/2019 12:00:00 | 09/05/2019 12:00:00 |  | 09/05/2019 12:00:00
3550497 | 675858896 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859330 |  |  |  |  | 09/05/2019 06:00:00 | 09/05/2019 06:00:00 |  | 09/05/2019 06:00:00
3550497 | 675858896 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859045 |  |  |  |  | 09/05/2019 17:00:00 | 09/05/2019 17:00:00 |  | 09/05/2019 17:00:00
3550497 | 675858896 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859153 |  |  |  |  | 01/14/2020 06:30:00 | 01/14/2020 06:30:00 |  | 01/13/2020 17:06:41
3550497 | 675858896 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062960 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550497 | 675858896 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063104 |  |  |  |  | 01/14/2020 06:30:00 | 12/27/2021 14:01:00
3550498 | 675858905 | act--02 Integration | 02 Integration | Completed | Activity | 675859528 | 11/14/2019 15:00:00 | 11/14/2019 15:00:00 | 11/14/2019 13:30:00 | 11/14/2019 15:00:00
3550498 | 675858905 | act--04 SSV | 04 SSV | Completed | Activity | 675859751 | 12/29/2019 15:30:00 | 12/29/2019 15:30:00 | 12/27/2019 07:24:06 | 12/27/2019 15:28:13
3550498 | 675858905 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860009 | 12/28/2019 06:30:00 | 12/28/2019 06:30:00 | 12/27/2021 14:13:30 | 12/27/2021 14:13:27
3550498 | 675858905 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859336 |  |  |  |  | 11/14/2019 11:30:00 | 11/14/2019 11:30:00 |  | 11/14/2019 11:30:00
3550498 | 675858905 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859248 |  |  |  |  | 11/14/2019 05:30:00 | 11/14/2019 05:30:00 |  | 11/14/2019 05:30:00
3550498 | 675858905 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859030 |  |  |  |  | 11/14/2019 16:30:00 | 11/14/2019 16:30:00 |  | 11/14/2019 16:30:00
3550498 | 675858905 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859129 |  |  |  |  | 12/28/2019 06:30:00 | 12/28/2019 06:30:00 |  | 12/28/2019 07:59:34
3550498 | 675858905 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062783 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550498 | 675858905 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063106 |  |  |  |  | 12/28/2019 06:30:00 | 07/30/2021 05:30:00
3550499 | 675858915 | act--02 Integration | 02 Integration | Completed | Activity | 675859516 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550499 | 675858915 | act--04 SSV | 04 SSV | Completed | Activity | 675859720 | 03/23/2021 05:30:00 | 03/23/2021 05:30:00 | 03/23/2021 05:05:00 | 03/25/2021 06:55:00
3550499 | 675858915 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859962 | 03/25/2021 08:55:00 | 03/25/2021 08:55:00 | 12/29/2021 09:28:35 | 12/29/2021 09:28:34
3550499 | 675858915 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859337 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550499 | 675858915 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859232 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550499 | 675858915 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859038 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550499 | 675858915 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859127 |  |  |  |  | 03/25/2021 08:55:00 | 03/25/2021 08:55:00 |  | 03/26/2021 05:00:00
3550499 | 675858915 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061522 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550499 | 675858915 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061623 |  |  |  |  | 03/25/2021 08:55:00 | 12/29/2021 09:28:34
3550500 | 675858922 | act--02 Integration | 02 Integration | Completed | Activity | 675859685 | 08/15/2019 15:00:00 | 08/15/2019 15:00:00 | 08/15/2019 13:30:00 | 08/15/2019 15:00:00
3550500 | 675858922 | act--04 SSV | 04 SSV | Completed | Activity | 675859909 | 08/26/2019 15:30:00 | 08/27/2019 15:30:00 | 08/25/2019 07:56:57 | 08/25/2019 13:23:29
3550500 | 675858922 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860173 | 12/28/2019 06:30:00 | 12/28/2019 06:30:00 | 12/27/2021 14:00:53 | 12/27/2021 14:00:51
3550500 | 675858922 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859515 |  |  |  |  | 08/15/2019 11:30:00 | 08/15/2019 11:30:00 |  | 08/15/2019 11:30:00
3550500 | 675858922 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859404 |  |  |  |  | 08/15/2019 05:30:00 | 08/15/2019 05:30:00 |  | 08/15/2019 05:30:00
3550500 | 675858922 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859143 |  |  |  |  | 08/15/2019 16:30:00 | 08/15/2019 16:30:00 |  | 08/15/2019 16:30:00
3550500 | 675858922 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859266 |  |  |  |  | 12/28/2019 06:30:00 | 12/28/2019 06:30:00 |  | 12/27/2019 16:55:02
3550500 | 675858922 | ms--07 PAC | 07 PAC | Completed | Milestone | 718060956 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550500 | 675858922 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061266 |  |  |  |  | 12/28/2019 06:30:00 | 12/27/2021 14:00:51
3550501 | 675858924 | act--02 Integration | 02 Integration | Completed | Activity | 675859762 | 03/06/2020 15:10:00 | 03/06/2020 15:10:00 | 03/06/2020 13:40:00 | 03/06/2020 15:10:00
3550501 | 675858924 | act--04 SSV | 04 SSV | Completed | Activity | 675860018 | 03/12/2020 15:30:00 | 03/11/2020 15:30:00 | 03/10/2020 07:03:53 | 03/10/2020 13:08:42
3550501 | 675858924 | act--06 Tuning | 06 Tuning | Completed | Activity | 675860271 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550501 | 675858924 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859598 |  |  |  |  | 03/06/2020 11:40:00 | 03/06/2020 11:40:00 |  | 03/06/2020 11:40:00
3550501 | 675858924 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859484 |  |  |  |  | 03/06/2020 05:40:00 | 03/06/2020 05:40:00 |  | 03/06/2020 05:40:00
3550501 | 675858924 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859161 |  |  |  |  | 03/06/2020 16:40:00 | 03/06/2020 16:40:00 |  | 03/06/2020 16:40:00
3550501 | 675858924 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859306 |  |  |  |  | 03/11/2020 06:30:00 | 03/11/2020 06:30:00 |  | 03/11/2020 08:41:16
3550501 | 675858924 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061309 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550501 | 675858924 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061585 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550502 | 675858923 | act--02 Integration | 02 Integration | Completed | Activity | 675859626 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550502 | 675858923 | act--04 SSV | 04 SSV | Completed | Activity | 675859820 | 01/06/2021 15:30:00 | 01/05/2021 15:30:00 | 01/05/2021 07:13:38 | 01/05/2021 13:06:23
3550502 | 675858923 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860061 | 01/06/2021 06:30:00 | 01/06/2021 06:30:00 | 12/27/2021 14:00:33 | 12/27/2021 14:00:31
3550502 | 675858923 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859455 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550502 | 675858923 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859356 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550502 | 675858923 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859111 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550502 | 675858923 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859207 |  |  |  |  | 01/06/2021 06:30:00 | 01/06/2021 06:30:00 |  | 01/06/2021 08:28:55
3550502 | 675858923 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061022 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550502 | 675858923 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061282 |  |  |  |  | 01/06/2021 06:30:00 | 12/27/2021 14:00:31
3550503 | 675858920 | act--02 Integration | 02 Integration | Completed | Activity | 675859771 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550503 | 675858920 | act--04 SSV | 04 SSV | Completed | Activity | 675860011 | 04/12/2021 05:30:00 | 04/12/2021 05:30:00 | 04/12/2021 06:17:00 | 04/14/2021 07:35:00
3550503 | 675858920 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860283 | 04/14/2021 09:55:00 | 04/14/2021 09:55:00 | 12/27/2021 14:12:56 | 12/27/2021 14:12:55
3550503 | 675858920 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859610 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550503 | 675858920 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859487 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550503 | 675858920 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859152 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550503 | 675858920 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859320 |  |  |  |  | 04/14/2021 09:55:00 | 04/14/2021 09:55:00 |  | 04/15/2021 05:00:00
3550503 | 675858920 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061075 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550503 | 675858920 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061338 |  |  |  |  | 04/14/2021 09:55:00 | 07/30/2021 05:30:00
3550504 | 675858918 | act--02 Integration | 02 Integration | Completed | Activity | 675859643 | 10/18/2019 15:00:00 | 10/18/2019 15:00:00 | 10/18/2019 13:40:01 | 10/18/2019 15:00:00
3550504 | 675858918 | act--04 SSV | 04 SSV | Completed | Activity | 675859858 | 10/12/2020 15:30:00 | 10/12/2020 15:30:00 | 10/11/2020 07:06:13 | 10/11/2020 14:54:34
3550504 | 675858918 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860072 | 01/06/2021 06:30:00 | 01/06/2021 06:30:00 | 12/27/2021 14:20:21 | 12/27/2021 14:20:20
3550504 | 675858918 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859475 |  |  |  |  | 10/21/2019 15:30:00 | 10/20/2019 15:30:00 |  | 10/18/2019 12:30:00
3550504 | 675858918 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859376 |  |  |  |  | 10/16/2019 06:30:00 | 10/17/2019 06:30:00 |  | 10/18/2019 06:30:00
3550504 | 675858918 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859108 |  |  |  |  | 10/18/2019 14:30:00 | 10/18/2019 15:00:00 |  | 10/18/2019 16:00:00
3550504 | 675858918 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859209 |  |  |  |  | 01/06/2021 06:30:00 | 01/06/2021 06:30:00 |  | 01/05/2021 16:31:14
3550504 | 675858918 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061292 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550504 | 675858918 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061584 |  |  |  |  | 01/06/2021 06:30:00 | 07/30/2021 05:30:00
3550505 | 675858921 | act--02 Integration | 02 Integration | Completed | Activity | 675859529 | 09/23/2019 15:00:00 | 09/23/2019 15:00:00 | 09/23/2019 13:30:00 | 09/23/2019 15:00:00
3550505 | 675858921 | act--04 SSV | 04 SSV | Completed | Activity | 675859741 | 10/24/2019 15:30:00 | 10/24/2019 15:30:00 | 10/22/2019 08:15:33 | 10/22/2019 13:36:35
3550505 | 675858921 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675859988 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:07:18 | 12/27/2021 14:07:15
3550505 | 675858921 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859357 |  |  |  |  | 09/23/2019 11:30:00 | 09/23/2019 11:30:00 |  | 09/23/2019 11:30:00
3550505 | 675858921 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859267 |  |  |  |  | 09/23/2019 05:30:00 | 09/23/2019 05:30:00 |  | 09/23/2019 05:30:00
3550505 | 675858921 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859049 |  |  |  |  | 09/23/2019 16:30:00 | 09/23/2019 16:30:00 |  | 09/23/2019 16:30:00
3550505 | 675858921 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859142 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/11/2020 17:50:51
3550505 | 675858921 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062114 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550505 | 675858921 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062588 |  |  |  |  | 10/12/2020 06:30:00 | 12/27/2021 14:07:15
3550506 | 675858919 | act--02 Integration | 02 Integration | Completed | Activity | 675859818 | 09/05/2019 15:00:00 | 09/05/2019 15:00:00 | 09/05/2019 13:30:00 | 09/05/2019 15:00:00
3550506 | 675858919 | act--04 SSV | 04 SSV | Completed | Activity | 675860031 | 03/30/2020 15:30:00 | 03/30/2020 15:30:00 | 03/29/2020 08:03:54 | 03/29/2020 14:20:19
3550506 | 675858919 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860305 | 03/30/2020 06:30:00 | 03/30/2020 06:30:00 | 12/27/2021 14:26:32 | 12/27/2021 14:26:29
3550506 | 675858919 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859644 |  |  |  |  | 09/05/2019 11:30:00 | 09/05/2019 11:30:00 |  | 09/05/2019 11:30:00
3550506 | 675858919 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859530 |  |  |  |  | 09/05/2019 05:30:00 | 09/05/2019 05:30:00 |  | 09/05/2019 05:30:00
3550506 | 675858919 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859177 |  |  |  |  | 09/05/2019 16:30:00 | 09/05/2019 16:30:00 |  | 09/05/2019 16:30:00
3550506 | 675858919 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859338 |  |  |  |  | 03/30/2020 06:30:00 | 03/30/2020 06:30:00 |  | 03/30/2020 08:12:41
3550506 | 675858919 | ms--07 PAC | 07 PAC | Completed | Milestone | 718059136 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550506 | 675858919 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718059768 |  |  |  |  | 03/30/2020 06:30:00 | 07/30/2021 05:30:00
3550507 | 675858965 | act--02 Integration | 02 Integration | Completed | Activity | 675859770 | 08/21/2019 15:00:00 | 08/21/2019 15:00:00 | 08/21/2019 13:30:00 | 08/21/2019 15:00:00
3550507 | 675858965 | act--04 SSV | 04 SSV | Completed | Activity | 675860022 | 08/31/2019 15:30:00 | 08/29/2019 15:30:00 | 08/29/2019 07:42:43 | 08/29/2019 14:20:09
3550507 | 675858965 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860262 | 03/30/2020 06:30:00 | 03/30/2020 06:30:00 | 12/27/2021 14:00:54 | 12/27/2021 14:00:50
3550507 | 675858965 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859601 |  |  |  |  | 08/21/2019 11:30:00 | 08/21/2019 11:30:00 |  | 08/21/2019 11:30:00
3550507 | 675858965 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859470 |  |  |  |  | 08/21/2019 05:30:00 | 08/21/2019 05:30:00 |  | 08/21/2019 05:30:00
3550507 | 675858965 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859159 |  |  |  |  | 08/21/2019 16:30:00 | 08/21/2019 16:30:00 |  | 08/21/2019 16:30:00
3550507 | 675858965 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859305 |  |  |  |  | 03/30/2020 06:30:00 | 03/30/2020 06:30:00 |  | 03/29/2020 17:16:28
3550507 | 675858965 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061937 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550507 | 675858965 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062379 |  |  |  |  | 03/30/2020 06:30:00 | 12/27/2021 14:00:50
3550508 | 675858968 | act--02 Integration | 02 Integration | Completed | Activity | 675859799 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550508 | 675858968 | act--04 SSV | 04 SSV | Completed | Activity | 675860026 | 01/12/2021 15:30:00 | 01/14/2021 15:30:00 | 01/12/2021 06:59:09 | 01/12/2021 15:28:15
3550508 | 675858968 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860308 | 01/13/2021 06:30:00 | 01/13/2021 06:30:00 | 12/27/2021 14:26:09 | 12/27/2021 14:26:07
3550508 | 675858968 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859653 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550508 | 675858968 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859534 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550508 | 675858968 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859184 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550508 | 675858968 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859346 |  |  |  |  | 01/13/2021 06:30:00 | 01/13/2021 06:30:00 |  | 01/13/2021 08:40:26
3550508 | 675858968 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061306 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550508 | 675858968 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061572 |  |  |  |  | 01/13/2021 06:30:00 | 07/30/2021 05:30:00
3550509 | 675858966 | act--02 Integration | 02 Integration | Completed | Activity | 675859807 | 08/21/2019 15:20:00 | 08/21/2019 15:20:00 | 08/21/2019 13:50:00 | 08/21/2019 15:20:00
3550509 | 675858966 | act--04 SSV | 04 SSV | Completed | Activity | 675860025 | 12/12/2019 15:30:00 | 12/10/2019 15:30:00 | 12/10/2019 08:23:52 | 12/10/2019 14:05:58
3550509 | 675858966 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860294 | 12/20/2019 06:30:00 | 12/20/2019 06:30:00 | 12/27/2021 14:26:28 | 12/27/2021 14:26:27
3550509 | 675858966 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859666 |  |  |  |  | 08/21/2019 11:50:00 | 08/21/2019 11:50:00 |  | 08/21/2019 11:50:00
3550509 | 675858966 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859556 |  |  |  |  | 08/21/2019 05:50:00 | 08/21/2019 05:50:00 |  | 08/21/2019 05:50:00
3550509 | 675858966 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859222 |  |  |  |  | 08/21/2019 16:50:00 | 08/21/2019 16:50:00 |  | 08/21/2019 16:50:00
3550509 | 675858966 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859371 |  |  |  |  | 12/20/2019 06:30:00 | 12/20/2019 06:30:00 |  | 12/20/2019 07:00:00
3550509 | 675858966 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061511 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550509 | 675858966 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061619 |  |  |  |  | 12/20/2019 06:30:00 | 07/30/2021 05:30:00
3550510 | 675858967 | act--02 Integration | 02 Integration | Completed | Activity | 675859690 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550510 | 675858967 | act--04 SSV | 04 SSV | Completed | Activity | 675859919 | 03/27/2021 05:30:00 | 03/27/2021 05:30:00 | 03/27/2021 08:30:00 | 03/29/2021 07:15:00
3550510 | 675858967 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860183 | 03/29/2021 09:15:00 | 03/29/2021 09:15:00 | 12/27/2021 14:20:25 | 12/27/2021 14:20:24
3550510 | 675858967 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859522 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550510 | 675858967 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859410 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550510 | 675858967 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859148 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550510 | 675858967 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859274 |  |  |  |  | 03/29/2021 09:15:00 | 03/29/2021 09:15:00 |  | 03/30/2021 05:00:00
3550510 | 675858967 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061541 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550510 | 675858967 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061651 |  |  |  |  | 03/29/2021 09:15:00 | 07/30/2021 05:30:00
3550511 | 675858973 | act--02 Integration | 02 Integration | Completed | Activity | 675859779 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550511 | 675858973 | act--04 SSV | 04 SSV | Completed | Activity | 675860017 | 03/24/2021 05:30:00 | 03/24/2021 05:30:00 | 03/24/2021 10:00:00 | 03/26/2021 10:20:00
3550511 | 675858973 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860277 | 03/26/2021 12:20:00 | 03/26/2021 12:20:00 | 12/27/2021 14:06:45 | 12/27/2021 14:06:44
3550511 | 675858973 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859627 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550511 | 675858973 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859500 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550511 | 675858973 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859188 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550511 | 675858973 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859329 |  |  |  |  | 03/26/2021 12:20:00 | 03/26/2021 12:20:00 |  | 03/27/2021 05:00:00
3550511 | 675858973 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061542 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550511 | 675858973 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061643 |  |  |  |  | 03/26/2021 12:20:00 | 12/27/2021 14:06:44
3550512 | 675859053 | act--02 Integration | 02 Integration | Completed | Activity | 675860245 | 09/04/2019 15:00:00 | 09/04/2019 15:00:00 | 09/04/2019 13:30:00 | 09/04/2019 15:00:00
3550512 | 675859053 | act--04 SSV | 04 SSV | Completed | Activity | 675860516 | 03/07/2020 15:30:00 | 03/07/2020 15:30:00 | 03/06/2020 06:44:46 | 03/06/2020 14:13:15
3550512 | 675859053 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860756 | 03/07/2020 06:30:00 | 03/07/2020 06:30:00 | 12/27/2021 14:13:26 | 12/27/2021 14:13:23
3550512 | 675859053 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860038 |  |  |  |  | 09/04/2019 11:30:00 | 09/04/2019 11:30:00 |  | 09/04/2019 11:30:00
3550512 | 675859053 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859908 |  |  |  |  | 09/04/2019 05:30:00 | 09/04/2019 05:30:00 |  | 09/04/2019 05:30:00
3550512 | 675859053 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859523 |  |  |  |  | 09/04/2019 16:30:00 | 09/04/2019 16:30:00 |  | 09/04/2019 16:30:00
3550512 | 675859053 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859700 |  |  |  |  | 03/07/2020 06:30:00 | 03/07/2020 06:30:00 |  | 03/07/2020 08:49:55
3550512 | 675859053 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061866 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550512 | 675859053 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062076 |  |  |  |  | 03/07/2020 06:30:00 | 07/30/2021 05:30:00
3550513 | 675859052 | act--02 Integration | 02 Integration | Completed | Activity | 675859963 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550513 | 675859052 | act--04 SSV | 04 SSV | Completed | Activity | 675860211 | 03/24/2021 05:30:00 | 03/24/2021 05:30:00 | 03/24/2021 04:50:00 | 03/25/2021 01:00:00
3550513 | 675859052 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860482 | 03/25/2021 09:00:00 | 03/25/2021 09:00:00 | 12/27/2021 14:06:18 | 12/27/2021 14:06:17
3550513 | 675859052 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859774 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550513 | 675859052 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859671 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550513 | 675859052 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859328 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550513 | 675859052 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859504 |  |  |  |  | 03/25/2021 09:00:00 | 03/25/2021 09:00:00 |  | 03/25/2021 17:00:00
3550513 | 675859052 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061487 |  |  |  |  | 07/31/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550513 | 675859052 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061614 |  |  |  |  | 03/25/2021 09:00:00 | 07/30/2021 05:30:00
3550514 | 675859081 | act--02 Integration | 02 Integration | Completed | Activity | 675860181 | 08/27/2019 15:00:00 | 08/27/2019 15:00:00 | 08/27/2019 13:30:00 | 08/27/2019 15:00:00
3550514 | 675859081 | act--04 SSV | 04 SSV | Completed | Activity | 675860437 | 09/05/2019 15:30:00 | 09/05/2019 15:30:00 | 09/03/2019 08:20:47 | 09/03/2019 13:10:19
3550514 | 675859081 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860708 | 03/07/2020 06:30:00 | 03/07/2020 06:30:00 | 12/27/2021 14:20:49 | 12/27/2021 14:20:48
3550514 | 675859081 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859989 |  |  |  |  | 08/27/2019 11:30:00 | 08/27/2019 11:30:00 |  | 08/27/2019 11:30:00
3550514 | 675859081 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859861 |  |  |  |  | 08/27/2019 05:30:00 | 08/27/2019 05:30:00 |  | 08/27/2019 05:30:00
3550514 | 675859081 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859538 |  |  |  |  | 08/27/2019 16:30:00 | 08/27/2019 16:30:00 |  | 08/27/2019 16:30:00
3550514 | 675859081 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859708 |  |  |  |  | 03/07/2020 06:30:00 | 03/07/2020 06:30:00 |  | 03/06/2020 17:20:21
3550514 | 675859081 | ms--07 PAC | 07 PAC | Completed | Milestone | 718060932 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550514 | 675859081 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061276 |  |  |  |  | 03/07/2020 06:30:00 | 07/30/2021 05:30:00
3550515 | 675859082 | act--02 Integration | 02 Integration | Completed | Activity | 675860020 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550515 | 675859082 | act--04 SSV | 04 SSV | Completed | Activity | 675860284 | 11/08/2020 15:30:00 | 11/09/2020 15:30:00 | 11/07/2020 08:22:05 | 11/07/2020 13:45:47
3550515 | 675859082 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860537 | 11/08/2020 06:30:00 | 11/08/2020 06:30:00 | 12/27/2021 14:06:19 | 12/27/2021 14:06:17
3550515 | 675859082 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859828 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550515 | 675859082 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859733 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550515 | 675859082 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859366 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550515 | 675859082 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859539 |  |  |  |  | 11/08/2020 06:30:00 | 11/08/2020 06:30:00 |  | 11/08/2020 07:00:08
3550515 | 675859082 | ms--07 PAC | 07 PAC | Completed | Milestone | 718060844 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550515 | 675859082 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061214 |  |  |  |  | 11/08/2020 06:30:00 | 07/30/2021 05:30:00
3550516 | 675859083 | act--02 Integration | 02 Integration | Completed | Activity | 675859999 | 11/02/2019 15:00:00 | 11/02/2019 15:00:00 | 11/02/2019 13:30:00 | 11/02/2019 15:00:00
3550516 | 675859083 | act--04 SSV | 04 SSV | Completed | Activity | 675860246 | 12/26/2019 15:30:00 | 12/25/2019 15:30:00 | 12/24/2019 08:18:48 | 12/24/2019 13:57:58
3550516 | 675859083 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860527 | 11/08/2020 06:30:00 | 11/08/2020 06:30:00 | 12/27/2021 14:00:59 | 12/27/2021 14:00:56
3550516 | 675859083 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859802 |  |  |  |  | 11/02/2019 11:30:00 | 11/02/2019 11:30:00 |  | 11/02/2019 11:30:00
3550516 | 675859083 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859712 |  |  |  |  | 11/02/2019 05:30:00 | 11/02/2019 05:30:00 |  | 11/02/2019 05:30:00
3550516 | 675859083 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859360 |  |  |  |  | 11/02/2019 16:30:00 | 11/02/2019 16:30:00 |  | 11/02/2019 16:30:00
3550516 | 675859083 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859531 |  |  |  |  | 11/08/2020 06:30:00 | 11/08/2020 06:30:00 |  | 11/07/2020 16:20:21
3550516 | 675859083 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061313 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550516 | 675859083 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061565 |  |  |  |  | 11/08/2020 06:30:00 | 12/27/2021 14:00:56
3550517 | 675859080 | act--02 Integration | 02 Integration | Completed | Activity | 675860090 | 03/25/2020 15:00:00 | 03/25/2020 15:00:00 | 03/25/2020 13:40:01 | 03/25/2020 15:00:00
3550517 | 675859080 | act--04 SSV | 04 SSV | Completed | Activity | 675860350 | 03/21/2021 05:30:00 | 03/21/2021 05:30:00 | 03/21/2021 03:20:00 | 03/23/2021 07:00:00
3550517 | 675859080 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860592 | 03/23/2021 09:00:00 | 03/23/2021 09:00:00 | 12/27/2021 14:00:47 | 12/27/2021 14:00:45
3550517 | 675859080 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859905 |  |  |  |  | 03/28/2020 15:30:00 | 03/27/2020 15:30:00 |  | 03/25/2020 12:30:00
3550517 | 675859080 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859808 |  |  |  |  | 03/23/2020 06:30:00 | 03/24/2020 06:30:00 |  | 03/25/2020 06:30:00
3550517 | 675859080 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859489 |  |  |  |  | 03/25/2020 14:30:00 | 03/25/2020 15:00:00 |  | 03/25/2020 16:00:00
3550517 | 675859080 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859665 |  |  |  |  | 03/23/2021 09:00:00 | 03/23/2021 09:00:00 |  | 03/24/2021 05:00:00
3550517 | 675859080 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062378 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550517 | 675859080 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062811 |  |  |  |  | 03/23/2021 09:00:00 | 12/27/2021 14:00:45
3550518 | 675859085 | act--02 Integration | 02 Integration | Completed | Activity | 675859906 | 11/15/2019 15:00:00 | 11/15/2019 15:00:00 | 11/15/2019 13:30:00 | 11/15/2019 15:00:00
3550518 | 675859085 | act--04 SSV | 04 SSV | Completed | Activity | 675860194 | 12/26/2019 15:30:00 | 12/26/2019 15:30:00 | 12/25/2019 08:51:02 | 12/25/2019 14:10:31
3550518 | 675859085 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860462 | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 | 12/27/2021 14:13:32 | 12/27/2021 14:13:29
3550518 | 675859085 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859735 |  |  |  |  | 11/15/2019 11:30:00 | 11/15/2019 11:30:00 |  | 11/15/2019 11:30:00
3550518 | 675859085 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859638 |  |  |  |  | 11/15/2019 05:30:00 | 11/15/2019 05:30:00 |  | 11/15/2019 05:30:00
3550518 | 675859085 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859318 |  |  |  |  | 11/15/2019 16:30:00 | 11/15/2019 16:30:00 |  | 11/15/2019 16:30:00
3550518 | 675859085 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859480 |  |  |  |  | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/26/2019 06:41:49
3550518 | 675859085 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062635 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550518 | 675859085 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062894 |  |  |  |  | 12/26/2019 06:30:00 | 07/30/2021 05:30:00
3550519 | 675859087 | act--02 Integration | 02 Integration | Completed | Activity | 675859994 | 09/19/2019 15:20:00 | 09/19/2019 15:20:00 | 09/19/2019 13:50:00 | 09/19/2019 15:20:00
3550519 | 675859087 | act--04 SSV | 04 SSV | Completed | Activity | 675860221 | 10/20/2019 15:30:00 | 10/20/2019 15:30:00 | 10/19/2019 07:37:10 | 10/19/2019 13:17:10
3550519 | 675859087 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860480 | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 | 12/27/2021 14:26:46 | 12/27/2021 14:26:43
3550519 | 675859087 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859803 |  |  |  |  | 09/19/2019 11:50:00 | 09/19/2019 11:50:00 |  | 09/19/2019 11:50:00
3550519 | 675859087 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859711 |  |  |  |  | 09/19/2019 05:50:00 | 09/19/2019 05:50:00 |  | 09/19/2019 05:50:00
3550519 | 675859087 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859368 |  |  |  |  | 09/19/2019 16:50:00 | 09/19/2019 16:50:00 |  | 09/19/2019 16:50:00
3550519 | 675859087 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859541 |  |  |  |  | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/25/2019 17:35:56
3550519 | 675859087 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061501 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550519 | 675859087 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061613 |  |  |  |  | 12/26/2019 06:30:00 | 07/30/2021 05:30:00
3550520 | 675859086 | act--02 Integration | 02 Integration | Completed | Activity | 675860177 | 11/06/2019 15:00:00 | 11/06/2019 15:00:00 | 11/06/2019 13:30:00 | 11/06/2019 15:00:00
3550520 | 675859086 | act--04 SSV | 04 SSV | Completed | Activity | 675860412 | 01/01/2020 15:30:00 | 12/30/2019 15:30:00 | 12/30/2019 08:08:44 | 12/30/2019 13:29:19
3550520 | 675859086 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860706 | 12/31/2019 06:30:00 | 12/31/2019 06:30:00 | 12/27/2021 14:07:10 | 12/27/2021 14:07:05
3550520 | 675859086 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859995 |  |  |  |  | 11/06/2019 11:30:00 | 11/06/2019 11:30:00 |  | 11/06/2019 11:30:00
3550520 | 675859086 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859859 |  |  |  |  | 11/06/2019 05:30:00 | 11/06/2019 05:30:00 |  | 11/06/2019 05:30:00
3550520 | 675859086 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859537 |  |  |  |  | 11/06/2019 16:30:00 | 11/06/2019 16:30:00 |  | 11/06/2019 16:30:00
3550520 | 675859086 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859709 |  |  |  |  | 12/31/2019 06:30:00 | 12/31/2019 06:30:00 |  | 12/31/2019 06:55:20
3550520 | 675859086 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061102 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550520 | 675859086 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061353 |  |  |  |  | 12/31/2019 06:30:00 | 12/27/2021 14:07:05
3550521 | 675859117 | act--02 Integration | 02 Integration | Completed | Activity | 675860021 | 09/20/2019 15:00:00 | 09/20/2019 15:00:00 | 09/20/2019 13:30:00 | 09/20/2019 15:00:00
3550521 | 675859117 | act--04 SSV | 04 SSV | Completed | Activity | 675860275 | 10/21/2019 15:30:00 | 10/22/2019 15:30:00 | 10/21/2019 08:19:38 | 10/21/2019 14:39:22
3550521 | 675859117 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860528 | 12/31/2019 06:30:00 | 12/31/2019 06:30:00 | 12/27/2021 14:20:54 | 12/27/2021 14:20:54
3550521 | 675859117 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675859841 |  |  |  |  | 09/20/2019 11:30:00 | 09/20/2019 11:30:00 |  | 09/20/2019 11:30:00
3550521 | 675859117 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859749 |  |  |  |  | 09/20/2019 05:30:00 | 09/20/2019 05:30:00 |  | 09/20/2019 05:30:00
3550521 | 675859117 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859386 |  |  |  |  | 09/20/2019 16:30:00 | 09/20/2019 16:30:00 |  | 09/20/2019 16:30:00
3550521 | 675859117 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859555 |  |  |  |  | 12/31/2019 06:30:00 | 12/31/2019 06:30:00 |  | 12/30/2019 16:48:59
3550521 | 675859117 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061318 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550521 | 675859117 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061570 |  |  |  |  | 12/31/2019 06:30:00 | 07/30/2021 05:30:00
3550522 | 675859140 | act--02 Integration | 02 Integration | Completed | Activity | 675860257 | 10/18/2019 15:00:00 | 10/18/2019 15:00:00 | 10/18/2019 13:40:01 | 10/18/2019 15:00:00
3550522 | 675859140 | act--04 SSV | 04 SSV | Completed | Activity | 675860517 | 09/28/2020 15:30:00 | 09/27/2020 15:30:00 | 09/26/2020 08:21:19 | 09/26/2020 13:33:01
3550522 | 675859140 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860759 | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 | 12/27/2021 14:19:48 | 12/27/2021 14:19:47
3550522 | 675859140 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860051 |  |  |  |  | 10/21/2019 15:30:00 | 10/20/2019 15:30:00 |  | 10/18/2019 12:30:00
3550522 | 675859140 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859923 |  |  |  |  | 10/16/2019 06:30:00 | 10/17/2019 06:30:00 |  | 10/18/2019 06:30:00
3550522 | 675859140 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859569 |  |  |  |  | 10/18/2019 14:30:00 | 10/18/2019 15:00:00 |  | 10/18/2019 16:00:00
3550522 | 675859140 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859746 |  |  |  |  | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 |  | 09/27/2020 07:37:03
3550522 | 675859140 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062025 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550522 | 675859140 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062394 |  |  |  |  | 09/27/2020 06:30:00 | 07/30/2021 05:30:00
3550523 | 675859145 | act--02 Integration | 02 Integration | Completed | Activity | 675860291 | 12/28/2019 15:00:00 | 12/28/2019 15:00:00 | 12/28/2019 13:30:00 | 12/28/2019 15:00:00
3550523 | 675859145 | act--04 SSV | 04 SSV | Completed | Activity | 675860582 | 01/12/2020 15:30:00 | 01/11/2020 15:30:00 | 01/11/2020 06:54:33 | 01/11/2020 13:16:54
3550523 | 675859145 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860808 | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 | 12/27/2021 14:13:06 | 12/27/2021 14:13:02
3550523 | 675859145 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860088 |  |  |  |  | 12/28/2019 11:30:00 | 12/28/2019 11:30:00 |  | 12/28/2019 11:30:00
3550523 | 675859145 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859980 |  |  |  |  | 12/28/2019 05:30:00 | 12/28/2019 05:30:00 |  | 12/28/2019 05:30:00
3550523 | 675859145 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859622 |  |  |  |  | 12/28/2019 16:30:00 | 12/28/2019 16:30:00 |  | 12/28/2019 16:30:00
3550523 | 675859145 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859791 |  |  |  |  | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 |  | 09/26/2020 17:03:45
3550523 | 675859145 | ms--07 PAC | 07 PAC | Completed | Milestone | 718060863 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550523 | 675859145 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061222 |  |  |  |  | 09/27/2020 06:30:00 | 07/30/2021 05:30:00
3550524 | 675859167 | act--02 Integration | 02 Integration | Completed | Activity | 675860507 | 10/30/2019 15:00:00 | 10/30/2019 15:00:00 | 10/30/2019 13:30:00 | 10/30/2019 15:00:00
3550524 | 675859167 | act--04 SSV | 04 SSV | Completed | Activity | 675860738 | 01/11/2020 15:30:00 | 01/12/2020 15:30:00 | 01/10/2020 06:31:17 | 01/10/2020 15:07:42
3550524 | 675859167 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860978 | 01/12/2020 06:30:00 | 01/12/2020 06:30:00 | 12/27/2021 14:26:14 | 12/27/2021 14:26:12
3550524 | 675859167 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860307 |  |  |  |  | 10/30/2019 11:30:00 | 10/30/2019 11:30:00 |  | 10/30/2019 11:30:00
3550524 | 675859167 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860187 |  |  |  |  | 10/30/2019 05:30:00 | 10/30/2019 05:30:00 |  | 10/30/2019 05:30:00
3550524 | 675859167 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859783 |  |  |  |  | 10/30/2019 16:30:00 | 10/30/2019 16:30:00 |  | 10/30/2019 16:30:00
3550524 | 675859167 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859979 |  |  |  |  | 01/12/2020 06:30:00 | 01/12/2020 06:30:00 |  | 01/11/2020 17:06:33
3550524 | 675859167 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062631 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550524 | 675859167 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062880 |  |  |  |  | 01/12/2020 06:30:00 | 07/30/2021 05:30:00
3550525 | 675859168 | act--02 Integration | 02 Integration | Completed | Activity | 675860445 | 04/07/2020 15:00:00 | 04/07/2020 15:00:00 | 04/07/2020 14:00:00 | 04/07/2020 15:00:00
3550525 | 675859168 | act--04 SSV | 04 SSV | Completed | Activity | 675860671 | 10/20/2020 15:30:00 | 10/20/2020 15:30:00 | 10/19/2020 06:33:58 | 10/19/2020 13:43:49
3550525 | 675859168 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860868 | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 | 12/27/2021 14:19:56 | 12/27/2021 14:19:49
3550525 | 675859168 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860249 |  |  |  |  | 04/10/2020 15:30:00 | 04/09/2020 15:30:00 |  | 04/07/2020 12:30:00
3550525 | 675859168 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860128 |  |  |  |  | 04/05/2020 06:30:00 | 04/06/2020 06:30:00 |  | 04/07/2020 06:30:00
3550525 | 675859168 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859767 |  |  |  |  | 04/07/2020 14:30:00 | 04/07/2020 15:00:00 |  | 04/07/2020 16:00:00
3550525 | 675859168 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859941 |  |  |  |  | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 |  | 10/20/2020 07:01:04
3550525 | 675859168 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062128 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550525 | 675859168 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062616 |  |  |  |  | 10/20/2020 06:30:00 | 07/30/2021 05:30:00
3550526 | 675859166 | act--02 Integration | 02 Integration | Completed | Activity | 675860299 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550526 | 675859166 | act--04 SSV | 04 SSV | Completed | Activity | 675860550 | 10/21/2020 15:30:00 | 10/22/2020 15:30:00 | 10/20/2020 08:19:19 | 10/20/2020 14:09:23
3550526 | 675859166 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860785 | 10/21/2020 06:30:00 | 10/21/2020 06:30:00 | 12/27/2021 13:59:53 | 12/27/2021 13:59:52
3550526 | 675859166 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860093 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550526 | 675859166 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859974 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550526 | 675859166 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859606 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550526 | 675859166 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859760 |  |  |  |  | 10/21/2020 06:30:00 | 10/21/2020 06:30:00 |  | 10/21/2020 07:09:18
3550526 | 675859166 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062630 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550526 | 675859166 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062904 |  |  |  |  | 10/21/2020 06:30:00 | 12/27/2021 13:59:52
3550527 | 675859169 | act--02 Integration | 02 Integration | Completed | Activity | 675860499 | 12/22/2019 15:00:00 | 12/22/2019 15:00:00 | 12/22/2019 13:40:01 | 12/22/2019 15:00:00
3550527 | 675859169 | act--04 SSV | 04 SSV | Completed | Activity | 675860713 | 09/26/2020 15:30:00 | 09/27/2020 15:30:00 | 09/26/2020 08:31:32 | 09/26/2020 13:28:35
3550527 | 675859169 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860943 | 10/21/2020 06:30:00 | 10/21/2020 06:30:00 | 12/27/2021 14:06:15 | 12/27/2021 14:06:13
3550527 | 675859169 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860285 |  |  |  |  | 12/25/2019 15:30:00 | 12/24/2019 15:30:00 |  | 12/22/2019 12:30:00
3550527 | 675859169 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860166 |  |  |  |  | 12/20/2019 06:30:00 | 12/21/2019 06:30:00 |  | 12/22/2019 06:30:00
3550527 | 675859169 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859759 |  |  |  |  | 12/22/2019 14:30:00 | 12/22/2019 15:00:00 |  | 12/22/2019 16:00:00
3550527 | 675859169 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859951 |  |  |  |  | 10/21/2020 06:30:00 | 10/21/2020 06:30:00 |  | 10/20/2020 17:43:42
3550527 | 675859169 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062034 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550527 | 675859169 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062421 |  |  |  |  | 10/21/2020 06:30:00 | 07/30/2021 05:30:00
3550528 | 675859175 | act--02 Integration | 02 Integration | Completed | Activity | 675860491 | 09/09/2019 15:00:00 | 09/09/2019 15:00:00 | 09/09/2019 13:30:00 | 09/09/2019 15:00:00
3550528 | 675859175 | act--04 SSV | 04 SSV | Completed | Activity | 675860737 | 10/20/2019 15:30:00 | 10/21/2019 15:30:00 | 10/20/2019 08:05:53 | 10/20/2019 13:59:06
3550528 | 675859175 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860972 | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 | 12/27/2021 14:26:43 | 12/27/2021 14:26:40
3550528 | 675859175 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860272 |  |  |  |  | 09/09/2019 11:30:00 | 09/09/2019 11:30:00 |  | 09/09/2019 11:30:00
3550528 | 675859175 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860147 |  |  |  |  | 09/09/2019 05:30:00 | 09/09/2019 05:30:00 |  | 09/09/2019 05:30:00
3550528 | 675859175 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859754 |  |  |  |  | 09/09/2019 16:30:00 | 09/09/2019 16:30:00 |  | 09/09/2019 16:30:00
3550528 | 675859175 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859942 |  |  |  |  | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 |  | 09/26/2020 15:52:32
3550528 | 675859175 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061544 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550528 | 675859175 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061653 |  |  |  |  | 09/27/2020 06:30:00 | 07/30/2021 05:30:00
3550529 | 675859174 | act--02 Integration | 02 Integration | Completed | Activity | 675860478 | 09/06/2019 15:00:00 | 09/06/2019 15:00:00 | 09/06/2019 13:30:00 | 09/06/2019 15:00:00
3550529 | 675859174 | act--04 SSV | 04 SSV | Completed | Activity | 675860702 | 01/03/2020 15:30:00 | 01/02/2020 15:30:00 | 01/02/2020 08:38:37 | 01/02/2020 15:04:57
3550529 | 675859174 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675860931 | 01/03/2020 06:30:00 | 01/03/2020 06:30:00 | 12/27/2021 14:26:09 | 12/27/2021 14:26:07
3550529 | 675859174 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860263 |  |  |  |  | 09/06/2019 11:30:00 | 09/06/2019 11:30:00 |  | 09/06/2019 11:30:00
3550529 | 675859174 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860141 |  |  |  |  | 09/06/2019 05:30:00 | 09/06/2019 05:30:00 |  | 09/06/2019 05:30:00
3550529 | 675859174 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859772 |  |  |  |  | 09/06/2019 16:30:00 | 09/06/2019 16:30:00 |  | 09/06/2019 16:30:00
3550529 | 675859174 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859946 |  |  |  |  | 01/03/2020 06:30:00 | 01/03/2020 06:30:00 |  | 01/03/2020 08:13:40
3550529 | 675859174 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061310 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550529 | 675859174 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061590 |  |  |  |  | 01/03/2020 06:30:00 | 07/30/2021 05:30:00
3550530 | 675859183 | act--02 Integration | 02 Integration | Completed | Activity | 675860306 | 09/19/2019 15:00:00 | 09/19/2019 15:00:00 | 09/19/2019 13:30:00 | 09/19/2019 15:00:00
3550530 | 675859183 | act--04 SSV | 04 SSV | Completed | Activity | 675860543 | 12/10/2019 15:30:00 | 12/09/2019 15:30:00 | 12/09/2019 08:12:36 | 12/09/2019 13:16:51
3550530 | 675859183 | act--06 Tuning | 06 Tuning | Completed | Activity | 675860776 | 04/26/2021 05:30:01 | 04/26/2021 05:30:01 | 04/01/2021 06:00:00 | 04/26/2021 06:00:01
3550530 | 675859183 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860096 |  |  |  |  | 09/19/2019 11:30:00 | 09/19/2019 11:30:00 |  | 09/19/2019 11:30:00
3550530 | 675859183 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675859977 |  |  |  |  | 09/19/2019 05:30:00 | 09/19/2019 05:30:00 |  | 09/19/2019 05:30:00
3550530 | 675859183 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859608 |  |  |  |  | 09/19/2019 16:30:00 | 09/19/2019 16:30:00 |  | 09/19/2019 16:30:00
3550530 | 675859183 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859790 |  |  |  |  | 01/03/2020 06:30:00 | 01/03/2020 06:30:00 |  | 01/02/2020 15:48:13
3550530 | 675859183 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061294 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550530 | 675859183 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061583 |  |  |  |  | 04/26/2021 05:30:01 | 07/30/2021 07:00:00
3550531 | 675859192 | act--02 Integration | 02 Integration | Completed | Activity | 675860403 | 11/04/2019 15:30:00 | 11/04/2019 15:30:00 | 11/04/2019 14:00:00 | 11/04/2019 15:30:00
3550531 | 675859192 | act--04 SSV | 04 SSV | Completed | Activity | 675860660 | 12/20/2019 15:30:00 | 12/20/2019 15:30:00 | 12/20/2019 06:52:28 | 12/20/2019 15:21:45
3550531 | 675859192 | act--06 Tuning | 06 Tuning | Completed | Activity | 675860853 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550531 | 675859192 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860219 |  |  |  |  | 11/04/2019 12:00:00 | 11/04/2019 12:00:00 |  | 11/04/2019 12:00:00
3550531 | 675859192 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860094 |  |  |  |  | 11/04/2019 06:00:00 | 11/04/2019 06:00:00 |  | 11/04/2019 06:00:00
3550531 | 675859192 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859740 |  |  |  |  | 11/04/2019 17:00:00 | 11/04/2019 17:00:00 |  | 11/04/2019 17:00:00
3550531 | 675859192 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675859904 |  |  |  |  | 12/21/2019 06:30:00 | 12/21/2019 06:30:00 |  | 12/21/2019 08:28:58
3550531 | 675859192 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061939 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550531 | 675859192 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062122 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550532 | 675859293 | act--02 Integration | 02 Integration | Completed | Activity | 675860606 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550532 | 675859293 | act--04 SSV | 04 SSV | Completed | Activity | 675860820 | 10/14/2020 15:30:00 | 10/13/2020 15:30:00 | 10/13/2020 06:37:21 | 10/13/2020 13:14:58
3550532 | 675859293 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861033 | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 | 12/27/2021 14:06:16 | 12/27/2021 14:06:15
3550532 | 675859293 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860442 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550532 | 675859293 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860315 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550532 | 675859293 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859934 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550532 | 675859293 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860117 |  |  |  |  | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 |  | 10/14/2020 08:43:08
3550532 | 675859293 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062132 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550532 | 675859293 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062685 |  |  |  |  | 10/14/2020 06:30:00 | 07/30/2021 05:30:00
3550533 | 675859294 | act--02 Integration | 02 Integration | Completed | Activity | 675860642 | 09/08/2019 15:00:00 | 09/08/2019 15:00:00 | 09/08/2019 13:40:01 | 09/08/2019 15:00:00
3550533 | 675859294 | act--04 SSV | 04 SSV | Completed | Activity | 675860846 | 10/09/2020 15:30:00 | 10/09/2020 15:30:00 | 10/08/2020 07:16:00 | 10/08/2020 13:57:10
3550533 | 675859294 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861067 | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 | 12/27/2021 13:59:56 | 12/27/2021 13:59:55
3550533 | 675859294 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860427 |  |  |  |  | 09/11/2019 15:30:00 | 09/10/2019 15:30:00 |  | 09/08/2019 12:30:00
3550533 | 675859294 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860295 |  |  |  |  | 09/06/2019 06:30:00 | 09/07/2019 06:30:00 |  | 09/08/2019 06:30:00
3550533 | 675859294 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859836 |  |  |  |  | 09/08/2019 14:30:00 | 09/08/2019 15:00:00 |  | 09/08/2019 16:00:00
3550533 | 675859294 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860080 |  |  |  |  | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 |  | 10/13/2020 17:17:56
3550533 | 675859294 | ms--07 PAC | 07 PAC | Completed | Milestone | 718063046 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550533 | 675859294 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718063136 |  |  |  |  | 10/14/2020 06:30:00 | 12/27/2021 13:59:55
3550534 | 675859295 | act--02 Integration | 02 Integration | Completed | Activity | 675860689 | 08/20/2019 15:40:00 | 08/20/2019 15:40:00 | 08/20/2019 14:10:00 | 08/20/2019 15:40:00
3550534 | 675859295 | act--04 SSV | 04 SSV | Completed | Activity | 675860930 | 08/25/2019 15:30:00 | 08/26/2019 15:30:00 | 08/25/2019 07:53:22 | 08/25/2019 15:23:25
3550534 | 675859295 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861129 | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 | 12/27/2021 14:07:03 | 12/27/2021 14:06:59
3550534 | 675859295 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860512 |  |  |  |  | 08/20/2019 12:10:00 | 08/20/2019 12:10:00 |  | 08/20/2019 12:10:00
3550534 | 675859295 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860389 |  |  |  |  | 08/20/2019 06:10:00 | 08/20/2019 06:10:00 |  | 08/20/2019 06:10:00
3550534 | 675859295 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860002 |  |  |  |  | 08/20/2019 17:10:00 | 08/20/2019 17:10:00 |  | 08/20/2019 17:10:00
3550534 | 675859295 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860201 |  |  |  |  | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 |  | 10/08/2020 16:33:10
3550534 | 675859295 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062116 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550534 | 675859295 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062590 |  |  |  |  | 10/09/2020 06:30:00 | 12/27/2021 14:06:59
3550535 | 675859304 | act--02 Integration | 02 Integration | Completed | Activity | 675860542 | 03/06/2020 15:30:00 | 03/06/2020 15:30:00 | 03/06/2020 14:00:00 | 03/06/2020 15:30:00
3550535 | 675859304 | act--04 SSV | 04 SSV | Completed | Activity | 675860768 | 03/14/2020 15:30:00 | 03/12/2020 15:30:00 | 03/12/2020 07:06:26 | 03/12/2020 14:34:41
3550535 | 675859304 | act--06 Tuning | 06 Tuning | Completed | Activity | 675860984 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550535 | 675859304 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860340 |  |  |  |  | 03/06/2020 12:00:00 | 03/06/2020 12:00:00 |  | 03/06/2020 12:00:00
3550535 | 675859304 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860230 |  |  |  |  | 03/06/2020 06:00:00 | 03/06/2020 06:00:00 |  | 03/06/2020 06:00:00
3550535 | 675859304 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675859870 |  |  |  |  | 03/06/2020 17:00:00 | 03/06/2020 17:00:00 |  | 03/06/2020 17:00:00
3550535 | 675859304 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860030 |  |  |  |  | 03/13/2020 06:30:00 | 03/13/2020 06:30:00 |  | 03/13/2020 08:16:06
3550535 | 675859304 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062040 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550535 | 675859304 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062577 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550536 | 675859351 | act--02 Integration | 02 Integration | Completed | Activity | 675861285 | 07/30/2020 15:00:00 | 07/30/2020 15:00:00 | 07/30/2020 14:00:00 | 07/30/2020 15:00:00
3550536 | 675859351 | act--04 SSV | 04 SSV | Completed | Activity | 675861403 | 03/26/2021 05:30:00 | 03/26/2021 05:30:00 | 03/26/2021 03:55:00 | 03/28/2021 02:15:00
3550536 | 675859351 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861498 | 03/28/2021 04:15:00 | 03/28/2021 04:15:00 | 12/27/2021 14:06:30 | 12/27/2021 14:06:29
3550536 | 675859351 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861187 |  |  |  |  | 08/02/2020 15:30:00 | 08/01/2020 15:30:00 |  | 07/30/2020 12:30:00
3550536 | 675859351 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861119 |  |  |  |  | 07/28/2020 06:30:00 | 07/29/2020 06:30:00 |  | 07/30/2020 06:30:00
3550536 | 675859351 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860802 |  |  |  |  | 07/30/2020 14:30:00 | 07/30/2020 15:00:00 |  | 07/30/2020 16:00:00
3550536 | 675859351 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860988 |  |  |  |  | 03/28/2021 04:15:00 | 03/28/2021 04:15:00 |  | 03/29/2021 05:00:00
3550536 | 675859351 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062383 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550536 | 675859351 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062842 |  |  |  |  | 03/28/2021 04:15:00 | 07/30/2021 05:30:00
3550537 | 675859352 | act--02 Integration | 02 Integration | Completed | Activity | 675860698 | 04/27/2020 15:00:00 | 04/27/2020 15:00:00 | 04/27/2020 14:00:00 | 04/27/2020 15:00:00
3550537 | 675859352 | act--04 SSV | 04 SSV | Completed | Activity | 675860924 | 10/10/2020 15:30:00 | 10/10/2020 15:30:00 | 10/08/2020 07:42:48 | 10/08/2020 14:04:08
3550537 | 675859352 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861128 | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 | 12/27/2021 14:19:59 | 12/27/2021 14:19:57
3550537 | 675859352 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860514 |  |  |  |  | 04/30/2020 15:30:00 | 04/29/2020 15:30:00 |  | 04/27/2020 12:30:00
3550537 | 675859352 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860377 |  |  |  |  | 04/25/2020 06:30:00 | 04/26/2020 06:30:00 |  | 04/27/2020 06:30:00
3550537 | 675859352 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860012 |  |  |  |  | 04/27/2020 14:30:00 | 04/27/2020 15:00:00 |  | 04/27/2020 16:00:00
3550537 | 675859352 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860198 |  |  |  |  | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 |  | 10/09/2020 06:49:09
3550537 | 675859352 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061301 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550537 | 675859352 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061567 |  |  |  |  | 10/09/2020 06:30:00 | 07/30/2021 05:30:00
3550538 | 675859364 | act--02 Integration | 02 Integration | Completed | Activity | 675862243 | 09/28/2019 15:00:00 | 09/28/2019 15:00:00 | 09/28/2019 13:30:00 | 09/28/2019 15:00:00
3550538 | 675859364 | act--04 SSV | 04 SSV | Completed | Activity | 675862374 | 12/20/2019 15:30:00 | 12/21/2019 15:30:00 | 12/19/2019 06:58:17 | 12/19/2019 14:20:27
3550538 | 675859364 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862516 | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 | 12/27/2021 14:26:12 | 12/27/2021 14:26:10
3550538 | 675859364 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862155 |  |  |  |  | 09/28/2019 11:30:00 | 09/28/2019 11:30:00 |  | 09/28/2019 11:30:00
3550538 | 675859364 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862117 |  |  |  |  | 09/28/2019 05:30:00 | 09/28/2019 05:30:00 |  | 09/28/2019 05:30:00
3550538 | 675859364 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861937 |  |  |  |  | 09/28/2019 16:30:00 | 09/28/2019 16:30:00 |  | 09/28/2019 16:30:00
3550538 | 675859364 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862024 |  |  |  |  | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 |  | 10/08/2020 15:40:35
3550538 | 675859364 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062637 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550538 | 675859364 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062902 |  |  |  |  | 10/09/2020 06:30:00 | 07/30/2021 05:30:00
3550539 | 675859367 | act--02 Integration | 02 Integration | Completed | Activity | 675861810 | 11/15/2019 15:30:00 | 11/15/2019 15:30:00 | 11/15/2019 14:00:00 | 11/15/2019 15:30:00
3550539 | 675859367 | act--04 SSV | 04 SSV | Completed | Activity | 675861839 | 03/09/2020 15:30:00 | 03/10/2020 15:30:00 | 03/09/2020 07:08:02 | 03/09/2020 13:44:25
3550539 | 675859367 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861867 | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 | 12/27/2021 14:13:28 | 12/27/2021 14:13:27
3550539 | 675859367 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861787 |  |  |  |  | 11/15/2019 12:00:00 | 11/15/2019 12:00:00 |  | 11/15/2019 12:00:00
3550539 | 675859367 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861777 |  |  |  |  | 11/15/2019 06:00:00 | 11/15/2019 06:00:00 |  | 11/15/2019 06:00:00
3550539 | 675859367 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861687 |  |  |  |  | 11/15/2019 17:00:00 | 11/15/2019 17:00:00 |  | 11/15/2019 17:00:00
3550539 | 675859367 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861744 |  |  |  |  | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 |  | 03/10/2020 06:51:16
3550539 | 675859367 | ms--07 PAC | 07 PAC | Completed | Milestone | 718060959 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550539 | 675859367 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061269 |  |  |  |  | 03/10/2020 06:30:00 | 07/30/2021 05:30:00
3550540 | 675859369 | act--02 Integration | 02 Integration | Completed | Activity | 675860744 | 09/11/2019 15:00:00 | 09/11/2019 15:00:00 | 09/11/2019 13:30:00 | 09/11/2019 15:00:00
3550540 | 675859369 | act--04 SSV | 04 SSV | Completed | Activity | 675860975 | 11/09/2019 15:30:00 | 11/09/2019 15:30:00 | 11/08/2019 07:47:38 | 11/08/2019 13:37:13
3550540 | 675859369 | act--06 Tuning | 06 Tuning | Completed | Activity | 675861152 | 04/28/2021 05:30:01 | 04/28/2021 05:30:01 | 04/01/2021 06:00:00 | 04/28/2021 06:00:01
3550540 | 675859369 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860562 |  |  |  |  | 09/11/2019 11:30:00 | 09/11/2019 11:30:00 |  | 09/11/2019 11:30:00
3550540 | 675859369 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860469 |  |  |  |  | 09/11/2019 05:30:00 | 09/11/2019 05:30:00 |  | 09/11/2019 05:30:00
3550540 | 675859369 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860035 |  |  |  |  | 09/11/2019 16:30:00 | 09/11/2019 16:30:00 |  | 09/11/2019 16:30:00
3550540 | 675859369 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860261 |  |  |  |  | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 |  | 03/09/2020 16:49:00
3550540 | 675859369 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062134 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550540 | 675859369 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062612 |  |  |  |  | 04/28/2021 05:30:01 | 07/30/2021 07:00:00
3550541 | 675859379 | act--02 Integration | 02 Integration | Completed | Activity | 675861259 | 09/22/2019 15:30:00 | 09/22/2019 15:30:00 | 09/22/2019 14:00:00 | 09/22/2019 15:30:00
3550541 | 675859379 | act--04 SSV | 04 SSV | Completed | Activity | 675861364 | 04/03/2020 15:30:00 | 04/04/2020 15:30:00 | 04/02/2020 08:05:27 | 04/02/2020 13:10:36
3550541 | 675859379 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861448 | 04/03/2020 06:30:00 | 04/03/2020 06:30:00 | 12/27/2021 14:13:24 | 12/27/2021 14:13:22
3550541 | 675859379 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861173 |  |  |  |  | 09/22/2019 12:00:00 | 09/22/2019 12:00:00 |  | 09/22/2019 12:00:00
3550541 | 675859379 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861096 |  |  |  |  | 09/22/2019 06:00:00 | 09/22/2019 06:00:00 |  | 09/22/2019 06:00:00
3550541 | 675859379 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860782 |  |  |  |  | 09/22/2019 17:00:00 | 09/22/2019 17:00:00 |  | 09/22/2019 17:00:00
3550541 | 675859379 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860960 |  |  |  |  | 04/03/2020 06:30:00 | 04/03/2020 06:30:00 |  | 04/03/2020 06:56:40
3550541 | 675859379 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061848 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550541 | 675859379 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062058 |  |  |  |  | 04/03/2020 06:30:00 | 07/30/2021 05:30:00
3550542 | 675859390 | act--02 Integration | 02 Integration | Completed | Activity | 675861202 | 01/13/2020 15:00:00 | 01/13/2020 15:00:00 | 01/13/2020 13:30:00 | 01/13/2020 15:00:00
3550542 | 675859390 | act--04 SSV | 04 SSV | Completed | Activity | 675861316 | 03/05/2020 15:30:00 | 03/05/2020 15:30:00 | 03/05/2020 08:43:39 | 03/05/2020 14:31:47
3550542 | 675859390 | act--06 Tuning | 06 Tuning | Completed | Activity | 675861395 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550542 | 675859390 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861082 |  |  |  |  | 01/13/2020 11:30:00 | 01/13/2020 11:30:00 |  | 01/13/2020 11:30:00
3550542 | 675859390 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860996 |  |  |  |  | 01/13/2020 05:30:00 | 01/13/2020 05:30:00 |  | 01/13/2020 05:30:00
3550542 | 675859390 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860687 |  |  |  |  | 01/13/2020 16:30:00 | 01/13/2020 16:30:00 |  | 01/13/2020 16:30:00
3550542 | 675859390 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860830 |  |  |  |  | 04/03/2020 06:30:00 | 04/03/2020 06:30:00 |  | 04/02/2020 17:52:48
3550542 | 675859390 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061530 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550542 | 675859390 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061626 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550543 | 675859391 | act--02 Integration | 02 Integration | Completed | Activity | 675861278 | 12/22/2019 15:00:00 | 12/22/2019 15:00:00 | 12/22/2019 13:40:01 | 12/22/2019 15:00:00
3550543 | 675859391 | act--04 SSV | 04 SSV | Completed | Activity | 675861401 | 09/28/2020 15:30:00 | 09/28/2020 15:30:00 | 09/27/2020 07:27:22 | 09/27/2020 13:12:22
3550543 | 675859391 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861499 | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 | 12/27/2021 14:06:46 | 12/27/2021 14:06:45
3550543 | 675859391 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861183 |  |  |  |  | 12/25/2019 15:30:00 | 12/24/2019 15:30:00 |  | 12/22/2019 12:30:00
3550543 | 675859391 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861118 |  |  |  |  | 12/20/2019 06:30:00 | 12/21/2019 06:30:00 |  | 12/22/2019 06:30:00
3550543 | 675859391 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860821 |  |  |  |  | 12/22/2019 14:30:00 | 12/22/2019 15:00:00 |  | 12/22/2019 16:00:00
3550543 | 675859391 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860989 |  |  |  |  | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 |  | 09/28/2020 08:25:32
3550543 | 675859391 | ms--07 PAC | 07 PAC | Completed | Milestone | 718059252 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550543 | 675859391 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718059766 |  |  |  |  | 09/28/2020 06:30:00 | 12/27/2021 14:06:45
3550544 | 675859395 | act--02 Integration | 02 Integration | Completed | Activity | 675861266 | 08/19/2019 15:20:00 | 08/19/2019 15:20:00 | 08/19/2019 13:50:00 | 08/19/2019 15:20:00
3550544 | 675859395 | act--04 SSV | 04 SSV | Completed | Activity | 675861373 | 08/26/2019 15:30:00 | 08/25/2019 15:30:00 | 08/25/2019 07:25:49 | 08/25/2019 13:55:05
3550544 | 675859395 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861471 | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 | 12/27/2021 14:06:49 | 12/27/2021 14:06:49
3550544 | 675859395 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861166 |  |  |  |  | 08/19/2019 11:50:00 | 08/19/2019 11:50:00 |  | 08/19/2019 11:50:00
3550544 | 675859395 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861094 |  |  |  |  | 08/19/2019 05:50:00 | 08/19/2019 05:50:00 |  | 08/19/2019 05:50:00
3550544 | 675859395 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860762 |  |  |  |  | 08/19/2019 16:50:00 | 08/19/2019 16:50:00 |  | 08/19/2019 16:50:00
3550544 | 675859395 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860950 |  |  |  |  | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 |  | 09/27/2020 16:00:28
3550544 | 675859395 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061108 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550544 | 675859395 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061488 |  |  |  |  | 09/28/2020 06:30:00 | 12/27/2021 14:06:49
3550545 | 675859396 | act--02 Integration | 02 Integration | Completed | Activity | 675862261 | 10/09/2019 15:00:00 | 10/09/2019 15:00:00 | 10/09/2019 13:30:00 | 10/09/2019 15:00:00
3550545 | 675859396 | act--04 SSV | 04 SSV | Completed | Activity | 675862375 | 12/04/2019 15:30:00 | 12/02/2019 15:30:00 | 12/02/2019 07:13:30 | 12/02/2019 13:14:07
3550545 | 675859396 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862526 | 12/03/2019 06:30:00 | 12/03/2019 06:30:00 | 12/27/2021 14:13:04 | 12/27/2021 14:13:00
3550545 | 675859396 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862165 |  |  |  |  | 10/09/2019 11:30:00 | 10/09/2019 11:30:00 |  | 10/09/2019 11:30:00
3550545 | 675859396 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862134 |  |  |  |  | 10/09/2019 05:30:00 | 10/09/2019 05:30:00 |  | 10/09/2019 05:30:00
3550545 | 675859396 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861953 |  |  |  |  | 10/09/2019 16:30:00 | 10/09/2019 16:30:00 |  | 10/09/2019 16:30:00
3550545 | 675859396 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862031 |  |  |  |  | 12/03/2019 06:30:00 | 12/03/2019 06:30:00 |  | 12/03/2019 06:53:43
3550545 | 675859396 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062124 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550545 | 675859396 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062707 |  |  |  |  | 12/03/2019 06:30:00 | 07/30/2021 05:30:00
3550546 | 675859403 | act--02 Integration | 02 Integration | Completed | Activity | 675861811 | 11/13/2019 15:00:00 | 11/13/2019 15:00:00 | 11/13/2019 13:40:01 | 11/13/2019 15:00:00
3550546 | 675859403 | act--04 SSV | 04 SSV | Completed | Activity | 675861838 | 10/21/2020 15:30:00 | 10/20/2020 15:30:00 | 10/19/2020 07:15:53 | 10/19/2020 15:21:01
3550546 | 675859403 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861871 | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 | 12/27/2021 14:20:10 | 12/27/2021 14:20:09
3550546 | 675859403 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861785 |  |  |  |  | 11/16/2019 15:30:00 | 11/15/2019 15:30:00 |  | 11/13/2019 12:30:00
3550546 | 675859403 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861775 |  |  |  |  | 11/11/2019 06:30:00 | 11/12/2019 06:30:00 |  | 11/13/2019 06:30:00
3550546 | 675859403 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861688 |  |  |  |  | 11/13/2019 14:30:00 | 11/13/2019 15:00:00 |  | 11/13/2019 16:00:00
3550546 | 675859403 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861738 |  |  |  |  | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 |  | 10/20/2020 07:10:57
3550546 | 675859403 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061789 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550546 | 675859403 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062060 |  |  |  |  | 10/20/2020 06:30:00 | 07/30/2021 05:30:00
3550547 | 675859409 | act--02 Integration | 02 Integration | Completed | Activity | 675860798 | 12/02/2019 15:00:00 | 12/02/2019 15:00:00 | 12/02/2019 13:40:01 | 12/02/2019 15:00:00
3550547 | 675859409 | act--04 SSV | 04 SSV | Completed | Activity | 675861005 | 10/06/2020 15:30:00 | 10/07/2020 15:30:00 | 10/06/2020 06:49:25 | 10/06/2020 15:28:16
3550547 | 675859409 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861185 | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 | 12/27/2021 14:26:07 | 12/27/2021 14:26:06
3550547 | 675859409 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675860624 |  |  |  |  | 12/05/2019 15:30:00 | 12/04/2019 15:30:00 |  | 12/02/2019 12:30:00
3550547 | 675859409 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675860525 |  |  |  |  | 11/30/2019 06:30:00 | 12/01/2019 06:30:00 |  | 12/02/2019 06:30:00
3550547 | 675859409 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860121 |  |  |  |  | 12/02/2019 14:30:00 | 12/02/2019 15:00:00 |  | 12/02/2019 16:00:00
3550547 | 675859409 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860328 |  |  |  |  | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 |  | 10/19/2020 17:05:03
3550547 | 675859409 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061023 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550547 | 675859409 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061280 |  |  |  |  | 10/20/2020 06:30:00 | 07/30/2021 05:30:00
3550548 | 675859418 | act--02 Integration | 02 Integration | Completed | Activity | 675861357 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550548 | 675859418 | act--04 SSV | 04 SSV | Completed | Activity | 675861446 | 03/23/2021 05:30:00 | 03/23/2021 05:30:00 | 03/23/2021 06:10:00 | 03/24/2021 22:55:00
3550548 | 675859418 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861524 | 03/25/2021 12:55:00 | 03/25/2021 12:55:00 | 12/27/2021 14:19:49 | 12/27/2021 14:19:45
3550548 | 675859418 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861254 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550548 | 675859418 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861196 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550548 | 675859418 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860880 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550548 | 675859418 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861070 |  |  |  |  | 03/25/2021 12:55:00 | 03/25/2021 12:55:00 |  | 03/26/2021 05:00:00
3550548 | 675859418 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061455 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550548 | 675859418 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061586 |  |  |  |  | 03/25/2021 12:55:00 | 07/30/2021 05:30:00
3550549 | 675859420 | act--02 Integration | 02 Integration | Completed | Activity | 675861242 | 08/20/2019 15:00:00 | 08/20/2019 15:00:00 | 08/20/2019 13:30:00 | 08/20/2019 15:00:00
3550549 | 675859420 | act--04 SSV | 04 SSV | Completed | Activity | 675861348 | 08/30/2019 15:30:00 | 08/30/2019 15:30:00 | 08/29/2019 07:51:02 | 08/29/2019 15:16:55
3550549 | 675859420 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861434 | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 | 12/27/2021 14:07:01 | 12/27/2021 14:07:00
3550549 | 675859420 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861145 |  |  |  |  | 08/20/2019 11:30:00 | 08/20/2019 11:30:00 |  | 08/20/2019 11:30:00
3550549 | 675859420 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861074 |  |  |  |  | 08/20/2019 05:30:00 | 08/20/2019 05:30:00 |  | 08/20/2019 05:30:00
3550549 | 675859420 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675860742 |  |  |  |  | 08/20/2019 16:30:00 | 08/20/2019 16:30:00 |  | 08/20/2019 16:30:00
3550549 | 675859420 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675860918 |  |  |  |  | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 |  | 10/06/2020 17:28:28
3550549 | 675859420 | ms--07 PAC | 07 PAC | Completed | Milestone | 718061545 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550549 | 675859420 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718061916 |  |  |  |  | 10/07/2020 06:30:00 | 12/27/2021 14:07:00
3550550 | 675859432 | act--02 Integration | 02 Integration | Completed | Activity | 675862249 | 09/16/2019 15:00:00 | 09/16/2019 15:00:00 | 09/16/2019 13:30:00 | 09/16/2019 15:00:00
3550550 | 675859432 | act--04 SSV | 04 SSV | Completed | Activity | 675862373 | 12/17/2019 15:30:00 | 12/17/2019 15:30:00 | 12/16/2019 06:31:59 | 12/16/2019 13:31:56
3550550 | 675859432 | act--06 Tuning | 06 Tuning | Completed | Activity | 675862518 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550550 | 675859432 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862151 |  |  |  |  | 09/16/2019 11:30:00 | 09/16/2019 11:30:00 |  | 09/16/2019 11:30:00
3550550 | 675859432 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862111 |  |  |  |  | 09/16/2019 05:30:00 | 09/16/2019 05:30:00 |  | 09/16/2019 05:30:00
3550550 | 675859432 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861930 |  |  |  |  | 09/16/2019 16:30:00 | 09/16/2019 16:30:00 |  | 09/16/2019 16:30:00
3550550 | 675859432 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862034 |  |  |  |  | 12/17/2019 06:30:00 | 12/17/2019 06:30:00 |  | 12/17/2019 07:00:43
3550550 | 675859432 | ms--07 PAC | 07 PAC | Completed | Milestone | 718062023 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550550 | 675859432 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718062391 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550551 | 675859433 | act--02 Integration | 02 Integration | Completed | Activity | 675862250 | 08/19/2019 15:00:00 | 08/19/2019 15:00:00 | 08/19/2019 13:30:00 | 08/19/2019 15:00:00
3550551 | 675859433 | act--04 SSV | 04 SSV | Completed | Activity | 675862372 | 08/27/2019 15:30:00 | 08/29/2019 15:30:00 | 08/27/2019 07:52:26 | 08/27/2019 13:57:50
3550551 | 675859433 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862515 | 12/17/2019 06:30:00 | 12/17/2019 06:30:00 | 12/27/2021 14:00:56 | 12/27/2021 14:00:54
3550551 | 675859433 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862149 |  |  |  |  | 08/19/2019 11:30:00 | 08/19/2019 11:30:00 |  | 08/19/2019 11:30:00
3550551 | 675859433 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862108 |  |  |  |  | 08/19/2019 05:30:00 | 08/19/2019 05:30:00 |  | 08/19/2019 05:30:00
3550551 | 675859433 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861936 |  |  |  |  | 08/19/2019 16:30:00 | 08/19/2019 16:30:00 |  | 08/19/2019 16:30:00
3550551 | 675859433 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862028 |  |  |  |  | 12/17/2019 06:30:00 | 12/17/2019 06:30:00 |  | 12/16/2019 17:10:43
3550551 | 675859433 | ms--07 PAC | 07 PAC | Completed | Milestone | 718059934 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550551 | 675859433 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718060706 |  |  |  |  | 12/17/2019 06:30:00 | 12/27/2021 14:00:54
3550552 | 675859464 | act--02 Integration | 02 Integration | Completed | Activity | 675861417 | 12/12/2019 15:00:00 | 12/12/2019 15:00:00 | 12/12/2019 13:40:01 | 12/12/2019 15:00:00
3550552 | 675859464 | act--04 SSV | 04 SSV | Completed | Activity | 675861504 | 03/25/2021 05:30:00 | 03/25/2021 05:30:00 | 03/25/2021 07:25:00 | 03/27/2021 09:05:00
3550552 | 675859464 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861591 | 03/27/2021 11:05:00 | 03/27/2021 11:05:00 | 12/27/2021 14:12:28 | 12/27/2021 14:12:27
3550552 | 675859464 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861353 |  |  |  |  | 12/15/2019 15:30:00 | 12/14/2019 15:30:00 |  | 12/12/2019 12:30:00
3550552 | 675859464 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861309 |  |  |  |  | 12/10/2019 06:30:00 | 12/11/2019 06:30:00 |  | 12/12/2019 06:30:00
3550552 | 675859464 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861113 |  |  |  |  | 12/12/2019 14:30:00 | 12/12/2019 15:00:00 |  | 12/12/2019 16:00:00
3550552 | 675859464 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861215 |  |  |  |  | 03/27/2021 11:05:00 | 03/27/2021 11:05:00 |  | 03/28/2021 05:00:00
3550552 | 675859464 | ms--07 PAC | 07 PAC | Completed | Milestone | 718063594 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550552 | 675859464 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718064108 |  |  |  |  | 03/27/2021 11:05:00 | 07/30/2021 05:30:00
3550553 | 675859501 | act--02 Integration | 02 Integration | Completed | Activity | 675861509 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550553 | 675859501 | act--04 SSV | 04 SSV | Completed | Activity | 675861598 | 10/06/2020 15:30:00 | 10/06/2020 15:30:00 | 10/06/2020 08:06:27 | 10/06/2020 15:14:11
3550553 | 675859501 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861655 | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 | 12/27/2021 14:06:20 | 12/27/2021 14:06:19
3550553 | 675859501 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861445 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550553 | 675859501 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861406 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550553 | 675859501 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861247 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550553 | 675859501 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861339 |  |  |  |  | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 |  | 10/07/2020 07:23:30
3550553 | 675859501 | ms--07 PAC | 07 PAC | Completed | Milestone | 718063578 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550553 | 675859501 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718064164 |  |  |  |  | 10/07/2020 06:30:00 | 07/30/2021 05:30:00
3550554 | 675859502 | act--02 Integration | 02 Integration | Completed | Activity | 675862289 | 08/24/2019 15:00:00 | 08/24/2019 15:00:00 | 08/24/2019 13:30:00 | 08/24/2019 15:00:00
3550554 | 675859502 | act--04 SSV | 04 SSV | Completed | Activity | 675862394 | 08/27/2019 15:30:00 | 08/27/2019 15:30:00 | 08/26/2019 08:31:57 | 08/26/2019 13:14:52
3550554 | 675859502 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862531 | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 | 12/27/2021 14:20:50 | 12/27/2021 14:20:48
3550554 | 675859502 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862238 |  |  |  |  | 08/24/2019 11:30:00 | 08/24/2019 11:30:00 |  | 08/24/2019 11:30:00
3550554 | 675859502 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862185 |  |  |  |  | 08/24/2019 05:30:00 | 08/24/2019 05:30:00 |  | 08/24/2019 05:30:00
3550554 | 675859502 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862030 |  |  |  |  | 08/24/2019 16:30:00 | 08/24/2019 16:30:00 |  | 08/24/2019 16:30:00
3550554 | 675859502 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862110 |  |  |  |  | 10/07/2020 06:30:00 | 10/07/2020 06:30:00 |  | 10/06/2020 16:07:11
3550554 | 675859502 | ms--07 PAC | 07 PAC | Completed | Milestone | 718063948 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550554 | 675859502 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718064188 |  |  |  |  | 10/07/2020 06:30:00 | 07/30/2021 05:30:00
3550555 | 675859503 | act--02 Integration | 02 Integration | Completed | Activity | 675863007 | 12/02/2019 15:00:00 | 12/02/2019 15:00:00 | 12/02/2019 13:40:01 | 12/02/2019 15:00:00
3550555 | 675859503 | act--04 SSV | 04 SSV | Completed | Activity | 675863243 | 01/31/2021 15:30:00 | 02/01/2021 15:30:00 | 01/31/2021 07:46:56 | 01/31/2021 13:50:41
3550555 | 675859503 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863455 | 02/01/2021 06:30:00 | 02/01/2021 06:30:00 | 12/27/2021 14:19:49 | 12/27/2021 14:19:46
3550555 | 675859503 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862904 |  |  |  |  | 12/05/2019 15:30:00 | 12/04/2019 15:30:00 |  | 12/02/2019 12:30:00
3550555 | 675859503 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862854 |  |  |  |  | 11/30/2019 06:30:00 | 12/01/2019 06:30:00 |  | 12/02/2019 06:30:00
3550555 | 675859503 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862482 |  |  |  |  | 12/02/2019 14:30:00 | 12/02/2019 15:00:00 |  | 12/02/2019 16:00:00
3550555 | 675859503 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862581 |  |  |  |  | 02/01/2021 06:30:00 | 02/01/2021 06:30:00 |  | 02/01/2021 07:46:29
3550555 | 675859503 | ms--07 PAC | 07 PAC | Completed | Milestone | 718064785 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550555 | 675859503 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718064867 |  |  |  |  | 02/01/2021 06:30:00 | 07/30/2021 05:30:00
3550557 | 675859512 | act--02 Integration | 02 Integration | Completed | Activity | 675861600 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550557 | 675859512 | act--04 SSV | 04 SSV | Completed | Activity | 675861647 | 03/24/2021 05:30:00 | 03/24/2021 05:30:00 | 03/24/2021 03:25:00 | 03/25/2021 01:25:00
3550557 | 675859512 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861697 | 03/25/2021 09:00:00 | 03/25/2021 09:00:00 | 12/27/2021 14:12:29 | 12/27/2021 14:12:28
3550557 | 675859512 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861514 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550557 | 675859512 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861481 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550557 | 675859512 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861341 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550557 | 675859512 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861412 |  |  |  |  | 03/25/2021 09:00:00 | 03/25/2021 09:00:00 |  | 03/25/2021 17:00:00
3550557 | 675859512 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065359 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550557 | 675859512 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065427 |  |  |  |  | 03/25/2021 09:00:00 | 07/30/2021 05:30:00
3550559 | 675859570 | act--02 Integration | 02 Integration | Completed | Activity | 675862254 | 03/06/2020 15:00:00 | 03/06/2020 15:00:00 | 03/06/2020 13:30:00 | 03/06/2020 15:00:00
3550559 | 675859570 | act--04 SSV | 04 SSV | Completed | Activity | 675862371 | 03/13/2020 15:30:00 | 03/11/2020 15:30:00 | 03/11/2020 07:58:46 | 03/11/2020 14:48:15
3550559 | 675859570 | act--06 Tuning | 06 Tuning | Completed | Activity | 675862528 | 05/28/2021 06:30:01 | 05/28/2021 06:30:01 | 05/01/2021 07:00:00 | 05/28/2021 07:00:01
3550559 | 675859570 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862164 |  |  |  |  | 03/06/2020 11:30:00 | 03/06/2020 11:30:00 |  | 03/06/2020 11:30:00
3550559 | 675859570 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862122 |  |  |  |  | 03/06/2020 05:30:00 | 03/06/2020 05:30:00 |  | 03/06/2020 05:30:00
3550559 | 675859570 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861933 |  |  |  |  | 03/06/2020 16:30:00 | 03/06/2020 16:30:00 |  | 03/06/2020 16:30:00
3550559 | 675859570 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862043 |  |  |  |  | 03/21/2020 06:30:00 | 03/21/2020 06:30:00 |  | 03/21/2020 07:00:00
3550559 | 675859570 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065903 |  |  |  |  | 07/30/2021 06:30:00 | 07/30/2021 06:30:00 |  | 07/30/2021 07:00:00
3550559 | 675859570 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065986 |  |  |  |  | 05/28/2021 06:30:01 | 07/30/2021 07:00:00
3550560 | 675859581 | act--02 Integration | 02 Integration | Completed | Activity | 675864737 | 04/01/2020 15:00:00 | 04/01/2020 15:00:00 | 04/01/2020 14:00:01 | 04/01/2020 15:00:00
3550560 | 675859581 | act--04 SSV | 04 SSV | Completed | Activity | 675865009 | 09/27/2020 15:30:00 | 09/25/2020 15:30:00 | 09/25/2020 06:47:07 | 09/25/2020 14:58:34
3550560 | 675859581 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865359 | 09/26/2020 06:30:00 | 09/26/2020 06:30:00 | 12/27/2021 14:12:23 | 12/27/2021 14:12:21
3550560 | 675859581 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864510 |  |  |  |  | 04/04/2020 15:30:00 | 04/03/2020 15:30:00 |  | 04/01/2020 12:30:00
3550560 | 675859581 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864370 |  |  |  |  | 03/30/2020 06:30:00 | 03/31/2020 06:30:00 |  | 04/01/2020 06:30:00
3550560 | 675859581 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864056 |  |  |  |  | 04/01/2020 14:30:00 | 04/01/2020 15:00:00 |  | 04/01/2020 16:00:00
3550560 | 675859581 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864205 |  |  |  |  | 09/26/2020 06:30:00 | 09/26/2020 06:30:00 |  | 09/26/2020 07:18:20
3550560 | 675859581 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066066 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550560 | 675859581 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066196 |  |  |  |  | 09/26/2020 06:30:00 | 07/30/2021 05:30:00
3550561 | 675859587 | act--02 Integration | 02 Integration | Completed | Activity | 675865383 | 11/05/2019 15:00:00 | 11/05/2019 15:00:00 | 11/05/2019 13:30:00 | 11/05/2019 15:00:00
3550561 | 675859587 | act--04 SSV | 04 SSV | Completed | Activity | 675865704 | 12/22/2019 15:30:00 | 12/21/2019 15:30:00 | 12/20/2019 07:04:16 | 12/20/2019 13:54:12
3550561 | 675859587 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865992 | 09/26/2020 06:30:00 | 09/26/2020 06:30:00 | 12/27/2021 14:07:06 | 12/27/2021 14:07:04
3550561 | 675859587 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865089 |  |  |  |  | 11/05/2019 11:30:00 | 11/05/2019 11:30:00 |  | 11/05/2019 11:30:00
3550561 | 675859587 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864901 |  |  |  |  | 11/05/2019 05:30:00 | 11/05/2019 05:30:00 |  | 11/05/2019 05:30:00
3550561 | 675859587 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864239 |  |  |  |  | 11/05/2019 16:30:00 | 11/05/2019 16:30:00 |  | 11/05/2019 16:30:00
3550561 | 675859587 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864524 |  |  |  |  | 09/26/2020 06:30:00 | 09/26/2020 06:30:00 |  | 09/25/2020 16:31:46
3550561 | 675859587 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065907 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550561 | 675859587 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065983 |  |  |  |  | 09/26/2020 06:30:00 | 12/27/2021 14:07:04
3550562 | 675859586 | act--02 Integration | 02 Integration | Completed | Activity | 675862257 | 12/11/2019 15:30:00 | 12/11/2019 15:30:00 | 12/11/2019 14:00:00 | 12/11/2019 15:30:00
3550562 | 675859586 | act--04 SSV | 04 SSV | Completed | Activity | 675862369 | 12/25/2019 15:30:00 | 12/25/2019 15:30:00 | 12/25/2019 07:19:59 | 12/25/2019 14:01:33
3550562 | 675859586 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862510 | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 | 12/27/2021 14:13:10 | 12/27/2021 14:13:07
3550562 | 675859586 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862161 |  |  |  |  | 12/11/2019 12:00:00 | 12/11/2019 12:00:00 |  | 12/11/2019 12:00:00
3550562 | 675859586 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862123 |  |  |  |  | 12/11/2019 06:00:00 | 12/11/2019 06:00:00 |  | 12/11/2019 06:00:00
3550562 | 675859586 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861939 |  |  |  |  | 12/11/2019 17:00:00 | 12/11/2019 17:00:00 |  | 12/11/2019 17:00:00
3550562 | 675859586 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862027 |  |  |  |  | 12/26/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/26/2019 07:20:10
3550562 | 675859586 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066275 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550562 | 675859586 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066347 |  |  |  |  | 12/26/2019 06:30:00 | 07/30/2021 05:30:00
3550563 | 675859583 | act--02 Integration | 02 Integration | Completed | Activity | 675862223 | 11/20/2019 15:00:00 | 11/20/2019 15:00:00 | 11/20/2019 13:30:00 | 11/20/2019 15:00:00
3550563 | 675859583 | act--04 SSV | 04 SSV | Completed | Activity | 675862295 | 03/10/2020 15:30:00 | 03/10/2020 15:30:00 | 03/09/2020 08:23:50 | 03/09/2020 14:56:02
3550563 | 675859583 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862396 | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 | 12/27/2021 14:21:01 | 12/27/2021 14:20:59
3550563 | 675859583 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862142 |  |  |  |  | 11/20/2019 11:30:00 | 11/20/2019 11:30:00 |  | 11/20/2019 11:30:00
3550563 | 675859583 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862104 |  |  |  |  | 11/20/2019 05:30:00 | 11/20/2019 05:30:00 |  | 11/20/2019 05:30:00
3550563 | 675859583 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861935 |  |  |  |  | 11/20/2019 16:30:00 | 11/20/2019 16:30:00 |  | 11/20/2019 16:30:00
3550563 | 675859583 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862014 |  |  |  |  | 03/10/2020 06:30:00 | 03/10/2020 06:30:00 |  | 03/10/2020 07:18:52
3550563 | 675859583 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065331 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550563 | 675859583 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065395 |  |  |  |  | 03/10/2020 06:30:00 | 07/30/2021 05:30:00
3550564 | 675859582 | act--02 Integration | 02 Integration | Completed | Activity | 675862255 | 11/13/2019 15:00:00 | 11/13/2019 15:00:00 | 11/13/2019 13:40:01 | 11/13/2019 15:00:00
3550564 | 675859582 | act--04 SSV | 04 SSV | Completed | Activity | 675862348 | 10/14/2020 15:30:00 | 10/12/2020 15:30:00 | 10/12/2020 08:36:38 | 10/12/2020 13:25:20
3550564 | 675859582 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862458 | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 | 12/27/2021 14:06:30 | 12/27/2021 14:06:28
3550564 | 675859582 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862177 |  |  |  |  | 11/16/2019 15:30:00 | 11/15/2019 15:30:00 |  | 11/13/2019 12:30:00
3550564 | 675859582 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862121 |  |  |  |  | 11/11/2019 06:30:00 | 11/12/2019 06:30:00 |  | 11/13/2019 06:30:00
3550564 | 675859582 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861938 |  |  |  |  | 11/13/2019 14:30:00 | 11/13/2019 15:00:00 |  | 11/13/2019 16:00:00
3550564 | 675859582 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862016 |  |  |  |  | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 |  | 10/13/2020 08:26:38
3550564 | 675859582 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065906 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550564 | 675859582 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065976 |  |  |  |  | 10/13/2020 06:30:00 | 07/30/2021 05:30:00
3550565 | 675859585 | act--02 Integration | 02 Integration | Completed | Activity | 675862242 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550565 | 675859585 | act--04 SSV | 04 SSV | Completed | Activity | 675862380 | 01/15/2021 15:30:00 | 01/16/2021 15:30:00 | 01/14/2021 06:45:27 | 01/14/2021 15:28:15
3550565 | 675859585 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862547 | 01/15/2021 06:30:00 | 01/15/2021 06:30:00 | 12/27/2021 14:00:32 | 12/27/2021 14:00:32
3550565 | 675859585 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862148 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550565 | 675859585 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862109 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550565 | 675859585 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861931 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550565 | 675859585 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862020 |  |  |  |  | 01/15/2021 06:30:00 | 01/15/2021 06:30:00 |  | 01/15/2021 07:00:30
3550565 | 675859585 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066272 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550565 | 675859585 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066353 |  |  |  |  | 01/15/2021 06:30:00 | 12/27/2021 14:00:32
3550566 | 675859584 | act--02 Integration | 02 Integration | Completed | Activity | 675862251 | 10/31/2019 15:00:00 | 10/31/2019 15:00:00 | 10/31/2019 13:40:01 | 10/31/2019 15:00:00
3550566 | 675859584 | act--04 SSV | 04 SSV | Completed | Activity | 675862382 | 03/25/2021 05:30:00 | 03/25/2021 05:30:00 | 03/25/2021 04:00:00 | 03/27/2021 07:05:00
3550566 | 675859584 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862519 | 03/27/2021 09:05:00 | 03/27/2021 09:05:00 | 12/27/2021 14:00:13 | 12/27/2021 14:00:12
3550566 | 675859584 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862167 |  |  |  |  | 11/03/2019 15:30:00 | 11/02/2019 15:30:00 |  | 10/31/2019 12:30:00
3550566 | 675859584 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862125 |  |  |  |  | 10/29/2019 06:30:00 | 10/30/2019 06:30:00 |  | 10/31/2019 06:30:00
3550566 | 675859584 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861932 |  |  |  |  | 10/31/2019 14:30:00 | 10/31/2019 15:00:00 |  | 10/31/2019 16:00:00
3550566 | 675859584 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862040 |  |  |  |  | 03/27/2021 09:05:00 | 03/27/2021 09:05:00 |  | 03/28/2021 05:00:00
3550566 | 675859584 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066297 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550566 | 675859584 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066382 |  |  |  |  | 03/27/2021 09:05:00 | 12/27/2021 14:00:12
3550568 | 675859641 | act--02 Integration | 02 Integration | Completed | Activity | 675865117 | 08/29/2019 15:00:00 | 08/29/2019 15:00:00 | 08/29/2019 13:30:00 | 08/29/2019 15:00:00
3550568 | 675859641 | act--04 SSV | 04 SSV | Completed | Activity | 675865509 | 12/19/2019 15:30:00 | 12/19/2019 15:30:00 | 12/18/2019 08:17:58 | 12/18/2019 14:39:45
3550568 | 675859641 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865842 | 12/25/2019 06:30:00 | 12/25/2019 06:30:00 | 12/27/2021 14:13:10 | 12/27/2021 14:13:08
3550568 | 675859641 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864823 |  |  |  |  | 08/29/2019 11:30:00 | 08/29/2019 11:30:00 |  | 08/29/2019 11:30:00
3550568 | 675859641 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864620 |  |  |  |  | 08/29/2019 05:30:00 | 08/29/2019 05:30:00 |  | 08/29/2019 05:30:00
3550568 | 675859641 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864148 |  |  |  |  | 08/29/2019 16:30:00 | 08/29/2019 16:30:00 |  | 08/29/2019 16:30:00
3550568 | 675859641 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864335 |  |  |  |  | 12/25/2019 06:30:00 | 12/25/2019 06:30:00 |  | 12/25/2019 07:00:00
3550568 | 675859641 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065905 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550568 | 675859641 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066000 |  |  |  |  | 12/25/2019 06:30:00 | 07/30/2021 05:30:00
3550569 | 675859683 | act--02 Integration | 02 Integration | Completed | Activity | 675864256 | 05/20/2020 15:00:00 | 05/20/2020 15:00:00 | 05/20/2020 14:00:00 | 05/20/2020 15:00:00
3550569 | 675859683 | act--04 SSV | 04 SSV | Completed | Activity | 675864601 | 01/15/2021 15:30:00 | 01/17/2021 15:30:00 | 01/15/2021 08:26:33 | 01/15/2021 13:27:03
3550569 | 675859683 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864928 | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 | 12/27/2021 14:06:45 | 12/27/2021 14:06:43
3550569 | 675859683 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864102 |  |  |  |  | 05/23/2020 15:30:00 | 05/22/2020 15:30:00 |  | 05/20/2020 12:30:00
3550569 | 675859683 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864015 |  |  |  |  | 05/18/2020 06:30:00 | 05/19/2020 06:30:00 |  | 05/20/2020 06:30:00
3550569 | 675859683 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863799 |  |  |  |  | 05/20/2020 14:30:00 | 05/20/2020 15:00:00 |  | 05/20/2020 16:00:00
3550569 | 675859683 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863890 |  |  |  |  | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 |  | 01/16/2021 08:26:11
3550569 | 675859683 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066165 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550569 | 675859683 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066306 |  |  |  |  | 01/16/2021 06:30:00 | 12/27/2021 14:06:43
3550570 | 675859687 | act--02 Integration | 02 Integration | Completed | Activity | 675862258 | 11/03/2019 15:00:00 | 11/03/2019 15:00:00 | 11/03/2019 13:40:01 | 11/03/2019 15:00:00
3550570 | 675859687 | act--04 SSV | 04 SSV | Completed | Activity | 675862379 | 03/31/2021 05:30:00 | 03/31/2021 05:30:00 | 03/31/2021 03:25:00 | 04/01/2021 03:05:00
3550570 | 675859687 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862525 | 04/01/2021 09:00:00 | 04/01/2021 09:00:00 | 12/27/2021 14:25:50 | 12/27/2021 14:25:49
3550570 | 675859687 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862166 |  |  |  |  | 11/06/2019 15:30:00 | 11/05/2019 15:30:00 |  | 11/03/2019 12:30:00
3550570 | 675859687 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862132 |  |  |  |  | 11/01/2019 06:30:00 | 11/02/2019 06:30:00 |  | 11/03/2019 06:30:00
3550570 | 675859687 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861955 |  |  |  |  | 11/03/2019 14:30:00 | 11/03/2019 15:00:00 |  | 11/03/2019 16:00:00
3550570 | 675859687 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862047 |  |  |  |  | 04/01/2021 09:00:00 | 04/01/2021 09:00:00 |  | 04/01/2021 17:00:00
3550570 | 675859687 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066317 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550570 | 675859687 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066424 |  |  |  |  | 04/01/2021 09:00:00 | 07/30/2021 05:30:00
3550571 | 675859725 | act--02 Integration | 02 Integration | Completed | Activity | 675861812 | 11/27/2019 15:00:00 | 11/27/2019 15:00:00 | 11/27/2019 13:40:01 | 11/27/2019 15:00:00
3550571 | 675859725 | act--04 SSV | 04 SSV | Completed | Activity | 675861837 | 11/13/2020 15:30:00 | 11/13/2020 15:30:00 | 11/11/2020 08:22:26 | 11/11/2020 13:23:29
3550571 | 675859725 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861868 | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 | 12/27/2021 14:25:52 | 12/27/2021 14:25:49
3550571 | 675859725 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861788 |  |  |  |  | 11/30/2019 15:30:00 | 11/29/2019 15:30:00 |  | 11/27/2019 12:30:00
3550571 | 675859725 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861778 |  |  |  |  | 11/25/2019 06:30:00 | 11/26/2019 06:30:00 |  | 11/27/2019 06:30:00
3550571 | 675859725 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861693 |  |  |  |  | 11/27/2019 14:30:00 | 11/27/2019 15:00:00 |  | 11/27/2019 16:00:00
3550571 | 675859725 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861739 |  |  |  |  | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 |  | 01/15/2021 16:21:20
3550571 | 675859725 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065848 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550571 | 675859725 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065910 |  |  |  |  | 01/16/2021 06:30:00 | 07/30/2021 05:30:00
3550572 | 675859727 | act--02 Integration | 02 Integration | Completed | Activity | 675861586 | 12/03/2019 15:00:00 | 12/03/2019 15:00:00 | 12/03/2019 13:40:01 | 12/03/2019 15:00:00
3550572 | 675859727 | act--04 SSV | 04 SSV | Completed | Activity | 675861642 | 10/12/2020 15:30:00 | 10/13/2020 15:30:00 | 10/12/2020 08:49:23 | 10/12/2020 13:10:53
3550572 | 675859727 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861691 | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 | 12/27/2021 14:06:28 | 12/27/2021 14:06:27
3550572 | 675859727 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861512 |  |  |  |  | 12/06/2019 15:30:00 | 12/05/2019 15:30:00 |  | 12/03/2019 12:30:00
3550572 | 675859727 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861476 |  |  |  |  | 12/01/2019 06:30:00 | 12/02/2019 06:30:00 |  | 12/03/2019 06:30:00
3550572 | 675859727 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861343 |  |  |  |  | 12/03/2019 14:30:00 | 12/03/2019 15:00:00 |  | 12/03/2019 16:00:00
3550572 | 675859727 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861408 |  |  |  |  | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 |  | 11/11/2020 16:59:40
3550572 | 675859727 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066065 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550572 | 675859727 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066174 |  |  |  |  | 11/12/2020 06:30:00 | 07/30/2021 05:30:00
3550573 | 675859786 | act--02 Integration | 02 Integration | Completed | Activity | 675865153 | 05/16/2020 15:00:00 | 05/16/2020 15:00:00 | 05/16/2020 14:00:00 | 05/16/2020 15:00:00
3550573 | 675859786 | act--04 SSV | 04 SSV | Completed | Activity | 675865597 | 03/23/2021 05:30:00 | 03/23/2021 05:30:00 | 03/23/2021 09:27:00 | 03/25/2021 09:05:00
3550573 | 675859786 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865912 | 03/25/2021 11:05:00 | 03/25/2021 11:05:00 | 12/27/2021 14:25:50 | 12/27/2021 14:25:49
3550573 | 675859786 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864838 |  |  |  |  | 05/19/2020 15:30:00 | 05/18/2020 15:30:00 |  | 05/16/2020 12:30:00
3550573 | 675859786 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864628 |  |  |  |  | 05/14/2020 06:30:00 | 05/15/2020 06:30:00 |  | 05/16/2020 06:30:00
3550573 | 675859786 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864144 |  |  |  |  | 05/16/2020 14:30:00 | 05/16/2020 15:00:00 |  | 05/16/2020 16:00:00
3550573 | 675859786 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864343 |  |  |  |  | 03/25/2021 11:05:00 | 03/25/2021 11:05:00 |  | 03/26/2021 05:00:00
3550573 | 675859786 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066023 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550573 | 675859786 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066197 |  |  |  |  | 03/25/2021 11:05:00 | 07/30/2021 05:30:00
3550574 | 675859787 | act--02 Integration | 02 Integration | Completed | Activity | 675862247 | 08/28/2019 15:00:00 | 08/28/2019 15:00:00 | 08/28/2019 13:40:00 | 08/28/2019 15:00:00
3550574 | 675859787 | act--04 SSV | 04 SSV | Completed | Activity | 675862388 | 09/28/2020 15:30:00 | 09/28/2020 15:30:00 | 09/27/2020 07:46:26 | 09/27/2020 14:18:59
3550574 | 675859787 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862520 | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 | 12/27/2021 14:00:14 | 12/27/2021 14:00:12
3550574 | 675859787 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862163 |  |  |  |  | 08/31/2019 15:30:00 | 08/30/2019 15:30:00 |  | 08/28/2019 12:30:00
3550574 | 675859787 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862126 |  |  |  |  | 08/26/2019 06:30:00 | 08/27/2019 06:30:00 |  | 08/28/2019 06:30:00
3550574 | 675859787 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861934 |  |  |  |  | 08/28/2019 14:30:00 | 08/28/2019 15:00:00 |  | 08/28/2019 16:00:00
3550574 | 675859787 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862019 |  |  |  |  | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 |  | 10/12/2020 17:25:17
3550574 | 675859787 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066063 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550574 | 675859787 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066193 |  |  |  |  | 10/13/2020 06:30:00 | 12/27/2021 14:00:12
3550575 | 675859811 | act--02 Integration | 02 Integration | Completed | Activity | 675863166 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550575 | 675859811 | act--04 SSV | 04 SSV | Completed | Activity | 675863401 | 10/15/2020 15:30:00 | 10/15/2020 15:30:00 | 10/13/2020 07:00:23 | 10/13/2020 13:28:09
3550575 | 675859811 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863570 | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 | 12/27/2021 13:59:54 | 12/27/2021 13:59:51
3550575 | 675859811 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863012 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550575 | 675859811 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862949 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550575 | 675859811 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862665 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550575 | 675859811 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862855 |  |  |  |  | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 |  | 10/14/2020 07:59:43
3550575 | 675859811 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066274 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550575 | 675859811 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066337 |  |  |  |  | 10/14/2020 06:30:00 | 12/27/2021 13:59:51
3550576 | 675859812 | act--02 Integration | 02 Integration | Completed | Activity | 675862497 | 09/08/2019 15:00:00 | 09/08/2019 15:00:00 | 09/08/2019 13:30:00 | 09/08/2019 15:00:00
3550576 | 675859812 | act--04 SSV | 04 SSV | Completed | Activity | 675862690 | 03/28/2020 15:30:00 | 03/27/2020 15:30:00 | 03/26/2020 06:32:52 | 03/26/2020 14:04:24
3550576 | 675859812 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862939 | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 | 12/27/2021 14:00:54 | 12/27/2021 14:00:53
3550576 | 675859812 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862391 |  |  |  |  | 09/08/2019 11:30:00 | 09/08/2019 11:30:00 |  | 09/08/2019 11:30:00
3550576 | 675859812 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862352 |  |  |  |  | 09/08/2019 05:30:00 | 09/08/2019 05:30:00 |  | 09/08/2019 05:30:00
3550576 | 675859812 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862188 |  |  |  |  | 09/08/2019 16:30:00 | 09/08/2019 16:30:00 |  | 09/08/2019 16:30:00
3550576 | 675859812 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862269 |  |  |  |  | 10/14/2020 06:30:00 | 10/14/2020 06:30:00 |  | 10/13/2020 17:24:48
3550576 | 675859812 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065821 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550576 | 675859812 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065885 |  |  |  |  | 10/14/2020 06:30:00 | 12/27/2021 14:00:53
3550577 | 675859907 | act--02 Integration | 02 Integration | Completed | Activity | 675862245 | 08/16/2019 15:00:00 | 08/16/2019 15:00:00 | 08/16/2019 13:40:05 | 08/16/2019 15:00:00
3550577 | 675859907 | act--04 SSV | 04 SSV | Completed | Activity | 675862378 | 03/09/2021 05:30:00 | 03/09/2021 05:30:00 | 03/09/2021 06:35:00 | 03/11/2021 07:25:00
3550577 | 675859907 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862514 | 03/11/2021 09:25:00 | 03/11/2021 09:25:00 | 12/27/2021 14:25:56 | 12/27/2021 14:25:55
3550577 | 675859907 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862152 |  |  |  |  | 08/19/2019 15:30:00 | 08/18/2019 15:30:00 |  | 08/16/2019 12:30:00
3550577 | 675859907 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862116 |  |  |  |  | 08/14/2019 06:30:00 | 08/15/2019 06:30:00 |  | 08/16/2019 06:30:00
3550577 | 675859907 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861948 |  |  |  |  | 08/16/2019 14:30:00 | 08/16/2019 15:00:00 |  | 08/16/2019 16:00:00
3550577 | 675859907 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862017 |  |  |  |  | 03/11/2021 09:25:00 | 03/11/2021 09:25:00 |  | 03/12/2021 05:00:00
3550577 | 675859907 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065949 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550577 | 675859907 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066010 |  |  |  |  | 03/11/2021 09:25:00 | 07/30/2021 05:30:00
3550578 | 675859910 | act--02 Integration | 02 Integration | Completed | Activity | 675865265 | 11/27/2019 15:00:00 | 11/27/2019 15:00:00 | 11/27/2019 13:40:01 | 11/27/2019 15:00:00
3550578 | 675859910 | act--04 SSV | 04 SSV | Completed | Activity | 675865625 | 11/12/2020 15:30:00 | 11/11/2020 15:30:00 | 11/11/2020 08:03:00 | 11/11/2020 13:25:54
3550578 | 675859910 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865937 | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 | 12/27/2021 14:12:42 | 12/27/2021 14:12:40
3550578 | 675859910 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864966 |  |  |  |  | 11/30/2019 15:30:00 | 11/29/2019 15:30:00 |  | 11/27/2019 12:30:00
3550578 | 675859910 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864771 |  |  |  |  | 11/25/2019 06:30:00 | 11/26/2019 06:30:00 |  | 11/27/2019 06:30:00
3550578 | 675859910 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864243 |  |  |  |  | 11/27/2019 14:30:00 | 11/27/2019 15:00:00 |  | 11/27/2019 16:00:00
3550578 | 675859910 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864559 |  |  |  |  | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 |  | 11/12/2020 06:34:40
3550578 | 675859910 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065847 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550578 | 675859910 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065928 |  |  |  |  | 11/12/2020 06:30:00 | 07/30/2021 05:30:00
3550579 | 675859913 | act--02 Integration | 02 Integration | Completed | Activity | 675863002 | 09/07/2019 15:00:00 | 09/07/2019 15:00:00 | 09/07/2019 13:30:00 | 09/07/2019 15:00:00
3550579 | 675859913 | act--04 SSV | 04 SSV | Completed | Activity | 675863195 | 10/16/2019 15:30:00 | 10/16/2019 15:30:00 | 10/15/2019 08:09:33 | 10/15/2019 13:22:35
3550579 | 675859913 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863432 | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 | 12/27/2021 14:20:58 | 12/27/2021 14:20:57
3550579 | 675859913 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862896 |  |  |  |  | 09/07/2019 11:30:00 | 09/07/2019 11:30:00 |  | 09/07/2019 11:30:00
3550579 | 675859913 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862844 |  |  |  |  | 09/07/2019 05:30:00 | 09/07/2019 05:30:00 |  | 09/07/2019 05:30:00
3550579 | 675859913 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862475 |  |  |  |  | 09/07/2019 16:30:00 | 09/07/2019 16:30:00 |  | 09/07/2019 16:30:00
3550579 | 675859913 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862602 |  |  |  |  | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 |  | 11/11/2020 15:58:21
3550579 | 675859913 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066858 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550579 | 675859913 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067051 |  |  |  |  | 11/12/2020 06:30:00 | 07/30/2021 05:30:00
3550580 | 675859918 | act--02 Integration | 02 Integration | Completed | Activity | 675864411 | 10/31/2019 15:00:00 | 10/31/2019 15:00:00 | 10/31/2019 13:40:01 | 10/31/2019 15:00:00
3550580 | 675859918 | act--04 SSV | 04 SSV | Completed | Activity | 675864681 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/29/2020 06:54:54 | 09/29/2020 14:03:03
3550580 | 675859918 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865015 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 14:25:51 | 12/27/2021 14:25:49
3550580 | 675859918 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864219 |  |  |  |  | 11/03/2019 15:30:00 | 11/02/2019 15:30:00 |  | 10/31/2019 12:30:00
3550580 | 675859918 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864122 |  |  |  |  | 10/29/2019 06:30:00 | 10/30/2019 06:30:00 |  | 10/31/2019 06:30:00
3550580 | 675859918 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863883 |  |  |  |  | 10/31/2019 14:30:00 | 10/31/2019 15:00:00 |  | 10/31/2019 16:00:00
3550580 | 675859918 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863989 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/30/2020 08:25:12
3550580 | 675859918 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066588 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550580 | 675859918 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066688 |  |  |  |  | 09/30/2020 06:30:00 | 07/30/2021 05:30:00
3550581 | 675859929 | act--02 Integration | 02 Integration | Completed | Activity | 675862933 | 10/23/2019 15:00:00 | 10/23/2019 15:00:00 | 10/23/2019 13:30:00 | 10/23/2019 15:00:00
3550581 | 675859929 | act--04 SSV | 04 SSV | Completed | Activity | 675863065 | 12/24/2019 15:30:00 | 12/24/2019 15:30:00 | 12/23/2019 08:40:09 | 12/23/2019 14:31:21
3550581 | 675859929 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863289 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 14:26:09 | 12/27/2021 14:26:08
3550581 | 675859929 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862838 |  |  |  |  | 10/23/2019 11:30:00 | 10/23/2019 11:30:00 |  | 10/23/2019 11:30:00
3550581 | 675859929 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862710 |  |  |  |  | 10/23/2019 05:30:00 | 10/23/2019 05:30:00 |  | 10/23/2019 05:30:00
3550581 | 675859929 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862404 |  |  |  |  | 10/23/2019 16:30:00 | 10/23/2019 16:30:00 |  | 10/23/2019 16:30:00
3550581 | 675859929 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862541 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/29/2020 16:32:45
3550581 | 675859929 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065970 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550581 | 675859929 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066172 |  |  |  |  | 09/30/2020 06:30:00 | 07/30/2021 05:30:00
3550582 | 675859960 | act--02 Integration | 02 Integration | Completed | Activity | 675861764 | 11/23/2019 15:00:00 | 11/23/2019 15:00:00 | 11/23/2019 13:40:01 | 11/23/2019 15:00:00
3550582 | 675859960 | act--04 SSV | 04 SSV | Completed | Activity | 675861792 | 03/21/2021 05:30:00 | 03/21/2021 05:30:00 | 03/21/2021 07:55:00 | 03/23/2021 07:05:00
3550582 | 675859960 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675861825 | 03/23/2021 09:05:00 | 03/23/2021 09:05:00 | 12/27/2021 13:59:55 | 12/27/2021 13:59:53
3550582 | 675859960 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675861727 |  |  |  |  | 11/26/2019 15:30:00 | 11/25/2019 15:30:00 |  | 11/23/2019 12:30:00
3550582 | 675859960 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675861700 |  |  |  |  | 11/21/2019 06:30:00 | 11/22/2019 06:30:00 |  | 11/23/2019 06:30:00
3550582 | 675859960 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861635 |  |  |  |  | 11/23/2019 14:30:00 | 11/23/2019 15:00:00 |  | 11/23/2019 16:00:00
3550582 | 675859960 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675861668 |  |  |  |  | 03/23/2021 09:05:00 | 03/23/2021 09:05:00 |  | 03/24/2021 05:00:00
3550582 | 675859960 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066093 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550582 | 675859960 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066175 |  |  |  |  | 03/23/2021 09:05:00 | 12/27/2021 13:59:53
3550583 | 675859961 | act--02 Integration | 02 Integration | Completed | Activity | 675863220 | 08/19/2019 15:30:00 | 08/19/2019 15:30:00 | 08/19/2019 14:00:00 | 08/19/2019 15:30:00
3550583 | 675859961 | act--04 SSV | 04 SSV | Completed | Activity | 675863437 | 08/28/2019 15:30:00 | 08/26/2019 15:30:00 | 08/26/2019 08:05:36 | 08/26/2019 14:38:07
3550583 | 675859961 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863605 | 12/24/2019 06:30:00 | 12/24/2019 06:30:00 | 12/27/2021 14:26:28 | 12/27/2021 14:26:26
3550583 | 675859961 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863056 |  |  |  |  | 08/19/2019 12:00:00 | 08/19/2019 12:00:00 |  | 08/19/2019 12:00:00
3550583 | 675859961 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862986 |  |  |  |  | 08/19/2019 06:00:00 | 08/19/2019 06:00:00 |  | 08/19/2019 06:00:00
3550583 | 675859961 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862680 |  |  |  |  | 08/19/2019 17:00:00 | 08/19/2019 17:00:00 |  | 08/19/2019 17:00:00
3550583 | 675859961 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862875 |  |  |  |  | 12/24/2019 06:30:00 | 12/24/2019 06:30:00 |  | 12/23/2019 17:03:28
3550583 | 675859961 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065328 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550583 | 675859961 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065396 |  |  |  |  | 12/24/2019 06:30:00 | 07/30/2021 05:30:00
3550584 | 675860036 | act--02 Integration | 02 Integration | Completed | Activity | 675863164 | 08/20/2019 15:30:00 | 08/20/2019 15:30:00 | 08/20/2019 14:00:00 | 08/20/2019 15:30:00
3550584 | 675860036 | act--04 SSV | 04 SSV | Completed | Activity | 675863418 | 03/12/2020 15:30:00 | 03/11/2020 15:30:00 | 03/11/2020 07:10:51 | 03/11/2020 15:20:04
3550584 | 675860036 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863577 | 03/12/2020 06:30:00 | 03/12/2020 06:30:00 | 12/27/2021 14:00:54 | 12/27/2021 14:00:52
3550584 | 675860036 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863014 |  |  |  |  | 08/20/2019 12:00:00 | 08/20/2019 12:00:00 |  | 08/20/2019 12:00:00
3550584 | 675860036 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862951 |  |  |  |  | 08/20/2019 06:00:00 | 08/20/2019 06:00:00 |  | 08/20/2019 06:00:00
3550584 | 675860036 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862681 |  |  |  |  | 08/20/2019 17:00:00 | 08/20/2019 17:00:00 |  | 08/20/2019 17:00:00
3550584 | 675860036 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862866 |  |  |  |  | 03/12/2020 06:30:00 | 03/12/2020 06:30:00 |  | 03/12/2020 07:38:39
3550584 | 675860036 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065901 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550584 | 675860036 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065985 |  |  |  |  | 03/12/2020 06:30:00 | 12/27/2021 14:00:52
3550585 | 675860034 | act--02 Integration | 02 Integration | Completed | Activity | 675863404 | 09/26/2019 15:00:00 | 09/26/2019 15:00:00 | 09/26/2019 13:30:00 | 09/26/2019 15:00:00
3550585 | 675860034 | act--04 SSV | 04 SSV | Completed | Activity | 675863575 | 10/27/2019 15:30:00 | 10/26/2019 15:30:00 | 10/26/2019 07:27:30 | 10/26/2019 13:39:33
3550585 | 675860034 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863719 | 03/12/2020 06:30:00 | 03/12/2020 06:30:00 | 12/27/2021 14:01:03 | 12/27/2021 14:01:00
3550585 | 675860034 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863232 |  |  |  |  | 09/26/2019 11:30:00 | 09/26/2019 11:30:00 |  | 09/26/2019 11:30:00
3550585 | 675860034 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863111 |  |  |  |  | 09/26/2019 05:30:00 | 09/26/2019 05:30:00 |  | 09/26/2019 05:30:00
3550585 | 675860034 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862889 |  |  |  |  | 09/26/2019 16:30:00 | 09/26/2019 16:30:00 |  | 09/26/2019 16:30:00
3550585 | 675860034 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862975 |  |  |  |  | 03/12/2020 06:30:00 | 03/12/2020 06:30:00 |  | 03/11/2020 16:04:22
3550585 | 675860034 | ms--07 PAC | 07 PAC | Completed | Milestone | 718069074 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550585 | 675860034 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070111 |  |  |  |  | 03/12/2020 06:30:00 | 12/27/2021 14:01:00
3550586 | 675860410 | act--02 Integration | 02 Integration | Completed | Activity | 675863010 | 12/31/2019 15:00:00 | 12/31/2019 15:00:00 | 12/31/2019 13:40:01 | 12/31/2019 15:00:00
3550586 | 675860410 | act--04 SSV | 04 SSV | Completed | Activity | 675863200 | 10/12/2020 15:30:00 | 10/13/2020 15:30:00 | 10/11/2020 06:46:24 | 10/11/2020 14:24:43
3550586 | 675860410 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863444 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:00:16 | 12/27/2021 14:00:15
3550586 | 675860410 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862902 |  |  |  |  | 01/03/2020 15:30:00 | 01/02/2020 15:30:00 |  | 12/31/2019 12:30:00
3550586 | 675860410 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862850 |  |  |  |  | 12/29/2019 06:30:00 | 12/30/2019 06:30:00 |  | 12/31/2019 06:30:00
3550586 | 675860410 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862476 |  |  |  |  | 12/31/2019 14:30:00 | 12/31/2019 15:00:00 |  | 12/31/2019 16:00:00
3550586 | 675860410 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862598 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/12/2020 08:13:52
3550586 | 675860410 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065902 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550586 | 675860410 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718065998 |  |  |  |  | 10/12/2020 06:30:00 | 12/27/2021 14:00:15
3550587 | 675860435 | act--02 Integration | 02 Integration | Completed | Activity | 675864664 | 04/02/2020 15:00:00 | 04/02/2020 15:00:00 | 04/02/2020 14:00:00 | 04/02/2020 15:00:00
3550587 | 675860435 | act--04 SSV | 04 SSV | Completed | Activity | 675864965 | 09/22/2020 05:30:00 | 09/22/2020 05:30:00 | 09/22/2020 09:10:00 | 09/24/2020 23:15:00
3550587 | 675860435 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865353 | 09/25/2020 01:15:00 | 09/25/2020 01:15:00 | 12/27/2021 14:19:48 | 12/27/2021 14:19:46
3550587 | 675860435 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864417 |  |  |  |  | 04/05/2020 15:30:00 | 04/04/2020 15:30:00 |  | 04/02/2020 12:30:00
3550587 | 675860435 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864252 |  |  |  |  | 03/31/2020 06:30:00 | 04/01/2020 06:30:00 |  | 04/02/2020 06:30:00
3550587 | 675860435 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863962 |  |  |  |  | 04/02/2020 14:30:00 | 04/02/2020 15:00:00 |  | 04/02/2020 16:00:00
3550587 | 675860435 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864098 |  |  |  |  | 09/25/2020 01:15:00 | 09/25/2020 01:15:00 |  | 09/26/2020 05:00:00
3550587 | 675860435 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066618 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550587 | 675860435 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066677 |  |  |  |  | 09/25/2020 01:15:00 | 07/30/2021 05:30:00
3550588 | 675860438 | act--02 Integration | 02 Integration | Completed | Activity | 675865291 | 12/29/2019 15:00:00 | 12/29/2019 15:00:00 | 12/29/2019 13:40:01 | 12/29/2019 15:00:00
3550588 | 675860438 | act--04 SSV | 04 SSV | Completed | Activity | 675865648 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/29/2020 08:08:31 | 09/29/2020 14:37:38
3550588 | 675860438 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865959 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:00:14 | 12/27/2021 14:00:13
3550588 | 675860438 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865012 |  |  |  |  | 01/01/2020 15:30:00 | 12/31/2019 15:30:00 |  | 12/29/2019 12:30:00
3550588 | 675860438 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864859 |  |  |  |  | 12/27/2019 06:30:00 | 12/28/2019 06:30:00 |  | 12/29/2019 06:30:00
3550588 | 675860438 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864245 |  |  |  |  | 12/29/2019 14:30:00 | 12/29/2019 15:00:00 |  | 12/29/2019 16:00:00
3550588 | 675860438 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864515 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/11/2020 15:53:51
3550588 | 675860438 | ms--07 PAC | 07 PAC | Completed | Milestone | 718065966 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550588 | 675860438 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066194 |  |  |  |  | 10/12/2020 06:30:00 | 12/27/2021 14:00:13
3550589 | 675860789 | act--02 Integration | 02 Integration | Completed | Activity | 675862997 | 03/16/2020 15:00:00 | 03/16/2020 15:00:00 | 03/16/2020 13:40:01 | 03/16/2020 15:00:00
3550589 | 675860789 | act--04 SSV | 04 SSV | Completed | Activity | 675863187 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/29/2020 08:00:35 | 09/29/2020 13:47:45
3550589 | 675860789 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863415 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 14:26:00 | 12/27/2021 14:25:58
3550589 | 675860789 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862895 |  |  |  |  | 03/19/2020 15:30:00 | 03/18/2020 15:30:00 |  | 03/16/2020 12:30:00
3550589 | 675860789 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862846 |  |  |  |  | 03/14/2020 06:30:00 | 03/15/2020 06:30:00 |  | 03/16/2020 06:30:00
3550589 | 675860789 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862483 |  |  |  |  | 03/16/2020 14:30:00 | 03/16/2020 15:00:00 |  | 03/16/2020 16:00:00
3550589 | 675860789 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862582 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/29/2020 17:00:48
3550589 | 675860789 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067409 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550589 | 675860789 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067531 |  |  |  |  | 09/30/2020 06:30:00 | 07/30/2021 05:30:00
3550590 | 675860893 | act--02 Integration | 02 Integration | Completed | Activity | 675863583 | 07/31/2020 15:00:00 | 07/31/2020 15:00:00 | 07/31/2020 14:00:00 | 07/31/2020 15:00:00
3550590 | 675860893 | act--04 SSV | 04 SSV | Completed | Activity | 675863715 | 02/01/2021 15:30:00 | 02/02/2021 15:30:00 | 01/31/2021 08:36:24 | 01/31/2021 13:39:47
3550590 | 675860893 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863829 | 02/01/2021 06:30:00 | 02/01/2021 06:30:00 | 12/27/2021 14:26:05 | 12/27/2021 14:26:04
3550590 | 675860893 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863463 |  |  |  |  | 08/03/2020 15:30:00 | 08/02/2020 15:30:00 |  | 07/31/2020 12:30:00
3550590 | 675860893 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863389 |  |  |  |  | 07/29/2020 06:30:00 | 07/30/2020 06:30:00 |  | 07/31/2020 06:30:00
3550590 | 675860893 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863052 |  |  |  |  | 07/31/2020 14:30:00 | 07/31/2020 15:00:00 |  | 07/31/2020 16:00:00
3550590 | 675860893 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863213 |  |  |  |  | 02/01/2021 06:30:00 | 02/01/2021 06:30:00 |  | 02/01/2021 06:39:12
3550590 | 675860893 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067877 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550590 | 675860893 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067972 |  |  |  |  | 02/01/2021 06:30:00 | 07/30/2021 05:30:00
3550591 | 675860889 | act--02 Integration | 02 Integration | Completed | Activity | 675863661 | 05/21/2020 15:00:00 | 05/21/2020 15:00:00 | 05/21/2020 14:00:00 | 05/21/2020 15:00:00
3550591 | 675860889 | act--04 SSV | 04 SSV | Completed | Activity | 675863776 | 03/26/2021 05:30:00 | 03/26/2021 05:30:00 | 03/26/2021 03:45:00 | 03/29/2021 10:05:00
3550591 | 675860889 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863898 | 03/29/2021 12:05:00 | 03/29/2021 12:05:00 | 12/27/2021 14:25:50 | 12/27/2021 14:25:48
3550591 | 675860889 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863557 |  |  |  |  | 05/24/2020 15:30:00 | 05/23/2020 15:30:00 |  | 05/21/2020 12:30:00
3550591 | 675860889 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863480 |  |  |  |  | 05/19/2020 06:30:00 | 05/20/2020 06:30:00 |  | 05/21/2020 06:30:00
3550591 | 675860889 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863180 |  |  |  |  | 05/21/2020 14:30:00 | 05/21/2020 15:00:00 |  | 05/21/2020 16:00:00
3550591 | 675860889 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863353 |  |  |  |  | 03/29/2021 12:05:00 | 03/29/2021 12:05:00 |  | 03/30/2021 05:00:00
3550591 | 675860889 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067069 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550591 | 675860889 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067225 |  |  |  |  | 03/29/2021 12:05:00 | 07/30/2021 05:30:00
3550592 | 675860891 | act--02 Integration | 02 Integration | Completed | Activity | 675863686 | 12/16/2019 15:00:00 | 12/16/2019 15:00:00 | 12/16/2019 13:40:01 | 12/16/2019 15:00:00
3550592 | 675860891 | act--04 SSV | 04 SSV | Completed | Activity | 675863787 | 03/25/2021 05:30:00 | 03/25/2021 05:30:00 | 03/25/2021 10:15:00 | 03/27/2021 01:30:00
3550592 | 675860891 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863919 | 03/27/2021 03:30:00 | 03/27/2021 03:30:00 | 12/27/2021 14:26:08 | 12/27/2021 14:26:07
3550592 | 675860891 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863573 |  |  |  |  | 12/19/2019 15:30:00 | 12/18/2019 15:30:00 |  | 12/16/2019 12:30:00
3550592 | 675860891 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863496 |  |  |  |  | 12/14/2019 06:30:00 | 12/15/2019 06:30:00 |  | 12/16/2019 06:30:00
3550592 | 675860891 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863201 |  |  |  |  | 12/16/2019 14:30:00 | 12/16/2019 15:00:00 |  | 12/16/2019 16:00:00
3550592 | 675860891 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863370 |  |  |  |  | 03/27/2021 03:30:00 | 03/27/2021 03:30:00 |  | 03/28/2021 05:00:00
3550592 | 675860891 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070425 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550592 | 675860891 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070509 |  |  |  |  | 03/27/2021 03:30:00 | 07/30/2021 05:30:00
3550594 | 675860898 | act--02 Integration | 02 Integration | Completed | Activity | 675864554 | 12/02/2019 15:00:00 | 12/02/2019 15:00:00 | 12/02/2019 12:30:01 | 12/02/2019 14:00:00
3550594 | 675860898 | act--04 SSV | 04 SSV | Completed | Activity | 675864943 | 10/12/2020 15:30:00 | 10/13/2020 15:30:00 | 10/11/2020 06:44:59 | 10/11/2020 13:31:55
3550594 | 675860898 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865325 | 10/12/2020 09:00:00 | 10/12/2020 10:00:00 | 12/27/2021 14:12:26 | 12/27/2021 14:12:23
3550594 | 675860898 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864269 |  |  |  |  | 12/05/2019 15:30:00 | 12/04/2019 15:30:00 |  | 12/02/2019 12:30:00
3550594 | 675860898 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864137 |  |  |  |  | 11/30/2019 06:30:00 | 12/01/2019 06:30:00 |  | 12/02/2019 06:30:00
3550594 | 675860898 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863884 |  |  |  |  | 12/02/2019 14:30:00 | 12/02/2019 15:00:00 |  | 12/02/2019 16:00:00
3550594 | 675860898 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863994 |  |  |  |  | 10/12/2020 09:00:00 | 10/12/2020 10:00:00 |  | 10/12/2020 10:30:00
3550594 | 675860898 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067029 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550594 | 675860898 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067176 |  |  |  |  | 10/12/2020 09:00:00 | 07/30/2021 05:30:00
3550595 | 675860888 | act--02 Integration | 02 Integration | Completed | Activity | 675864232 | 06/05/2020 15:00:00 | 06/05/2020 15:00:00 | 06/05/2020 14:00:00 | 06/05/2020 15:00:00
3550595 | 675860888 | act--04 SSV | 04 SSV | Completed | Activity | 675864565 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/29/2020 06:41:45 | 09/29/2020 13:19:45
3550595 | 675860888 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864948 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:00:17 | 12/27/2021 14:00:15
3550595 | 675860888 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864086 |  |  |  |  | 06/08/2020 15:30:00 | 06/07/2020 15:30:00 |  | 06/05/2020 12:30:00
3550595 | 675860888 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864006 |  |  |  |  | 06/03/2020 06:30:00 | 06/04/2020 06:30:00 |  | 06/05/2020 06:30:00
3550595 | 675860888 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863796 |  |  |  |  | 06/05/2020 14:30:00 | 06/05/2020 15:00:00 |  | 06/05/2020 16:00:00
3550595 | 675860888 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863896 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/11/2020 16:57:00
3550595 | 675860888 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066860 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550595 | 675860888 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067056 |  |  |  |  | 10/12/2020 06:30:00 | 12/27/2021 14:00:15
3550596 | 675860890 | act--02 Integration | 02 Integration | Completed | Activity | 675864764 | 11/30/2019 15:00:00 | 11/30/2019 15:00:00 | 11/30/2019 13:40:01 | 11/30/2019 15:00:00
3550596 | 675860890 | act--04 SSV | 04 SSV | Completed | Activity | 675865074 | 01/17/2021 15:30:00 | 01/16/2021 15:30:00 | 01/15/2021 08:28:24 | 01/15/2021 13:30:28
3550596 | 675860890 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865486 | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 | 12/27/2021 14:26:08 | 12/27/2021 14:26:08
3550596 | 675860890 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864538 |  |  |  |  | 12/03/2019 15:30:00 | 12/02/2019 15:30:00 |  | 11/30/2019 12:30:00
3550596 | 675860890 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864376 |  |  |  |  | 11/28/2019 06:30:00 | 11/29/2019 06:30:00 |  | 11/30/2019 06:30:00
3550596 | 675860890 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864059 |  |  |  |  | 11/30/2019 14:30:00 | 11/30/2019 15:00:00 |  | 11/30/2019 16:00:00
3550596 | 675860890 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864207 |  |  |  |  | 01/16/2021 06:30:00 | 01/16/2021 06:30:00 |  | 01/16/2021 08:44:41
3550596 | 675860890 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067030 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550596 | 675860890 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067178 |  |  |  |  | 01/16/2021 06:30:00 | 07/30/2021 05:30:00
3550599 | 675860887 | act--02 Integration | 02 Integration | Completed | Activity | 675864352 | 11/04/2019 15:30:00 | 11/01/2019 14:00:00 | 11/01/2019 12:30:01 | 11/01/2019 14:00:00
3550599 | 675860887 | act--04 SSV | 04 SSV | Completed | Activity | 675864671 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/28/2020 08:11:43 | 09/28/2020 14:07:50
3550599 | 675860887 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864980 | 09/29/2020 09:00:00 | 09/29/2020 10:00:00 | 12/27/2021 14:00:15 | 12/27/2021 14:00:13
3550599 | 675860887 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864160 |  |  |  |  | 11/04/2019 15:30:00 | 11/03/2019 15:30:00 |  | 11/01/2019 12:30:00
3550599 | 675860887 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864064 |  |  |  |  | 10/30/2019 06:30:00 | 10/31/2019 06:30:00 |  | 11/01/2019 06:30:00
3550599 | 675860887 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863827 |  |  |  |  | 11/01/2019 14:30:00 | 11/01/2019 15:00:00 |  | 11/01/2019 16:00:00
3550599 | 675860887 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863938 |  |  |  |  | 09/29/2020 09:00:00 | 09/29/2020 10:00:00 |  | 09/29/2020 10:30:00
3550599 | 675860887 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066801 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550599 | 675860887 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066917 |  |  |  |  | 09/29/2020 09:00:00 | 12/27/2021 14:00:13
3550600 | 675860894 | act--02 Integration | 02 Integration | Completed | Activity | 675865047 | 12/31/2019 15:00:00 | 12/31/2019 15:00:00 | 12/31/2019 13:40:01 | 12/31/2019 15:00:00
3550600 | 675860894 | act--04 SSV | 04 SSV | Completed | Activity | 675865418 | 09/27/2020 15:30:00 | 09/25/2020 15:30:00 | 09/25/2020 08:36:27 | 09/25/2020 14:16:03
3550600 | 675860894 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865756 | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 | 12/27/2021 14:12:59 | 12/27/2021 14:12:58
3550600 | 675860894 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864791 |  |  |  |  | 01/03/2020 15:30:00 | 01/02/2020 15:30:00 |  | 12/31/2019 12:30:00
3550600 | 675860894 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864635 |  |  |  |  | 12/29/2019 06:30:00 | 12/30/2019 06:30:00 |  | 12/31/2019 06:30:00
3550600 | 675860894 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864170 |  |  |  |  | 12/31/2019 14:30:00 | 12/31/2019 15:00:00 |  | 12/31/2019 16:00:00
3550600 | 675860894 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864348 |  |  |  |  | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 |  | 09/28/2020 16:35:13
3550600 | 675860894 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067861 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550600 | 675860894 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067950 |  |  |  |  | 09/29/2020 06:30:00 | 07/30/2021 05:30:00
3550601 | 675860895 | act--02 Integration | 02 Integration | Completed | Activity | 675862903 | 11/10/2019 15:00:00 | 11/10/2019 15:00:00 | 11/10/2019 13:40:01 | 11/10/2019 15:00:00
3550601 | 675860895 | act--04 SSV | 04 SSV | Completed | Activity | 675863043 | 09/27/2020 15:30:00 | 09/27/2020 15:30:00 | 09/27/2020 07:46:28 | 09/27/2020 13:49:59
3550601 | 675860895 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863276 | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 | 12/27/2021 14:00:15 | 12/27/2021 14:00:14
3550601 | 675860895 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862789 |  |  |  |  | 11/13/2019 15:30:00 | 11/12/2019 15:30:00 |  | 11/10/2019 12:30:00
3550601 | 675860895 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862686 |  |  |  |  | 11/08/2019 06:30:00 | 11/09/2019 06:30:00 |  | 11/10/2019 06:30:00
3550601 | 675860895 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862400 |  |  |  |  | 11/10/2019 14:30:00 | 11/10/2019 15:00:00 |  | 11/10/2019 16:00:00
3550601 | 675860895 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862529 |  |  |  |  | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 |  | 09/28/2020 07:24:33
3550601 | 675860895 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067408 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550601 | 675860895 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067536 |  |  |  |  | 09/28/2020 06:30:00 | 12/27/2021 14:00:14
3550603 | 675860926 | act--02 Integration | 02 Integration | Completed | Activity | 675863694 | 11/20/2019 15:00:00 | 11/20/2019 15:00:00 | 11/20/2019 13:40:01 | 11/20/2019 15:00:00
3550603 | 675860926 | act--04 SSV | 04 SSV | Completed | Activity | 675863789 | 03/19/2021 05:30:00 | 03/19/2021 05:30:00 | 03/19/2021 02:25:00 | 03/21/2021 07:05:00
3550603 | 675860926 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863920 | 03/21/2021 09:05:00 | 03/21/2021 09:05:00 | 12/27/2021 14:12:45 | 12/27/2021 14:12:44
3550603 | 675860926 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863587 |  |  |  |  | 11/23/2019 15:30:00 | 11/22/2019 15:30:00 |  | 11/20/2019 12:30:00
3550603 | 675860926 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863500 |  |  |  |  | 11/18/2019 06:30:00 | 11/19/2019 06:30:00 |  | 11/20/2019 06:30:00
3550603 | 675860926 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863202 |  |  |  |  | 11/20/2019 14:30:00 | 11/20/2019 15:00:00 |  | 11/20/2019 16:00:00
3550603 | 675860926 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863374 |  |  |  |  | 03/21/2021 09:05:00 | 03/21/2021 09:05:00 |  | 03/22/2021 05:00:00
3550603 | 675860926 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071411 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550603 | 675860926 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071841 |  |  |  |  | 03/21/2021 09:05:00 | 07/30/2021 05:30:00
3550604 | 675861107 | act--02 Integration | 02 Integration | Completed | Activity | 675864337 | 11/18/2019 15:00:00 | 11/18/2019 15:00:00 | 11/18/2019 13:40:01 | 11/18/2019 15:00:00
3550604 | 675861107 | act--04 SSV | 04 SSV | Completed | Activity | 675864668 | 11/12/2020 15:30:00 | 11/12/2020 15:30:00 | 11/11/2020 07:11:19 | 11/11/2020 13:16:40
3550604 | 675861107 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865035 | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 | 12/27/2021 14:19:47 | 12/27/2021 14:19:44
3550604 | 675861107 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864141 |  |  |  |  | 11/21/2019 15:30:00 | 11/20/2019 15:30:00 |  | 11/18/2019 12:30:00
3550604 | 675861107 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864066 |  |  |  |  | 11/16/2019 06:30:00 | 11/17/2019 06:30:00 |  | 11/18/2019 06:30:00
3550604 | 675861107 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863828 |  |  |  |  | 11/18/2019 14:30:00 | 11/18/2019 15:00:00 |  | 11/18/2019 16:00:00
3550604 | 675861107 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863930 |  |  |  |  | 11/12/2020 06:30:00 | 11/12/2020 06:30:00 |  | 11/12/2020 08:06:31
3550604 | 675861107 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067025 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550604 | 675861107 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067167 |  |  |  |  | 11/12/2020 06:30:00 | 07/30/2021 05:30:00
3550605 | 675861109 | act--02 Integration | 02 Integration | Completed | Activity | 675862259 | 05/08/2020 15:00:00 | 05/08/2020 15:00:00 | 05/08/2020 14:00:00 | 05/08/2020 15:00:00
3550605 | 675861109 | act--04 SSV | 04 SSV | Completed | Activity | 675862381 | 03/30/2021 05:30:00 | 03/30/2021 05:30:00 | 03/30/2021 08:40:00 | 04/01/2021 07:25:00
3550605 | 675861109 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862513 | 04/01/2021 09:25:00 | 04/01/2021 09:25:00 | 12/27/2021 13:59:54 | 12/27/2021 13:59:53
3550605 | 675861109 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862178 |  |  |  |  | 05/11/2020 15:30:00 | 05/10/2020 15:30:00 |  | 05/08/2020 12:30:00
3550605 | 675861109 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862139 |  |  |  |  | 05/06/2020 06:30:00 | 05/07/2020 06:30:00 |  | 05/08/2020 06:30:00
3550605 | 675861109 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675861959 |  |  |  |  | 05/08/2020 14:30:00 | 05/08/2020 15:00:00 |  | 05/08/2020 16:00:00
3550605 | 675861109 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862050 |  |  |  |  | 04/01/2021 09:25:00 | 04/01/2021 09:25:00 |  | 04/02/2021 05:00:00
3550605 | 675861109 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066616 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550605 | 675861109 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066686 |  |  |  |  | 04/01/2021 09:25:00 | 12/27/2021 13:59:53
3550607 | 675861246 | act--02 Integration | 02 Integration | Completed | Activity | 675865135 | 01/03/2020 15:00:00 | 01/03/2020 15:00:00 | 01/03/2020 13:40:01 | 01/03/2020 15:00:00
3550607 | 675861246 | act--04 SSV | 04 SSV | Completed | Activity | 675865480 | 01/06/2021 15:30:00 | 01/05/2021 15:30:00 | 01/04/2021 06:44:05 | 01/04/2021 13:06:54
3550607 | 675861246 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865765 | 01/05/2021 06:30:00 | 01/05/2021 06:30:00 | 12/27/2021 14:20:44 | 12/27/2021 14:20:41
3550607 | 675861246 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864856 |  |  |  |  | 01/06/2020 15:30:00 | 01/05/2020 15:30:00 |  | 01/03/2020 12:30:00
3550607 | 675861246 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864675 |  |  |  |  | 01/01/2020 06:30:00 | 01/02/2020 06:30:00 |  | 01/03/2020 06:30:00
3550607 | 675861246 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864241 |  |  |  |  | 01/03/2020 14:30:00 | 01/03/2020 15:00:00 |  | 01/03/2020 16:00:00
3550607 | 675861246 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864469 |  |  |  |  | 01/05/2021 06:30:00 | 01/05/2021 06:30:00 |  | 01/05/2021 07:57:02
3550607 | 675861246 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066781 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550607 | 675861246 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066888 |  |  |  |  | 01/05/2021 06:30:00 | 07/30/2021 05:30:00
3550608 | 675861264 | act--02 Integration | 02 Integration | Completed | Activity | 675865341 | 10/20/2019 15:00:00 | 10/20/2019 15:00:00 | 10/20/2019 13:40:01 | 10/20/2019 15:00:00
3550608 | 675861264 | act--04 SSV | 04 SSV | Completed | Activity | 675865680 | 04/10/2021 05:30:00 | 04/10/2021 05:30:00 | 04/10/2021 03:25:00 | 04/13/2021 07:40:00
3550608 | 675861264 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865982 | 04/13/2021 09:40:00 | 04/13/2021 09:40:00 | 12/27/2021 13:59:57 | 12/27/2021 13:59:56
3550608 | 675861264 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865044 |  |  |  |  | 10/23/2019 15:30:00 | 10/22/2019 15:30:00 |  | 10/20/2019 12:30:00
3550608 | 675861264 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864835 |  |  |  |  | 10/18/2019 06:30:00 | 10/19/2019 06:30:00 |  | 10/20/2019 06:30:00
3550608 | 675861264 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864265 |  |  |  |  | 10/20/2019 14:30:00 | 10/20/2019 15:00:00 |  | 10/20/2019 16:00:00
3550608 | 675861264 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864523 |  |  |  |  | 04/13/2021 09:40:00 | 04/13/2021 09:40:00 |  | 04/14/2021 05:00:00
3550608 | 675861264 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066807 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550608 | 675861264 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066913 |  |  |  |  | 04/13/2021 09:40:00 | 12/27/2021 13:59:56
3550609 | 675861269 | act--02 Integration | 02 Integration | Completed | Activity | 675864402 | 04/22/2020 15:00:00 | 04/22/2020 15:00:00 | 04/22/2020 14:00:00 | 04/22/2020 15:00:00
3550609 | 675861269 | act--04 SSV | 04 SSV | Completed | Activity | 675864690 | 03/29/2021 05:30:00 | 03/29/2021 05:30:00 | 03/29/2021 09:45:00 | 03/30/2021 01:05:00
3550609 | 675861269 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864987 | 03/30/2021 09:00:00 | 03/30/2021 09:00:00 | 12/27/2021 14:12:51 | 12/27/2021 14:12:50
3550609 | 675861269 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864222 |  |  |  |  | 04/25/2020 15:30:00 | 04/24/2020 15:30:00 |  | 04/22/2020 12:30:00
3550609 | 675861269 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864129 |  |  |  |  | 04/20/2020 06:30:00 | 04/21/2020 06:30:00 |  | 04/22/2020 06:30:00
3550609 | 675861269 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863885 |  |  |  |  | 04/22/2020 14:30:00 | 04/22/2020 15:00:00 |  | 04/22/2020 16:00:00
3550609 | 675861269 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863991 |  |  |  |  | 03/30/2021 09:00:00 | 03/30/2021 09:00:00 |  | 03/30/2021 17:00:00
3550609 | 675861269 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067919 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550609 | 675861269 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718068020 |  |  |  |  | 03/30/2021 09:00:00 | 07/30/2021 05:30:00
3550610 | 675861273 | act--02 Integration | 02 Integration | Completed | Activity | 675862328 | 12/03/2019 15:00:00 | 12/03/2019 15:00:00 | 12/03/2019 13:40:01 | 12/03/2019 15:00:00
3550610 | 675861273 | act--04 SSV | 04 SSV | Completed | Activity | 675862401 | 03/27/2021 05:30:00 | 03/27/2021 05:30:00 | 03/27/2021 10:50:00 | 03/28/2021 07:25:00
3550610 | 675861273 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862558 | 03/28/2021 09:00:00 | 03/28/2021 09:00:00 | 12/27/2021 14:06:32 | 12/27/2021 14:06:31
3550610 | 675861273 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862246 |  |  |  |  | 12/06/2019 15:30:00 | 12/05/2019 15:30:00 |  | 12/03/2019 12:30:00
3550610 | 675861273 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862190 |  |  |  |  | 12/01/2019 06:30:00 | 12/02/2019 06:30:00 |  | 12/03/2019 06:30:00
3550610 | 675861273 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862038 |  |  |  |  | 12/03/2019 14:30:00 | 12/03/2019 15:00:00 |  | 12/03/2019 16:00:00
3550610 | 675861273 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862124 |  |  |  |  | 03/28/2021 09:00:00 | 03/28/2021 09:00:00 |  | 03/28/2021 17:00:00
3550610 | 675861273 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066617 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550610 | 675861273 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066679 |  |  |  |  | 03/28/2021 09:00:00 | 07/30/2021 05:30:00
3550611 | 675861295 | act--02 Integration | 02 Integration | Completed | Activity | 675864076 | 05/16/2020 15:00:00 | 05/16/2020 15:00:00 | 05/16/2020 14:00:00 | 05/16/2020 15:00:00
3550611 | 675861295 | act--04 SSV | 04 SSV | Completed | Activity | 675864305 | 10/12/2020 15:30:00 | 10/13/2020 15:30:00 | 10/11/2020 07:07:15 | 10/11/2020 14:56:31
3550611 | 675861295 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864657 | 01/05/2021 06:30:00 | 01/05/2021 06:30:00 | 12/27/2021 14:12:29 | 12/27/2021 14:12:28
3550611 | 675861295 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863950 |  |  |  |  | 05/19/2020 15:30:00 | 05/18/2020 15:30:00 |  | 05/16/2020 12:30:00
3550611 | 675861295 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863908 |  |  |  |  | 05/14/2020 06:30:00 | 05/15/2020 06:30:00 |  | 05/16/2020 06:30:00
3550611 | 675861295 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863678 |  |  |  |  | 05/16/2020 14:30:00 | 05/16/2020 15:00:00 |  | 05/16/2020 16:00:00
3550611 | 675861295 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863809 |  |  |  |  | 01/05/2021 06:30:00 | 01/05/2021 06:30:00 |  | 01/04/2021 15:51:51
3550611 | 675861295 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067396 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550611 | 675861295 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067532 |  |  |  |  | 01/05/2021 06:30:00 | 07/30/2021 05:30:00
3550612 | 675861296 | act--02 Integration | 02 Integration | Completed | Activity | 675862913 | 05/18/2020 15:00:00 | 05/18/2020 15:00:00 | 05/18/2020 14:00:00 | 05/18/2020 15:00:00
3550612 | 675861296 | act--04 SSV | 04 SSV | Completed | Activity | 675863055 | 10/01/2020 15:30:00 | 09/30/2020 15:30:00 | 09/29/2020 08:51:28 | 09/29/2020 13:31:58
3550612 | 675861296 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863267 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:20:15 | 12/27/2021 14:20:13
3550612 | 675861296 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862805 |  |  |  |  | 05/21/2020 15:30:00 | 05/20/2020 15:30:00 |  | 05/18/2020 12:30:00
3550612 | 675861296 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862691 |  |  |  |  | 05/16/2020 06:30:00 | 05/17/2020 06:30:00 |  | 05/18/2020 06:30:00
3550612 | 675861296 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862403 |  |  |  |  | 05/18/2020 14:30:00 | 05/18/2020 15:00:00 |  | 05/18/2020 16:00:00
3550612 | 675861296 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862533 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/11/2020 16:41:05
3550612 | 675861296 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067406 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550612 | 675861296 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067548 |  |  |  |  | 10/12/2020 06:30:00 | 07/30/2021 05:30:00
3550613 | 675861292 | act--02 Integration | 02 Integration | Completed | Activity | 675864611 | 04/21/2020 15:00:00 | 04/21/2020 15:00:00 | 04/21/2020 14:00:00 | 04/21/2020 15:00:00
3550613 | 675861292 | act--04 SSV | 04 SSV | Completed | Activity | 675864929 | 10/19/2020 15:30:00 | 10/20/2020 15:30:00 | 10/18/2020 08:41:01 | 10/18/2020 14:46:00
3550613 | 675861292 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865312 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:12:45 | 12/27/2021 14:12:42
3550613 | 675861292 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864320 |  |  |  |  | 04/24/2020 15:30:00 | 04/23/2020 15:30:00 |  | 04/21/2020 12:30:00
3550613 | 675861292 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864200 |  |  |  |  | 04/19/2020 06:30:00 | 04/20/2020 06:30:00 |  | 04/21/2020 06:30:00
3550613 | 675861292 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863927 |  |  |  |  | 04/21/2020 14:30:00 | 04/21/2020 15:00:00 |  | 04/21/2020 16:00:00
3550613 | 675861292 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864049 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/19/2020 07:26:36
3550613 | 675861292 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066756 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550613 | 675861292 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066885 |  |  |  |  | 10/19/2020 06:30:00 | 07/30/2021 05:30:00
3550614 | 675861290 | act--02 Integration | 02 Integration | Completed | Activity | 675865286 | 12/03/2019 15:00:00 | 12/03/2019 15:00:00 | 12/03/2019 13:40:01 | 12/03/2019 15:00:00
3550614 | 675861290 | act--04 SSV | 04 SSV | Completed | Activity | 675865641 | 03/27/2021 05:30:00 | 03/27/2021 05:30:00 | 03/27/2021 03:15:00 | 03/29/2021 01:55:00
3550614 | 675861290 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866155 | 03/29/2021 03:55:00 | 03/29/2021 03:55:00 | 12/27/2021 14:12:25 | 12/27/2021 14:12:23
3550614 | 675861290 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865013 |  |  |  |  | 12/06/2019 15:30:00 | 12/05/2019 15:30:00 |  | 12/03/2019 12:30:00
3550614 | 675861290 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864803 |  |  |  |  | 12/01/2019 06:30:00 | 12/02/2019 06:30:00 |  | 12/03/2019 06:30:00
3550614 | 675861290 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864248 |  |  |  |  | 12/03/2019 14:30:00 | 12/03/2019 15:00:00 |  | 12/03/2019 16:00:00
3550614 | 675861290 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864497 |  |  |  |  | 03/29/2021 03:55:00 | 03/29/2021 03:55:00 |  | 03/30/2021 05:00:00
3550614 | 675861290 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066805 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550614 | 675861290 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718066914 |  |  |  |  | 03/29/2021 03:55:00 | 07/30/2021 05:30:00
3550616 | 675861294 | act--02 Integration | 02 Integration | Completed | Activity | 675865134 | 12/27/2019 15:00:00 | 12/27/2019 15:00:00 | 12/27/2019 13:40:01 | 12/27/2019 15:00:00
3550616 | 675861294 | act--04 SSV | 04 SSV | Completed | Activity | 675865526 | 04/12/2021 05:30:00 | 04/12/2021 05:30:00 | 04/12/2021 11:25:00 | 04/14/2021 07:45:00
3550616 | 675861294 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865847 | 04/14/2021 09:45:00 | 04/14/2021 09:45:00 | 12/27/2021 14:00:17 | 12/27/2021 14:00:14
3550616 | 675861294 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864830 |  |  |  |  | 12/30/2019 15:30:00 | 12/29/2019 15:30:00 |  | 12/27/2019 12:30:00
3550616 | 675861294 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864655 |  |  |  |  | 12/25/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/27/2019 06:30:00
3550616 | 675861294 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864177 |  |  |  |  | 12/27/2019 14:30:00 | 12/27/2019 15:00:00 |  | 12/27/2019 16:00:00
3550616 | 675861294 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864371 |  |  |  |  | 04/14/2021 09:45:00 | 04/14/2021 09:45:00 |  | 04/15/2021 05:00:00
3550616 | 675861294 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067477 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550616 | 675861294 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067604 |  |  |  |  | 04/14/2021 09:45:00 | 12/27/2021 14:00:14
3550617 | 675861331 | act--02 Integration | 02 Integration | Completed | Activity | 675864933 | 07/29/2020 15:00:00 | 07/29/2020 15:00:00 | 07/29/2020 14:00:00 | 07/29/2020 15:00:00
3550617 | 675861331 | act--04 SSV | 04 SSV | Completed | Activity | 675865281 | 10/09/2020 15:30:00 | 10/09/2020 15:30:00 | 10/08/2020 07:50:33 | 10/08/2020 13:48:04
3550617 | 675861331 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865619 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:12:35 | 12/27/2021 14:12:34
3550617 | 675861331 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864656 |  |  |  |  | 08/01/2020 15:30:00 | 07/31/2020 15:30:00 |  | 07/29/2020 12:30:00
3550617 | 675861331 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864468 |  |  |  |  | 07/27/2020 06:30:00 | 07/28/2020 06:30:00 |  | 07/29/2020 06:30:00
3550617 | 675861331 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864083 |  |  |  |  | 07/29/2020 14:30:00 | 07/29/2020 15:00:00 |  | 07/29/2020 16:00:00
3550617 | 675861331 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864234 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/18/2020 17:27:05
3550617 | 675861331 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066857 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550617 | 675861331 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067076 |  |  |  |  | 10/19/2020 06:30:00 | 07/30/2021 05:30:00
3550618 | 675861340 | act--02 Integration | 02 Integration | Completed | Activity | 675865173 | 07/10/2020 15:00:00 | 07/10/2020 15:00:00 | 07/10/2020 14:00:00 | 07/10/2020 15:00:00
3550618 | 675861340 | act--04 SSV | 04 SSV | Completed | Activity | 675865562 | 09/30/2020 15:30:00 | 10/01/2020 15:30:00 | 09/29/2020 08:08:42 | 09/29/2020 13:53:40
3550618 | 675861340 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865925 | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 | 12/27/2021 14:12:32 | 12/27/2021 14:12:30
3550618 | 675861340 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864883 |  |  |  |  | 07/13/2020 15:30:00 | 07/12/2020 15:30:00 |  | 07/10/2020 12:30:00
3550618 | 675861340 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864710 |  |  |  |  | 07/08/2020 06:30:00 | 07/09/2020 06:30:00 |  | 07/10/2020 06:30:00
3550618 | 675861340 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864267 |  |  |  |  | 07/10/2020 14:30:00 | 07/10/2020 15:00:00 |  | 07/10/2020 16:00:00
3550618 | 675861340 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864484 |  |  |  |  | 10/09/2020 06:30:00 | 10/09/2020 06:30:00 |  | 10/08/2020 17:38:31
3550618 | 675861340 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067431 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550618 | 675861340 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067566 |  |  |  |  | 10/09/2020 06:30:00 | 07/30/2021 05:30:00
3550619 | 675861361 | act--02 Integration | 02 Integration | Completed | Activity | 675865119 | 10/27/2019 15:00:00 | 10/27/2019 15:00:00 | 10/27/2019 13:40:01 | 10/27/2019 15:00:00
3550619 | 675861361 | act--04 SSV | 04 SSV | Completed | Activity | 675865487 | 09/26/2020 15:30:00 | 09/28/2020 15:30:00 | 09/26/2020 08:11:13 | 09/26/2020 14:55:50
3550619 | 675861361 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865783 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 14:12:55 | 12/27/2021 14:12:53
3550619 | 675861361 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864818 |  |  |  |  | 10/30/2019 15:30:00 | 10/29/2019 15:30:00 |  | 10/27/2019 12:30:00
3550619 | 675861361 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864631 |  |  |  |  | 10/25/2019 06:30:00 | 10/26/2019 06:30:00 |  | 10/27/2019 06:30:00
3550619 | 675861361 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864162 |  |  |  |  | 10/27/2019 14:30:00 | 10/27/2019 15:00:00 |  | 10/27/2019 16:00:00
3550619 | 675861361 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864361 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/29/2020 15:41:20
3550619 | 675861361 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070929 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550619 | 675861361 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071013 |  |  |  |  | 09/30/2020 06:30:00 | 07/30/2021 05:30:00
3550620 | 675861366 | act--02 Integration | 02 Integration | Completed | Activity | 675865218 | 10/31/2019 15:00:00 | 10/31/2019 15:00:00 | 10/31/2019 13:40:01 | 10/31/2019 15:00:00
3550620 | 675861366 | act--04 SSV | 04 SSV | Completed | Activity | 675865566 | 10/11/2020 15:30:00 | 10/13/2020 15:30:00 | 10/11/2020 08:42:25 | 10/11/2020 14:41:57
3550620 | 675861366 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865867 | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 | 12/27/2021 14:19:55 | 12/27/2021 14:19:54
3550620 | 675861366 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864917 |  |  |  |  | 11/03/2019 15:30:00 | 01/03/1900 05:30:00 |  | 10/31/2019 12:30:00
3550620 | 675861366 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864730 |  |  |  |  | 10/29/2019 06:30:00 | 10/30/2019 06:30:00 |  | 10/31/2019 06:30:00
3550620 | 675861366 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864242 |  |  |  |  | 10/31/2019 14:30:00 | 10/31/2019 15:00:00 |  | 10/31/2019 16:00:00
3550620 | 675861366 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864489 |  |  |  |  | 10/12/2020 06:30:00 | 10/12/2020 06:30:00 |  | 10/12/2020 07:41:48
3550620 | 675861366 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067399 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550620 | 675861366 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067535 |  |  |  |  | 10/12/2020 06:30:00 | 07/30/2021 05:30:00
3550621 | 675861382 | act--02 Integration | 02 Integration | Completed | Activity | 675864996 | 04/15/2020 15:00:00 | 04/15/2020 15:00:00 | 04/15/2020 14:00:00 | 04/15/2020 15:00:00
3550621 | 675861382 | act--04 SSV | 04 SSV | Completed | Activity | 675865330 | 01/14/2021 15:30:00 | 01/14/2021 15:30:00 | 01/13/2021 08:14:58 | 01/13/2021 14:08:52
3550621 | 675861382 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865716 | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 | 12/27/2021 14:06:15 | 12/27/2021 14:06:13
3550621 | 675861382 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864752 |  |  |  |  | 04/18/2020 15:30:00 | 04/17/2020 15:30:00 |  | 04/15/2020 12:30:00
3550621 | 675861382 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864615 |  |  |  |  | 04/13/2020 06:30:00 | 04/14/2020 06:30:00 |  | 04/15/2020 06:30:00
3550621 | 675861382 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864146 |  |  |  |  | 04/15/2020 14:30:00 | 04/15/2020 15:00:00 |  | 04/15/2020 16:00:00
3550621 | 675861382 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864338 |  |  |  |  | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 |  | 01/14/2021 07:25:18
3550621 | 675861382 | ms--07 PAC | 07 PAC | Completed | Milestone | 718066859 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550621 | 675861382 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067077 |  |  |  |  | 01/14/2021 06:30:00 | 07/30/2021 05:30:00
3550622 | 675861414 | act--02 Integration | 02 Integration | Completed | Activity | 675865212 | 12/31/2019 15:00:00 | 12/31/2019 15:00:00 | 12/31/2019 12:30:01 | 12/31/2019 14:00:00
3550622 | 675861414 | act--04 SSV | 04 SSV | Completed | Activity | 675865595 | 09/27/2020 15:30:00 | 09/27/2020 15:30:00 | 09/26/2020 07:42:09 | 09/26/2020 14:06:04
3550622 | 675861414 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865907 | 09/27/2020 09:00:00 | 09/27/2020 10:00:00 | 12/27/2021 13:59:56 | 12/27/2021 13:59:55
3550622 | 675861414 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864960 |  |  |  |  | 01/03/2020 15:30:00 | 01/02/2020 15:30:00 |  | 12/31/2019 12:30:00
3550622 | 675861414 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864769 |  |  |  |  | 12/29/2019 06:30:00 | 12/30/2019 06:30:00 |  | 12/31/2019 06:30:00
3550622 | 675861414 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864247 |  |  |  |  | 12/31/2019 14:30:00 | 12/31/2019 15:00:00 |  | 12/31/2019 16:00:00
3550622 | 675861414 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864493 |  |  |  |  | 09/27/2020 09:00:00 | 09/27/2020 10:00:00 |  | 09/27/2020 10:30:00
3550622 | 675861414 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070550 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550622 | 675861414 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070649 |  |  |  |  | 09/27/2020 09:00:00 | 12/27/2021 13:59:55
3550623 | 675861423 | act--02 Integration | 02 Integration | Completed | Activity | 675863030 | 07/30/2020 15:00:00 | 07/30/2020 15:00:00 | 07/30/2020 14:00:00 | 07/30/2020 15:00:00
3550623 | 675861423 | act--04 SSV | 04 SSV | Completed | Activity | 675863228 | 03/28/2021 05:30:00 | 03/28/2021 05:30:00 | 03/28/2021 06:15:00 | 03/30/2021 06:45:00
3550623 | 675861423 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863453 | 03/30/2021 08:45:00 | 03/30/2021 08:45:00 | 12/27/2021 14:12:21 | 12/27/2021 14:12:21
3550623 | 675861423 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862930 |  |  |  |  | 08/02/2020 15:30:00 | 08/01/2020 15:30:00 |  | 07/30/2020 12:30:00
3550623 | 675861423 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862867 |  |  |  |  | 07/28/2020 06:30:00 | 07/29/2020 06:30:00 |  | 07/30/2020 06:30:00
3550623 | 675861423 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862517 |  |  |  |  | 07/30/2020 14:30:00 | 07/30/2020 15:00:00 |  | 07/30/2020 16:00:00
3550623 | 675861423 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862655 |  |  |  |  | 03/30/2021 08:45:00 | 03/30/2021 08:45:00 |  | 03/31/2021 05:00:00
3550623 | 675861423 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070157 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550623 | 675861423 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070398 |  |  |  |  | 03/30/2021 08:45:00 | 07/30/2021 05:30:00
3550625 | 675861439 | act--02 Integration | 02 Integration | Completed | Activity | 675864254 | 11/25/2019 15:00:00 | 11/25/2019 15:00:00 | 11/25/2019 13:40:01 | 11/25/2019 15:00:00
3550625 | 675861439 | act--04 SSV | 04 SSV | Completed | Activity | 675864617 | 03/27/2021 05:30:00 | 03/27/2021 05:30:00 | 03/27/2021 12:25:00 | 03/28/2021 22:45:00
3550625 | 675861439 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864953 | 03/29/2021 12:45:00 | 03/29/2021 12:45:00 | 12/27/2021 14:20:00 | 12/27/2021 14:19:57
3550625 | 675861439 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864088 |  |  |  |  | 11/28/2019 15:30:00 | 11/27/2019 15:30:00 |  | 11/25/2019 12:30:00
3550625 | 675861439 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864000 |  |  |  |  | 11/23/2019 06:30:00 | 11/24/2019 06:30:00 |  | 11/25/2019 06:30:00
3550625 | 675861439 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863792 |  |  |  |  | 11/25/2019 14:30:00 | 11/25/2019 15:00:00 |  | 11/25/2019 16:00:00
3550625 | 675861439 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863889 |  |  |  |  | 03/29/2021 12:45:00 | 03/29/2021 12:45:00 |  | 03/30/2021 05:00:00
3550625 | 675861439 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071150 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550625 | 675861439 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071259 |  |  |  |  | 03/29/2021 12:45:00 | 07/30/2021 05:30:00
3550626 | 675861451 | act--02 Integration | 02 Integration | Completed | Activity | 675865304 | 12/20/2019 15:00:00 | 12/20/2019 15:00:00 | 12/20/2019 13:40:01 | 12/20/2019 15:00:00
3550626 | 675861451 | act--04 SSV | 04 SSV | Completed | Activity | 675865645 | 09/30/2020 15:30:00 | 09/29/2020 15:30:00 | 09/29/2020 08:51:02 | 09/29/2020 15:16:43
3550626 | 675861451 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865950 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 13:59:53 | 12/27/2021 13:59:51
3550626 | 675861451 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865014 |  |  |  |  | 12/23/2019 15:30:00 | 12/22/2019 15:30:00 |  | 12/20/2019 12:30:00
3550626 | 675861451 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864875 |  |  |  |  | 12/18/2019 06:30:00 | 12/19/2019 06:30:00 |  | 12/20/2019 06:30:00
3550626 | 675861451 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864240 |  |  |  |  | 12/20/2019 14:30:00 | 12/20/2019 15:00:00 |  | 12/20/2019 16:00:00
3550626 | 675861451 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864536 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/30/2020 07:47:56
3550626 | 675861451 | ms--07 PAC | 07 PAC | Completed | Milestone | 718069092 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550626 | 675861451 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070119 |  |  |  |  | 09/30/2020 06:30:00 | 12/27/2021 13:59:51
3550627 | 675861456 | act--02 Integration | 02 Integration | Completed | Activity | 675865011 | 04/02/2020 15:00:00 | 04/02/2020 15:00:00 | 04/02/2020 14:00:00 | 04/02/2020 15:00:00
3550627 | 675861456 | act--04 SSV | 04 SSV | Completed | Activity | 675865364 | 09/28/2020 15:30:00 | 09/29/2020 15:30:00 | 09/28/2020 07:42:24 | 09/28/2020 13:09:19
3550627 | 675861456 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865722 | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 | 12/27/2021 14:12:45 | 12/27/2021 14:12:44
3550627 | 675861456 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864761 |  |  |  |  | 04/05/2020 15:30:00 | 04/04/2020 15:30:00 |  | 04/02/2020 12:30:00
3550627 | 675861456 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864634 |  |  |  |  | 03/31/2020 06:30:00 | 04/01/2020 06:30:00 |  | 04/02/2020 06:30:00
3550627 | 675861456 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864176 |  |  |  |  | 04/02/2020 14:30:00 | 04/02/2020 15:00:00 |  | 04/02/2020 16:00:00
3550627 | 675861456 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864355 |  |  |  |  | 09/30/2020 06:30:00 | 09/30/2020 06:30:00 |  | 09/29/2020 17:22:58
3550627 | 675861456 | ms--07 PAC | 07 PAC | Completed | Milestone | 718067909 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550627 | 675861456 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718067989 |  |  |  |  | 09/30/2020 06:30:00 | 07/30/2021 05:30:00
3550628 | 675861457 | act--02 Integration | 02 Integration | Completed | Activity | 675865071 | 11/21/2019 15:00:00 | 11/21/2019 15:00:00 | 11/21/2019 13:40:01 | 11/21/2019 15:00:00
3550628 | 675861457 | act--04 SSV | 04 SSV | Completed | Activity | 675865429 | 03/24/2021 05:30:00 | 03/24/2021 05:30:00 | 03/24/2021 01:10:00 | 03/26/2021 07:15:00
3550628 | 675861457 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865718 | 03/26/2021 09:15:00 | 03/26/2021 09:15:00 | 12/27/2021 14:06:36 | 12/27/2021 14:06:34
3550628 | 675861457 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864811 |  |  |  |  | 11/24/2019 15:30:00 | 11/23/2019 15:30:00 |  | 11/21/2019 12:30:00
3550628 | 675861457 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864629 |  |  |  |  | 11/19/2019 06:30:00 | 11/20/2019 06:30:00 |  | 11/21/2019 06:30:00
3550628 | 675861457 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864168 |  |  |  |  | 11/21/2019 14:30:00 | 11/21/2019 15:00:00 |  | 11/21/2019 16:00:00
3550628 | 675861457 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864349 |  |  |  |  | 03/26/2021 09:15:00 | 03/26/2021 09:15:00 |  | 03/27/2021 05:00:00
3550628 | 675861457 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075176 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550628 | 675861457 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075342 |  |  |  |  | 03/26/2021 09:15:00 | 07/30/2021 05:30:00
3550629 | 675861547 | act--02 Integration | 02 Integration | Completed | Activity | 675865247 | 11/04/2019 15:00:00 | 11/04/2019 15:00:00 | 11/04/2019 13:40:01 | 11/04/2019 15:00:00
3550629 | 675861547 | act--04 SSV | 04 SSV | Completed | Activity | 675865633 | 09/27/2020 15:30:00 | 09/28/2020 15:30:00 | 09/27/2020 08:14:59 | 09/27/2020 14:12:02
3550629 | 675861547 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865991 | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 | 12/27/2021 14:12:50 | 12/27/2021 14:12:49
3550629 | 675861547 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864993 |  |  |  |  | 11/07/2019 15:30:00 | 11/06/2019 15:30:00 |  | 11/04/2019 12:30:00
3550629 | 675861547 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864821 |  |  |  |  | 11/02/2019 06:30:00 | 11/03/2019 06:30:00 |  | 11/04/2019 06:30:00
3550629 | 675861547 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864263 |  |  |  |  | 11/04/2019 14:30:00 | 11/04/2019 15:00:00 |  | 11/04/2019 16:00:00
3550629 | 675861547 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864586 |  |  |  |  | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 |  | 09/28/2020 17:13:11
3550629 | 675861547 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075274 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550629 | 675861547 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075501 |  |  |  |  | 09/29/2020 06:30:00 | 07/30/2021 05:30:00
3550630 | 675861552 | act--02 Integration | 02 Integration | Completed | Activity | 675864653 | 12/31/2019 15:00:00 | 12/31/2019 15:00:00 | 12/31/2019 13:40:01 | 12/31/2019 15:00:00
3550630 | 675861552 | act--04 SSV | 04 SSV | Completed | Activity | 675864979 | 02/02/2021 15:30:00 | 02/01/2021 15:30:00 | 02/01/2021 07:53:24 | 02/01/2021 13:34:09
3550630 | 675861552 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865611 | 02/02/2021 06:30:00 | 02/02/2021 06:30:00 | 12/27/2021 14:20:01 | 12/27/2021 14:19:59
3550630 | 675861552 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864364 |  |  |  |  | 01/03/2020 15:30:00 | 01/02/2020 15:30:00 |  | 12/31/2019 12:30:00
3550630 | 675861552 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864228 |  |  |  |  | 12/29/2019 06:30:00 | 12/30/2019 06:30:00 |  | 12/31/2019 06:30:00
3550630 | 675861552 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863960 |  |  |  |  | 12/31/2019 14:30:00 | 12/31/2019 15:00:00 |  | 12/31/2019 16:00:00
3550630 | 675861552 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864072 |  |  |  |  | 02/02/2021 06:30:00 | 02/02/2021 06:30:00 |  | 02/02/2021 08:24:26
3550630 | 675861552 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071379 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550630 | 675861552 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071937 |  |  |  |  | 02/02/2021 06:30:00 | 07/30/2021 05:30:00
3550634 | 675861571 | act--02 Integration | 02 Integration | Completed | Activity | 675863144 | 05/16/2020 15:00:00 | 05/16/2020 15:00:00 | 05/16/2020 12:30:01 | 05/16/2020 14:00:00
3550634 | 675861571 | act--04 SSV | 04 SSV | Completed | Activity | 675863364 | 09/24/2020 15:30:00 | 09/23/2020 15:30:00 | 09/22/2020 06:42:19 | 09/22/2020 15:20:32
3550634 | 675861571 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863591 | 09/23/2020 12:00:00 | 09/23/2020 13:00:00 | 12/27/2021 13:59:50 | 12/27/2021 13:59:49
3550634 | 675861571 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863004 |  |  |  |  | 05/19/2020 15:30:00 | 05/18/2020 15:30:00 |  | 05/16/2020 12:30:00
3550634 | 675861571 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862942 |  |  |  |  | 05/14/2020 06:30:00 | 05/15/2020 06:30:00 |  | 05/16/2020 06:30:00
3550634 | 675861571 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862607 |  |  |  |  | 05/16/2020 14:30:00 | 05/16/2020 15:00:00 |  | 05/16/2020 16:00:00
3550634 | 675861571 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862856 |  |  |  |  | 09/23/2020 12:00:00 | 09/23/2020 13:00:00 |  | 09/23/2020 13:30:00
3550634 | 675861571 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070673 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550634 | 675861571 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070707 |  |  |  |  | 09/23/2020 12:00:00 | 12/27/2021 13:59:49
3550635 | 675861572 | act--02 Integration | 02 Integration | Completed | Activity | 675862474 | 11/25/2019 15:00:00 | 11/25/2019 15:00:00 | 11/25/2019 13:40:01 | 11/25/2019 15:00:00
3550635 | 675861572 | act--04 SSV | 04 SSV | Completed | Activity | 675862656 | 10/13/2020 15:30:00 | 10/13/2020 15:30:00 | 10/12/2020 08:37:36 | 10/12/2020 13:24:43
3550635 | 675861572 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675862882 | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 | 12/27/2021 14:12:32 | 12/27/2021 14:12:31
3550635 | 675861572 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862385 |  |  |  |  | 11/28/2019 15:30:00 | 11/27/2019 15:30:00 |  | 11/25/2019 12:30:00
3550635 | 675861572 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862343 |  |  |  |  | 11/23/2019 06:30:00 | 11/24/2019 06:30:00 |  | 11/25/2019 06:30:00
3550635 | 675861572 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862191 |  |  |  |  | 11/25/2019 14:30:00 | 11/25/2019 15:00:00 |  | 11/25/2019 16:00:00
3550635 | 675861572 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862265 |  |  |  |  | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 |  | 10/13/2020 06:39:21
3550635 | 675861572 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075278 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550635 | 675861572 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075510 |  |  |  |  | 10/13/2020 06:30:00 | 07/30/2021 05:30:00
3550636 | 675861574 | act--02 Integration | 02 Integration | Completed | Activity | 675864255 | 11/25/2019 15:00:00 | 11/25/2019 15:00:00 | 11/25/2019 13:40:01 | 11/25/2019 15:00:00
3550636 | 675861574 | act--04 SSV | 04 SSV | Completed | Activity | 675864622 | 09/29/2020 15:30:00 | 09/28/2020 15:30:00 | 09/28/2020 07:52:31 | 09/28/2020 14:26:06
3550636 | 675861574 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675864970 | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 | 12/27/2021 14:00:17 | 12/27/2021 14:00:14
3550636 | 675861574 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864106 |  |  |  |  | 11/28/2019 15:30:00 | 11/27/2019 15:30:00 |  | 11/25/2019 12:30:00
3550636 | 675861574 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864017 |  |  |  |  | 11/23/2019 06:30:00 | 11/24/2019 06:30:00 |  | 11/25/2019 06:30:00
3550636 | 675861574 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863790 |  |  |  |  | 11/25/2019 14:30:00 | 11/25/2019 15:00:00 |  | 11/25/2019 16:00:00
3550636 | 675861574 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863902 |  |  |  |  | 10/13/2020 06:30:00 | 10/13/2020 06:30:00 |  | 10/12/2020 17:40:52
3550636 | 675861574 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071223 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550636 | 675861574 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071848 |  |  |  |  | 10/13/2020 06:30:00 | 12/27/2021 14:00:14
3550637 | 675861569 | act--02 Integration | 02 Integration | Completed | Activity | 675865287 | 07/31/2020 15:00:00 | 07/31/2020 15:00:00 | 07/31/2020 14:00:00 | 07/31/2020 15:00:00
3550637 | 675861569 | act--04 SSV | 04 SSV | Completed | Activity | 675865700 | 04/14/2021 05:30:00 | 04/14/2021 05:30:00 | 04/14/2021 09:15:00 | 04/16/2021 07:45:00
3550637 | 675861569 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866062 | 04/16/2021 09:45:00 | 04/16/2021 09:45:00 | 12/27/2021 14:12:33 | 12/27/2021 14:12:31
3550637 | 675861569 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864975 |  |  |  |  | 08/03/2020 15:30:00 | 08/02/2020 15:30:00 |  | 07/31/2020 12:30:00
3550637 | 675861569 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864759 |  |  |  |  | 07/29/2020 06:30:00 | 07/30/2020 06:30:00 |  | 07/31/2020 06:30:00
3550637 | 675861569 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864244 |  |  |  |  | 07/31/2020 14:30:00 | 07/31/2020 15:00:00 |  | 07/31/2020 16:00:00
3550637 | 675861569 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864519 |  |  |  |  | 04/16/2021 09:45:00 | 04/16/2021 09:45:00 |  | 04/17/2021 05:00:00
3550637 | 675861569 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075357 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550637 | 675861569 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075539 |  |  |  |  | 04/16/2021 09:45:00 | 07/30/2021 05:30:00
3550638 | 675861657 | act--02 Integration | 02 Integration | Completed | Activity | 675865157 | 12/27/2019 15:00:00 | 12/27/2019 15:00:00 | 12/27/2019 13:40:01 | 12/27/2019 15:00:00
3550638 | 675861657 | act--04 SSV | 04 SSV | Completed | Activity | 675865537 | 09/24/2020 15:30:00 | 09/24/2020 15:30:00 | 09/23/2020 08:47:48 | 09/23/2020 14:29:20
3550638 | 675861657 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865863 | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 | 12/27/2021 14:00:47 | 12/27/2021 14:00:45
3550638 | 675861657 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864860 |  |  |  |  | 12/30/2019 15:30:00 | 12/29/2019 15:30:00 |  | 12/27/2019 12:30:00
3550638 | 675861657 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864661 |  |  |  |  | 12/25/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/27/2019 06:30:00
3550638 | 675861657 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864172 |  |  |  |  | 12/27/2019 14:30:00 | 12/27/2019 15:00:00 |  | 12/27/2019 16:00:00
3550638 | 675861657 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864356 |  |  |  |  | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 |  | 09/28/2020 17:44:05
3550638 | 675861657 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072150 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550638 | 675861657 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072406 |  |  |  |  | 09/29/2020 06:30:00 | 12/27/2021 14:00:45
3550639 | 675861656 | act--02 Integration | 02 Integration | Completed | Activity | 675864626 | 11/25/2019 15:00:00 | 11/25/2019 15:00:00 | 11/25/2019 13:40:01 | 11/25/2019 15:00:00
3550639 | 675861656 | act--04 SSV | 04 SSV | Completed | Activity | 675864957 | 01/14/2021 15:30:00 | 01/15/2021 15:30:00 | 01/13/2021 07:30:40 | 01/13/2021 14:16:19
3550639 | 675861656 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865273 | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 | 12/27/2021 14:06:14 | 12/27/2021 14:06:13
3550639 | 675861656 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864363 |  |  |  |  | 11/28/2019 15:30:00 | 11/27/2019 15:30:00 |  | 11/25/2019 12:30:00
3550639 | 675861656 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864223 |  |  |  |  | 11/23/2019 06:30:00 | 11/24/2019 06:30:00 |  | 11/25/2019 06:30:00
3550639 | 675861656 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675863958 |  |  |  |  | 11/25/2019 14:30:00 | 11/25/2019 15:00:00 |  | 11/25/2019 16:00:00
3550639 | 675861656 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864073 |  |  |  |  | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 |  | 01/14/2021 08:08:38
3550639 | 675861656 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071378 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550639 | 675861656 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071909 |  |  |  |  | 01/14/2021 06:30:00 | 07/30/2021 05:30:00
3550640 | 675861663 | act--02 Integration | 02 Integration | Completed | Activity | 675863042 | 12/13/2019 15:00:00 | 12/13/2019 15:00:00 | 12/13/2019 13:40:01 | 12/13/2019 15:00:00
3550640 | 675861663 | act--04 SSV | 04 SSV | Completed | Activity | 675863268 | 01/05/2021 15:30:00 | 01/05/2021 15:30:00 | 01/04/2021 07:08:54 | 01/04/2021 13:59:10
3550640 | 675861663 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863476 | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 | 12/27/2021 14:19:49 | 12/27/2021 14:19:47
3550640 | 675861663 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862936 |  |  |  |  | 12/16/2019 15:30:00 | 12/15/2019 15:30:00 |  | 12/13/2019 12:30:00
3550640 | 675861663 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862884 |  |  |  |  | 12/11/2019 06:30:00 | 12/12/2019 06:30:00 |  | 12/13/2019 06:30:00
3550640 | 675861663 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862552 |  |  |  |  | 12/13/2019 14:30:00 | 12/13/2019 15:00:00 |  | 12/13/2019 16:00:00
3550640 | 675861663 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862706 |  |  |  |  | 01/14/2021 06:30:00 | 01/14/2021 06:30:00 |  | 01/13/2021 16:13:16
3550640 | 675861663 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075281 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550640 | 675861663 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075526 |  |  |  |  | 01/14/2021 06:30:00 | 07/30/2021 05:30:00
3550642 | 675861709 | act--02 Integration | 02 Integration | Completed | Activity | 675864672 | 12/22/2019 15:00:00 | 12/22/2019 15:00:00 | 12/22/2019 12:30:01 | 12/22/2019 14:00:00
3550642 | 675861709 | act--04 SSV | 04 SSV | Completed | Activity | 675864972 | 09/24/2020 15:30:00 | 09/25/2020 15:30:00 | 09/24/2020 07:07:12 | 09/24/2020 14:13:15
3550642 | 675861709 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865345 | 09/25/2020 09:30:00 | 09/25/2020 10:30:00 | 12/27/2021 14:00:11 | 12/27/2021 14:00:09
3550642 | 675861709 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864452 |  |  |  |  | 12/25/2019 15:30:00 | 12/24/2019 15:30:00 |  | 12/22/2019 12:30:00
3550642 | 675861709 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864307 |  |  |  |  | 12/20/2019 06:30:00 | 12/21/2019 06:30:00 |  | 12/22/2019 06:30:00
3550642 | 675861709 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864009 |  |  |  |  | 12/22/2019 14:30:00 | 12/22/2019 15:00:00 |  | 12/22/2019 16:00:00
3550642 | 675861709 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864128 |  |  |  |  | 09/25/2020 09:30:00 | 09/25/2020 10:30:00 |  | 09/25/2020 11:00:00
3550642 | 675861709 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075283 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550642 | 675861709 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075503 |  |  |  |  | 09/25/2020 09:30:00 | 12/27/2021 14:00:09
3550643 | 675861708 | act--02 Integration | 02 Integration | Completed | Activity | 675865183 | 01/03/2020 15:00:00 | 01/03/2020 15:00:00 | 01/03/2020 13:40:01 | 01/03/2020 15:00:00
3550643 | 675861708 | act--04 SSV | 04 SSV | Completed | Activity | 675865573 | 09/29/2020 15:30:00 | 09/27/2020 15:30:00 | 09/27/2020 06:44:31 | 09/27/2020 13:06:54
3550643 | 675861708 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865892 | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 | 12/27/2021 14:25:52 | 12/27/2021 14:25:51
3550643 | 675861708 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864940 |  |  |  |  | 01/06/2020 15:30:00 | 01/05/2020 15:30:00 |  | 01/03/2020 12:30:00
3550643 | 675861708 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864748 |  |  |  |  | 01/01/2020 06:30:00 | 01/02/2020 06:30:00 |  | 01/03/2020 06:30:00
3550643 | 675861708 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864271 |  |  |  |  | 01/03/2020 14:30:00 | 01/03/2020 15:00:00 |  | 01/03/2020 16:00:00
3550643 | 675861708 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864513 |  |  |  |  | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 |  | 09/28/2020 08:02:03
3550643 | 675861708 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072160 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550643 | 675861708 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072395 |  |  |  |  | 09/28/2020 06:30:00 | 07/30/2021 05:30:00
3550644 | 675861710 | act--02 Integration | 02 Integration | Completed | Activity | 675865066 | 11/30/2019 15:00:00 | 11/30/2019 15:00:00 | 11/30/2019 13:40:01 | 11/30/2019 15:00:00
3550644 | 675861710 | act--04 SSV | 04 SSV | Completed | Activity | 675865468 | 10/19/2020 15:30:00 | 10/18/2020 15:30:00 | 10/18/2020 06:33:44 | 10/18/2020 13:38:31
3550644 | 675861710 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865828 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:00:00 | 12/27/2021 13:59:59
3550644 | 675861710 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864789 |  |  |  |  | 12/03/2019 15:30:00 | 12/02/2019 15:30:00 |  | 11/30/2019 12:30:00
3550644 | 675861710 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864651 |  |  |  |  | 11/28/2019 06:30:00 | 11/29/2019 06:30:00 |  | 11/30/2019 06:30:00
3550644 | 675861710 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864143 |  |  |  |  | 11/30/2019 14:30:00 | 11/30/2019 15:00:00 |  | 11/30/2019 16:00:00
3550644 | 675861710 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864345 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/19/2020 08:15:29
3550644 | 675861710 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070390 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550644 | 675861710 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718070482 |  |  |  |  | 10/19/2020 06:30:00 | 12/27/2021 13:59:59
3550645 | 675861793 | act--02 Integration | 02 Integration | Completed | Activity | 675863019 | 06/24/2020 15:00:00 | 06/24/2020 15:00:00 | 06/24/2020 14:00:00 | 06/24/2020 15:00:00
3550645 | 675861793 | act--04 SSV | 04 SSV | Completed | Activity | 675863216 | 10/13/2020 15:30:00 | 10/13/2020 15:30:00 | 10/11/2020 08:45:11 | 10/11/2020 15:24:30
3550645 | 675861793 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863441 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:26:08 | 12/27/2021 14:26:06
3550645 | 675861793 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675862919 |  |  |  |  | 06/27/2020 15:30:00 | 06/26/2020 15:30:00 |  | 06/24/2020 12:30:00
3550645 | 675861793 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862874 |  |  |  |  | 06/22/2020 06:30:00 | 06/23/2020 06:30:00 |  | 06/24/2020 06:30:00
3550645 | 675861793 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862544 |  |  |  |  | 06/24/2020 14:30:00 | 06/24/2020 15:00:00 |  | 06/24/2020 16:00:00
3550645 | 675861793 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862698 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/18/2020 15:51:48
3550645 | 675861793 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075149 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550645 | 675861793 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075341 |  |  |  |  | 10/19/2020 06:30:00 | 07/30/2021 05:30:00
3550646 | 675861797 | act--02 Integration | 02 Integration | Completed | Activity | 675865059 | 03/30/2020 15:00:00 | 03/30/2020 15:00:00 | 03/30/2020 13:40:01 | 03/30/2020 15:00:00
3550646 | 675861797 | act--04 SSV | 04 SSV | Completed | Activity | 675865454 | 03/20/2021 05:30:00 | 03/20/2021 05:30:00 | 03/20/2021 10:10:00 | 03/21/2021 23:25:00
3550646 | 675861797 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865763 | 03/22/2021 01:25:00 | 03/22/2021 01:25:00 | 12/29/2021 09:28:35 | 12/29/2021 09:28:33
3550646 | 675861797 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675864778 |  |  |  |  | 04/02/2020 15:30:00 | 04/01/2020 15:30:00 |  | 03/30/2020 12:30:00
3550646 | 675861797 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864564 |  |  |  |  | 03/28/2020 06:30:00 | 03/29/2020 06:30:00 |  | 03/30/2020 06:30:00
3550646 | 675861797 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864116 |  |  |  |  | 03/30/2020 14:30:00 | 03/30/2020 15:00:00 |  | 03/30/2020 16:00:00
3550646 | 675861797 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864287 |  |  |  |  | 03/22/2021 01:25:00 | 03/22/2021 01:25:00 |  | 03/23/2021 05:00:00
3550646 | 675861797 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075361 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550646 | 675861797 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075551 |  |  |  |  | 03/22/2021 01:25:00 | 12/29/2021 09:28:33
3550647 | 675861802 | act--02 Integration | 02 Integration | Completed | Activity | 675863219 | 12/03/2019 15:00:00 | 12/03/2019 15:00:00 | 12/03/2019 13:40:01 | 12/03/2019 15:00:00
3550647 | 675861802 | act--04 SSV | 04 SSV | Completed | Activity | 675863440 | 04/15/2021 05:30:00 | 04/15/2021 05:30:00 | 04/15/2021 09:10:00 | 04/17/2021 07:25:00
3550647 | 675861802 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863613 | 04/17/2021 09:25:00 | 04/17/2021 09:25:00 | 12/27/2021 13:59:51 | 12/27/2021 13:59:49
3550647 | 675861802 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863047 |  |  |  |  | 12/06/2019 15:30:00 | 12/05/2019 15:30:00 |  | 12/03/2019 12:30:00
3550647 | 675861802 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675862970 |  |  |  |  | 12/01/2019 06:30:00 | 12/02/2019 06:30:00 |  | 12/03/2019 06:30:00
3550647 | 675861802 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862666 |  |  |  |  | 12/03/2019 14:30:00 | 12/03/2019 15:00:00 |  | 12/03/2019 16:00:00
3550647 | 675861802 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862861 |  |  |  |  | 04/17/2021 09:25:00 | 04/17/2021 09:25:00 |  | 04/18/2021 05:00:00
3550647 | 675861802 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072513 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550647 | 675861802 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072744 |  |  |  |  | 04/17/2021 09:25:00 | 12/27/2021 13:59:49
3550648 | 675861816 | act--02 Integration | 02 Integration | Completed | Activity | 675863245 | 03/16/2020 15:00:00 | 03/16/2020 15:00:00 | 03/16/2020 13:40:01 | 03/16/2020 15:00:00
3550648 | 675861816 | act--04 SSV | 04 SSV | Completed | Activity | 675863448 | 10/19/2020 15:30:00 | 10/18/2020 15:30:00 | 10/18/2020 08:32:43 | 10/18/2020 15:26:40
3550648 | 675861816 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863601 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:20:41 | 12/27/2021 14:20:39
3550648 | 675861816 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863077 |  |  |  |  | 03/19/2020 15:30:00 | 03/18/2020 15:30:00 |  | 03/16/2020 12:30:00
3550648 | 675861816 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863018 |  |  |  |  | 03/14/2020 06:30:00 | 03/15/2020 06:30:00 |  | 03/16/2020 06:30:00
3550648 | 675861816 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862818 |  |  |  |  | 03/16/2020 14:30:00 | 03/16/2020 15:00:00 |  | 03/16/2020 16:00:00
3550648 | 675861816 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675862912 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/19/2020 08:37:49
3550648 | 675861816 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075284 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550648 | 675861816 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075513 |  |  |  |  | 10/19/2020 06:30:00 | 07/30/2021 05:30:00
3550650 | 675861913 | act--02 Integration | 02 Integration | Completed | Activity | 675863439 | 12/18/2019 15:00:00 | 12/18/2019 15:00:00 | 12/18/2019 13:40:01 | 12/18/2019 15:00:00
3550650 | 675861913 | act--04 SSV | 04 SSV | Completed | Activity | 675863602 | 09/29/2020 15:30:00 | 09/28/2020 15:30:00 | 09/28/2020 06:55:07 | 09/28/2020 14:22:54
3550650 | 675861913 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675863726 | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 | 12/27/2021 14:06:35 | 12/27/2021 14:06:33
3550650 | 675861913 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675863271 |  |  |  |  | 12/21/2019 15:30:00 | 12/20/2019 15:30:00 |  | 12/18/2019 12:30:00
3550650 | 675861913 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675863181 |  |  |  |  | 12/16/2019 06:30:00 | 12/17/2019 06:30:00 |  | 12/18/2019 06:30:00
3550650 | 675861913 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675862927 |  |  |  |  | 12/18/2019 14:30:00 | 12/18/2019 15:00:00 |  | 12/18/2019 16:00:00
3550650 | 675861913 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675863028 |  |  |  |  | 10/19/2020 06:30:00 | 10/19/2020 06:30:00 |  | 10/18/2020 17:49:17
3550650 | 675861913 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072151 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550650 | 675861913 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072390 |  |  |  |  | 10/19/2020 06:30:00 | 07/30/2021 05:30:00
3550651 | 675861925 | act--02 Integration | 02 Integration | Completed | Activity | 675865396 | 12/27/2019 15:00:00 | 12/27/2019 15:00:00 | 12/27/2019 13:40:01 | 12/27/2019 15:00:00
3550651 | 675861925 | act--04 SSV | 04 SSV | Completed | Activity | 675865717 | 09/26/2020 15:30:00 | 09/27/2020 15:30:00 | 09/26/2020 06:53:50 | 09/26/2020 13:36:44
3550651 | 675861925 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866047 | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 | 12/27/2021 14:06:15 | 12/27/2021 14:06:14
3550651 | 675861925 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865107 |  |  |  |  | 12/30/2019 15:30:00 | 12/29/2019 15:30:00 |  | 12/27/2019 12:30:00
3550651 | 675861925 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864934 |  |  |  |  | 12/25/2019 06:30:00 | 12/26/2019 06:30:00 |  | 12/27/2019 06:30:00
3550651 | 675861925 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864362 |  |  |  |  | 12/27/2019 14:30:00 | 12/27/2019 15:00:00 |  | 12/27/2019 16:00:00
3550651 | 675861925 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864639 |  |  |  |  | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 |  | 09/28/2020 15:49:38
3550651 | 675861925 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071222 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550651 | 675861925 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071934 |  |  |  |  | 09/29/2020 06:30:00 | 07/30/2021 05:30:00
3550652 | 675861957 | act--02 Integration | 02 Integration | Completed | Activity | 675865381 | 03/23/2020 15:00:00 | 03/23/2020 15:00:00 | 03/23/2020 13:40:01 | 03/23/2020 15:00:00
3550652 | 675861957 | act--04 SSV | 04 SSV | Completed | Activity | 675865740 | 03/27/2021 05:30:00 | 03/27/2021 05:30:00 | 03/27/2021 03:20:00 | 03/29/2021 02:00:00
3550652 | 675861957 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866035 | 03/29/2021 04:00:00 | 03/29/2021 04:00:00 | 12/27/2021 14:06:15 | 12/27/2021 14:06:14
3550652 | 675861957 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865096 |  |  |  |  | 03/26/2020 15:30:00 | 03/25/2020 15:30:00 |  | 03/23/2020 12:30:00
3550652 | 675861957 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864947 |  |  |  |  | 03/21/2020 06:30:00 | 03/22/2020 06:30:00 |  | 03/23/2020 06:30:00
3550652 | 675861957 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864476 |  |  |  |  | 03/23/2020 14:30:00 | 03/23/2020 15:00:00 |  | 03/23/2020 16:00:00
3550652 | 675861957 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864693 |  |  |  |  | 03/29/2021 04:00:00 | 03/29/2021 04:00:00 |  | 03/30/2021 05:00:00
3550652 | 675861957 | ms--07 PAC | 07 PAC | Completed | Milestone | 718070962 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550652 | 675861957 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071041 |  |  |  |  | 03/29/2021 04:00:00 | 07/30/2021 05:30:00
3550653 | 675861958 | act--02 Integration | 02 Integration | Completed | Activity | 675865377 | 03/18/2020 15:00:00 | 03/18/2020 15:00:00 | 03/18/2020 13:40:01 | 03/18/2020 15:00:00
3550653 | 675861958 | act--04 SSV | 04 SSV | Completed | Activity | 675865670 | 04/12/2021 05:30:00 | 04/12/2021 05:30:00 | 04/12/2021 09:10:00 | 04/14/2021 00:50:00
3550653 | 675861958 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675865996 | 04/14/2021 02:50:00 | 04/14/2021 02:50:00 | 12/27/2021 14:06:50 | 12/27/2021 14:06:49
3550653 | 675861958 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865093 |  |  |  |  | 03/21/2020 15:30:00 | 03/20/2020 15:30:00 |  | 03/18/2020 12:30:00
3550653 | 675861958 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675864909 |  |  |  |  | 03/16/2020 06:30:00 | 03/17/2020 06:30:00 |  | 03/18/2020 06:30:00
3550653 | 675861958 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864319 |  |  |  |  | 03/18/2020 14:30:00 | 03/18/2020 15:00:00 |  | 03/18/2020 16:00:00
3550653 | 675861958 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864572 |  |  |  |  | 04/14/2021 02:50:00 | 04/14/2021 02:50:00 |  | 04/15/2021 05:00:00
3550653 | 675861958 | ms--07 PAC | 07 PAC | Completed | Milestone | 718071412 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550653 | 675861958 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718071843 |  |  |  |  | 04/14/2021 02:50:00 | 12/27/2021 14:06:49
3550654 | 675862917 | act--02 Integration | 02 Integration | Completed | Activity | 675865525 | 11/26/2019 15:00:00 | 11/26/2019 15:00:00 | 11/26/2019 13:40:01 | 11/26/2019 15:00:00
3550654 | 675862917 | act--04 SSV | 04 SSV | Completed | Activity | 675865850 | 04/15/2021 05:30:00 | 04/15/2021 05:30:00 | 04/15/2021 10:20:00 | 04/17/2021 07:00:00
3550654 | 675862917 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866212 | 04/17/2021 09:00:00 | 04/17/2021 09:00:00 | 12/27/2021 14:12:29 | 12/27/2021 14:12:28
3550654 | 675862917 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865226 |  |  |  |  | 11/29/2019 15:30:00 | 11/28/2019 15:30:00 |  | 11/26/2019 12:30:00
3550654 | 675862917 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865039 |  |  |  |  | 11/24/2019 06:30:00 | 11/25/2019 06:30:00 |  | 11/26/2019 06:30:00
3550654 | 675862917 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864552 |  |  |  |  | 11/26/2019 14:30:00 | 11/26/2019 15:00:00 |  | 11/26/2019 16:00:00
3550654 | 675862917 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864767 |  |  |  |  | 04/17/2021 09:00:00 | 04/17/2021 09:00:00 |  | 04/18/2021 05:00:00
3550654 | 675862917 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072255 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550654 | 675862917 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072785 |  |  |  |  | 04/17/2021 09:00:00 | 07/30/2021 05:30:00
3550655 | 675862922 | act--02 Integration | 02 Integration | Completed | Activity | 675865559 | 11/01/2019 15:00:00 | 11/01/2019 15:00:00 | 11/01/2019 13:40:01 | 11/01/2019 15:00:00
3550655 | 675862922 | act--04 SSV | 04 SSV | Completed | Activity | 675865848 | 09/27/2020 15:30:00 | 09/26/2020 15:30:00 | 09/26/2020 06:36:52 | 09/26/2020 15:15:32
3550655 | 675862922 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866080 | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 | 12/27/2021 14:00:35 | 12/27/2021 14:00:32
3550655 | 675862922 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865248 |  |  |  |  | 11/04/2019 15:30:00 | 11/03/2019 15:30:00 |  | 11/01/2019 12:30:00
3550655 | 675862922 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865068 |  |  |  |  | 10/30/2019 06:30:00 | 10/31/2019 06:30:00 |  | 11/01/2019 06:30:00
3550655 | 675862922 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864543 |  |  |  |  | 11/01/2019 14:30:00 | 11/01/2019 15:00:00 |  | 11/01/2019 16:00:00
3550655 | 675862922 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864851 |  |  |  |  | 09/27/2020 06:30:00 | 09/27/2020 06:30:00 |  | 09/26/2020 17:51:53
3550655 | 675862922 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072147 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550655 | 675862922 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072410 |  |  |  |  | 09/27/2020 06:30:00 | 12/27/2021 14:00:32
3550656 | 675863025 | act--02 Integration | 02 Integration | Completed | Activity | 675865550 | 12/29/2019 15:00:00 | 12/29/2019 15:00:00 | 12/29/2019 13:40:01 | 12/29/2019 15:00:00
3550656 | 675863025 | act--04 SSV | 04 SSV | Completed | Activity | 675865834 | 09/28/2020 15:30:00 | 09/29/2020 15:30:00 | 09/27/2020 07:57:15 | 09/27/2020 13:54:48
3550656 | 675863025 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866082 | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 | 12/27/2021 14:20:06 | 12/27/2021 14:20:04
3550656 | 675863025 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865250 |  |  |  |  | 01/01/2020 15:30:00 | 12/31/2019 15:30:00 |  | 12/29/2019 12:30:00
3550656 | 675863025 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865077 |  |  |  |  | 12/27/2019 06:30:00 | 12/28/2019 06:30:00 |  | 12/29/2019 06:30:00
3550656 | 675863025 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864558 |  |  |  |  | 12/29/2019 14:30:00 | 12/29/2019 15:00:00 |  | 12/29/2019 16:00:00
3550656 | 675863025 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864862 |  |  |  |  | 09/28/2020 06:30:00 | 09/28/2020 06:30:00 |  | 09/28/2020 06:42:22
3550656 | 675863025 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072148 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550656 | 675863025 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072398 |  |  |  |  | 09/28/2020 06:30:00 | 07/30/2021 05:30:00
3550657 | 675863031 | act--02 Integration | 02 Integration | Completed | Activity | 675865638 | 04/10/2020 15:00:00 | 04/10/2020 15:00:00 | 04/10/2020 14:00:00 | 04/10/2020 15:00:00
3550657 | 675863031 | act--04 SSV | 04 SSV | Completed | Activity | 675865941 | 03/29/2021 05:30:00 | 03/29/2021 05:30:00 | 03/29/2021 10:55:00 | 03/31/2021 07:55:00
3550657 | 675863031 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866265 | 03/31/2021 09:55:00 | 03/31/2021 09:55:00 | 12/27/2021 14:06:16 | 12/27/2021 14:06:15
3550657 | 675863031 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865388 |  |  |  |  | 04/13/2020 15:30:00 | 04/12/2020 15:30:00 |  | 04/10/2020 12:30:00
3550657 | 675863031 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865211 |  |  |  |  | 04/08/2020 06:30:00 | 04/09/2020 06:30:00 |  | 04/10/2020 06:30:00
3550657 | 675863031 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864567 |  |  |  |  | 04/10/2020 14:30:00 | 04/10/2020 15:00:00 |  | 04/10/2020 16:00:00
3550657 | 675863031 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864886 |  |  |  |  | 03/31/2021 09:55:00 | 03/31/2021 09:55:00 |  | 04/01/2021 05:00:00
3550657 | 675863031 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075358 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550657 | 675863031 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075543 |  |  |  |  | 03/31/2021 09:55:00 | 07/30/2021 05:30:00
3550658 | 675863037 | act--02 Integration | 02 Integration | Completed | Activity | 675865555 | 07/10/2020 15:00:00 | 07/10/2020 15:00:00 | 07/10/2020 14:00:00 | 07/10/2020 15:00:00
3550658 | 675863037 | act--04 SSV | 04 SSV | Completed | Activity | 675865878 | 09/29/2020 15:30:00 | 09/29/2020 15:30:00 | 09/28/2020 08:49:52 | 09/28/2020 13:39:15
3550658 | 675863037 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866136 | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 | 12/27/2021 13:59:52 | 12/27/2021 13:59:50
3550658 | 675863037 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865266 |  |  |  |  | 07/13/2020 15:30:00 | 07/12/2020 15:30:00 |  | 07/10/2020 12:30:00
3550658 | 675863037 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865092 |  |  |  |  | 07/08/2020 06:30:00 | 07/09/2020 06:30:00 |  | 07/10/2020 06:30:00
3550658 | 675863037 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864594 |  |  |  |  | 07/10/2020 14:30:00 | 07/10/2020 15:00:00 |  | 07/10/2020 16:00:00
3550658 | 675863037 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864893 |  |  |  |  | 09/29/2020 06:30:00 | 09/29/2020 06:30:00 |  | 09/29/2020 06:35:57
3550658 | 675863037 | ms--07 PAC | 07 PAC | Completed | Milestone | 718072172 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550658 | 675863037 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718072401 |  |  |  |  | 09/29/2020 06:30:00 | 12/27/2021 13:59:50
3550659 | 675863039 | act--02 Integration | 02 Integration | Completed | Activity | 675865656 | 07/14/2020 15:00:00 | 07/14/2020 15:00:00 | 07/14/2020 14:00:00 | 07/14/2020 15:00:00
3550659 | 675863039 | act--04 SSV | 04 SSV | Completed | Activity | 675865945 | 10/19/2020 15:30:00 | 10/20/2020 15:30:00 | 10/19/2020 07:10:29 | 10/19/2020 13:25:22
3550659 | 675863039 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 675866213 | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 | 12/27/2021 14:25:54 | 12/27/2021 14:25:53
3550659 | 675863039 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 675865376 |  |  |  |  | 07/17/2020 15:30:00 | 07/16/2020 15:30:00 |  | 07/14/2020 12:30:00
3550659 | 675863039 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 675865216 |  |  |  |  | 07/12/2020 06:30:00 | 07/13/2020 06:30:00 |  | 07/14/2020 06:30:00
3550659 | 675863039 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 675864605 |  |  |  |  | 07/14/2020 14:30:00 | 07/14/2020 15:00:00 |  | 07/14/2020 16:00:00
3550659 | 675863039 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 675864930 |  |  |  |  | 10/20/2020 06:30:00 | 10/20/2020 06:30:00 |  | 10/20/2020 08:42:17
3550659 | 675863039 | ms--07 PAC | 07 PAC | Completed | Milestone | 718075287 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3550659 | 675863039 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 718075514 |  |  |  |  | 10/20/2020 06:30:00 | 07/30/2021 05:30:00
3819436 | 745819936 | act--02 Integration | 02 Integration | Completed | Activity | 745821765 | 07/28/2020 15:00:00 | 07/28/2020 15:00:00 | 07/28/2020 14:00:00 | 07/28/2020 15:00:00
3819436 | 745819936 | act--04 SSV | 04 SSV | Completed | Activity | 745822476 | 01/01/2000 13:30:01 | 07/28/2020 17:12:01 | 03/13/2021 10:00:03 | 03/13/2021 16:00:03
3819436 | 745819936 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823055 | 03/15/2021 08:55:03 | 03/15/2021 08:55:03 | 12/27/2021 14:20:15 | 12/27/2021 14:20:14
3819436 | 745819936 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821187 |  |  |  |  | 07/28/2020 18:00:00 | 07/28/2020 18:00:00 |  | 07/28/2020 13:00:00
3819436 | 745819936 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821081 |  |  |  |  | 07/28/2020 08:00:00 | 07/28/2020 08:00:00 |  | 07/28/2020 09:00:00
3819436 | 745819936 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820142 |  |  |  |  | 07/28/2020 15:30:00 | 07/28/2020 16:06:00 |  | 07/28/2020 17:12:00
3819436 | 745819936 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820680 |  |  |  |  | 03/15/2021 08:55:03 | 03/15/2021 08:55:03 |  | 03/16/2021 17:00:03
3819436 | 745819936 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821500 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819436 | 745819936 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821634 |  |  |  |  | 03/15/2021 08:55:03 | 07/30/2021 05:30:00
3819437 | 745819942 | act--02 Integration | 02 Integration | Completed | Activity | 745821813 | 08/17/2020 15:00:00 | 08/17/2020 15:00:00 | 08/17/2020 14:00:00 | 08/17/2020 15:00:00
3819437 | 745819942 | act--04 SSV | 04 SSV | Completed | Activity | 745822430 | 01/01/2000 13:30:01 | 08/17/2020 17:12:01 | 03/30/2021 10:00:03 | 03/30/2021 16:00:03
3819437 | 745819942 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823089 | 04/01/2021 09:55:04 | 04/01/2021 09:55:04 | 12/27/2021 13:59:56 | 12/27/2021 13:59:54
3819437 | 745819942 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821168 |  |  |  |  | 08/17/2020 18:00:00 | 08/17/2020 18:00:00 |  | 08/17/2020 13:00:00
3819437 | 745819942 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821013 |  |  |  |  | 08/17/2020 08:00:00 | 08/17/2020 08:00:00 |  | 08/17/2020 09:00:00
3819437 | 745819942 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820249 |  |  |  |  | 08/17/2020 15:30:00 | 08/17/2020 16:06:00 |  | 08/17/2020 17:12:00
3819437 | 745819942 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820678 |  |  |  |  | 04/01/2021 09:55:04 | 04/01/2021 09:55:04 |  | 04/02/2021 17:00:04
3819437 | 745819942 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821546 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819437 | 745819942 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821671 |  |  |  |  | 04/01/2021 09:55:04 | 12/27/2021 13:59:54
3819438 | 745819966 | act--02 Integration | 02 Integration | Completed | Activity | 745821869 | 05/11/2020 15:00:00 | 05/11/2020 15:00:00 | 05/11/2020 14:00:00 | 05/11/2020 15:00:00
3819438 | 745819966 | act--04 SSV | 04 SSV | Completed | Activity | 745822532 | 01/01/2000 13:30:01 | 05/11/2020 17:12:01 | 03/22/2021 10:00:03 | 03/22/2021 16:00:03
3819438 | 745819966 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823126 | 03/24/2021 09:15:03 | 03/24/2021 09:15:03 | 12/27/2021 14:19:50 | 12/27/2021 14:19:45
3819438 | 745819966 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821218 |  |  |  |  | 05/11/2020 18:00:00 | 05/11/2020 18:00:00 |  | 05/11/2020 13:00:00
3819438 | 745819966 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821126 |  |  |  |  | 05/11/2020 08:00:00 | 05/11/2020 08:00:00 |  | 05/11/2020 09:00:00
3819438 | 745819966 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820150 |  |  |  |  | 05/11/2020 15:30:00 | 05/11/2020 16:06:00 |  | 05/11/2020 17:12:00
3819438 | 745819966 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820722 |  |  |  |  | 03/24/2021 09:15:03 | 03/24/2021 09:15:03 |  | 03/25/2021 17:00:03
3819438 | 745819966 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821548 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819438 | 745819966 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821699 |  |  |  |  | 03/24/2021 09:15:03 | 07/30/2021 05:30:00
3819439 | 745819946 | act--02 Integration | 02 Integration | Completed | Activity | 745821947 | 03/20/2020 14:30:00 | 03/20/2020 14:30:00 | 03/20/2020 13:40:01 | 03/20/2020 14:30:00
3819439 | 745819946 | act--04 SSV | 04 SSV | Completed | Activity | 745822539 | 01/01/2000 13:30:01 | 03/20/2020 17:12:01 | 03/16/2021 10:00:03 | 03/16/2021 16:00:03
3819439 | 745819946 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823295 | 03/18/2021 12:20:03 | 03/18/2021 12:20:03 | 12/27/2021 14:19:54 | 12/27/2021 14:19:52
3819439 | 745819946 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821249 |  |  |  |  | 03/20/2020 18:00:00 | 03/20/2020 18:00:00 |  | 03/20/2020 13:00:00
3819439 | 745819946 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821112 |  |  |  |  | 03/20/2020 08:00:00 | 03/20/2020 08:00:00 |  | 03/20/2020 09:00:00
3819439 | 745819946 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820213 |  |  |  |  | 03/20/2020 15:30:00 | 03/20/2020 16:06:00 |  | 03/20/2020 17:12:00
3819439 | 745819946 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820704 |  |  |  |  | 03/18/2021 12:20:03 | 03/18/2021 12:20:03 |  | 03/19/2021 17:00:03
3819439 | 745819946 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821625 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819439 | 745819946 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821734 |  |  |  |  | 03/18/2021 12:20:03 | 07/30/2021 05:30:00
3819440 | 745819947 | act--02 Integration | 02 Integration | Completed | Activity | 745822035 | 06/06/2020 15:00:00 | 06/06/2020 15:00:00 | 06/06/2020 14:00:00 | 06/06/2020 15:00:00
3819440 | 745819947 | act--04 SSV | 04 SSV | Completed | Activity | 745822541 | 01/01/2000 13:30:01 | 06/06/2020 17:12:01 | 03/16/2021 10:00:03 | 03/16/2021 16:00:03
3819440 | 745819947 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823125 | 03/18/2021 15:00:03 | 03/18/2021 15:00:03 | 12/27/2021 14:06:15 | 12/27/2021 14:06:13
3819440 | 745819947 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821192 |  |  |  |  | 06/06/2020 18:00:00 | 06/06/2020 18:00:00 |  | 06/06/2020 13:00:00
3819440 | 745819947 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821015 |  |  |  |  | 06/06/2020 08:00:00 | 06/06/2020 08:00:00 |  | 06/06/2020 09:00:00
3819440 | 745819947 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820316 |  |  |  |  | 06/06/2020 15:30:00 | 06/06/2020 16:06:00 |  | 06/06/2020 17:12:00
3819440 | 745819947 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820713 |  |  |  |  | 03/18/2021 15:00:03 | 03/18/2021 15:00:03 |  | 03/19/2021 17:00:03
3819440 | 745819947 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821675 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819440 | 745819947 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821785 |  |  |  |  | 03/18/2021 15:00:03 | 07/30/2021 05:30:00
3819442 | 745819938 | act--02 Integration | 02 Integration | Completed | Activity | 745821767 | 04/23/2020 15:00:00 | 04/23/2020 15:00:00 | 04/23/2020 14:00:00 | 04/23/2020 15:00:00
3819442 | 745819938 | act--04 SSV | 04 SSV | Completed | Activity | 745822421 | 01/01/2000 13:30:01 | 04/23/2020 17:12:01 | 03/16/2021 10:00:03 | 03/16/2021 16:00:03
3819442 | 745819938 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823135 | 03/18/2021 09:00:03 | 03/18/2021 09:00:03 | 12/27/2021 14:00:13 | 12/27/2021 14:00:12
3819442 | 745819938 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821215 |  |  |  |  | 04/23/2020 18:00:00 | 04/23/2020 18:00:00 |  | 04/23/2020 13:00:00
3819442 | 745819938 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821083 |  |  |  |  | 04/23/2020 08:00:00 | 04/23/2020 08:00:00 |  | 04/23/2020 09:00:00
3819442 | 745819938 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820293 |  |  |  |  | 04/23/2020 15:30:00 | 04/23/2020 16:06:00 |  | 04/23/2020 17:12:00
3819442 | 745819938 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820753 |  |  |  |  | 03/18/2021 09:00:03 | 03/18/2021 09:00:03 |  | 03/19/2021 17:00:03
3819442 | 745819938 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821491 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819442 | 745819938 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821660 |  |  |  |  | 03/18/2021 09:00:03 | 12/27/2021 14:00:12
3819448 | 745820009 | act--02 Integration | 02 Integration | Completed | Activity | 745821814 | 04/02/2020 15:00:00 | 04/02/2020 15:00:00 | 04/02/2020 14:00:00 | 04/02/2020 15:00:00
3819448 | 745820009 | act--04 SSV | 04 SSV | Completed | Activity | 745822510 | 01/01/2000 13:30:01 | 04/02/2020 17:12:01 | 03/15/2021 10:00:03 | 03/15/2021 16:00:03
3819448 | 745820009 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823094 | 03/17/2021 16:15:03 | 03/17/2021 16:15:03 | 12/27/2021 14:12:31 | 12/27/2021 14:12:31
3819448 | 745820009 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821204 |  |  |  |  | 04/02/2020 18:00:00 | 04/02/2020 18:00:00 |  | 04/02/2020 13:00:00
3819448 | 745820009 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821067 |  |  |  |  | 04/02/2020 08:00:00 | 04/02/2020 08:00:00 |  | 04/02/2020 09:00:00
3819448 | 745820009 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820222 |  |  |  |  | 04/02/2020 15:30:00 | 04/02/2020 16:06:00 |  | 04/02/2020 17:12:00
3819448 | 745820009 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820662 |  |  |  |  | 03/17/2021 16:15:03 | 03/17/2021 16:15:03 |  | 03/18/2021 17:00:03
3819448 | 745820009 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821554 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819448 | 745820009 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821644 |  |  |  |  | 03/17/2021 16:15:03 | 07/30/2021 05:30:00
3819451 | 745819965 | act--02 Integration | 02 Integration | Completed | Activity | 745821761 | 11/13/2020 15:00:00 | 11/13/2020 15:00:00 | 11/13/2020 14:00:00 | 11/13/2020 15:00:00
3819451 | 745819965 | act--04 SSV | 04 SSV | Completed | Activity | 745822426 | 01/01/2000 13:30:01 | 11/13/2020 17:12:01 | 03/31/2021 10:00:03 | 03/31/2021 16:00:03
3819451 | 745819965 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823072 | 04/02/2021 12:55:04 | 04/02/2021 12:55:04 | 12/27/2021 14:25:55 | 12/27/2021 14:25:53
3819451 | 745819965 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821149 |  |  |  |  | 11/13/2020 18:00:00 | 11/13/2020 18:00:00 |  | 11/13/2020 13:00:00
3819451 | 745819965 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821011 |  |  |  |  | 11/13/2020 08:00:00 | 11/13/2020 08:00:00 |  | 11/13/2020 09:00:00
3819451 | 745819965 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820318 |  |  |  |  | 11/13/2020 15:30:00 | 11/13/2020 16:06:00 |  | 11/13/2020 17:12:00
3819451 | 745819965 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820652 |  |  |  |  | 04/02/2021 12:55:04 | 04/02/2021 12:55:04 |  | 04/03/2021 17:00:04
3819451 | 745819965 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821478 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819451 | 745819965 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821636 |  |  |  |  | 04/02/2021 12:55:04 | 07/30/2021 05:30:00
3819456 | 745819987 | act--02 Integration | 02 Integration | Completed | Activity | 745821818 | 04/27/2020 15:00:00 | 04/27/2020 15:00:00 | 04/27/2020 14:00:00 | 04/27/2020 15:00:00
3819456 | 745819987 | act--04 SSV | 04 SSV | Completed | Activity | 745822398 | 01/01/2000 13:30:01 | 04/27/2020 17:12:01 | 04/01/2021 10:00:04 | 04/01/2021 16:00:04
3819456 | 745819987 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823060 | 04/03/2021 11:05:04 | 04/03/2021 11:05:04 | 12/27/2021 14:06:31 | 12/27/2021 14:06:29
3819456 | 745819987 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821197 |  |  |  |  | 04/27/2020 18:00:00 | 04/27/2020 18:00:00 |  | 04/27/2020 13:00:00
3819456 | 745819987 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821038 |  |  |  |  | 04/27/2020 08:00:00 | 04/27/2020 08:00:00 |  | 04/27/2020 09:00:00
3819456 | 745819987 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820238 |  |  |  |  | 04/27/2020 15:30:00 | 04/27/2020 16:06:00 |  | 04/27/2020 17:12:00
3819456 | 745819987 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820661 |  |  |  |  | 04/03/2021 11:05:04 | 04/03/2021 11:05:04 |  | 04/04/2021 17:00:04
3819456 | 745819987 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821494 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819456 | 745819987 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821629 |  |  |  |  | 04/03/2021 11:05:04 | 07/30/2021 05:30:00
3819457 | 745819959 | act--02 Integration | 02 Integration | Completed | Activity | 745821826 | 08/10/2020 15:00:00 | 08/10/2020 15:00:00 | 08/10/2020 14:00:00 | 08/10/2020 15:00:00
3819457 | 745819959 | act--04 SSV | 04 SSV | Completed | Activity | 745822455 | 01/01/2000 13:30:01 | 08/10/2020 17:12:01 | 03/09/2021 10:00:03 | 03/09/2021 16:00:03
3819457 | 745819959 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823120 | 03/11/2021 15:25:03 | 03/11/2021 15:25:03 | 12/27/2021 13:59:59 | 12/27/2021 13:59:57
3819457 | 745819959 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821103 |  |  |  |  | 08/10/2020 18:00:00 | 08/10/2020 18:00:00 |  | 08/10/2020 13:00:00
3819457 | 745819959 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745820968 |  |  |  |  | 08/10/2020 08:00:00 | 08/10/2020 08:00:00 |  | 08/10/2020 09:00:00
3819457 | 745819959 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820232 |  |  |  |  | 08/10/2020 15:30:00 | 08/10/2020 16:06:00 |  | 08/10/2020 17:12:00
3819457 | 745819959 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820657 |  |  |  |  | 03/11/2021 15:25:03 | 03/11/2021 15:25:03 |  | 03/12/2021 17:00:03
3819457 | 745819959 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821523 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819457 | 745819959 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821628 |  |  |  |  | 03/11/2021 15:25:03 | 12/27/2021 13:59:57
3819461 | 745820022 | act--02 Integration | 02 Integration | Completed | Activity | 745821775 | 07/20/2020 15:00:00 | 07/20/2020 15:00:00 | 07/20/2020 14:00:00 | 07/20/2020 15:00:00
3819461 | 745820022 | act--04 SSV | 04 SSV | Completed | Activity | 745822432 | 01/01/2000 13:30:01 | 07/20/2020 17:12:01 | 04/01/2021 10:00:04 | 04/01/2021 16:00:04
3819461 | 745820022 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823173 | 04/03/2021 09:05:04 | 04/03/2021 09:05:04 | 12/27/2021 13:59:53 | 12/27/2021 13:59:50
3819461 | 745820022 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821128 |  |  |  |  | 07/20/2020 18:00:00 | 07/20/2020 18:00:00 |  | 07/20/2020 13:00:00
3819461 | 745820022 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745820941 |  |  |  |  | 07/20/2020 08:00:00 | 07/20/2020 08:00:00 |  | 07/20/2020 09:00:00
3819461 | 745820022 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820233 |  |  |  |  | 07/20/2020 15:30:00 | 07/20/2020 16:06:00 |  | 07/20/2020 17:12:00
3819461 | 745820022 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820653 |  |  |  |  | 04/03/2021 09:05:04 | 04/03/2021 09:05:04 |  | 04/04/2021 17:00:04
3819461 | 745820022 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821471 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819461 | 745820022 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821627 |  |  |  |  | 04/03/2021 09:05:04 | 12/27/2021 13:59:50
3819463 | 745819990 | act--02 Integration | 02 Integration | Completed | Activity | 745822068 | 09/11/2020 15:00:00 | 09/11/2020 15:00:00 | 09/11/2020 14:00:00 | 09/11/2020 15:00:00
3819463 | 745819990 | act--04 SSV | 04 SSV | Completed | Activity | 745822666 | 01/01/2000 13:30:01 | 09/11/2020 17:12:01 | 04/01/2021 10:00:04 | 04/01/2021 16:00:04
3819463 | 745819990 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823269 | 04/03/2021 17:05:04 | 04/03/2021 17:05:04 | 12/27/2021 14:20:12 | 12/27/2021 14:20:10
3819463 | 745819990 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821348 |  |  |  |  | 09/11/2020 18:00:00 | 09/11/2020 18:00:00 |  | 09/11/2020 13:00:00
3819463 | 745819990 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821143 |  |  |  |  | 09/11/2020 08:00:00 | 09/11/2020 08:00:00 |  | 09/11/2020 09:00:00
3819463 | 745819990 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820245 |  |  |  |  | 09/11/2020 15:30:00 | 09/11/2020 16:06:00 |  | 09/11/2020 17:12:00
3819463 | 745819990 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820676 |  |  |  |  | 04/03/2021 17:05:04 | 04/03/2021 17:05:04 |  | 04/04/2021 17:00:04
3819463 | 745819990 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821686 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819463 | 745819990 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821845 |  |  |  |  | 04/03/2021 17:05:04 | 07/30/2021 05:30:00
3819464 | 745820037 | act--02 Integration | 02 Integration | Completed | Activity | 745821776 | 04/03/2020 15:00:00 | 04/03/2020 15:00:00 | 04/03/2020 14:00:00 | 04/03/2020 15:00:00
3819464 | 745820037 | act--04 SSV | 04 SSV | Completed | Activity | 745822449 | 01/01/2000 13:30:01 | 04/03/2020 17:12:01 | 04/01/2021 10:00:04 | 04/01/2021 16:00:04
3819464 | 745820037 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823065 | 04/03/2021 11:05:04 | 04/03/2021 11:05:04 | 12/27/2021 14:20:08 | 12/27/2021 14:20:06
3819464 | 745820037 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821186 |  |  |  |  | 04/03/2020 18:00:00 | 04/03/2020 18:00:00 |  | 04/03/2020 13:00:00
3819464 | 745820037 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821054 |  |  |  |  | 04/03/2020 08:00:00 | 04/03/2020 08:00:00 |  | 04/03/2020 09:00:00
3819464 | 745820037 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820317 |  |  |  |  | 04/03/2020 15:30:00 | 04/03/2020 16:06:00 |  | 04/03/2020 17:12:00
3819464 | 745820037 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820649 |  |  |  |  | 04/03/2021 11:05:04 | 04/03/2021 11:05:04 |  | 04/04/2021 17:00:04
3819464 | 745820037 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821561 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819464 | 745820037 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821683 |  |  |  |  | 04/03/2021 11:05:04 | 07/30/2021 05:30:00
3819468 | 745820027 | act--02 Integration | 02 Integration | Completed | Activity | 745821663 | 05/17/2020 15:00:00 | 05/17/2020 15:00:00 | 05/17/2020 14:00:00 | 05/17/2020 15:00:00
3819468 | 745820027 | act--04 SSV | 04 SSV | Completed | Activity | 745822411 | 01/01/2000 13:30:01 | 05/17/2020 17:12:01 | 03/16/2021 10:00:03 | 03/16/2021 16:00:03
3819468 | 745820027 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823037 | 03/18/2021 09:25:03 | 03/18/2021 09:25:03 | 12/27/2021 14:06:27 | 12/27/2021 14:06:26
3819468 | 745820027 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821098 |  |  |  |  | 05/17/2020 18:00:00 | 05/17/2020 18:00:00 |  | 05/17/2020 13:00:00
3819468 | 745820027 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821002 |  |  |  |  | 05/17/2020 08:00:00 | 05/17/2020 08:00:00 |  | 05/17/2020 09:00:00
3819468 | 745820027 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820337 |  |  |  |  | 05/17/2020 15:30:00 | 05/17/2020 16:06:00 |  | 05/17/2020 17:12:00
3819468 | 745820027 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820663 |  |  |  |  | 03/18/2021 09:25:03 | 03/18/2021 09:25:03 |  | 03/19/2021 17:00:03
3819468 | 745820027 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821397 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819468 | 745820027 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821538 |  |  |  |  | 03/18/2021 09:25:03 | 07/30/2021 05:30:00
3819471 | 745820062 | act--02 Integration | 02 Integration | Completed | Activity | 745821838 | 04/23/2020 15:00:00 | 04/23/2020 15:00:00 | 04/23/2020 14:00:00 | 04/23/2020 15:00:00
3819471 | 745820062 | act--04 SSV | 04 SSV | Completed | Activity | 745822406 | 01/01/2000 13:30:01 | 04/23/2020 17:12:01 | 03/16/2021 10:00:03 | 03/16/2021 16:00:03
3819471 | 745820062 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823033 | 03/18/2021 09:05:03 | 03/18/2021 09:05:03 | 12/27/2021 14:12:47 | 12/27/2021 14:12:45
3819471 | 745820062 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821111 |  |  |  |  | 04/23/2020 18:00:00 | 04/23/2020 18:00:00 |  | 04/23/2020 13:00:00
3819471 | 745820062 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821000 |  |  |  |  | 04/23/2020 08:00:00 | 04/23/2020 08:00:00 |  | 04/23/2020 09:00:00
3819471 | 745820062 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820273 |  |  |  |  | 04/23/2020 15:30:00 | 04/23/2020 16:06:00 |  | 04/23/2020 17:12:00
3819471 | 745820062 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820647 |  |  |  |  | 03/18/2021 09:05:03 | 03/18/2021 09:05:03 |  | 03/19/2021 17:00:03
3819471 | 745820062 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821454 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819471 | 745820062 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821635 |  |  |  |  | 03/18/2021 09:05:03 | 07/30/2021 05:30:00
3819480 | 745820083 | act--02 Integration | 02 Integration | Completed | Activity | 745821903 | 04/24/2020 15:00:00 | 04/24/2020 15:00:00 | 04/24/2020 14:00:00 | 04/24/2020 15:00:00
3819480 | 745820083 | act--04 SSV | 04 SSV | Completed | Activity | 745822518 | 01/01/2000 13:30:01 | 04/24/2020 17:12:01 | 02/27/2021 10:00:02 | 02/27/2021 16:00:02
3819480 | 745820083 | act--06 Tuning | 06 Tuning | Not Applicable | Activity | 745823030 | 03/01/2021 09:05:03 | 03/01/2021 09:05:03 | 12/27/2021 14:06:33 | 12/27/2021 14:06:32
3819480 | 745820083 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 745821203 |  |  |  |  | 04/24/2020 18:00:00 | 04/24/2020 18:00:00 |  | 04/24/2020 13:00:00
3819480 | 745820083 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 745821071 |  |  |  |  | 04/24/2020 08:00:00 | 04/24/2020 08:00:00 |  | 04/24/2020 09:00:00
3819480 | 745820083 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 745820315 |  |  |  |  | 04/24/2020 15:30:00 | 04/24/2020 16:06:00 |  | 04/24/2020 17:12:00
3819480 | 745820083 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 745820658 |  |  |  |  | 03/01/2021 09:05:03 | 03/01/2021 09:05:03 |  | 03/02/2021 17:00:03
3819480 | 745820083 | ms--07 PAC | 07 PAC | Completed | Milestone | 745821640 |  |  |  |  | 07/30/2021 05:30:00 | 07/30/2021 05:30:00 |  | 07/30/2021 05:30:00
3819480 | 745820083 | ms--08 FAC | 08 FAC | Ready to Start | Milestone | 745821773 |  |  |  |  | 03/01/2021 09:05:03 | 07/30/2021 05:30:00
4244886 | 883892937 | act--02 Integration | 02 Integration | Completed | Activity | 883892960 | 07/28/2022 08:30:12 | 07/28/2022 08:30:12 | 07/28/2022 07:33:11 | 07/28/2022 08:45:11
4244886 | 883892937 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883892982 | 07/28/2022 08:30:13 | 07/28/2022 10:01:54
4244886 | 883892937 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893019 | 07/28/2022 08:30:14 | 07/28/2022 10:01:55
4244886 | 883892937 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893235 |  |  |  |  | 07/27/2022 12:03:11 | 07/27/2022 12:03:11 |  | 07/27/2022 12:03:11
4244886 | 883892937 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893169 |  |  |  |  | 07/27/2022 06:30:11 | 07/27/2022 06:30:11 |  | 07/27/2022 06:30:11
4244886 | 883892937 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893070 |  |  |  |  | 07/28/2022 08:30:12 | 07/28/2022 08:45:11 |  | 07/28/2022 09:50:57
4244886 | 883892937 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893112 |  |  |  |  | 07/28/2022 08:30:13 | 07/28/2022 10:01:54
4244886 | 883892937 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893326 |  |  |  |  | 07/28/2022 08:30:14 | 07/28/2022 10:01:55
4244886 | 883892937 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893384 |  |  |  |  | 07/28/2022 08:30:14 | 07/28/2022 10:01:55
4244887 | 883892938 | act--02 Integration | 02 Integration | Completed | Activity | 883892959 | 07/28/2022 08:30:05 | 07/28/2022 08:30:05 | 07/28/2022 07:40:04 | 07/28/2022 08:52:05
4244887 | 883892938 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883892983 | 07/28/2022 08:30:06 | 07/28/2022 09:47:07
4244887 | 883892938 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893024 | 07/28/2022 08:30:07 | 07/28/2022 09:47:08
4244887 | 883892938 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893252 |  |  |  |  | 07/27/2022 12:30:04 | 07/27/2022 12:30:04 |  | 07/27/2022 11:49:04
4244887 | 883892938 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893172 |  |  |  |  | 07/27/2022 06:30:04 | 07/27/2022 06:30:04 |  | 07/27/2022 06:35:04
4244887 | 883892938 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893073 |  |  |  |  | 07/28/2022 08:30:05 | 07/28/2022 08:52:05 |  | 07/28/2022 09:47:06
4244887 | 883892938 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893108 |  |  |  |  | 07/28/2022 08:30:06 | 07/28/2022 09:47:07
4244887 | 883892938 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893323 |  |  |  |  | 07/28/2022 08:30:07 | 07/28/2022 09:47:08
4244887 | 883892938 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893396 |  |  |  |  | 07/28/2022 08:30:07 | 07/28/2022 09:47:08
4244888 | 883892949 | act--02 Integration | 02 Integration | Completed | Activity | 883892988 | 07/29/2022 08:30:30 | 07/29/2022 08:30:30 | 07/29/2022 07:37:29 | 07/29/2022 08:46:30
4244888 | 883892949 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893021 | 07/29/2022 08:30:31 | 07/29/2022 09:54:40
4244888 | 883892949 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893078 | 07/29/2022 08:30:32 | 07/29/2022 09:54:41
4244888 | 883892949 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893338 |  |  |  |  | 07/28/2022 12:30:29 | 07/28/2022 12:30:29 |  | 07/28/2022 11:53:29
4244888 | 883892949 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893270 |  |  |  |  | 07/28/2022 06:30:29 | 07/28/2022 06:30:29 |  | 07/28/2022 06:40:29
4244888 | 883892949 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893144 |  |  |  |  | 07/29/2022 08:30:30 | 07/29/2022 08:46:30 |  | 07/29/2022 09:54:39
4244888 | 883892949 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893224 |  |  |  |  | 07/29/2022 08:30:31 | 07/29/2022 09:54:40
4244888 | 883892949 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893422 |  |  |  |  | 07/29/2022 08:30:32 | 07/29/2022 09:54:41
4244888 | 883892949 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893475 |  |  |  |  | 07/29/2022 08:30:32 | 07/29/2022 09:54:41
4244889 | 883892948 | act--02 Integration | 02 Integration | Completed | Activity | 883892989 | 07/27/2022 08:30:21 | 07/27/2022 08:30:21 | 07/27/2022 07:38:20 | 07/27/2022 08:51:21
4244889 | 883892948 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893025 | 07/27/2022 08:30:22 | 07/27/2022 09:38:42
4244889 | 883892948 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893077 | 07/27/2022 08:30:23 | 07/27/2022 09:38:43
4244889 | 883892948 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893337 |  |  |  |  | 07/26/2022 12:30:20 | 07/26/2022 12:30:20 |  | 07/26/2022 12:00:20
4244889 | 883892948 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893273 |  |  |  |  | 07/26/2022 06:30:20 | 07/26/2022 06:30:20 |  | 07/26/2022 06:40:20
4244889 | 883892948 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893152 |  |  |  |  | 07/27/2022 08:30:21 | 07/27/2022 08:51:21 |  | 07/27/2022 09:38:41
4244889 | 883892948 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893208 |  |  |  |  | 07/27/2022 08:30:22 | 07/27/2022 09:38:42
4244889 | 883892948 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893423 |  |  |  |  | 07/27/2022 08:30:23 | 07/27/2022 09:38:43
4244889 | 883892948 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893470 |  |  |  |  | 07/27/2022 08:30:23 | 07/27/2022 09:38:43
4244890 | 883892950 | act--02 Integration | 02 Integration | Completed | Activity | 883892987 | 07/28/2022 08:30:03 | 07/29/2022 08:30:03 | 07/29/2022 07:42:02 | 07/29/2022 08:54:03
4244890 | 883892950 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893018 | 07/28/2022 08:30:04 | 07/29/2022 10:04:04
4244890 | 883892950 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893066 | 07/28/2022 08:30:05 | 07/29/2022 10:04:05
4244890 | 883892950 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893311 |  |  |  |  | 07/28/2022 12:30:02 | 07/28/2022 12:30:02 |  | 07/28/2022 11:48:02
4244890 | 883892950 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893250 |  |  |  |  | 07/28/2022 06:30:02 | 07/28/2022 06:30:02 |  | 07/28/2022 06:33:02
4244890 | 883892950 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893118 |  |  |  |  | 07/28/2022 08:30:03 | 07/29/2022 08:54:03 |  | 07/29/2022 10:04:03
4244890 | 883892950 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893199 |  |  |  |  | 07/28/2022 08:30:04 | 07/29/2022 10:04:04
4244890 | 883892950 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893385 |  |  |  |  | 07/28/2022 08:30:05 | 07/29/2022 10:04:05
4244890 | 883892950 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893439 |  |  |  |  | 07/28/2022 08:30:05 | 07/29/2022 10:04:05
4244891 | 883892962 | act--02 Integration | 02 Integration | Completed | Activity | 883893002 | 07/29/2022 08:30:30 | 07/29/2022 08:30:30 | 07/29/2022 07:39:29 | 07/29/2022 08:46:30
4244891 | 883892962 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893045 | 07/29/2022 08:30:31 | 08/16/2022 10:51:23
4244891 | 883892962 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893092 | 07/29/2022 08:30:32 | 08/16/2022 10:51:24
4244891 | 883892962 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893328 |  |  |  |  | 07/28/2022 12:30:29 | 07/28/2022 12:30:29 |  | 07/28/2022 11:52:29
4244891 | 883892962 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893269 |  |  |  |  | 07/28/2022 06:30:29 | 07/28/2022 06:30:29 |  | 07/28/2022 06:40:29
4244891 | 883892962 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893157 |  |  |  |  | 07/29/2022 08:30:30 | 07/29/2022 10:00:30 |  | 08/16/2022 10:51:22
4244891 | 883892962 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893206 |  |  |  |  | 07/29/2022 08:30:31 | 08/16/2022 10:51:23
4244891 | 883892962 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893412 |  |  |  |  | 07/29/2022 08:30:32 | 08/16/2022 10:51:24
4244891 | 883892962 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893451 |  |  |  |  | 07/29/2022 08:30:32 | 08/16/2022 10:51:24
4244892 | 883892961 | act--02 Integration | 02 Integration | Completed | Activity | 883893005 | 07/27/2022 08:30:21 | 07/27/2022 08:30:21 | 07/27/2022 07:39:20 | 07/27/2022 08:45:21
4244892 | 883892961 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893042 | 07/27/2022 08:30:22 | 07/27/2022 09:55:22
4244892 | 883892961 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893093 | 07/27/2022 08:30:23 | 07/27/2022 09:55:23
4244892 | 883892961 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893333 |  |  |  |  | 07/26/2022 12:30:20 | 07/26/2022 12:30:20 |  | 07/26/2022 11:33:20
4244892 | 883892961 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893271 |  |  |  |  | 07/26/2022 06:30:20 | 07/26/2022 06:30:20 |  | 07/26/2022 06:31:20
4244892 | 883892961 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893158 |  |  |  |  | 07/27/2022 08:30:21 | 07/27/2022 08:45:21 |  | 07/27/2022 09:55:21
4244892 | 883892961 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893216 |  |  |  |  | 07/27/2022 08:30:22 | 07/27/2022 09:55:22
4244892 | 883892961 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893419 |  |  |  |  | 07/27/2022 08:30:23 | 07/27/2022 09:55:23
4244892 | 883892961 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893471 |  |  |  |  | 07/27/2022 08:30:23 | 07/27/2022 09:55:23
4244893 | 883892969 | act--02 Integration | 02 Integration | Completed | Activity | 883893022 | 08/03/2022 08:30:11 | 08/03/2022 08:30:11 | 08/03/2022 07:44:10 | 08/03/2022 08:56:10
4244893 | 883892969 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893085 | 08/03/2022 08:30:12 | 08/03/2022 09:46:11
4244893 | 883892969 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893142 | 08/03/2022 08:30:13 | 08/03/2022 09:46:12
4244893 | 883892969 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893464 |  |  |  |  | 08/02/2022 12:30:10 | 08/02/2022 12:30:10 |  | 08/02/2022 11:51:10
4244893 | 883892969 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893387 |  |  |  |  | 08/02/2022 06:30:10 | 08/02/2022 06:30:10 |  | 08/02/2022 06:33:10
4244893 | 883892969 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893243 |  |  |  |  | 08/03/2022 08:30:11 | 08/03/2022 08:56:10 |  | 08/03/2022 09:46:10
4244893 | 883892969 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893316 |  |  |  |  | 08/03/2022 08:30:12 | 08/03/2022 09:46:11
4244893 | 883892969 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893597 |  |  |  |  | 08/03/2022 08:30:13 | 08/03/2022 09:46:12
4244893 | 883892969 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893669 |  |  |  |  | 08/03/2022 08:30:13 | 08/03/2022 09:46:12
4244894 | 883892968 | act--02 Integration | 02 Integration | Completed | Activity | 883893030 | 11/30/2022 13:30:01 | 11/30/2022 13:30:01 | 11/30/2022 12:56:00 | 11/30/2022 14:03:01
4244894 | 883892968 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883893081 | 11/30/2022 13:30:02 | 11/30/2022 14:03:02
4244894 | 883892968 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893155 | 11/30/2022 13:30:03 | 11/30/2022 14:03:03
4244894 | 883892968 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893446 |  |  |  |  | 11/30/2022 11:30:00 | 11/30/2022 11:30:00 |  | 11/30/2022 11:17:00
4244894 | 883892968 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893382 |  |  |  |  | 11/30/2022 05:30:00 | 11/30/2022 05:30:00 |  | 11/30/2022 05:52:00
4244894 | 883892968 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Ready to Start | Milestone | 883893240 |  |  |  |  | 11/30/2022 13:30:01 | 11/30/2022 14:03:01
4244894 | 883892968 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893298 |  |  |  |  | 11/30/2022 13:30:02 | 11/30/2022 14:03:02
4244894 | 883892968 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893599 |  |  |  |  | 11/30/2022 13:30:03 | 11/30/2022 14:03:03
4244894 | 883892968 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893651 |  |  |  |  | 11/30/2022 13:30:03 | 11/30/2022 14:03:03
4244895 | 883892972 | act--02 Integration | 02 Integration | Completed | Activity | 883893015 | 07/21/2022 08:30:37 | 07/21/2022 08:30:37 | 07/21/2022 07:40:36 | 07/21/2022 08:51:37
4244895 | 883892972 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893075 | 07/21/2022 08:30:38 | 07/21/2022 10:16:38
4244895 | 883892972 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893132 | 07/21/2022 08:30:39 | 07/21/2022 10:16:39
4244895 | 883892972 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893413 |  |  |  |  | 07/20/2022 12:14:36 | 07/20/2022 12:14:36 |  | 07/20/2022 12:11:36
4244895 | 883892972 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893352 |  |  |  |  | 07/20/2022 06:34:36 | 07/20/2022 06:34:36 |  | 07/20/2022 06:34:36
4244895 | 883892972 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893217 |  |  |  |  | 07/21/2022 08:30:37 | 07/21/2022 08:51:37 |  | 07/21/2022 10:16:37
4244895 | 883892972 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893283 |  |  |  |  | 07/21/2022 08:30:38 | 07/21/2022 10:16:38
4244895 | 883892972 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893533 |  |  |  |  | 07/21/2022 08:30:39 | 07/21/2022 10:16:39
4244895 | 883892972 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893624 |  |  |  |  | 07/21/2022 08:30:39 | 07/21/2022 10:16:39
4244896 | 883892978 | act--02 Integration | 02 Integration | Completed | Activity | 883893082 | 07/25/2022 08:30:22 | 07/25/2022 08:30:22 | 07/25/2022 07:40:21 | 07/25/2022 08:53:21
4244896 | 883892978 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893156 | 07/25/2022 08:30:23 | 07/25/2022 10:19:22
4244896 | 883892978 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893223 | 07/25/2022 08:30:24 | 07/25/2022 10:19:23
4244896 | 883892978 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893477 |  |  |  |  | 07/24/2022 12:30:21 | 07/24/2022 12:30:21 |  | 07/24/2022 12:04:21
4244896 | 883892978 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893424 |  |  |  |  | 07/24/2022 06:30:21 | 07/24/2022 06:30:21 |  | 07/24/2022 06:37:21
4244896 | 883892978 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893276 |  |  |  |  | 07/25/2022 08:30:22 | 07/25/2022 08:53:21 |  | 07/25/2022 10:19:21
4244896 | 883892978 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893343 |  |  |  |  | 07/25/2022 08:30:23 | 07/25/2022 10:19:22
4244896 | 883892978 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893625 |  |  |  |  | 07/25/2022 08:30:24 | 07/25/2022 10:19:23
4244896 | 883892978 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893679 |  |  |  |  | 07/25/2022 08:30:24 | 07/25/2022 10:19:23
4244897 | 883892980 | act--02 Integration | 02 Integration | Completed | Activity | 883893052 | 07/21/2022 08:30:07 | 07/21/2022 08:30:07 | 07/21/2022 07:38:06 | 07/21/2022 08:41:07
4244897 | 883892980 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893098 | 07/21/2022 08:30:08 | 07/21/2022 09:21:49
4244897 | 883892980 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893168 | 07/21/2022 08:30:09 | 07/21/2022 09:21:50
4244897 | 883892980 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893457 |  |  |  |  | 07/20/2022 12:30:06 | 07/20/2022 12:30:06 |  | 07/20/2022 11:51:06
4244897 | 883892980 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893394 |  |  |  |  | 07/20/2022 06:30:06 | 07/20/2022 06:30:06 |  | 07/20/2022 06:34:06
4244897 | 883892980 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893247 |  |  |  |  | 07/21/2022 08:30:07 | 07/21/2022 08:41:07 |  | 07/21/2022 09:21:48
4244897 | 883892980 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893315 |  |  |  |  | 07/21/2022 08:30:08 | 07/21/2022 09:21:49
4244897 | 883892980 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893600 |  |  |  |  | 07/21/2022 08:30:09 | 07/21/2022 09:21:50
4244897 | 883892980 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893688 |  |  |  |  | 07/21/2022 08:30:09 | 07/21/2022 09:21:50
4244898 | 883892990 | act--02 Integration | 02 Integration | Completed | Activity | 883893063 | 07/25/2022 08:30:07 | 07/25/2022 08:30:07 | 07/25/2022 07:52:06 | 07/25/2022 09:09:07
4244898 | 883892990 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893131 | 07/25/2022 08:30:08 | 07/25/2022 09:45:28
4244898 | 883892990 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893232 | 07/25/2022 08:30:09 | 07/25/2022 09:45:29
4244898 | 883892990 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893589 |  |  |  |  | 07/24/2022 12:30:06 | 07/24/2022 12:30:06 |  | 07/24/2022 12:14:06
4244898 | 883892990 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893449 |  |  |  |  | 07/24/2022 06:30:06 | 07/24/2022 06:30:06 |  | 07/24/2022 06:37:06
4244898 | 883892990 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893308 |  |  |  |  | 07/25/2022 08:30:07 | 07/25/2022 09:09:07 |  | 07/25/2022 09:45:27
4244898 | 883892990 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893389 |  |  |  |  | 07/25/2022 08:30:08 | 07/25/2022 09:45:28
4244898 | 883892990 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893658 |  |  |  |  | 07/25/2022 08:30:09 | 07/25/2022 09:45:29
4244898 | 883892990 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893729 |  |  |  |  | 07/25/2022 08:30:09 | 07/25/2022 09:45:29
4244899 | 883892994 | act--02 Integration | 02 Integration | Completed | Activity | 883893079 | 07/21/2022 08:30:35 | 07/21/2022 08:30:35 | 07/21/2022 07:41:34 | 07/21/2022 08:39:35
4244899 | 883892994 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893151 | 07/21/2022 08:30:36 | 07/21/2022 09:27:16
4244899 | 883892994 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893227 | 07/21/2022 08:30:37 | 07/21/2022 09:27:17
4244899 | 883892994 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893593 |  |  |  |  | 07/20/2022 12:30:34 | 07/20/2022 12:30:34 |  | 07/20/2022 12:12:34
4244899 | 883892994 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893463 |  |  |  |  | 07/20/2022 06:30:35 | 07/20/2022 06:30:35 |  | 07/20/2022 06:33:35
4244899 | 883892994 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893304 |  |  |  |  | 07/21/2022 08:30:35 | 07/21/2022 08:39:35 |  | 07/21/2022 09:27:15
4244899 | 883892994 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893380 |  |  |  |  | 07/21/2022 08:30:36 | 07/21/2022 09:27:16
4244899 | 883892994 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893685 |  |  |  |  | 07/21/2022 08:30:37 | 07/21/2022 09:27:17
4244899 | 883892994 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893755 |  |  |  |  | 07/21/2022 08:30:37 | 07/21/2022 09:27:17
4244900 | 883892996 | act--02 Integration | 02 Integration | Completed | Activity | 883893083 | 07/21/2022 08:30:02 | 07/21/2022 08:30:02 | 07/21/2022 07:42:01 | 07/21/2022 08:53:01
4244900 | 883892996 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893143 | 07/21/2022 08:30:03 | 07/21/2022 10:33:02
4244900 | 883892996 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893212 | 07/21/2022 08:30:04 | 07/21/2022 10:33:03
4244900 | 883892996 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893479 |  |  |  |  | 07/20/2022 12:30:01 | 07/20/2022 12:30:01 |  | 07/20/2022 12:03:01
4244900 | 883892996 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893426 |  |  |  |  | 07/20/2022 06:30:03 | 07/20/2022 06:30:03 |  | 07/20/2022 06:35:03
4244900 | 883892996 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893290 |  |  |  |  | 07/21/2022 08:30:02 | 07/21/2022 08:53:01 |  | 07/21/2022 10:33:01
4244900 | 883892996 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893349 |  |  |  |  | 07/21/2022 08:30:03 | 07/21/2022 10:33:02
4244900 | 883892996 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893614 |  |  |  |  | 07/21/2022 08:30:04 | 07/21/2022 10:33:03
4244900 | 883892996 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893700 |  |  |  |  | 07/21/2022 08:30:04 | 07/21/2022 10:33:03
4244901 | 883893020 | act--02 Integration | 02 Integration | Completed | Activity | 883893090 | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 | 08/05/2022 10:55:00 | 08/05/2022 11:45:00
4244901 | 883893020 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893154 | 08/05/2022 11:45:01 | 08/05/2022 12:25:01
4244901 | 883893020 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893225 | 08/05/2022 11:45:02 | 08/05/2022 12:25:02
4244901 | 883893020 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893466 |  |  |  |  | 08/05/2022 10:50:00 | 08/05/2022 10:50:00 |  | 08/05/2022 10:50:00
4244901 | 883893020 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893417 |  |  |  |  | 08/05/2022 06:00:00 | 08/05/2022 06:00:00 |  | 08/05/2022 06:00:00
4244901 | 883893020 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893293 |  |  |  |  | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 |  | 08/05/2022 12:25:00
4244901 | 883893020 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893351 |  |  |  |  | 08/05/2022 11:45:01 | 08/05/2022 12:25:01
4244901 | 883893020 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893616 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:25:02
4244901 | 883893020 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893676 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:25:02
4244902 | 883893033 | act--02 Integration | 02 Integration | Completed | Activity | 883893117 | 08/10/2022 11:45:00 | 08/10/2022 11:45:00 | 08/10/2022 10:55:00 | 08/10/2022 11:45:00
4244902 | 883893033 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893192 | 08/10/2022 11:45:01 | 08/10/2022 12:35:01
4244902 | 883893033 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893266 | 08/10/2022 11:45:02 | 08/10/2022 12:35:02
4244902 | 883893033 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893607 |  |  |  |  | 08/10/2022 10:50:00 | 08/10/2022 10:50:00 |  | 08/10/2022 10:50:00
4244902 | 883893033 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893473 |  |  |  |  | 08/10/2022 06:00:00 | 08/10/2022 06:00:00 |  | 08/10/2022 06:00:00
4244902 | 883893033 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893345 |  |  |  |  | 08/10/2022 11:45:00 | 08/10/2022 11:45:00 |  | 08/10/2022 12:35:00
4244902 | 883893033 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893416 |  |  |  |  | 08/10/2022 11:45:01 | 08/10/2022 12:35:01
4244902 | 883893033 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893711 |  |  |  |  | 08/10/2022 11:45:02 | 08/10/2022 12:35:02
4244902 | 883893033 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893792 |  |  |  |  | 08/10/2022 11:45:02 | 08/10/2022 12:35:02
4244903 | 883893037 | act--02 Integration | 02 Integration | Completed | Activity | 883893137 | 07/29/2022 11:45:00 | 07/29/2022 11:45:00 | 07/29/2022 10:55:00 | 07/29/2022 11:45:00
4244903 | 883893037 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893236 | 07/29/2022 11:45:01 | 07/29/2022 12:25:01
4244903 | 883893037 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893321 | 07/29/2022 11:45:02 | 07/29/2022 12:25:02
4244903 | 883893037 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893638 |  |  |  |  | 07/29/2022 10:50:00 | 07/29/2022 10:50:00 |  | 07/29/2022 10:50:00
4244903 | 883893037 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893568 |  |  |  |  | 07/29/2022 06:00:00 | 07/29/2022 06:00:00 |  | 07/29/2022 06:00:00
4244903 | 883893037 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893395 |  |  |  |  | 07/29/2022 11:45:00 | 07/29/2022 11:45:00 |  | 07/29/2022 12:25:00
4244903 | 883893037 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893455 |  |  |  |  | 07/29/2022 11:45:01 | 07/29/2022 12:25:01
4244903 | 883893037 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893732 |  |  |  |  | 07/29/2022 11:45:02 | 07/29/2022 12:25:02
4244903 | 883893037 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893808 |  |  |  |  | 07/29/2022 11:45:02 | 07/29/2022 12:25:02
4244904 | 883893036 | act--02 Integration | 02 Integration | Completed | Activity | 883893145 | 07/29/2022 11:45:00 | 07/29/2022 11:45:00 | 07/29/2022 10:55:00 | 07/29/2022 11:45:00
4244904 | 883893036 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893228 | 07/29/2022 10:50:02 | 08/16/2022 17:07:01
4244904 | 883893036 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893306 | 07/29/2022 10:50:03 | 08/16/2022 17:07:02
4244904 | 883893036 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893666 |  |  |  |  | 07/29/2022 10:50:00 | 07/29/2022 10:50:00 |  | 07/29/2022 10:50:00
4244904 | 883893036 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893583 |  |  |  |  | 07/29/2022 06:00:00 | 07/29/2022 06:00:00 |  | 07/29/2022 06:00:00
4244904 | 883893036 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893400 |  |  |  |  | 07/29/2022 10:50:01 | 08/16/2022 17:07:00 |  | 07/29/2022 12:41:47
4244904 | 883893036 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893456 |  |  |  |  | 07/29/2022 10:50:02 | 08/16/2022 17:07:01
4244904 | 883893036 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893759 |  |  |  |  | 07/29/2022 10:50:03 | 08/16/2022 17:07:02
4244904 | 883893036 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893866 |  |  |  |  | 07/29/2022 10:50:03 | 08/16/2022 17:07:02
4244905 | 883893035 | act--02 Integration | 02 Integration | Completed | Activity | 883893148 | 08/08/2022 11:45:00 | 08/08/2022 11:45:00 | 08/08/2022 10:55:00 | 08/08/2022 11:45:00
4244905 | 883893035 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893238 | 08/08/2022 11:45:01 | 08/08/2022 12:28:04
4244905 | 883893035 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893331 | 08/08/2022 11:45:02 | 08/08/2022 12:28:05
4244905 | 883893035 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893723 |  |  |  |  | 08/08/2022 10:50:00 | 08/08/2022 10:50:00 |  | 08/08/2022 10:50:00
4244905 | 883893035 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893662 |  |  |  |  | 08/08/2022 06:00:00 | 08/08/2022 06:00:00 |  | 08/08/2022 06:00:00
4244905 | 883893035 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893431 |  |  |  |  | 08/08/2022 11:45:00 | 08/08/2022 11:45:00 |  | 08/08/2022 12:28:03
4244905 | 883893035 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893538 |  |  |  |  | 08/08/2022 11:45:01 | 08/08/2022 12:28:04
4244905 | 883893035 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893840 |  |  |  |  | 08/08/2022 11:45:02 | 08/08/2022 12:28:05
4244905 | 883893035 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893955 |  |  |  |  | 08/08/2022 11:45:02 | 08/08/2022 12:28:05
4244906 | 883893043 | act--02 Integration | 02 Integration | Completed | Activity | 883893138 | 08/03/2022 11:45:00 | 08/03/2022 11:45:00 | 08/03/2022 10:55:00 | 08/03/2022 11:45:00
4244906 | 883893043 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893242 | 08/03/2022 11:45:01 | 08/03/2022 12:32:35
4244906 | 883893043 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893309 | 08/03/2022 11:45:02 | 08/03/2022 12:32:36
4244906 | 883893043 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893646 |  |  |  |  | 08/03/2022 10:50:00 | 08/03/2022 10:50:00 |  | 08/03/2022 10:50:00
4244906 | 883893043 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893542 |  |  |  |  | 08/03/2022 06:00:00 | 08/03/2022 06:00:00 |  | 08/03/2022 06:00:00
4244906 | 883893043 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893374 |  |  |  |  | 08/03/2022 11:45:00 | 08/03/2022 11:45:00 |  | 08/03/2022 12:32:34
4244906 | 883893043 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893442 |  |  |  |  | 08/03/2022 11:45:01 | 08/03/2022 12:32:35
4244906 | 883893043 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893762 |  |  |  |  | 08/03/2022 11:45:02 | 08/03/2022 12:32:36
4244906 | 883893043 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893842 |  |  |  |  | 08/03/2022 11:45:02 | 08/03/2022 12:32:36
4244907 | 883893038 | act--02 Integration | 02 Integration | Completed | Activity | 883893140 | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 | 08/05/2022 10:55:00 | 08/05/2022 11:45:00
4244907 | 883893038 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893229 | 08/05/2022 11:45:01 | 08/05/2022 12:33:01
4244907 | 883893038 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893287 | 08/05/2022 11:45:02 | 08/05/2022 12:33:02
4244907 | 883893038 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883893706 |  |  |  |  | 08/05/2022 10:50:00 | 08/05/2022 10:50:00 |  | 08/05/2022 10:50:00
4244907 | 883893038 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883893554 |  |  |  |  | 08/05/2022 06:00:00 | 08/05/2022 06:00:00 |  | 08/05/2022 06:00:00
4244907 | 883893038 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883893372 |  |  |  |  | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 |  | 08/05/2022 12:33:00
4244907 | 883893038 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883893436 |  |  |  |  | 08/05/2022 11:45:01 | 08/05/2022 12:33:01
4244907 | 883893038 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883893816 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:33:02
4244907 | 883893038 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883893950 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:33:02
4244908 | 883893301 | act--02 Integration | 02 Integration | Completed | Activity | 883893631 | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 | 08/05/2022 10:55:00 | 08/05/2022 11:45:00
4244908 | 883893301 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893790 | 08/05/2022 11:45:01 | 08/05/2022 12:19:02
4244908 | 883893301 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893987 | 08/05/2022 11:45:02 | 08/05/2022 12:19:03
4244908 | 883893301 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894652 |  |  |  |  | 08/05/2022 10:50:00 | 08/05/2022 10:50:00 |  | 08/05/2022 10:50:00
4244908 | 883893301 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894503 |  |  |  |  | 08/05/2022 06:00:00 | 08/05/2022 06:00:00 |  | 08/05/2022 06:00:00
4244908 | 883893301 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894174 |  |  |  |  | 08/05/2022 11:45:00 | 08/05/2022 11:45:00 |  | 08/05/2022 12:19:01
4244908 | 883893301 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894318 |  |  |  |  | 08/05/2022 11:45:01 | 08/05/2022 12:19:02
4244908 | 883893301 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894798 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:19:03
4244908 | 883893301 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894890 |  |  |  |  | 08/05/2022 11:45:02 | 08/05/2022 12:19:03
4244909 | 883893314 | act--02 Integration | 02 Integration | Completed | Activity | 883893697 | 08/09/2022 11:45:00 | 08/09/2022 11:45:00 | 08/09/2022 10:55:00 | 08/09/2022 11:45:00
4244909 | 883893314 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893802 | 08/09/2022 11:45:01 | 08/09/2022 12:41:54
4244909 | 883893314 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893976 | 08/09/2022 11:45:02 | 08/09/2022 12:41:55
4244909 | 883893314 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894575 |  |  |  |  | 08/09/2022 10:50:00 | 08/09/2022 10:50:00 |  | 08/09/2022 10:50:00
4244909 | 883893314 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894446 |  |  |  |  | 08/09/2022 06:00:00 | 08/09/2022 06:00:00 |  | 08/09/2022 06:00:00
4244909 | 883893314 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894095 |  |  |  |  | 08/09/2022 11:45:00 | 08/09/2022 11:45:00 |  | 08/09/2022 12:41:53
4244909 | 883893314 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894285 |  |  |  |  | 08/09/2022 11:45:01 | 08/09/2022 12:41:54
4244909 | 883893314 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894761 |  |  |  |  | 08/09/2022 11:45:02 | 08/09/2022 12:41:55
4244909 | 883893314 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894887 |  |  |  |  | 08/09/2022 11:45:02 | 08/09/2022 12:41:55
4244910 | 883893322 | act--02 Integration | 02 Integration | Completed | Activity | 883893635 | 08/03/2022 11:45:00 | 08/03/2022 11:45:00 | 08/03/2022 10:55:00 | 08/03/2022 11:45:00
4244910 | 883893322 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893774 | 08/03/2022 11:45:01 | 08/03/2022 12:49:00
4244910 | 883893322 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893914 | 08/03/2022 11:45:02 | 08/03/2022 12:49:01
4244910 | 883893322 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894545 |  |  |  |  | 08/03/2022 10:50:00 | 08/03/2022 10:50:00 |  | 08/03/2022 10:50:00
4244910 | 883893322 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894356 |  |  |  |  | 08/03/2022 06:00:00 | 08/03/2022 06:00:00 |  | 08/03/2022 06:00:00
4244910 | 883893322 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894102 |  |  |  |  | 08/03/2022 11:45:00 | 08/03/2022 11:45:00 |  | 08/03/2022 12:48:59
4244910 | 883893322 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894217 |  |  |  |  | 08/03/2022 11:45:01 | 08/03/2022 12:49:00
4244910 | 883893322 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894703 |  |  |  |  | 08/03/2022 11:45:02 | 08/03/2022 12:49:01
4244910 | 883893322 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894829 |  |  |  |  | 08/03/2022 11:45:02 | 08/03/2022 12:49:01
4244911 | 883893364 | act--02 Integration | 02 Integration | Completed | Activity | 883893701 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244911 | 883893364 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893882 | 09/26/2022 11:45:01 | 10/11/2022 15:02:16
4244911 | 883893364 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894060 | 09/26/2022 11:45:02 | 10/11/2022 15:02:17
4244911 | 883893364 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894722 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244911 | 883893364 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894586 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244911 | 883893364 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894242 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:02:15
4244911 | 883893364 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894390 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:02:16
4244911 | 883893364 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894898 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:02:17
4244911 | 883893364 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894979 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:02:17
4244912 | 883893366 | act--02 Integration | 02 Integration | Completed | Activity | 883893643 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244912 | 883893366 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893756 | 09/26/2022 11:45:01 | 10/11/2022 15:07:45
4244912 | 883893366 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893921 | 09/26/2022 11:45:02 | 10/11/2022 15:07:46
4244912 | 883893366 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894506 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244912 | 883893366 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894369 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244912 | 883893366 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894112 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:07:44
4244912 | 883893366 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894228 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:07:45
4244912 | 883893366 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894640 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:07:46
4244912 | 883893366 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894729 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:07:46
4244913 | 883893365 | act--02 Integration | 02 Integration | Completed | Activity | 883893693 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244913 | 883893365 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893843 | 09/26/2022 11:45:01 | 10/11/2022 15:09:02
4244913 | 883893365 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894036 | 09/26/2022 11:45:02 | 10/11/2022 15:09:03
4244913 | 883893365 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894663 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244913 | 883893365 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894522 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244913 | 883893365 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894222 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:09:01
4244913 | 883893365 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894349 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:09:02
4244913 | 883893365 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894894 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:09:03
4244913 | 883893365 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895059 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:09:03
4244914 | 883893435 | act--02 Integration | 02 Integration | Completed | Activity | 883893692 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244914 | 883893435 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893810 | 09/26/2022 11:45:01 | 10/11/2022 15:10:50
4244914 | 883893435 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893971 | 09/26/2022 11:45:02 | 10/11/2022 15:10:51
4244914 | 883893435 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894633 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244914 | 883893435 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894460 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244914 | 883893435 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894059 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:10:49
4244914 | 883893435 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894266 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:10:50
4244914 | 883893435 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894875 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:10:51
4244914 | 883893435 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894977 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:10:51
4244915 | 883893454 | act--02 Integration | 02 Integration | Completed | Activity | 883893698 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244915 | 883893454 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893854 | 09/26/2022 11:45:01 | 10/11/2022 15:14:53
4244915 | 883893454 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894056 | 09/26/2022 11:45:02 | 10/11/2022 15:14:54
4244915 | 883893454 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894765 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244915 | 883893454 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894687 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244915 | 883893454 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894227 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:14:52
4244915 | 883893454 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894431 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:14:53
4244915 | 883893454 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894921 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:14:54
4244915 | 883893454 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895051 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:14:54
4244916 | 883893490 | act--02 Integration | 02 Integration | Completed | Activity | 883893744 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244916 | 883893490 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893962 | 09/26/2022 11:45:01 | 10/11/2022 15:16:12
4244916 | 883893490 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894181 | 09/26/2022 11:45:02 | 10/11/2022 15:16:13
4244916 | 883893490 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894864 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244916 | 883893490 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894735 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244916 | 883893490 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894389 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:16:11
4244916 | 883893490 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894554 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:16:12
4244916 | 883893490 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895041 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:16:13
4244916 | 883893490 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895134 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:16:13
4244917 | 883893493 | act--02 Integration | 02 Integration | Completed | Activity | 883893908 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244917 | 883893493 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894166 | 09/26/2022 11:45:01 | 10/11/2022 15:26:58
4244917 | 883893493 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894344 | 09/26/2022 11:45:02 | 10/11/2022 15:26:59
4244917 | 883893493 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895014 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244917 | 883893493 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894803 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244917 | 883893493 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894489 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:26:57
4244917 | 883893493 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894674 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:26:58
4244917 | 883893493 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895202 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:26:59
4244917 | 883893493 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895387 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:26:59
4244918 | 883893495 | act--02 Integration | 02 Integration | Completed | Activity | 883893741 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244918 | 883893495 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893942 | 09/26/2022 11:45:01 | 10/11/2022 15:27:59
4244918 | 883893495 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894070 | 09/26/2022 11:45:02 | 10/11/2022 15:28:00
4244918 | 883893495 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894665 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244918 | 883893495 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894512 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244918 | 883893495 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894239 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:27:58
4244918 | 883893495 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894355 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:27:59
4244918 | 883893495 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894863 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:28:00
4244918 | 883893495 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894936 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:28:00
4244919 | 883893494 | act--02 Integration | 02 Integration | Completed | Activity | 883893709 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244919 | 883893494 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893850 | 09/26/2022 11:45:01 | 10/11/2022 15:28:41
4244919 | 883893494 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894005 | 09/26/2022 11:45:02 | 10/11/2022 15:28:42
4244919 | 883893494 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894581 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244919 | 883893494 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894402 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244919 | 883893494 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894178 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:28:40
4244919 | 883893494 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894269 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:28:41
4244919 | 883893494 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894760 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:28:42
4244919 | 883893494 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894906 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:28:42
4244920 | 883893497 | act--02 Integration | 02 Integration | Completed | Activity | 883893710 | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 | 09/26/2022 10:55:00 | 09/26/2022 11:45:00
4244920 | 883893497 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893920 | 09/26/2022 11:45:01 | 10/11/2022 15:29:27
4244920 | 883893497 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894097 | 09/26/2022 11:45:02 | 10/11/2022 15:29:28
4244920 | 883893497 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894728 |  |  |  |  | 09/26/2022 10:50:00 | 09/26/2022 10:50:00 |  | 09/26/2022 10:50:00
4244920 | 883893497 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894591 |  |  |  |  | 09/26/2022 06:00:00 | 09/26/2022 06:00:00 |  | 09/26/2022 06:00:00
4244920 | 883893497 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894240 |  |  |  |  | 09/26/2022 11:45:00 | 09/26/2022 11:45:00 |  | 10/11/2022 15:29:26
4244920 | 883893497 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894388 |  |  |  |  | 09/26/2022 11:45:01 | 10/11/2022 15:29:27
4244920 | 883893497 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894874 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:29:28
4244920 | 883893497 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894988 |  |  |  |  | 09/26/2022 11:45:02 | 10/11/2022 15:29:28
4244921 | 883893491 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893754 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244921 | 883893491 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883893923 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244921 | 883893491 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894052 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244921 | 883893491 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894815 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244921 | 883893491 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894626 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244921 | 883893491 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894282 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244921 | 883893491 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894448 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244921 | 883893491 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894960 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244921 | 883893491 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895129 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893696 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244922 | 883893489 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883893832 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244922 | 883893489 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883893982 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244922 | 883893489 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894637 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894469 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894132 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894260 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894773 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244922 | 883893489 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894893 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893900 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244923 | 883893509 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883894096 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244923 | 883893509 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894267 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244923 | 883893509 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894987 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894740 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894416 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894568 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895264 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244923 | 883893509 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895393 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893705 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244924 | 883893496 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883893963 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244924 | 883893496 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894175 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244924 | 883893496 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894792 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894699 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894325 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894488 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894954 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244924 | 883893496 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895123 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244925 | 883893513 | act--02 Integration | 02 Integration | Completed | Activity | 883893916 | 10/14/2022 13:10:01 | 10/14/2022 12:00:01 | 10/14/2022 11:10:00 | 10/14/2022 13:10:00
4244925 | 883893513 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894107 | 10/14/2022 13:10:02 | 10/14/2022 13:52:01
4244925 | 883893513 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894304 | 10/14/2022 13:10:03 | 10/14/2022 13:52:02
4244925 | 883893513 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894901 |  |  |  |  | 10/14/2022 11:00:00 | 10/14/2022 11:00:00 |  | 10/14/2022 11:00:00
4244925 | 883893513 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894784 |  |  |  |  | 10/14/2022 05:50:00 | 10/14/2022 05:50:00 |  | 10/14/2022 05:50:00
4244925 | 883893513 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894457 |  |  |  |  | 10/14/2022 13:10:01 | 10/14/2022 13:10:00 |  | 10/14/2022 13:52:00
4244925 | 883893513 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894616 |  |  |  |  | 10/14/2022 13:10:02 | 10/14/2022 13:52:01
4244925 | 883893513 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895054 |  |  |  |  | 10/14/2022 13:10:03 | 10/14/2022 13:52:02
4244925 | 883893513 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895187 |  |  |  |  | 10/14/2022 13:10:03 | 10/14/2022 13:52:02
4244926 | 883893492 | act--02 Integration | 02 Integration | Completed | Activity | 883893730 | 10/13/2022 11:25:00 | 10/13/2022 11:25:00 | 10/13/2022 11:25:00 | 10/13/2022 12:25:00
4244926 | 883893492 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893919 | 10/13/2022 05:50:02 | 10/13/2022 13:09:01
4244926 | 883893492 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894080 | 10/13/2022 05:50:03 | 10/13/2022 13:09:02
4244926 | 883893492 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894673 |  |  |  |  | 10/13/2022 10:20:00 | 10/13/2022 10:20:00 |  | 10/13/2022 10:20:00
4244926 | 883893492 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894542 |  |  |  |  | 10/13/2022 05:50:00 | 10/13/2022 05:50:00 |  | 10/13/2022 05:50:00
4244926 | 883893492 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894261 |  |  |  |  | 10/13/2022 05:50:01 | 10/13/2022 12:25:00 |  | 10/13/2022 13:09:00
4244926 | 883893492 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894391 |  |  |  |  | 10/13/2022 05:50:02 | 10/13/2022 13:09:01
4244926 | 883893492 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894866 |  |  |  |  | 10/13/2022 05:50:03 | 10/13/2022 13:09:02
4244926 | 883893492 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895034 |  |  |  |  | 10/13/2022 05:50:03 | 10/13/2022 13:09:02
4244927 | 883893500 | act--02 Integration | 02 Integration | Completed | Activity | 883893829 | 10/13/2022 14:00:01 | 10/13/2022 14:00:01 | 10/13/2022 12:00:00 | 10/13/2022 13:00:00
4244927 | 883893500 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894004 | 10/13/2022 14:00:02 | 10/13/2022 14:00:02
4244927 | 883893500 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894195 | 10/13/2022 14:00:03 | 10/13/2022 14:00:03
4244927 | 883893500 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894734 |  |  |  |  | 10/13/2022 11:50:00 | 10/13/2022 11:50:00 |  | 10/13/2022 11:50:00
4244927 | 883893500 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894607 |  |  |  |  | 10/13/2022 06:50:00 | 10/13/2022 06:50:00 |  | 10/13/2022 06:50:00
4244927 | 883893500 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894319 |  |  |  |  | 10/13/2022 14:00:01 | 10/13/2022 14:00:01 |  | 10/13/2022 13:50:01
4244927 | 883893500 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894442 |  |  |  |  | 10/13/2022 14:00:02 | 10/13/2022 14:00:02
4244927 | 883893500 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894963 |  |  |  |  | 10/13/2022 14:00:03 | 10/13/2022 14:00:03
4244927 | 883893500 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895078 |  |  |  |  | 10/13/2022 14:00:03 | 10/13/2022 14:00:03
4244928 | 883893515 | act--02 Integration | 02 Integration | Completed | Activity | 883893695 | 10/13/2022 11:50:01 | 10/13/2022 11:40:01 | 10/13/2022 10:50:00 | 10/13/2022 11:40:00
4244928 | 883893515 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893825 | 10/13/2022 11:50:02 | 10/13/2022 12:23:22
4244928 | 883893515 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894008 | 10/13/2022 11:50:03 | 10/13/2022 12:23:23
4244928 | 883893515 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894632 |  |  |  |  | 10/13/2022 10:40:00 | 10/13/2022 10:40:00 |  | 10/13/2022 10:40:00
4244928 | 883893515 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894443 |  |  |  |  | 10/13/2022 05:40:00 | 10/13/2022 05:40:00 |  | 10/13/2022 05:40:00
4244928 | 883893515 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894191 |  |  |  |  | 10/13/2022 11:50:01 | 10/13/2022 11:40:01 |  | 10/13/2022 12:23:21
4244928 | 883893515 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894334 |  |  |  |  | 10/13/2022 11:50:02 | 10/13/2022 12:23:22
4244928 | 883893515 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894883 |  |  |  |  | 10/13/2022 11:50:03 | 10/13/2022 12:23:23
4244928 | 883893515 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883894952 |  |  |  |  | 10/13/2022 11:50:03 | 10/13/2022 12:23:23
4244929 | 883893518 | act--02 Integration | 02 Integration | Completed | Activity | 883893881 | 11/29/2022 11:30:01 | 11/29/2022 11:30:01 | 11/29/2022 09:40:00 | 11/29/2022 10:40:00
4244929 | 883893518 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894091 | 11/29/2022 11:30:02 | 11/29/2022 11:30:02
4244929 | 883893518 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894278 | 11/29/2022 11:30:03 | 11/29/2022 11:30:03
4244929 | 883893518 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894879 |  |  |  |  | 11/29/2022 09:30:00 | 11/29/2022 09:30:00 |  | 11/29/2022 09:30:00
4244929 | 883893518 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894744 |  |  |  |  | 11/29/2022 05:30:00 | 11/29/2022 05:30:00 |  | 11/29/2022 05:30:00
4244929 | 883893518 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894435 |  |  |  |  | 11/29/2022 11:30:01 | 11/29/2022 11:30:01 |  | 11/29/2022 11:30:01
4244929 | 883893518 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894617 |  |  |  |  | 11/29/2022 11:30:02 | 11/29/2022 11:30:02
4244929 | 883893518 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895152 |  |  |  |  | 11/29/2022 11:30:03 | 11/29/2022 11:30:03
4244929 | 883893518 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895298 |  |  |  |  | 11/29/2022 11:30:03 | 11/29/2022 11:30:03
4244930 | 883893528 | act--02 Integration | 02 Integration | Completed | Activity | 883893742 | 11/29/2022 11:33:01 | 11/29/2022 11:33:01 | 11/29/2022 10:40:00 | 11/29/2022 11:40:00
4244930 | 883893528 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883893927 | 11/29/2022 11:33:02 | 11/29/2022 12:39:01
4244930 | 883893528 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894082 | 11/29/2022 11:33:03 | 11/29/2022 12:39:02
4244930 | 883893528 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894826 |  |  |  |  | 11/29/2022 10:33:00 | 11/29/2022 10:33:00 |  | 11/29/2022 10:33:00
4244930 | 883893528 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894670 |  |  |  |  | 11/29/2022 05:33:00 | 11/29/2022 05:33:00 |  | 11/29/2022 05:33:00
4244930 | 883893528 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894287 |  |  |  |  | 11/29/2022 11:33:01 | 11/29/2022 11:40:00 |  | 11/29/2022 12:39:00
4244930 | 883893528 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894471 |  |  |  |  | 11/29/2022 11:33:02 | 11/29/2022 12:39:01
4244930 | 883893528 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894972 |  |  |  |  | 11/29/2022 11:33:03 | 11/29/2022 12:39:02
4244930 | 883893528 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895115 |  |  |  |  | 11/29/2022 11:33:03 | 11/29/2022 12:39:02
4244931 | 883893510 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893915 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244931 | 883893510 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883894167 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244931 | 883893510 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894308 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244931 | 883893510 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894955 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244931 | 883893510 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894824 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244931 | 883893510 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894481 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244931 | 883893510 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894669 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244931 | 883893510 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895215 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244931 | 883893510 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895359 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893793 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244932 | 883893511 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883894069 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244932 | 883893511 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894279 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244932 | 883893511 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894989 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894819 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894478 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894672 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895245 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244932 | 883893511 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895408 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244933 | 883893508 | act--02 Integration | 02 Integration | Completed | Activity | 883893869 | 11/30/2022 13:05:01 | 11/30/2022 13:00:01 | 11/30/2022 11:05:00 | 11/30/2022 12:05:00
4244933 | 883893508 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894047 | 11/30/2022 13:05:02 | 11/30/2022 13:00:02
4244933 | 883893508 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894213 | 11/30/2022 13:05:03 | 11/30/2022 13:00:03
4244933 | 883893508 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894823 |  |  |  |  | 11/30/2022 11:00:00 | 11/30/2022 11:00:00 |  | 11/30/2022 11:00:00
4244933 | 883893508 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894702 |  |  |  |  | 11/30/2022 06:00:00 | 11/30/2022 06:00:00 |  | 11/30/2022 06:00:00
4244933 | 883893508 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894362 |  |  |  |  | 11/30/2022 13:05:01 | 11/30/2022 13:00:01 |  | 11/30/2022 13:00:01
4244933 | 883893508 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894528 |  |  |  |  | 11/30/2022 13:05:02 | 11/30/2022 13:00:02
4244933 | 883893508 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894994 |  |  |  |  | 11/30/2022 13:05:03 | 11/30/2022 13:00:03
4244933 | 883893508 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895121 |  |  |  |  | 11/30/2022 13:05:03 | 11/30/2022 13:00:03
4244934 | 883893512 | act--02 Integration | 02 Integration | Completed | Activity | 883893760 | 11/30/2022 12:55:01 | 11/30/2022 12:55:01 | 11/30/2022 10:55:00 | 11/30/2022 12:00:00
4244934 | 883893512 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883893954 | 11/30/2022 12:55:02 | 11/30/2022 12:55:02
4244934 | 883893512 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894139 | 11/30/2022 12:55:03 | 11/30/2022 12:55:03
4244934 | 883893512 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894769 |  |  |  |  | 11/30/2022 10:55:00 | 11/30/2022 10:55:00 |  | 11/30/2022 10:55:00
4244934 | 883893512 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894647 |  |  |  |  | 11/30/2022 05:35:00 | 11/30/2022 05:35:00 |  | 11/30/2022 05:35:00
4244934 | 883893512 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Ready to Start | Milestone | 883894305 |  |  |  |  | 11/30/2022 12:55:01 | 11/30/2022 12:55:01
4244934 | 883893512 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894455 |  |  |  |  | 11/30/2022 12:55:02 | 11/30/2022 12:55:02
4244934 | 883893512 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883894975 |  |  |  |  | 11/30/2022 12:55:03 | 11/30/2022 12:55:03
4244934 | 883893512 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895110 |  |  |  |  | 11/30/2022 12:55:03 | 11/30/2022 12:55:03
4244935 | 883893541 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893906 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244935 | 883893541 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883894142 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244935 | 883893541 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894321 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244935 | 883893541 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894918 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244935 | 883893541 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894775 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244935 | 883893541 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894484 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244935 | 883893541 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894621 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244935 | 883893541 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895079 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244935 | 883893541 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895174 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244936 | 883893539 | act--02 Integration | 02 Integration | Completed | Activity | 883893917 | 11/30/2022 13:31:01 | 11/30/2022 13:31:01 | 11/30/2022 11:29:00 | 11/30/2022 12:29:00
4244936 | 883893539 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894087 | 11/30/2022 13:31:02 | 11/30/2022 13:31:02
4244936 | 883893539 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894286 | 11/30/2022 13:31:03 | 11/30/2022 13:31:03
4244936 | 883893539 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895010 |  |  |  |  | 11/30/2022 11:29:00 | 11/30/2022 11:29:00 |  | 11/30/2022 11:29:00
4244936 | 883893539 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894782 |  |  |  |  | 11/30/2022 06:29:00 | 11/30/2022 06:29:00 |  | 11/30/2022 06:29:00
4244936 | 883893539 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894452 |  |  |  |  | 11/30/2022 13:31:01 | 11/30/2022 13:31:01 |  | 11/30/2022 13:31:01
4244936 | 883893539 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894650 |  |  |  |  | 11/30/2022 13:31:02 | 11/30/2022 13:31:02
4244936 | 883893539 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895295 |  |  |  |  | 11/30/2022 13:31:03 | 11/30/2022 13:31:03
4244936 | 883893539 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895407 |  |  |  |  | 11/30/2022 13:31:03 | 11/30/2022 13:31:03
4244937 | 883893565 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 883893899 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244937 | 883893565 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 883894078 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244937 | 883893565 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894299 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244937 | 883893565 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 883894995 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244937 | 883893565 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 883894820 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244937 | 883893565 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 883894510 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244937 | 883893565 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894597 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244937 | 883893565 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895171 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244937 | 883893565 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895293 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244938 | 883893562 | act--02 Integration | 02 Integration | Completed | Activity | 883893952 | 10/14/2022 11:40:01 | 10/14/2022 11:30:01 | 10/14/2022 10:40:00 | 10/14/2022 11:40:00
4244938 | 883893562 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894103 | 10/14/2022 11:40:02 | 10/14/2022 13:40:01
4244938 | 883893562 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894312 | 10/14/2022 11:40:03 | 10/14/2022 13:40:02
4244938 | 883893562 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894920 |  |  |  |  | 10/14/2022 10:30:00 | 10/14/2022 10:30:00 |  | 10/14/2022 10:30:00
4244938 | 883893562 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894790 |  |  |  |  | 10/14/2022 05:30:00 | 10/14/2022 05:30:00 |  | 10/14/2022 05:30:00
4244938 | 883893562 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894491 |  |  |  |  | 10/14/2022 11:40:01 | 10/14/2022 11:40:00 |  | 10/14/2022 13:40:00
4244938 | 883893562 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894629 |  |  |  |  | 10/14/2022 11:40:02 | 10/14/2022 13:40:01
4244938 | 883893562 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895105 |  |  |  |  | 10/14/2022 11:40:03 | 10/14/2022 13:40:02
4244938 | 883893562 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895241 |  |  |  |  | 10/14/2022 11:40:03 | 10/14/2022 13:40:02
4244939 | 883893561 | act--02 Integration | 02 Integration | Completed | Activity | 883893931 | 10/14/2022 12:30:01 | 10/14/2022 12:30:01 | 10/14/2022 11:30:00 | 10/14/2022 12:30:00
4244939 | 883893561 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894058 | 10/14/2022 12:30:02 | 10/14/2022 13:16:01
4244939 | 883893561 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894270 | 10/14/2022 12:30:03 | 10/14/2022 13:16:02
4244939 | 883893561 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894912 |  |  |  |  | 10/14/2022 11:20:00 | 10/14/2022 11:20:00 |  | 10/14/2022 11:20:00
4244939 | 883893561 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894802 |  |  |  |  | 10/14/2022 06:20:00 | 10/14/2022 06:20:00 |  | 10/14/2022 06:20:00
4244939 | 883893561 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894449 |  |  |  |  | 10/14/2022 12:30:01 | 10/14/2022 12:30:01 |  | 10/14/2022 13:16:00
4244939 | 883893561 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894630 |  |  |  |  | 10/14/2022 12:30:02 | 10/14/2022 13:16:01
4244939 | 883893561 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895085 |  |  |  |  | 10/14/2022 12:30:03 | 10/14/2022 13:16:02
4244939 | 883893561 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895209 |  |  |  |  | 10/14/2022 12:30:03 | 10/14/2022 13:16:02
4244940 | 883893574 | act--02 Integration | 02 Integration | Completed | Activity | 883893930 | 10/14/2022 12:25:01 | 10/14/2022 12:25:01 | 10/14/2022 11:30:00 | 10/14/2022 12:25:01
4244940 | 883893574 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894122 | 10/14/2022 12:25:02 | 10/14/2022 13:05:02
4244940 | 883893574 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894309 | 10/14/2022 12:25:03 | 10/14/2022 13:05:03
4244940 | 883893574 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883894974 |  |  |  |  | 10/14/2022 11:00:00 | 10/14/2022 11:00:00 |  | 10/14/2022 11:00:00
4244940 | 883893574 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883894835 |  |  |  |  | 10/14/2022 06:00:00 | 10/14/2022 06:00:00 |  | 10/14/2022 06:00:00
4244940 | 883893574 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883894534 |  |  |  |  | 10/14/2022 12:25:01 | 10/14/2022 12:25:01 |  | 10/14/2022 13:05:01
4244940 | 883893574 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883894635 |  |  |  |  | 10/14/2022 12:25:02 | 10/14/2022 13:05:02
4244940 | 883893574 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895172 |  |  |  |  | 10/14/2022 12:25:03 | 10/14/2022 13:05:03
4244940 | 883893574 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895347 |  |  |  |  | 10/14/2022 12:25:03 | 10/14/2022 13:05:03
4244941 | 883893576 | act--02 Integration | 02 Integration | Created | Activity | 883893941 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244941 | 883893576 | act--04 SSV | 04 SSV | Created | Activity | 883894144 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244941 | 883893576 | act--06 Tuning | 06 Tuning | Created | Activity | 883894291 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244941 | 883893576 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883894993 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244941 | 883893576 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894836 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244941 | 883893576 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894464 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244941 | 883893576 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894628 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244941 | 883893576 | ms--07 PAC | 07 PAC | Created | Milestone | 883895136 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244941 | 883893576 | ms--08 FAC | 08 FAC | Created | Milestone | 883895247 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | act--02 Integration | 02 Integration | Created | Activity | 883893938 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244942 | 883893577 | act--04 SSV | 04 SSV | Created | Activity | 883894134 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244942 | 883893577 | act--06 Tuning | 06 Tuning | Created | Activity | 883894326 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244942 | 883893577 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895106 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894926 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894576 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894758 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | ms--07 PAC | 07 PAC | Created | Milestone | 883895319 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244942 | 883893577 | ms--08 FAC | 08 FAC | Created | Milestone | 883895440 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | act--02 Integration | 02 Integration | Created | Activity | 883893918 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244943 | 883893578 | act--04 SSV | 04 SSV | Created | Activity | 883894133 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244943 | 883893578 | act--06 Tuning | 06 Tuning | Created | Activity | 883894307 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244943 | 883893578 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883894997 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894859 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894461 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894662 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | ms--07 PAC | 07 PAC | Created | Milestone | 883895265 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244943 | 883893578 | ms--08 FAC | 08 FAC | Created | Milestone | 883895400 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | act--02 Integration | 02 Integration | Created | Activity | 883893925 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244944 | 883893567 | act--04 SSV | 04 SSV | Created | Activity | 883894153 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244944 | 883893567 | act--06 Tuning | 06 Tuning | Created | Activity | 883894350 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244944 | 883893567 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883894996 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894833 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894547 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894706 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | ms--07 PAC | 07 PAC | Created | Milestone | 883895285 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244944 | 883893567 | ms--08 FAC | 08 FAC | Created | Milestone | 883895422 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | act--02 Integration | 02 Integration | Created | Activity | 883893990 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244945 | 883893779 | act--04 SSV | 04 SSV | Created | Activity | 883894168 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244945 | 883893779 | act--06 Tuning | 06 Tuning | Created | Activity | 883894414 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244945 | 883893779 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895002 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894839 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894571 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894716 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | ms--07 PAC | 07 PAC | Created | Milestone | 883895249 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244945 | 883893779 | ms--08 FAC | 08 FAC | Created | Milestone | 883895370 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | act--02 Integration | 02 Integration | Created | Activity | 883894006 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244946 | 883893776 | act--04 SSV | 04 SSV | Created | Activity | 883894165 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244946 | 883893776 | act--06 Tuning | 06 Tuning | Created | Activity | 883894342 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244946 | 883893776 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895013 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894801 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894520 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894638 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | ms--07 PAC | 07 PAC | Created | Milestone | 883895227 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244946 | 883893776 | ms--08 FAC | 08 FAC | Created | Milestone | 883895364 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | act--02 Integration | 02 Integration | Created | Activity | 883894026 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244947 | 883893807 | act--04 SSV | 04 SSV | Created | Activity | 883894212 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244947 | 883893807 | act--06 Tuning | 06 Tuning | Created | Activity | 883894375 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244947 | 883893807 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895084 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894892 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894574 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894745 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | ms--07 PAC | 07 PAC | Created | Milestone | 883895354 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244947 | 883893807 | ms--08 FAC | 08 FAC | Created | Milestone | 883895454 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | act--02 Integration | 02 Integration | Created | Activity | 883894104 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244948 | 883893822 | act--04 SSV | 04 SSV | Created | Activity | 883894283 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244948 | 883893822 | act--06 Tuning | 06 Tuning | Created | Activity | 883894450 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244948 | 883893822 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895077 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894948 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894611 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894795 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | ms--07 PAC | 07 PAC | Created | Milestone | 883895325 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244948 | 883893822 | ms--08 FAC | 08 FAC | Created | Milestone | 883895460 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | act--02 Integration | 02 Integration | Created | Activity | 883894038 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244949 | 883893848 | act--04 SSV | 04 SSV | Created | Activity | 883894230 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244949 | 883893848 | act--06 Tuning | 06 Tuning | Created | Activity | 883894454 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244949 | 883893848 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895026 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894924 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894643 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894764 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | ms--07 PAC | 07 PAC | Created | Milestone | 883895243 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244949 | 883893848 | ms--08 FAC | 08 FAC | Created | Milestone | 883895402 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | act--02 Integration | 02 Integration | Created | Activity | 883894120 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244950 | 883893875 | act--04 SSV | 04 SSV | Created | Activity | 883894281 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244950 | 883893875 | act--06 Tuning | 06 Tuning | Created | Activity | 883894490 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244950 | 883893875 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895089 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883894913 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894625 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894748 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | ms--07 PAC | 07 PAC | Created | Milestone | 883895316 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244950 | 883893875 | ms--08 FAC | 08 FAC | Created | Milestone | 883895477 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | act--02 Integration | 02 Integration | Created | Activity | 883894161 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244951 | 883893876 | act--04 SSV | 04 SSV | Created | Activity | 883894330 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244951 | 883893876 | act--06 Tuning | 06 Tuning | Created | Activity | 883894505 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244951 | 883893876 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895277 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895100 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894714 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883894855 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | ms--07 PAC | 07 PAC | Created | Milestone | 883895476 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244951 | 883893876 | ms--08 FAC | 08 FAC | Created | Milestone | 883895588 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | act--02 Integration | 02 Integration | Created | Activity | 883894271 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244952 | 883894063 | act--04 SSV | 04 SSV | Created | Activity | 883894496 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244952 | 883894063 | act--06 Tuning | 06 Tuning | Created | Activity | 883894713 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244952 | 883894063 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895355 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895246 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894888 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895027 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | ms--07 PAC | 07 PAC | Created | Milestone | 883895551 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244952 | 883894063 | ms--08 FAC | 08 FAC | Created | Milestone | 883895684 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | act--02 Integration | 02 Integration | Created | Activity | 883894347 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244953 | 883894072 | act--04 SSV | 04 SSV | Created | Activity | 883894577 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244953 | 883894072 | act--06 Tuning | 06 Tuning | Created | Activity | 883894793 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244953 | 883894072 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895523 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895356 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894949 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895151 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | ms--07 PAC | 07 PAC | Created | Milestone | 883895735 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244953 | 883894072 | ms--08 FAC | 08 FAC | Created | Milestone | 883895883 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | act--02 Integration | 02 Integration | Created | Activity | 883894336 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244954 | 883894124 | act--04 SSV | 04 SSV | Created | Activity | 883894666 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244954 | 883894124 | act--06 Tuning | 06 Tuning | Created | Activity | 883894871 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244954 | 883894124 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895614 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895498 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883895094 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895297 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | ms--07 PAC | 07 PAC | Created | Milestone | 883895825 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244954 | 883894124 | ms--08 FAC | 08 FAC | Created | Milestone | 883895924 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | act--02 Integration | 02 Integration | Created | Activity | 883894413 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244955 | 883894140 | act--04 SSV | 04 SSV | Created | Activity | 883894570 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244955 | 883894140 | act--06 Tuning | 06 Tuning | Created | Activity | 883894723 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244955 | 883894140 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895507 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895327 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894938 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895091 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | ms--07 PAC | 07 PAC | Created | Milestone | 883895687 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244955 | 883894140 | ms--08 FAC | 08 FAC | Created | Milestone | 883895828 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | act--02 Integration | 02 Integration | Created | Activity | 883894451 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244956 | 883894141 | act--04 SSV | 04 SSV | Created | Activity | 883894681 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244956 | 883894141 | act--06 Tuning | 06 Tuning | Created | Activity | 883894846 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244956 | 883894141 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895525 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895386 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883895056 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895208 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | ms--07 PAC | 07 PAC | Created | Milestone | 883895697 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244956 | 883894141 | ms--08 FAC | 08 FAC | Created | Milestone | 883895818 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | act--02 Integration | 02 Integration | Created | Activity | 883894345 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244957 | 883894147 | act--04 SSV | 04 SSV | Created | Activity | 883894606 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244957 | 883894147 | act--06 Tuning | 06 Tuning | Created | Activity | 883894861 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244957 | 883894147 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895535 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895414 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883895025 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895212 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | ms--07 PAC | 07 PAC | Created | Milestone | 883895758 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244957 | 883894147 | ms--08 FAC | 08 FAC | Created | Milestone | 883895870 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | act--02 Integration | 02 Integration | Created | Activity | 883894387 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244958 | 883894127 | act--04 SSV | 04 SSV | Created | Activity | 883894563 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244958 | 883894127 | act--06 Tuning | 06 Tuning | Created | Activity | 883894799 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244958 | 883894127 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895545 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895445 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883894962 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895236 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | ms--07 PAC | 07 PAC | Created | Milestone | 883895761 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244958 | 883894127 | ms--08 FAC | 08 FAC | Created | Milestone | 883895908 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | act--02 Integration | 02 Integration | Created | Activity | 883894434 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244959 | 883894138 | act--04 SSV | 04 SSV | Created | Activity | 883894612 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244959 | 883894138 | act--06 Tuning | 06 Tuning | Created | Activity | 883894822 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244959 | 883894138 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895724 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895593 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883895031 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895324 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | ms--07 PAC | 07 PAC | Created | Milestone | 883895928 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244959 | 883894138 | ms--08 FAC | 08 FAC | Created | Milestone | 883896129 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | act--02 Integration | 02 Integration | Created | Activity | 883894441 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244960 | 883894163 | act--04 SSV | 04 SSV | Created | Activity | 883894695 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4244960 | 883894163 | act--06 Tuning | 06 Tuning | Created | Activity | 883894915 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4244960 | 883894163 | ms--01 Installation End | 01 Installation End | Created | Milestone | 883895729 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 883895595 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 883895144 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 883895405 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | ms--07 PAC | 07 PAC | Created | Milestone | 883896060 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244960 | 883894163 | ms--08 FAC | 08 FAC | Created | Milestone | 883896185 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4244961 | 883894256 | act--02 Integration | 02 Integration | Completed | Activity | 883894526 | 11/08/2022 13:30:01 | 11/08/2022 13:30:01 | 11/08/2022 12:00:00 | 11/08/2022 12:52:01
4244961 | 883894256 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894705 | 11/08/2022 13:30:02 | 11/08/2022 13:33:35
4244961 | 883894256 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894910 | 11/08/2022 13:30:03 | 11/08/2022 13:33:36
4244961 | 883894256 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895615 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:40:00
4244961 | 883894256 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895471 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:40:00
4244961 | 883894256 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895141 |  |  |  |  | 11/08/2022 13:30:01 | 11/08/2022 13:30:01 |  | 11/08/2022 13:33:34
4244961 | 883894256 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895302 |  |  |  |  | 11/08/2022 13:30:02 | 11/08/2022 13:33:35
4244961 | 883894256 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895812 |  |  |  |  | 11/08/2022 13:30:03 | 11/08/2022 13:33:36
4244961 | 883894256 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895981 |  |  |  |  | 11/08/2022 13:30:03 | 11/08/2022 13:33:36
4244962 | 883894300 | act--02 Integration | 02 Integration | Completed | Activity | 883894525 | 11/08/2022 12:30:01 | 11/08/2022 12:30:01 | 11/08/2022 11:33:00 | 11/08/2022 12:41:01
4244962 | 883894300 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894718 | 11/08/2022 12:30:02 | 11/08/2022 13:22:07
4244962 | 883894300 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894914 | 11/08/2022 12:30:03 | 11/08/2022 13:22:08
4244962 | 883894300 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895560 |  |  |  |  | 11/08/2022 11:30:00 | 11/08/2022 11:30:00 |  | 11/08/2022 10:41:00
4244962 | 883894300 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895429 |  |  |  |  | 11/08/2022 05:30:00 | 11/08/2022 05:30:00 |  | 11/08/2022 05:39:00
4244962 | 883894300 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895086 |  |  |  |  | 11/08/2022 12:30:01 | 11/08/2022 12:41:01 |  | 11/08/2022 13:22:06
4244962 | 883894300 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895251 |  |  |  |  | 11/08/2022 12:30:02 | 11/08/2022 13:22:07
4244962 | 883894300 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895773 |  |  |  |  | 11/08/2022 12:30:03 | 11/08/2022 13:22:08
4244962 | 883894300 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883895916 |  |  |  |  | 11/08/2022 12:30:03 | 11/08/2022 13:22:08
4244963 | 883894295 | act--02 Integration | 02 Integration | Completed | Activity | 883894623 | 11/08/2022 13:30:01 | 11/08/2022 13:30:01 | 11/08/2022 13:35:00 | 11/08/2022 14:34:01
4244963 | 883894295 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894867 | 11/08/2022 13:30:02 | 11/08/2022 15:09:14
4244963 | 883894295 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883895072 | 11/08/2022 13:30:03 | 11/08/2022 15:09:15
4244963 | 883894295 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895861 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:50:00
4244963 | 883894295 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895698 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:33:00
4244963 | 883894295 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895335 |  |  |  |  | 11/08/2022 13:30:01 | 11/08/2022 14:34:01 |  | 11/08/2022 15:09:13
4244963 | 883894295 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895490 |  |  |  |  | 11/08/2022 13:30:02 | 11/08/2022 15:09:14
4244963 | 883894295 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883896094 |  |  |  |  | 11/08/2022 13:30:03 | 11/08/2022 15:09:15
4244963 | 883894295 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883896175 |  |  |  |  | 11/08/2022 13:30:03 | 11/08/2022 15:09:15
4244964 | 883894333 | act--02 Integration | 02 Integration | Completed | Activity | 883894588 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:40:00 | 11/08/2022 14:41:01
4244964 | 883894333 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894778 | 11/08/2022 14:30:02 | 11/08/2022 15:20:14
4244964 | 883894333 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883894961 | 11/08/2022 14:30:03 | 11/08/2022 15:20:15
4244964 | 883894333 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895876 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:41:00 |  | 11/08/2022 12:03:00
4244964 | 883894333 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895662 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:11 |  | 11/08/2022 06:41:00
4244964 | 883894333 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895221 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:41:01 |  | 11/08/2022 15:20:13
4244964 | 883894333 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895415 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:20:14
4244964 | 883894333 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883896122 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:20:15
4244964 | 883894333 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883896183 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:20:15
4244965 | 883894408 | act--02 Integration | 02 Integration | Completed | Activity | 883894678 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:35:00 | 11/08/2022 14:39:01
4244965 | 883894408 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894872 | 11/08/2022 14:30:02 | 11/08/2022 15:11:16
4244965 | 883894408 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883895053 | 11/08/2022 14:30:03 | 11/08/2022 15:11:17
4244965 | 883894408 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895811 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:52:00
4244965 | 883894408 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895648 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:32:00
4244965 | 883894408 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895250 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:39:01 |  | 11/08/2022 15:11:15
4244965 | 883894408 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895409 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:11:16
4244965 | 883894408 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883895993 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:11:17
4244965 | 883894408 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883896104 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:11:17
4244966 | 883894472 | act--02 Integration | 02 Integration | Completed | Activity | 883894719 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:37:00 | 11/08/2022 14:41:01
4244966 | 883894472 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883894909 | 11/08/2022 14:30:02 | 11/08/2022 15:18:02
4244966 | 883894472 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883895164 | 11/08/2022 14:30:03 | 11/08/2022 15:18:03
4244966 | 883894472 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883895777 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:53:00
4244966 | 883894472 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883895641 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:40:00
4244966 | 883894472 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883895374 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:41:01 |  | 11/08/2022 15:18:01
4244966 | 883894472 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883895492 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:18:02
4244966 | 883894472 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883896005 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:18:03
4244966 | 883894472 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883896156 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:18:03
4244967 | 883895401 | act--02 Integration | 02 Integration | Completed | Activity | 883895669 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:36:00 | 11/08/2022 14:41:01
4244967 | 883895401 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883896025 | 11/08/2022 14:30:02 | 11/08/2022 15:22:02
4244967 | 883895401 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883896197 | 11/08/2022 14:30:03 | 11/08/2022 15:22:03
4244967 | 883895401 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883896990 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:43:11
4244967 | 883895401 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883896756 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:41:00
4244967 | 883895401 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883896376 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:41:01 |  | 11/08/2022 15:22:01
4244967 | 883895401 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883896536 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:22:02
4244967 | 883895401 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883897227 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:22:03
4244967 | 883895401 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883897272 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:22:03
4244968 | 883895463 | act--02 Integration | 02 Integration | Completed | Activity | 883895737 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:41:00 | 11/08/2022 14:45:01
4244968 | 883895463 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883895991 | 11/08/2022 14:30:02 | 11/08/2022 15:19:02
4244968 | 883895463 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883896211 | 11/08/2022 14:30:03 | 11/08/2022 15:19:03
4244968 | 883895463 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883897046 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 11:54:00
4244968 | 883895463 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883896858 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:37:00
4244968 | 883895463 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883896465 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:45:01 |  | 11/08/2022 15:19:01
4244968 | 883895463 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883896682 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:19:02
4244968 | 883895463 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883897260 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:19:03
4244968 | 883895463 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883897280 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:19:03
4244969 | 883895464 | act--02 Integration | 02 Integration | Completed | Activity | 883895755 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:39:00 | 11/08/2022 14:41:01
4244969 | 883895464 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883896075 | 11/08/2022 14:30:02 | 11/08/2022 15:30:02
4244969 | 883895464 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883896284 | 11/08/2022 14:30:03 | 11/08/2022 15:30:03
4244969 | 883895464 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883897122 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 12:03:00
4244969 | 883895464 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883896958 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:37:00
4244969 | 883895464 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883896524 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:41:01 |  | 11/08/2022 15:30:01
4244969 | 883895464 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883896738 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:30:02
4244969 | 883895464 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883897270 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:30:03
4244969 | 883895464 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883897284 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:30:03
4244970 | 883895527 | act--02 Integration | 02 Integration | Completed | Activity | 883895763 | 11/08/2022 14:30:01 | 11/08/2022 14:30:01 | 11/08/2022 13:33:00 | 11/08/2022 14:42:01
4244970 | 883895527 | act--04 SSV | 04 SSV | Ready to Start | Activity | 883896033 | 11/08/2022 14:30:02 | 11/08/2022 15:32:02
4244970 | 883895527 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 883896217 | 11/08/2022 14:30:03 | 11/08/2022 15:32:03
4244970 | 883895527 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 883897068 |  |  |  |  | 11/08/2022 12:30:00 | 11/08/2022 12:30:00 |  | 11/08/2022 12:11:00
4244970 | 883895527 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 883896853 |  |  |  |  | 11/08/2022 06:30:00 | 11/08/2022 06:30:00 |  | 11/08/2022 06:35:00
4244970 | 883895527 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 883896484 |  |  |  |  | 11/08/2022 14:30:01 | 11/08/2022 14:42:01 |  | 11/08/2022 15:32:01
4244970 | 883895527 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 883896647 |  |  |  |  | 11/08/2022 14:30:02 | 11/08/2022 15:32:02
4244970 | 883895527 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 883897267 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:32:03
4244970 | 883895527 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 883897282 |  |  |  |  | 11/08/2022 14:30:03 | 11/08/2022 15:32:03
4512561 | 930107132 | act--02 Integration | 02 Integration | Created | Activity | 930107153 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512561 | 930107132 | act--04 SSV | 04 SSV | Created | Activity | 930107163 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512561 | 930107132 | act--06 Tuning | 06 Tuning | Created | Activity | 930107196 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512561 | 930107132 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107405 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512561 | 930107132 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107339 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512561 | 930107132 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107245 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512561 | 930107132 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107291 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512561 | 930107132 | ms--07 PAC | 07 PAC | Created | Milestone | 930107472 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512561 | 930107132 | ms--08 FAC | 08 FAC | Created | Milestone | 930107520 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | act--02 Integration | 02 Integration | Created | Activity | 930107154 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512562 | 930107131 | act--04 SSV | 04 SSV | Created | Activity | 930107162 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512562 | 930107131 | act--06 Tuning | 06 Tuning | Created | Activity | 930107189 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512562 | 930107131 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107465 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107379 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107240 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107304 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | ms--07 PAC | 07 PAC | Created | Milestone | 930107543 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512562 | 930107131 | ms--08 FAC | 08 FAC | Created | Milestone | 930107600 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | act--02 Integration | 02 Integration | Created | Activity | 930107156 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512563 | 930107135 | act--04 SSV | 04 SSV | Created | Activity | 930107170 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512563 | 930107135 | act--06 Tuning | 06 Tuning | Created | Activity | 930107201 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512563 | 930107135 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107463 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107356 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107248 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107295 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | ms--07 PAC | 07 PAC | Created | Milestone | 930107532 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512563 | 930107135 | ms--08 FAC | 08 FAC | Created | Milestone | 930107593 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | act--02 Integration | 02 Integration | Created | Activity | 930107198 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512564 | 930107143 | act--04 SSV | 04 SSV | Created | Activity | 930107243 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512564 | 930107143 | act--06 Tuning | 06 Tuning | Created | Activity | 930107303 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512564 | 930107143 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107603 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107537 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107377 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107449 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | ms--07 PAC | 07 PAC | Created | Milestone | 930107671 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512564 | 930107143 | ms--08 FAC | 08 FAC | Created | Milestone | 930107728 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | act--02 Integration | 02 Integration | Created | Activity | 930107188 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512565 | 930107144 | act--04 SSV | 04 SSV | Created | Activity | 930107237 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512565 | 930107144 | act--06 Tuning | 06 Tuning | Created | Activity | 930107298 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512565 | 930107144 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107586 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107527 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107366 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107450 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | ms--07 PAC | 07 PAC | Created | Milestone | 930107661 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512565 | 930107144 | ms--08 FAC | 08 FAC | Created | Milestone | 930107722 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | act--02 Integration | 02 Integration | Created | Activity | 930107194 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512566 | 930107145 | act--04 SSV | 04 SSV | Created | Activity | 930107244 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512566 | 930107145 | act--06 Tuning | 06 Tuning | Created | Activity | 930107299 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512566 | 930107145 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107602 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107529 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107376 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107468 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | ms--07 PAC | 07 PAC | Created | Milestone | 930107686 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512566 | 930107145 | ms--08 FAC | 08 FAC | Created | Milestone | 930107738 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | act--02 Integration | 02 Integration | Created | Activity | 930107192 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512567 | 930107146 | act--04 SSV | 04 SSV | Created | Activity | 930107242 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512567 | 930107146 | act--06 Tuning | 06 Tuning | Created | Activity | 930107306 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512567 | 930107146 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107647 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107582 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107385 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107498 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | ms--07 PAC | 07 PAC | Created | Milestone | 930107732 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512567 | 930107146 | ms--08 FAC | 08 FAC | Created | Milestone | 930107766 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | act--02 Integration | 02 Integration | Created | Activity | 930107191 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512568 | 930107149 | act--04 SSV | 04 SSV | Created | Activity | 930107239 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512568 | 930107149 | act--06 Tuning | 06 Tuning | Created | Activity | 930107300 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512568 | 930107149 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107612 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107539 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107378 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107461 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | ms--07 PAC | 07 PAC | Created | Milestone | 930107682 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512568 | 930107149 | ms--08 FAC | 08 FAC | Created | Milestone | 930107734 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | act--02 Integration | 02 Integration | Created | Activity | 930107283 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512569 | 930107193 | act--04 SSV | 04 SSV | Created | Activity | 930107336 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512569 | 930107193 | act--06 Tuning | 06 Tuning | Created | Activity | 930107445 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512569 | 930107193 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107750 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107692 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107546 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107613 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | ms--07 PAC | 07 PAC | Created | Milestone | 930107795 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512569 | 930107193 | ms--08 FAC | 08 FAC | Created | Milestone | 930107839 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | act--02 Integration | 02 Integration | Created | Activity | 930107294 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512570 | 930107195 | act--04 SSV | 04 SSV | Created | Activity | 930107357 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512570 | 930107195 | act--06 Tuning | 06 Tuning | Created | Activity | 930107460 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512570 | 930107195 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107742 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107680 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107547 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107620 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | ms--07 PAC | 07 PAC | Created | Milestone | 930107785 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512570 | 930107195 | ms--08 FAC | 08 FAC | Created | Milestone | 930107835 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | act--02 Integration | 02 Integration | Created | Activity | 930107307 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512571 | 930107213 | act--04 SSV | 04 SSV | Created | Activity | 930107381 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512571 | 930107213 | act--06 Tuning | 06 Tuning | Created | Activity | 930107479 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512571 | 930107213 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107756 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107695 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107568 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107636 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | ms--07 PAC | 07 PAC | Created | Milestone | 930107797 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512571 | 930107213 | ms--08 FAC | 08 FAC | Created | Milestone | 930107848 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | act--02 Integration | 02 Integration | Created | Activity | 930107310 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512572 | 930107216 | act--04 SSV | 04 SSV | Created | Activity | 930107387 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512572 | 930107216 | act--06 Tuning | 06 Tuning | Created | Activity | 930107464 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512572 | 930107216 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107737 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107665 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107533 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107608 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | ms--07 PAC | 07 PAC | Created | Milestone | 930107789 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512572 | 930107216 | ms--08 FAC | 08 FAC | Created | Milestone | 930107831 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | act--02 Integration | 02 Integration | Created | Activity | 930107325 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512573 | 930107214 | act--04 SSV | 04 SSV | Created | Activity | 930107390 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512573 | 930107214 | act--06 Tuning | 06 Tuning | Created | Activity | 930107504 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512573 | 930107214 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107758 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107711 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107576 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107639 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | ms--07 PAC | 07 PAC | Created | Milestone | 930107807 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512573 | 930107214 | ms--08 FAC | 08 FAC | Created | Milestone | 930107849 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | act--02 Integration | 02 Integration | Created | Activity | 930107315 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512574 | 930107215 | act--04 SSV | 04 SSV | Created | Activity | 930107383 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512574 | 930107215 | act--06 Tuning | 06 Tuning | Created | Activity | 930107494 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512574 | 930107215 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107778 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107743 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107579 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107654 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | ms--07 PAC | 07 PAC | Created | Milestone | 930107838 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512574 | 930107215 | ms--08 FAC | 08 FAC | Created | Milestone | 930107877 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | act--02 Integration | 02 Integration | Created | Activity | 930107312 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512575 | 930107217 | act--04 SSV | 04 SSV | Created | Activity | 930107404 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4512575 | 930107217 | act--06 Tuning | 06 Tuning | Created | Activity | 930107497 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4512575 | 930107217 | ms--01 Installation End | 01 Installation End | Created | Milestone | 930107774 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | ms--01 Installation Start | 01 Installation Start | Created | Milestone | 930107736 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Created | Milestone | 930107616 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Created | Milestone | 930107664 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | ms--07 PAC | 07 PAC | Created | Milestone | 930107843 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4512575 | 930107217 | ms--08 FAC | 08 FAC | Created | Milestone | 930107875 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00

## UDF ITEM
WP ID | Workplan--SystemRecordID | PLO name | PLO--SystemRecordID | UDF Name | UDF - System Record ID | UDF Category Name | UDF CategorySystem Record ID | UDF item Name | UDF Item--SystemRecordID | UDF Value
3550483 | 675858528 | 01 Installation End | 675858586 | 01 Lead Time Comments | 675858595 | 01 Lead Time | 675858600 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858609
3550483 | 675858528 | 02 Integration | 675858612 | 02 Lead Time Comments | 675858636 | 02 Lead Time | 675858637 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858642
3550483 | 675858528 | 02 Integration | 675858612 | 02 Lead Time Comments | 675858636 | 02 Lead Time | 675858637 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858645
3550483 | 675858528 | 03 Integration Confirmed By NRO Technical Leader | 675858539 | 03 Lead Time Comments | 675858545 | 03 Lead Time | 675858546 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858547
3550483 | 675858528 | 04 SSV | 675858653 | 04 Lead Time Comments | 675858674 | 04 Lead Time | 675858677 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675858679
3550483 | 675858528 | 04 SSV | 675858653 | 04 Lead Time Comments | 675858674 | 04 Lead Time | 675858677 | actcl--04 SSV--04 Lead Time Comments--Duration | 675858690
3550483 | 675858528 | 05 SSV Confirmed By NDO Technical Leader | 675858550 | 05 Lead Time Comments | 675858561 | 05 Lead Time | 675858562 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858564
3550483 | 675858528 | 06 Tuning | 675858707 | 06 Lead Time Comments | 675858754 | 06 Lead Time | 675858763 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675858771
3550483 | 675858528 | 06 Tuning | 675858707 | 06 Lead Time Comments | 675858754 | 06 Lead Time | 675858763 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675858782
3550484 | 675858527 | 01 Installation End | 675858578 | 01 Lead Time Comments | 675858589 | 01 Lead Time | 675858592 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858596
3550484 | 675858527 | 02 Integration | 675858604 | 02 Lead Time Comments | 675858628 | 02 Lead Time | 675858635 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858638
3550484 | 675858527 | 02 Integration | 675858604 | 02 Lead Time Comments | 675858628 | 02 Lead Time | 675858635 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858644
3550484 | 675858527 | 03 Integration Confirmed By NRO Technical Leader | 675858531 | 03 Lead Time Comments | 675858542 | 03 Lead Time | 675858543 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858544
3550484 | 675858527 | 04 SSV | 675858650 | 04 Lead Time Comments | 675858673 | 04 Lead Time | 675858675 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675858684
3550484 | 675858527 | 04 SSV | 675858650 | 04 Lead Time Comments | 675858673 | 04 Lead Time | 675858675 | actcl--04 SSV--04 Lead Time Comments--Duration | 675858698
3550484 | 675858527 | 05 SSV Confirmed By NDO Technical Leader | 675858548 | 05 Lead Time Comments | 675858553 | 05 Lead Time | 675858556 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858558
3550484 | 675858527 | 06 Tuning | 675858713 | 06 Lead Time Comments | 675858751 | 06 Lead Time | 675858761 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675858770
3550484 | 675858527 | 06 Tuning | 675858713 | 06 Lead Time Comments | 675858751 | 06 Lead Time | 675858761 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675858781
3550485 | 675858534 | 01 Installation End | 675858623 | 01 Lead Time Comments | 675858648 | 01 Lead Time | 675858652 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858655
3550485 | 675858534 | 02 Integration | 675858661 | 02 Lead Time Comments | 675858687 | 02 Lead Time | 675858694 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858702
3550485 | 675858534 | 02 Integration | 675858661 | 02 Lead Time Comments | 675858687 | 02 Lead Time | 675858694 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858717
3550485 | 675858534 | 03 Integration Confirmed By NRO Technical Leader | 675858552 | 03 Lead Time Comments | 675858567 | 03 Lead Time | 675858570 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858575
3550485 | 675858534 | 04 SSV | 675858731 | 04 Lead Time Comments | 675858819 | 04 Lead Time | 675858834 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675858854
3550485 | 675858534 | 04 SSV | 675858731 | 04 Lead Time Comments | 675858819 | 04 Lead Time | 675858834 | actcl--04 SSV--04 Lead Time Comments--Duration | 675858874
3550485 | 675858534 | 05 SSV Confirmed By NDO Technical Leader | 675858580 | 05 Lead Time Comments | 675858590 | 05 Lead Time | 675858593 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858597
3550485 | 675858534 | 06 Tuning | 675858895 | 06 Lead Time Comments | 675858949 | 06 Lead Time | 675858955 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675858959
3550485 | 675858534 | 06 Tuning | 675858895 | 06 Lead Time Comments | 675858949 | 06 Lead Time | 675858955 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675858981
3550486 | 675858535 | 01 Installation End | 675858619 | 01 Lead Time Comments | 675858651 | 01 Lead Time | 675858657 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858659
3550486 | 675858535 | 02 Integration | 675858671 | 02 Lead Time Comments | 675858704 | 02 Lead Time | 675858708 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858719
3550486 | 675858535 | 02 Integration | 675858671 | 02 Lead Time Comments | 675858704 | 02 Lead Time | 675858708 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858727
3550486 | 675858535 | 03 Integration Confirmed By NRO Technical Leader | 675858555 | 03 Lead Time Comments | 675858568 | 03 Lead Time | 675858569 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858574
3550486 | 675858535 | 04 SSV | 675858734 | 04 Lead Time Comments | 675858808 | 04 Lead Time | 675858822 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675858836
3550486 | 675858535 | 04 SSV | 675858734 | 04 Lead Time Comments | 675858808 | 04 Lead Time | 675858822 | actcl--04 SSV--04 Lead Time Comments--Duration | 675858868
3550486 | 675858535 | 05 SSV Confirmed By NDO Technical Leader | 675858579 | 05 Lead Time Comments | 675858588 | 05 Lead Time | 675858591 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858594
3550486 | 675858535 | 06 Tuning | 675858884 | 06 Lead Time Comments | 675858947 | 06 Lead Time | 675858952 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675858958
3550486 | 675858535 | 06 Tuning | 675858884 | 06 Lead Time Comments | 675858947 | 06 Lead Time | 675858952 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675858977
3550487 | 675858538 | 01 Installation End | 675858632 | 01 Lead Time Comments | 675858649 | 01 Lead Time | 675858654 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858656
3550487 | 675858538 | 02 Integration | 675858665 | 02 Lead Time Comments | 675858700 | 02 Lead Time | 675858706 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858712
3550487 | 675858538 | 02 Integration | 675858665 | 02 Lead Time Comments | 675858700 | 02 Lead Time | 675858706 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858725
3550487 | 675858538 | 03 Integration Confirmed By NRO Technical Leader | 675858559 | 03 Lead Time Comments | 675858571 | 03 Lead Time | 675858576 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858577
3550487 | 675858538 | 04 SSV | 675858735 | 04 Lead Time Comments | 675858810 | 04 Lead Time | 675858821 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675858837
3550487 | 675858538 | 04 SSV | 675858735 | 04 Lead Time Comments | 675858810 | 04 Lead Time | 675858821 | actcl--04 SSV--04 Lead Time Comments--Duration | 675858866
3550487 | 675858538 | 05 SSV Confirmed By NDO Technical Leader | 675858584 | 05 Lead Time Comments | 675858598 | 05 Lead Time | 675858599 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858603
3550487 | 675858538 | 06 Tuning | 675858885 | 06 Lead Time Comments | 675858943 | 06 Lead Time | 675858950 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675858956
3550487 | 675858538 | 06 Tuning | 675858885 | 06 Lead Time Comments | 675858943 | 06 Lead Time | 675858950 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675858963
3550488 | 675858602 | 01 Installation End | 675858796 | 01 Lead Time Comments | 675858875 | 01 Lead Time | 675858879 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858891
3550488 | 675858602 | 02 Integration | 675858904 | 02 Lead Time Comments | 675858957 | 02 Lead Time | 675858961 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675858964
3550488 | 675858602 | 02 Integration | 675858904 | 02 Lead Time Comments | 675858957 | 02 Lead Time | 675858961 | actcl--02 Integration--02 Lead Time Comments--Duration | 675858985
3550488 | 675858602 | 03 Integration Confirmed By NRO Technical Leader | 675858646 | 03 Lead Time Comments | 675858662 | 03 Lead Time | 675858668 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858669
3550488 | 675858602 | 04 SSV | 675859005 | 04 Lead Time Comments | 675859046 | 04 Lead Time | 675859048 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859051
3550488 | 675858602 | 04 SSV | 675859005 | 04 Lead Time Comments | 675859046 | 04 Lead Time | 675859048 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859065
3550488 | 675858602 | 05 SSV Confirmed By NDO Technical Leader | 675858680 | 05 Lead Time Comments | 675858724 | 05 Lead Time | 675858726 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858730
3550488 | 675858602 | 06 Tuning | 675859110 | 06 Lead Time Comments | 675859162 | 06 Lead Time | 675859179 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859200
3550488 | 675858602 | 06 Tuning | 675859110 | 06 Lead Time Comments | 675859162 | 06 Lead Time | 675859179 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859229
3550489 | 675858614 | 01 Installation End | 675858842 | 01 Lead Time Comments | 675858893 | 01 Lead Time | 675858903 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858910
3550489 | 675858614 | 02 Integration | 675858941 | 02 Lead Time Comments | 675858986 | 02 Lead Time | 675858995 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859007
3550489 | 675858614 | 02 Integration | 675858941 | 02 Lead Time Comments | 675858986 | 02 Lead Time | 675858995 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859024
3550489 | 675858614 | 03 Integration Confirmed By NRO Technical Leader | 675858658 | 03 Lead Time Comments | 675858676 | 03 Lead Time | 675858678 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858686
3550489 | 675858614 | 04 SSV | 675859041 | 04 Lead Time Comments | 675859070 | 04 Lead Time | 675859084 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859103
3550489 | 675858614 | 04 SSV | 675859041 | 04 Lead Time Comments | 675859070 | 04 Lead Time | 675859084 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859121
3550489 | 675858614 | 05 SSV Confirmed By NDO Technical Leader | 675858703 | 05 Lead Time Comments | 675858732 | 05 Lead Time | 675858737 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858743
3550489 | 675858614 | 06 Tuning | 675859136 | 06 Lead Time Comments | 675859204 | 06 Lead Time | 675859219 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859235
3550489 | 675858614 | 06 Tuning | 675859136 | 06 Lead Time Comments | 675859204 | 06 Lead Time | 675859219 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859258
3550490 | 675858616 | 01 Installation End | 675858857 | 01 Lead Time Comments | 675858901 | 01 Lead Time | 675858908 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858913
3550490 | 675858616 | 02 Integration | 675858944 | 02 Lead Time Comments | 675858990 | 02 Lead Time | 675859000 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859010
3550490 | 675858616 | 02 Integration | 675858944 | 02 Lead Time Comments | 675858990 | 02 Lead Time | 675859000 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859029
3550490 | 675858616 | 03 Integration Confirmed By NRO Technical Leader | 675858666 | 03 Lead Time Comments | 675858685 | 03 Lead Time | 675858689 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858701
3550490 | 675858616 | 04 SSV | 675859042 | 04 Lead Time Comments | 675859073 | 04 Lead Time | 675859104 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859112
3550490 | 675858616 | 04 SSV | 675859042 | 04 Lead Time Comments | 675859073 | 04 Lead Time | 675859104 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859133
3550490 | 675858616 | 05 SSV Confirmed By NDO Technical Leader | 675858718 | 05 Lead Time Comments | 675858740 | 05 Lead Time | 675858750 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858759
3550490 | 675858616 | 06 Tuning | 675859149 | 06 Lead Time Comments | 675859226 | 06 Lead Time | 675859241 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859250
3550490 | 675858616 | 06 Tuning | 675859149 | 06 Lead Time Comments | 675859226 | 06 Lead Time | 675859241 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859282
3550491 | 675858613 | 01 Installation End | 675858863 | 01 Lead Time Comments | 675858900 | 01 Lead Time | 675858906 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858912
3550491 | 675858613 | 02 Integration | 675858942 | 02 Lead Time Comments | 675858987 | 02 Lead Time | 675858994 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859009
3550491 | 675858613 | 02 Integration | 675858942 | 02 Lead Time Comments | 675858987 | 02 Lead Time | 675858994 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859025
3550491 | 675858613 | 03 Integration Confirmed By NRO Technical Leader | 675858663 | 03 Lead Time Comments | 675858682 | 03 Lead Time | 675858688 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858695
3550491 | 675858613 | 04 SSV | 675859040 | 04 Lead Time Comments | 675859071 | 04 Lead Time | 675859088 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859105
3550491 | 675858613 | 04 SSV | 675859040 | 04 Lead Time Comments | 675859071 | 04 Lead Time | 675859088 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859122
3550491 | 675858613 | 05 SSV Confirmed By NDO Technical Leader | 675858710 | 05 Lead Time Comments | 675858745 | 05 Lead Time | 675858755 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858762
3550491 | 675858613 | 06 Tuning | 675859138 | 06 Lead Time Comments | 675859203 | 06 Lead Time | 675859231 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859249
3550491 | 675858613 | 06 Tuning | 675859138 | 06 Lead Time Comments | 675859203 | 06 Lead Time | 675859231 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859280
3550492 | 675858621 | 01 Installation End | 675858960 | 01 Lead Time Comments | 675859001 | 01 Lead Time | 675859014 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859021
3550492 | 675858621 | 02 Integration | 675859043 | 02 Lead Time Comments | 675859075 | 02 Lead Time | 675859097 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859107
3550492 | 675858621 | 02 Integration | 675859043 | 02 Lead Time Comments | 675859075 | 02 Lead Time | 675859097 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859124
3550492 | 675858621 | 03 Integration Confirmed By NRO Technical Leader | 675858721 | 03 Lead Time Comments | 675858748 | 03 Lead Time | 675858766 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858772
3550492 | 675858621 | 04 SSV | 675859144 | 04 Lead Time Comments | 675859228 | 04 Lead Time | 675859242 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859252
3550492 | 675858621 | 04 SSV | 675859144 | 04 Lead Time Comments | 675859228 | 04 Lead Time | 675859242 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859281
3550492 | 675858621 | 05 SSV Confirmed By NDO Technical Leader | 675858815 | 05 Lead Time Comments | 675858880 | 05 Lead Time | 675858892 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858894
3550492 | 675858621 | 06 Tuning | 675859319 | 06 Lead Time Comments | 675859431 | 06 Lead Time | 675859447 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859460
3550492 | 675858621 | 06 Tuning | 675859319 | 06 Lead Time Comments | 675859431 | 06 Lead Time | 675859447 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859497
3550493 | 675858625 | 01 Installation End | 675858951 | 01 Lead Time Comments | 675858988 | 01 Lead Time | 675858996 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859008
3550493 | 675858625 | 02 Integration | 675859031 | 02 Lead Time Comments | 675859064 | 02 Lead Time | 675859077 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859099
3550493 | 675858625 | 02 Integration | 675859031 | 02 Lead Time Comments | 675859064 | 02 Lead Time | 675859077 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859118
3550493 | 675858625 | 03 Integration Confirmed By NRO Technical Leader | 675858711 | 03 Lead Time Comments | 675858749 | 03 Lead Time | 675858757 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858769
3550493 | 675858625 | 04 SSV | 675859137 | 04 Lead Time Comments | 675859220 | 04 Lead Time | 675859233 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859247
3550493 | 675858625 | 04 SSV | 675859137 | 04 Lead Time Comments | 675859220 | 04 Lead Time | 675859233 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859277
3550493 | 675858625 | 05 SSV Confirmed By NDO Technical Leader | 675858783 | 05 Lead Time Comments | 675858870 | 05 Lead Time | 675858876 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858882
3550493 | 675858625 | 06 Tuning | 675859331 | 06 Lead Time Comments | 675859440 | 06 Lead Time | 675859454 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859472
3550493 | 675858625 | 06 Tuning | 675859331 | 06 Lead Time Comments | 675859440 | 06 Lead Time | 675859454 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859511
3550494 | 675858629 | 01 Installation End | 675858933 | 01 Lead Time Comments | 675858975 | 01 Lead Time | 675858989 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858997
3550494 | 675858629 | 02 Integration | 675859019 | 02 Lead Time Comments | 675859074 | 02 Lead Time | 675859094 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859106
3550494 | 675858629 | 02 Integration | 675859019 | 02 Lead Time Comments | 675859074 | 02 Lead Time | 675859094 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859125
3550494 | 675858629 | 03 Integration Confirmed By NRO Technical Leader | 675858691 | 03 Lead Time Comments | 675858728 | 03 Lead Time | 675858736 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858741
3550494 | 675858629 | 04 SSV | 675859139 | 04 Lead Time Comments | 675859211 | 04 Lead Time | 675859225 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859239
3550494 | 675858629 | 04 SSV | 675859139 | 04 Lead Time Comments | 675859211 | 04 Lead Time | 675859225 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859263
3550494 | 675858629 | 05 SSV Confirmed By NDO Technical Leader | 675858764 | 05 Lead Time Comments | 675858820 | 05 Lead Time | 675858833 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858855
3550494 | 675858629 | 06 Tuning | 675859312 | 06 Lead Time Comments | 675859412 | 06 Lead Time | 675859426 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859443
3550494 | 675858629 | 06 Tuning | 675859312 | 06 Lead Time Comments | 675859412 | 06 Lead Time | 675859426 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859474
3550495 | 675858639 | 01 Installation End | 675858935 | 01 Lead Time Comments | 675858974 | 01 Lead Time | 675858983 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858992
3550495 | 675858639 | 02 Integration | 675859023 | 02 Lead Time Comments | 675859066 | 02 Lead Time | 675859076 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859098
3550495 | 675858639 | 02 Integration | 675859023 | 02 Lead Time Comments | 675859066 | 02 Lead Time | 675859076 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859116
3550495 | 675858639 | 03 Integration Confirmed By NRO Technical Leader | 675858697 | 03 Lead Time Comments | 675858729 | 03 Lead Time | 675858733 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858738
3550495 | 675858639 | 04 SSV | 675859134 | 04 Lead Time Comments | 675859205 | 04 Lead Time | 675859218 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859234
3550495 | 675858639 | 04 SSV | 675859134 | 04 Lead Time Comments | 675859205 | 04 Lead Time | 675859218 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859256
3550495 | 675858639 | 05 SSV Confirmed By NDO Technical Leader | 675858756 | 05 Lead Time Comments | 675858814 | 05 Lead Time | 675858843 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858871
3550495 | 675858639 | 06 Tuning | 675859290 | 06 Lead Time Comments | 675859388 | 06 Lead Time | 675859401 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859419
3550495 | 675858639 | 06 Tuning | 675859290 | 06 Lead Time Comments | 675859388 | 06 Lead Time | 675859401 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859453
3550496 | 675858641 | 01 Installation End | 675858934 | 01 Lead Time Comments | 675858976 | 01 Lead Time | 675858984 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675858993
3550496 | 675858641 | 02 Integration | 675859016 | 02 Lead Time Comments | 675859069 | 02 Lead Time | 675859079 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859102
3550496 | 675858641 | 02 Integration | 675859016 | 02 Lead Time Comments | 675859069 | 02 Lead Time | 675859079 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859119
3550496 | 675858641 | 03 Integration Confirmed By NRO Technical Leader | 675858709 | 03 Lead Time Comments | 675858744 | 03 Lead Time | 675858752 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675858760
3550496 | 675858641 | 04 SSV | 675859135 | 04 Lead Time Comments | 675859206 | 04 Lead Time | 675859221 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859237
3550496 | 675858641 | 04 SSV | 675859135 | 04 Lead Time Comments | 675859206 | 04 Lead Time | 675859221 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859264
3550496 | 675858641 | 05 SSV Confirmed By NDO Technical Leader | 675858775 | 05 Lead Time Comments | 675858847 | 05 Lead Time | 675858864 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675858872
3550496 | 675858641 | 06 Tuning | 675859297 | 06 Lead Time Comments | 675859397 | 06 Lead Time | 675859411 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675859427
3550496 | 675858641 | 06 Tuning | 675859297 | 06 Lead Time Comments | 675859397 | 06 Lead Time | 675859411 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675859459
3550497 | 675858896 | 01 Installation End | 675859444 | 01 Lead Time Comments | 675859548 | 01 Lead Time | 675859560 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859575
3550497 | 675858896 | 02 Integration | 675859621 | 02 Lead Time Comments | 675859717 | 02 Lead Time | 675859732 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859778
3550497 | 675858896 | 02 Integration | 675859621 | 02 Lead Time Comments | 675859717 | 02 Lead Time | 675859732 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859801
3550497 | 675858896 | 03 Integration Confirmed By NRO Technical Leader | 675859045 | 03 Lead Time Comments | 675859113 | 03 Lead Time | 675859123 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859131
3550497 | 675858896 | 04 SSV | 675859830 | 04 Lead Time Comments | 675859975 | 04 Lead Time | 675859996 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860010
3550497 | 675858896 | 04 SSV | 675859830 | 04 Lead Time Comments | 675859975 | 04 Lead Time | 675859996 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860024
3550497 | 675858896 | 05 SSV Confirmed By NDO Technical Leader | 675859153 | 05 Lead Time Comments | 675859253 | 05 Lead Time | 675859268 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859285
3550497 | 675858896 | 06 Tuning | 675860052 | 06 Lead Time Comments | 675860190 | 06 Lead Time | 675860212 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860236
3550497 | 675858896 | 06 Tuning | 675860052 | 06 Lead Time Comments | 675860190 | 06 Lead Time | 675860212 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860270
3550498 | 675858905 | 01 Installation End | 675859336 | 01 Lead Time Comments | 675859450 | 01 Lead Time | 675859466 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859486
3550498 | 675858905 | 02 Integration | 675859528 | 02 Lead Time Comments | 675859654 | 02 Lead Time | 675859669 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859680
3550498 | 675858905 | 02 Integration | 675859528 | 02 Lead Time Comments | 675859654 | 02 Lead Time | 675859669 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859706
3550498 | 675858905 | 03 Integration Confirmed By NRO Technical Leader | 675859030 | 03 Lead Time Comments | 675859068 | 03 Lead Time | 675859078 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859101
3550498 | 675858905 | 04 SSV | 675859751 | 04 Lead Time Comments | 675859854 | 04 Lead Time | 675859879 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859916
3550498 | 675858905 | 04 SSV | 675859751 | 04 Lead Time Comments | 675859854 | 04 Lead Time | 675859879 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859969
3550498 | 675858905 | 05 SSV Confirmed By NDO Technical Leader | 675859129 | 05 Lead Time Comments | 675859191 | 05 Lead Time | 675859202 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859216
3550498 | 675858905 | 06 Tuning | 675860009 | 06 Lead Time Comments | 675860125 | 06 Lead Time | 675860153 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860176
3550498 | 675858905 | 06 Tuning | 675860009 | 06 Lead Time Comments | 675860125 | 06 Lead Time | 675860153 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860218
3550499 | 675858915 | 01 Installation End | 675859337 | 01 Lead Time Comments | 675859436 | 01 Lead Time | 675859451 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859469
3550499 | 675858915 | 02 Integration | 675859516 | 02 Lead Time Comments | 675859632 | 02 Lead Time | 675859640 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859659
3550499 | 675858915 | 02 Integration | 675859516 | 02 Lead Time Comments | 675859632 | 02 Lead Time | 675859640 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859682
3550499 | 675858915 | 03 Integration Confirmed By NRO Technical Leader | 675859038 | 03 Lead Time Comments | 675859062 | 03 Lead Time | 675859072 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859100
3550499 | 675858915 | 04 SSV | 675859720 | 04 Lead Time Comments | 675859823 | 04 Lead Time | 675859835 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859849
3550499 | 675858915 | 04 SSV | 675859720 | 04 Lead Time Comments | 675859823 | 04 Lead Time | 675859835 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859893
3550499 | 675858915 | 05 SSV Confirmed By NDO Technical Leader | 675859127 | 05 Lead Time Comments | 675859170 | 05 Lead Time | 675859189 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859201
3550499 | 675858915 | 06 Tuning | 675859962 | 06 Lead Time Comments | 675860078 | 06 Lead Time | 675860103 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860124
3550499 | 675858915 | 06 Tuning | 675859962 | 06 Lead Time Comments | 675860078 | 06 Lead Time | 675860103 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860174
3550500 | 675858922 | 01 Installation End | 675859515 | 01 Lead Time Comments | 675859625 | 01 Lead Time | 675859634 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859656
3550500 | 675858922 | 02 Integration | 675859685 | 02 Lead Time Comments | 675859804 | 02 Lead Time | 675859819 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859827
3550500 | 675858922 | 02 Integration | 675859685 | 02 Lead Time Comments | 675859804 | 02 Lead Time | 675859819 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859864
3550500 | 675858922 | 03 Integration Confirmed By NRO Technical Leader | 675859143 | 03 Lead Time Comments | 675859208 | 03 Lead Time | 675859223 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859236
3550500 | 675858922 | 04 SSV | 675859909 | 04 Lead Time Comments | 675860049 | 04 Lead Time | 675860064 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860075
3550500 | 675858922 | 04 SSV | 675859909 | 04 Lead Time Comments | 675860049 | 04 Lead Time | 675860064 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860116
3550500 | 675858922 | 05 SSV Confirmed By NDO Technical Leader | 675859266 | 05 Lead Time Comments | 675859345 | 05 Lead Time | 675859355 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859380
3550500 | 675858922 | 06 Tuning | 675860173 | 06 Lead Time Comments | 675860318 | 06 Lead Time | 675860336 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860351
3550500 | 675858922 | 06 Tuning | 675860173 | 06 Lead Time Comments | 675860318 | 06 Lead Time | 675860336 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860381
3550501 | 675858924 | 01 Installation End | 675859598 | 01 Lead Time Comments | 675859684 | 01 Lead Time | 675859698 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859719
3550501 | 675858924 | 02 Integration | 675859762 | 02 Lead Time Comments | 675859878 | 02 Lead Time | 675859895 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859917
3550501 | 675858924 | 02 Integration | 675859762 | 02 Lead Time Comments | 675859878 | 02 Lead Time | 675859895 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859970
3550501 | 675858924 | 03 Integration Confirmed By NRO Technical Leader | 675859161 | 03 Lead Time Comments | 675859246 | 03 Lead Time | 675859259 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859276
3550501 | 675858924 | 04 SSV | 675860018 | 04 Lead Time Comments | 675860138 | 04 Lead Time | 675860162 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860185
3550501 | 675858924 | 04 SSV | 675860018 | 04 Lead Time Comments | 675860138 | 04 Lead Time | 675860162 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860226
3550501 | 675858924 | 05 SSV Confirmed By NDO Technical Leader | 675859306 | 05 Lead Time Comments | 675859406 | 05 Lead Time | 675859425 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859442
3550501 | 675858924 | 06 Tuning | 675860271 | 06 Lead Time Comments | 675860399 | 06 Lead Time | 675860430 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860456
3550501 | 675858924 | 06 Tuning | 675860271 | 06 Lead Time Comments | 675860399 | 06 Lead Time | 675860430 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860495
3550502 | 675858923 | 01 Installation End | 675859455 | 01 Lead Time Comments | 675859553 | 01 Lead Time | 675859564 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859592
3550502 | 675858923 | 02 Integration | 675859626 | 02 Lead Time Comments | 675859728 | 02 Lead Time | 675859744 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859764
3550502 | 675858923 | 02 Integration | 675859626 | 02 Lead Time Comments | 675859728 | 02 Lead Time | 675859744 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859789
3550502 | 675858923 | 03 Integration Confirmed By NRO Technical Leader | 675859111 | 03 Lead Time Comments | 675859158 | 03 Lead Time | 675859165 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859182
3550502 | 675858923 | 04 SSV | 675859820 | 04 Lead Time Comments | 675859959 | 04 Lead Time | 675859978 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859998
3550502 | 675858923 | 04 SSV | 675859820 | 04 Lead Time Comments | 675859959 | 04 Lead Time | 675859978 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860023
3550502 | 675858923 | 05 SSV Confirmed By NDO Technical Leader | 675859207 | 05 Lead Time Comments | 675859284 | 05 Lead Time | 675859298 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859313
3550502 | 675858923 | 06 Tuning | 675860061 | 06 Lead Time Comments | 675860196 | 06 Lead Time | 675860217 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860242
3550502 | 675858923 | 06 Tuning | 675860061 | 06 Lead Time Comments | 675860196 | 06 Lead Time | 675860217 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860278
3550503 | 675858920 | 01 Installation End | 675859610 | 01 Lead Time Comments | 675859688 | 01 Lead Time | 675859703 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859723
3550503 | 675858920 | 02 Integration | 675859771 | 02 Lead Time Comments | 675859881 | 02 Lead Time | 675859899 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859927
3550503 | 675858920 | 02 Integration | 675859771 | 02 Lead Time Comments | 675859881 | 02 Lead Time | 675859899 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859971
3550503 | 675858920 | 03 Integration Confirmed By NRO Technical Leader | 675859152 | 03 Lead Time Comments | 675859244 | 03 Lead Time | 675859254 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859283
3550503 | 675858920 | 04 SSV | 675860011 | 04 Lead Time Comments | 675860139 | 04 Lead Time | 675860161 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860186
3550503 | 675858920 | 04 SSV | 675860011 | 04 Lead Time Comments | 675860139 | 04 Lead Time | 675860161 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860225
3550503 | 675858920 | 05 SSV Confirmed By NDO Technical Leader | 675859320 | 05 Lead Time Comments | 675859413 | 05 Lead Time | 675859429 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859448
3550503 | 675858920 | 06 Tuning | 675860283 | 06 Lead Time Comments | 675860428 | 06 Lead Time | 675860459 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860483
3550503 | 675858920 | 06 Tuning | 675860283 | 06 Lead Time Comments | 675860428 | 06 Lead Time | 675860459 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860509
3550504 | 675858918 | 01 Installation End | 675859475 | 01 Lead Time Comments | 675859566 | 01 Lead Time | 675859599 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859620
3550504 | 675858918 | 02 Integration | 675859643 | 02 Lead Time Comments | 675859761 | 02 Lead Time | 675859780 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859788
3550504 | 675858918 | 02 Integration | 675859643 | 02 Lead Time Comments | 675859761 | 02 Lead Time | 675859780 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859824
3550504 | 675858918 | 03 Integration Confirmed By NRO Technical Leader | 675859108 | 03 Lead Time Comments | 675859155 | 03 Lead Time | 675859164 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859180
3550504 | 675858918 | 04 SSV | 675859858 | 04 Lead Time Comments | 675860000 | 04 Lead Time | 675860013 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860019
3550504 | 675858918 | 04 SSV | 675859858 | 04 Lead Time Comments | 675860000 | 04 Lead Time | 675860013 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860042
3550504 | 675858918 | 05 SSV Confirmed By NDO Technical Leader | 675859209 | 05 Lead Time Comments | 675859291 | 05 Lead Time | 675859307 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859335
3550504 | 675858918 | 06 Tuning | 675860072 | 06 Lead Time Comments | 675860208 | 06 Lead Time | 675860234 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860248
3550504 | 675858918 | 06 Tuning | 675860072 | 06 Lead Time Comments | 675860208 | 06 Lead Time | 675860234 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860287
3550505 | 675858921 | 01 Installation End | 675859357 | 01 Lead Time Comments | 675859456 | 01 Lead Time | 675859471 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859490
3550505 | 675858921 | 02 Integration | 675859529 | 02 Lead Time Comments | 675859647 | 02 Lead Time | 675859661 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859673
3550505 | 675858921 | 02 Integration | 675859529 | 02 Lead Time Comments | 675859647 | 02 Lead Time | 675859661 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859696
3550505 | 675858921 | 03 Integration Confirmed By NRO Technical Leader | 675859049 | 03 Lead Time Comments | 675859115 | 03 Lead Time | 675859126 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859132
3550505 | 675858921 | 04 SSV | 675859741 | 04 Lead Time Comments | 675859843 | 04 Lead Time | 675859865 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675859887
3550505 | 675858921 | 04 SSV | 675859741 | 04 Lead Time Comments | 675859843 | 04 Lead Time | 675859865 | actcl--04 SSV--04 Lead Time Comments--Duration | 675859939
3550505 | 675858921 | 05 SSV Confirmed By NDO Technical Leader | 675859142 | 05 Lead Time Comments | 675859210 | 05 Lead Time | 675859224 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859240
3550505 | 675858921 | 06 Tuning | 675859988 | 06 Lead Time Comments | 675860104 | 06 Lead Time | 675860133 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860158
3550505 | 675858921 | 06 Tuning | 675859988 | 06 Lead Time Comments | 675860104 | 06 Lead Time | 675860133 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860199
3550506 | 675858919 | 01 Installation End | 675859644 | 01 Lead Time Comments | 675859734 | 01 Lead Time | 675859755 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859776
3550506 | 675858919 | 02 Integration | 675859818 | 02 Lead Time Comments | 675859954 | 02 Lead Time | 675859972 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859991
3550506 | 675858919 | 02 Integration | 675859818 | 02 Lead Time Comments | 675859954 | 02 Lead Time | 675859972 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860015
3550506 | 675858919 | 03 Integration Confirmed By NRO Technical Leader | 675859177 | 03 Lead Time Comments | 675859260 | 03 Lead Time | 675859275 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859288
3550506 | 675858919 | 04 SSV | 675860031 | 04 Lead Time Comments | 675860182 | 04 Lead Time | 675860206 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860224
3550506 | 675858919 | 04 SSV | 675860031 | 04 Lead Time Comments | 675860182 | 04 Lead Time | 675860206 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860260
3550506 | 675858919 | 05 SSV Confirmed By NDO Technical Leader | 675859338 | 05 Lead Time Comments | 675859438 | 05 Lead Time | 675859452 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859468
3550506 | 675858919 | 06 Tuning | 675860305 | 06 Lead Time Comments | 675860466 | 06 Lead Time | 675860487 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860501
3550506 | 675858919 | 06 Tuning | 675860305 | 06 Lead Time Comments | 675860466 | 06 Lead Time | 675860487 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860529
3550507 | 675858965 | 01 Installation End | 675859601 | 01 Lead Time Comments | 675859689 | 01 Lead Time | 675859701 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859724
3550507 | 675858965 | 02 Integration | 675859770 | 02 Lead Time Comments | 675859885 | 02 Lead Time | 675859944 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859966
3550507 | 675858965 | 02 Integration | 675859770 | 02 Lead Time Comments | 675859885 | 02 Lead Time | 675859944 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860003
3550507 | 675858965 | 03 Integration Confirmed By NRO Technical Leader | 675859159 | 03 Lead Time Comments | 675859245 | 03 Lead Time | 675859257 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859271
3550507 | 675858965 | 04 SSV | 675860022 | 04 Lead Time Comments | 675860151 | 04 Lead Time | 675860170 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860193
3550507 | 675858965 | 04 SSV | 675860022 | 04 Lead Time Comments | 675860151 | 04 Lead Time | 675860170 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860223
3550507 | 675858965 | 05 SSV Confirmed By NDO Technical Leader | 675859305 | 05 Lead Time Comments | 675859400 | 05 Lead Time | 675859416 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859434
3550507 | 675858965 | 06 Tuning | 675860262 | 06 Lead Time Comments | 675860376 | 06 Lead Time | 675860398 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860422
3550507 | 675858965 | 06 Tuning | 675860262 | 06 Lead Time Comments | 675860376 | 06 Lead Time | 675860398 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860464
3550508 | 675858968 | 01 Installation End | 675859653 | 01 Lead Time Comments | 675859730 | 01 Lead Time | 675859747 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859766
3550508 | 675858968 | 02 Integration | 675859799 | 02 Lead Time Comments | 675859903 | 02 Lead Time | 675859943 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859965
3550508 | 675858968 | 02 Integration | 675859799 | 02 Lead Time Comments | 675859903 | 02 Lead Time | 675859943 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860004
3550508 | 675858968 | 03 Integration Confirmed By NRO Technical Leader | 675859184 | 03 Lead Time Comments | 675859255 | 03 Lead Time | 675859270 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859286
3550508 | 675858968 | 04 SSV | 675860026 | 04 Lead Time Comments | 675860171 | 04 Lead Time | 675860210 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860232
3550508 | 675858968 | 04 SSV | 675860026 | 04 Lead Time Comments | 675860171 | 04 Lead Time | 675860210 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860264
3550508 | 675858968 | 05 SSV Confirmed By NDO Technical Leader | 675859346 | 05 Lead Time Comments | 675859445 | 05 Lead Time | 675859473 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859492
3550508 | 675858968 | 06 Tuning | 675860308 | 06 Lead Time Comments | 675860449 | 06 Lead Time | 675860473 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860510
3550508 | 675858968 | 06 Tuning | 675860308 | 06 Lead Time Comments | 675860449 | 06 Lead Time | 675860473 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860535
3550509 | 675858966 | 01 Installation End | 675859666 | 01 Lead Time Comments | 675859748 | 01 Lead Time | 675859763 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859781
3550509 | 675858966 | 02 Integration | 675859807 | 02 Lead Time Comments | 675859931 | 02 Lead Time | 675859955 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859976
3550509 | 675858966 | 02 Integration | 675859807 | 02 Lead Time Comments | 675859931 | 02 Lead Time | 675859955 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860008
3550509 | 675858966 | 03 Integration Confirmed By NRO Technical Leader | 675859222 | 03 Lead Time Comments | 675859296 | 03 Lead Time | 675859310 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859324
3550509 | 675858966 | 04 SSV | 675860025 | 04 Lead Time Comments | 675860163 | 04 Lead Time | 675860188 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860207
3550509 | 675858966 | 04 SSV | 675860025 | 04 Lead Time Comments | 675860163 | 04 Lead Time | 675860188 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860258
3550509 | 675858966 | 05 SSV Confirmed By NDO Technical Leader | 675859371 | 05 Lead Time Comments | 675859482 | 05 Lead Time | 675859498 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859518
3550509 | 675858966 | 06 Tuning | 675860294 | 06 Lead Time Comments | 675860439 | 06 Lead Time | 675860465 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860486
3550509 | 675858966 | 06 Tuning | 675860294 | 06 Lead Time Comments | 675860439 | 06 Lead Time | 675860465 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860511
3550510 | 675858967 | 01 Installation End | 675859522 | 01 Lead Time Comments | 675859633 | 01 Lead Time | 675859642 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859660
3550510 | 675858967 | 02 Integration | 675859690 | 02 Lead Time Comments | 675859797 | 02 Lead Time | 675859809 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859822
3550510 | 675858967 | 02 Integration | 675859690 | 02 Lead Time Comments | 675859797 | 02 Lead Time | 675859809 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859862
3550510 | 675858967 | 03 Integration Confirmed By NRO Technical Leader | 675859148 | 03 Lead Time Comments | 675859215 | 03 Lead Time | 675859230 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859243
3550510 | 675858967 | 04 SSV | 675859919 | 04 Lead Time Comments | 675860056 | 04 Lead Time | 675860067 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860081
3550510 | 675858967 | 04 SSV | 675859919 | 04 Lead Time Comments | 675860056 | 04 Lead Time | 675860067 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860132
3550510 | 675858967 | 05 SSV Confirmed By NDO Technical Leader | 675859274 | 05 Lead Time Comments | 675859347 | 05 Lead Time | 675859362 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859384
3550510 | 675858967 | 06 Tuning | 675860183 | 06 Lead Time Comments | 675860312 | 06 Lead Time | 675860329 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860347
3550510 | 675858967 | 06 Tuning | 675860183 | 06 Lead Time Comments | 675860312 | 06 Lead Time | 675860329 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860372
3550511 | 675858973 | 01 Installation End | 675859627 | 01 Lead Time Comments | 675859707 | 01 Lead Time | 675859722 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859737
3550511 | 675858973 | 02 Integration | 675859779 | 02 Lead Time Comments | 675859891 | 02 Lead Time | 675859915 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675859949
3550511 | 675858973 | 02 Integration | 675859779 | 02 Lead Time Comments | 675859891 | 02 Lead Time | 675859915 | actcl--02 Integration--02 Lead Time Comments--Duration | 675859986
3550511 | 675858973 | 03 Integration Confirmed By NRO Technical Leader | 675859188 | 03 Lead Time Comments | 675859262 | 03 Lead Time | 675859278 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859289
3550511 | 675858973 | 04 SSV | 675860017 | 04 Lead Time Comments | 675860130 | 04 Lead Time | 675860155 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860180
3550511 | 675858973 | 04 SSV | 675860017 | 04 Lead Time Comments | 675860130 | 04 Lead Time | 675860155 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860235
3550511 | 675858973 | 05 SSV Confirmed By NDO Technical Leader | 675859329 | 05 Lead Time Comments | 675859423 | 05 Lead Time | 675859441 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859457
3550511 | 675858973 | 06 Tuning | 675860277 | 06 Lead Time Comments | 675860404 | 06 Lead Time | 675860440 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860463
3550511 | 675858973 | 06 Tuning | 675860277 | 06 Lead Time Comments | 675860404 | 06 Lead Time | 675860440 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860500
3550512 | 675859053 | 01 Installation End | 675860038 | 01 Lead Time Comments | 675860154 | 01 Lead Time | 675860179 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860200
3550512 | 675859053 | 02 Integration | 675860245 | 02 Lead Time Comments | 675860362 | 02 Lead Time | 675860401 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860425
3550512 | 675859053 | 02 Integration | 675860245 | 02 Lead Time Comments | 675860362 | 02 Lead Time | 675860401 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860477
3550512 | 675859053 | 03 Integration Confirmed By NRO Technical Leader | 675859523 | 03 Lead Time Comments | 675859631 | 03 Lead Time | 675859639 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859658
3550512 | 675859053 | 04 SSV | 675860516 | 04 Lead Time Comments | 675860640 | 04 Lead Time | 675860657 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860691
3550512 | 675859053 | 04 SSV | 675860516 | 04 Lead Time Comments | 675860640 | 04 Lead Time | 675860657 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860716
3550512 | 675859053 | 05 SSV Confirmed By NDO Technical Leader | 675859700 | 05 Lead Time Comments | 675859832 | 05 Lead Time | 675859845 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859866
3550512 | 675859053 | 06 Tuning | 675860756 | 06 Lead Time Comments | 675860852 | 06 Lead Time | 675860870 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860917
3550512 | 675859053 | 06 Tuning | 675860756 | 06 Lead Time Comments | 675860852 | 06 Lead Time | 675860870 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860951
3550513 | 675859052 | 01 Installation End | 675859774 | 01 Lead Time Comments | 675859857 | 01 Lead Time | 675859880 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859896
3550513 | 675859052 | 02 Integration | 675859963 | 02 Lead Time Comments | 675860071 | 02 Lead Time | 675860092 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860115
3550513 | 675859052 | 02 Integration | 675859963 | 02 Lead Time Comments | 675860071 | 02 Lead Time | 675860092 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860156
3550513 | 675859052 | 03 Integration Confirmed By NRO Technical Leader | 675859328 | 03 Lead Time Comments | 675859430 | 03 Lead Time | 675859446 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859462
3550513 | 675859052 | 04 SSV | 675860211 | 04 Lead Time Comments | 675860337 | 04 Lead Time | 675860360 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860375
3550513 | 675859052 | 04 SSV | 675860211 | 04 Lead Time Comments | 675860337 | 04 Lead Time | 675860360 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860419
3550513 | 675859052 | 05 SSV Confirmed By NDO Technical Leader | 675859504 | 05 Lead Time Comments | 675859619 | 05 Lead Time | 675859629 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859636
3550513 | 675859052 | 06 Tuning | 675860482 | 06 Lead Time Comments | 675860587 | 06 Lead Time | 675860608 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860637
3550513 | 675859052 | 06 Tuning | 675860482 | 06 Lead Time Comments | 675860587 | 06 Lead Time | 675860608 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860678
3550514 | 675859081 | 01 Installation End | 675859989 | 01 Lead Time Comments | 675860086 | 01 Lead Time | 675860109 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860131
3550514 | 675859081 | 02 Integration | 675860181 | 02 Lead Time Comments | 675860310 | 02 Lead Time | 675860326 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860344
3550514 | 675859081 | 02 Integration | 675860181 | 02 Lead Time Comments | 675860310 | 02 Lead Time | 675860326 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860374
3550514 | 675859081 | 03 Integration Confirmed By NRO Technical Leader | 675859538 | 03 Lead Time Comments | 675859652 | 03 Lead Time | 675859667 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859675
3550514 | 675859081 | 04 SSV | 675860437 | 04 Lead Time Comments | 675860566 | 04 Lead Time | 675860586 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860618
3550514 | 675859081 | 04 SSV | 675860437 | 04 Lead Time Comments | 675860566 | 04 Lead Time | 675860586 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860669
3550514 | 675859081 | 05 SSV Confirmed By NDO Technical Leader | 675859708 | 05 Lead Time Comments | 675859800 | 05 Lead Time | 675859816 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859825
3550514 | 675859081 | 06 Tuning | 675860708 | 06 Lead Time Comments | 675860812 | 06 Lead Time | 675860826 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860841
3550514 | 675859081 | 06 Tuning | 675860708 | 06 Lead Time Comments | 675860812 | 06 Lead Time | 675860826 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860869
3550515 | 675859082 | 01 Installation End | 675859828 | 01 Lead Time Comments | 675859950 | 01 Lead Time | 675859973 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859992
3550515 | 675859082 | 02 Integration | 675860020 | 02 Lead Time Comments | 675860142 | 02 Lead Time | 675860167 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860191
3550515 | 675859082 | 02 Integration | 675860020 | 02 Lead Time Comments | 675860142 | 02 Lead Time | 675860167 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860231
3550515 | 675859082 | 03 Integration Confirmed By NRO Technical Leader | 675859366 | 03 Lead Time Comments | 675859465 | 03 Lead Time | 675859481 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859495
3550515 | 675859082 | 04 SSV | 675860284 | 04 Lead Time Comments | 675860418 | 04 Lead Time | 675860454 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860475
3550515 | 675859082 | 04 SSV | 675860284 | 04 Lead Time Comments | 675860418 | 04 Lead Time | 675860454 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860505
3550515 | 675859082 | 05 SSV Confirmed By NDO Technical Leader | 675859539 | 05 Lead Time Comments | 675859657 | 05 Lead Time | 675859681 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859695
3550515 | 675859082 | 06 Tuning | 675860537 | 06 Lead Time Comments | 675860658 | 06 Lead Time | 675860677 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860695
3550515 | 675859082 | 06 Tuning | 675860537 | 06 Lead Time Comments | 675860658 | 06 Lead Time | 675860677 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860721
3550516 | 675859083 | 01 Installation End | 675859802 | 01 Lead Time Comments | 675859897 | 01 Lead Time | 675859925 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859953
3550516 | 675859083 | 02 Integration | 675859999 | 02 Lead Time Comments | 675860098 | 02 Lead Time | 675860136 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860157
3550516 | 675859083 | 02 Integration | 675859999 | 02 Lead Time Comments | 675860098 | 02 Lead Time | 675860136 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860204
3550516 | 675859083 | 03 Integration Confirmed By NRO Technical Leader | 675859360 | 03 Lead Time Comments | 675859458 | 03 Lead Time | 675859476 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859493
3550516 | 675859083 | 04 SSV | 675860246 | 04 Lead Time Comments | 675860391 | 04 Lead Time | 675860417 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860453
3550516 | 675859083 | 04 SSV | 675860246 | 04 Lead Time Comments | 675860391 | 04 Lead Time | 675860417 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860493
3550516 | 675859083 | 05 SSV Confirmed By NDO Technical Leader | 675859531 | 05 Lead Time Comments | 675859650 | 05 Lead Time | 675859664 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859677
3550516 | 675859083 | 06 Tuning | 675860527 | 06 Lead Time Comments | 675860653 | 06 Lead Time | 675860675 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860692
3550516 | 675859083 | 06 Tuning | 675860527 | 06 Lead Time Comments | 675860653 | 06 Lead Time | 675860675 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860727
3550517 | 675859080 | 01 Installation End | 675859905 | 01 Lead Time Comments | 675860028 | 01 Lead Time | 675860047 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860057
3550517 | 675859080 | 02 Integration | 675860090 | 02 Lead Time Comments | 675860237 | 02 Lead Time | 675860251 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860276
3550517 | 675859080 | 02 Integration | 675860090 | 02 Lead Time Comments | 675860237 | 02 Lead Time | 675860251 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860309
3550517 | 675859080 | 03 Integration Confirmed By NRO Technical Leader | 675859489 | 03 Lead Time Comments | 675859609 | 03 Lead Time | 675859617 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859628
3550517 | 675859080 | 04 SSV | 675860350 | 04 Lead Time Comments | 675860489 | 04 Lead Time | 675860503 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860522
3550517 | 675859080 | 04 SSV | 675860350 | 04 Lead Time Comments | 675860489 | 04 Lead Time | 675860503 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860546
3550517 | 675859080 | 05 SSV Confirmed By NDO Technical Leader | 675859665 | 05 Lead Time Comments | 675859750 | 05 Lead Time | 675859765 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859782
3550517 | 675859080 | 06 Tuning | 675860592 | 06 Lead Time Comments | 675860717 | 06 Lead Time | 675860732 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860749
3550517 | 675859080 | 06 Tuning | 675860592 | 06 Lead Time Comments | 675860717 | 06 Lead Time | 675860732 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860781
3550518 | 675859085 | 01 Installation End | 675859735 | 01 Lead Time Comments | 675859826 | 01 Lead Time | 675859840 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859860
3550518 | 675859085 | 02 Integration | 675859906 | 02 Lead Time Comments | 675860045 | 02 Lead Time | 675860058 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860066
3550518 | 675859085 | 02 Integration | 675859906 | 02 Lead Time Comments | 675860045 | 02 Lead Time | 675860058 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860137
3550518 | 675859085 | 03 Integration Confirmed By NRO Technical Leader | 675859318 | 03 Lead Time Comments | 675859408 | 03 Lead Time | 675859422 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859439
3550518 | 675859085 | 04 SSV | 675860194 | 04 Lead Time Comments | 675860334 | 04 Lead Time | 675860352 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860364
3550518 | 675859085 | 04 SSV | 675860194 | 04 Lead Time Comments | 675860334 | 04 Lead Time | 675860352 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860400
3550518 | 675859085 | 05 SSV Confirmed By NDO Technical Leader | 675859480 | 05 Lead Time Comments | 675859579 | 05 Lead Time | 675859607 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859616
3550518 | 675859085 | 06 Tuning | 675860462 | 06 Lead Time Comments | 675860567 | 06 Lead Time | 675860585 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860607
3550518 | 675859085 | 06 Tuning | 675860462 | 06 Lead Time Comments | 675860567 | 06 Lead Time | 675860585 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860652
3550519 | 675859087 | 01 Installation End | 675859803 | 01 Lead Time Comments | 675859894 | 01 Lead Time | 675859911 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675859945
3550519 | 675859087 | 02 Integration | 675859994 | 02 Lead Time Comments | 675860095 | 02 Lead Time | 675860111 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860134
3550519 | 675859087 | 02 Integration | 675859994 | 02 Lead Time Comments | 675860095 | 02 Lead Time | 675860111 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860175
3550519 | 675859087 | 03 Integration Confirmed By NRO Technical Leader | 675859368 | 03 Lead Time Comments | 675859461 | 03 Lead Time | 675859478 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859496
3550519 | 675859087 | 04 SSV | 675860221 | 04 Lead Time Comments | 675860349 | 04 Lead Time | 675860361 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860378
3550519 | 675859087 | 04 SSV | 675860221 | 04 Lead Time Comments | 675860349 | 04 Lead Time | 675860361 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860415
3550519 | 675859087 | 05 SSV Confirmed By NDO Technical Leader | 675859541 | 05 Lead Time Comments | 675859646 | 05 Lead Time | 675859663 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859676
3550519 | 675859087 | 06 Tuning | 675860480 | 06 Lead Time Comments | 675860591 | 06 Lead Time | 675860612 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860639
3550519 | 675859087 | 06 Tuning | 675860480 | 06 Lead Time Comments | 675860591 | 06 Lead Time | 675860612 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860679
3550520 | 675859086 | 01 Installation End | 675859995 | 01 Lead Time Comments | 675860091 | 01 Lead Time | 675860108 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860126
3550520 | 675859086 | 02 Integration | 675860177 | 02 Lead Time Comments | 675860301 | 02 Lead Time | 675860321 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860339
3550520 | 675859086 | 02 Integration | 675860177 | 02 Lead Time Comments | 675860301 | 02 Lead Time | 675860321 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860366
3550520 | 675859086 | 03 Integration Confirmed By NRO Technical Leader | 675859537 | 03 Lead Time Comments | 675859649 | 03 Lead Time | 675859662 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859674
3550520 | 675859086 | 04 SSV | 675860412 | 04 Lead Time Comments | 675860571 | 04 Lead Time | 675860589 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860620
3550520 | 675859086 | 04 SSV | 675860412 | 04 Lead Time Comments | 675860571 | 04 Lead Time | 675860589 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860665
3550520 | 675859086 | 05 SSV Confirmed By NDO Technical Leader | 675859709 | 05 Lead Time Comments | 675859798 | 05 Lead Time | 675859810 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859821
3550520 | 675859086 | 06 Tuning | 675860706 | 06 Lead Time Comments | 675860806 | 06 Lead Time | 675860822 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860839
3550520 | 675859086 | 06 Tuning | 675860706 | 06 Lead Time Comments | 675860806 | 06 Lead Time | 675860822 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860867
3550521 | 675859117 | 01 Installation End | 675859841 | 01 Lead Time Comments | 675859968 | 01 Lead Time | 675859987 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860005
3550521 | 675859117 | 02 Integration | 675860021 | 02 Lead Time Comments | 675860145 | 02 Lead Time | 675860165 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860189
3550521 | 675859117 | 02 Integration | 675860021 | 02 Lead Time Comments | 675860145 | 02 Lead Time | 675860165 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860227
3550521 | 675859117 | 03 Integration Confirmed By NRO Technical Leader | 675859386 | 03 Lead Time Comments | 675859483 | 03 Lead Time | 675859499 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859520
3550521 | 675859117 | 04 SSV | 675860275 | 04 Lead Time Comments | 675860408 | 04 Lead Time | 675860431 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860458
3550521 | 675859117 | 04 SSV | 675860275 | 04 Lead Time Comments | 675860408 | 04 Lead Time | 675860431 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860496
3550521 | 675859117 | 05 SSV Confirmed By NDO Technical Leader | 675859555 | 05 Lead Time Comments | 675859679 | 05 Lead Time | 675859692 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859702
3550521 | 675859117 | 06 Tuning | 675860528 | 06 Lead Time Comments | 675860646 | 06 Lead Time | 675860670 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860685
3550521 | 675859117 | 06 Tuning | 675860528 | 06 Lead Time Comments | 675860646 | 06 Lead Time | 675860670 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860714
3550522 | 675859140 | 01 Installation End | 675860051 | 01 Lead Time Comments | 675860169 | 01 Lead Time | 675860192 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860213
3550522 | 675859140 | 02 Integration | 675860257 | 02 Lead Time Comments | 675860380 | 02 Lead Time | 675860405 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860433
3550522 | 675859140 | 02 Integration | 675860257 | 02 Lead Time Comments | 675860380 | 02 Lead Time | 675860405 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860481
3550522 | 675859140 | 03 Integration Confirmed By NRO Technical Leader | 675859569 | 03 Lead Time Comments | 675859678 | 03 Lead Time | 675859693 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859704
3550522 | 675859140 | 04 SSV | 675860517 | 04 Lead Time Comments | 675860641 | 04 Lead Time | 675860662 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860681
3550522 | 675859140 | 04 SSV | 675860517 | 04 Lead Time Comments | 675860641 | 04 Lead Time | 675860662 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860726
3550522 | 675859140 | 05 SSV Confirmed By NDO Technical Leader | 675859746 | 05 Lead Time Comments | 675859831 | 05 Lead Time | 675859846 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859873
3550522 | 675859140 | 06 Tuning | 675860759 | 06 Lead Time Comments | 675860857 | 06 Lead Time | 675860876 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860912
3550522 | 675859140 | 06 Tuning | 675860759 | 06 Lead Time Comments | 675860857 | 06 Lead Time | 675860876 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860947
3550523 | 675859145 | 01 Installation End | 675860088 | 01 Lead Time Comments | 675860209 | 01 Lead Time | 675860233 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860247
3550523 | 675859145 | 02 Integration | 675860291 | 02 Lead Time Comments | 675860461 | 02 Lead Time | 675860484 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860515
3550523 | 675859145 | 02 Integration | 675860291 | 02 Lead Time Comments | 675860461 | 02 Lead Time | 675860484 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860541
3550523 | 675859145 | 03 Integration Confirmed By NRO Technical Leader | 675859622 | 03 Lead Time Comments | 675859721 | 03 Lead Time | 675859736 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859757
3550523 | 675859145 | 04 SSV | 675860582 | 04 Lead Time Comments | 675860710 | 04 Lead Time | 675860722 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860734
3550523 | 675859145 | 04 SSV | 675860582 | 04 Lead Time Comments | 675860710 | 04 Lead Time | 675860722 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860763
3550523 | 675859145 | 05 SSV Confirmed By NDO Technical Leader | 675859791 | 05 Lead Time Comments | 675859882 | 05 Lead Time | 675859898 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859935
3550523 | 675859145 | 06 Tuning | 675860808 | 06 Lead Time Comments | 675860938 | 06 Lead Time | 675860953 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860966
3550523 | 675859145 | 06 Tuning | 675860808 | 06 Lead Time Comments | 675860938 | 06 Lead Time | 675860953 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860986
3550524 | 675859167 | 01 Installation End | 675860307 | 01 Lead Time Comments | 675860429 | 01 Lead Time | 675860457 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860476
3550524 | 675859167 | 02 Integration | 675860507 | 02 Lead Time Comments | 675860622 | 02 Lead Time | 675860651 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860674
3550524 | 675859167 | 02 Integration | 675860507 | 02 Lead Time Comments | 675860622 | 02 Lead Time | 675860651 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860703
3550524 | 675859167 | 03 Integration Confirmed By NRO Technical Leader | 675859783 | 03 Lead Time Comments | 675859884 | 03 Lead Time | 675859900 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859933
3550524 | 675859167 | 04 SSV | 675860738 | 04 Lead Time Comments | 675860856 | 04 Lead Time | 675860878 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860913
3550524 | 675859167 | 04 SSV | 675860738 | 04 Lead Time Comments | 675860856 | 04 Lead Time | 675860878 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860948
3550524 | 675859167 | 05 SSV Confirmed By NDO Technical Leader | 675859979 | 05 Lead Time Comments | 675860082 | 05 Lead Time | 675860107 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860129
3550524 | 675859167 | 06 Tuning | 675860978 | 06 Lead Time Comments | 675861066 | 06 Lead Time | 675861081 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861100
3550524 | 675859167 | 06 Tuning | 675860978 | 06 Lead Time Comments | 675861066 | 06 Lead Time | 675861081 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861121
3550525 | 675859168 | 01 Installation End | 675860249 | 01 Lead Time Comments | 675860357 | 01 Lead Time | 675860371 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860392
3550525 | 675859168 | 02 Integration | 675860445 | 02 Lead Time Comments | 675860556 | 02 Lead Time | 675860573 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860590
3550525 | 675859168 | 02 Integration | 675860445 | 02 Lead Time Comments | 675860556 | 02 Lead Time | 675860573 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860625
3550525 | 675859168 | 03 Integration Confirmed By NRO Technical Leader | 675859767 | 03 Lead Time Comments | 675859850 | 03 Lead Time | 675859869 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859886
3550525 | 675859168 | 04 SSV | 675860671 | 04 Lead Time Comments | 675860771 | 04 Lead Time | 675860787 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860805
3550525 | 675859168 | 04 SSV | 675860671 | 04 Lead Time Comments | 675860771 | 04 Lead Time | 675860787 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860833
3550525 | 675859168 | 05 SSV Confirmed By NDO Technical Leader | 675859941 | 05 Lead Time Comments | 675860055 | 05 Lead Time | 675860065 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860079
3550525 | 675859168 | 06 Tuning | 675860868 | 06 Lead Time Comments | 675860997 | 06 Lead Time | 675861009 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861019
3550525 | 675859168 | 06 Tuning | 675860868 | 06 Lead Time Comments | 675860997 | 06 Lead Time | 675861009 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861049
3550526 | 675859166 | 01 Installation End | 675860093 | 01 Lead Time Comments | 675860216 | 01 Lead Time | 675860241 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860254
3550526 | 675859166 | 02 Integration | 675860299 | 02 Lead Time Comments | 675860450 | 02 Lead Time | 675860472 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860492
3550526 | 675859166 | 02 Integration | 675860299 | 02 Lead Time Comments | 675860450 | 02 Lead Time | 675860472 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860520
3550526 | 675859166 | 03 Integration Confirmed By NRO Technical Leader | 675859606 | 03 Lead Time Comments | 675859691 | 03 Lead Time | 675859699 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859718
3550526 | 675859166 | 04 SSV | 675860550 | 04 Lead Time Comments | 675860683 | 04 Lead Time | 675860700 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860715
3550526 | 675859166 | 04 SSV | 675860550 | 04 Lead Time Comments | 675860683 | 04 Lead Time | 675860700 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860743
3550526 | 675859166 | 05 SSV Confirmed By NDO Technical Leader | 675859760 | 05 Lead Time Comments | 675859847 | 05 Lead Time | 675859871 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859888
3550526 | 675859166 | 06 Tuning | 675860785 | 06 Lead Time Comments | 675860884 | 06 Lead Time | 675860923 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860944
3550526 | 675859166 | 06 Tuning | 675860785 | 06 Lead Time Comments | 675860884 | 06 Lead Time | 675860923 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860973
3550527 | 675859169 | 01 Installation End | 675860285 | 01 Lead Time Comments | 675860395 | 01 Lead Time | 675860416 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860452
3550527 | 675859169 | 02 Integration | 675860499 | 02 Lead Time Comments | 675860600 | 02 Lead Time | 675860619 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860644
3550527 | 675859169 | 02 Integration | 675860499 | 02 Lead Time Comments | 675860600 | 02 Lead Time | 675860619 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860680
3550527 | 675859169 | 03 Integration Confirmed By NRO Technical Leader | 675859759 | 03 Lead Time Comments | 675859848 | 03 Lead Time | 675859872 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859890
3550527 | 675859169 | 04 SSV | 675860713 | 04 Lead Time Comments | 675860816 | 04 Lead Time | 675860829 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860845
3550527 | 675859169 | 04 SSV | 675860713 | 04 Lead Time Comments | 675860816 | 04 Lead Time | 675860829 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860875
3550527 | 675859169 | 05 SSV Confirmed By NDO Technical Leader | 675859951 | 05 Lead Time Comments | 675860070 | 05 Lead Time | 675860085 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860110
3550527 | 675859169 | 06 Tuning | 675860943 | 06 Lead Time Comments | 675861037 | 06 Lead Time | 675861054 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861068
3550527 | 675859169 | 06 Tuning | 675860943 | 06 Lead Time Comments | 675861037 | 06 Lead Time | 675861054 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861104
3550528 | 675859175 | 01 Installation End | 675860272 | 01 Lead Time Comments | 675860382 | 01 Lead Time | 675860407 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860436
3550528 | 675859175 | 02 Integration | 675860491 | 02 Lead Time Comments | 675860597 | 02 Lead Time | 675860636 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860655
3550528 | 675859175 | 02 Integration | 675860491 | 02 Lead Time Comments | 675860597 | 02 Lead Time | 675860636 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860688
3550528 | 675859175 | 03 Integration Confirmed By NRO Technical Leader | 675859754 | 03 Lead Time Comments | 675859837 | 03 Lead Time | 675859855 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859877
3550528 | 675859175 | 04 SSV | 675860737 | 04 Lead Time Comments | 675860847 | 04 Lead Time | 675860858 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860879
3550528 | 675859175 | 04 SSV | 675860737 | 04 Lead Time Comments | 675860847 | 04 Lead Time | 675860858 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860937
3550528 | 675859175 | 05 SSV Confirmed By NDO Technical Leader | 675859942 | 05 Lead Time Comments | 675860059 | 05 Lead Time | 675860069 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860083
3550528 | 675859175 | 06 Tuning | 675860972 | 06 Lead Time Comments | 675861073 | 06 Lead Time | 675861099 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861110
3550528 | 675859175 | 06 Tuning | 675860972 | 06 Lead Time Comments | 675861073 | 06 Lead Time | 675861099 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861136
3550529 | 675859174 | 01 Installation End | 675860263 | 01 Lead Time Comments | 675860379 | 01 Lead Time | 675860396 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860420
3550529 | 675859174 | 02 Integration | 675860478 | 02 Lead Time Comments | 675860581 | 02 Lead Time | 675860599 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860621
3550529 | 675859174 | 02 Integration | 675860478 | 02 Lead Time Comments | 675860581 | 02 Lead Time | 675860599 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860668
3550529 | 675859174 | 03 Integration Confirmed By NRO Technical Leader | 675859772 | 03 Lead Time Comments | 675859852 | 03 Lead Time | 675859876 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859889
3550529 | 675859174 | 04 SSV | 675860702 | 04 Lead Time Comments | 675860811 | 04 Lead Time | 675860825 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860842
3550529 | 675859174 | 04 SSV | 675860702 | 04 Lead Time Comments | 675860811 | 04 Lead Time | 675860825 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860866
3550529 | 675859174 | 05 SSV Confirmed By NDO Technical Leader | 675859946 | 05 Lead Time Comments | 675860063 | 05 Lead Time | 675860073 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860089
3550529 | 675859174 | 06 Tuning | 675860931 | 06 Lead Time Comments | 675861024 | 06 Lead Time | 675861044 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861057
3550529 | 675859174 | 06 Tuning | 675860931 | 06 Lead Time Comments | 675861024 | 06 Lead Time | 675861044 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861087
3550530 | 675859183 | 01 Installation End | 675860096 | 01 Lead Time Comments | 675860228 | 01 Lead Time | 675860244 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860267
3550530 | 675859183 | 02 Integration | 675860306 | 02 Lead Time Comments | 675860448 | 02 Lead Time | 675860471 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860488
3550530 | 675859183 | 02 Integration | 675860306 | 02 Lead Time Comments | 675860448 | 02 Lead Time | 675860471 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860513
3550530 | 675859183 | 03 Integration Confirmed By NRO Technical Leader | 675859608 | 03 Lead Time Comments | 675859726 | 03 Lead Time | 675859739 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859756
3550530 | 675859183 | 04 SSV | 675860543 | 04 Lead Time Comments | 675860693 | 04 Lead Time | 675860704 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860720
3550530 | 675859183 | 04 SSV | 675860543 | 04 Lead Time Comments | 675860693 | 04 Lead Time | 675860704 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860747
3550530 | 675859183 | 05 SSV Confirmed By NDO Technical Leader | 675859790 | 05 Lead Time Comments | 675859883 | 05 Lead Time | 675859901 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675859926
3550530 | 675859183 | 06 Tuning | 675860776 | 06 Lead Time Comments | 675860874 | 06 Lead Time | 675860915 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675860934
3550530 | 675859183 | 06 Tuning | 675860776 | 06 Lead Time Comments | 675860874 | 06 Lead Time | 675860915 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675860965
3550531 | 675859192 | 01 Installation End | 675860219 | 01 Lead Time Comments | 675860327 | 01 Lead Time | 675860345 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860359
3550531 | 675859192 | 02 Integration | 675860403 | 02 Lead Time Comments | 675860533 | 02 Lead Time | 675860547 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860565
3550531 | 675859192 | 02 Integration | 675860403 | 02 Lead Time Comments | 675860533 | 02 Lead Time | 675860547 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860601
3550531 | 675859192 | 03 Integration Confirmed By NRO Technical Leader | 675859740 | 03 Lead Time Comments | 675859833 | 03 Lead Time | 675859844 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675859867
3550531 | 675859192 | 04 SSV | 675860660 | 04 Lead Time Comments | 675860761 | 04 Lead Time | 675860774 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860792
3550531 | 675859192 | 04 SSV | 675860660 | 04 Lead Time Comments | 675860761 | 04 Lead Time | 675860774 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860824
3550531 | 675859192 | 05 SSV Confirmed By NDO Technical Leader | 675859904 | 05 Lead Time Comments | 675860029 | 05 Lead Time | 675860048 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860060
3550531 | 675859192 | 06 Tuning | 675860853 | 06 Lead Time Comments | 675860980 | 06 Lead Time | 675860994 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861003
3550531 | 675859192 | 06 Tuning | 675860853 | 06 Lead Time Comments | 675860980 | 06 Lead Time | 675860994 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861022
3550532 | 675859293 | 01 Installation End | 675860442 | 01 Lead Time Comments | 675860538 | 01 Lead Time | 675860553 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860564
3550532 | 675859293 | 02 Integration | 675860606 | 02 Lead Time Comments | 675860723 | 02 Lead Time | 675860735 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860750
3550532 | 675859293 | 02 Integration | 675860606 | 02 Lead Time Comments | 675860723 | 02 Lead Time | 675860735 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860778
3550532 | 675859293 | 03 Integration Confirmed By NRO Technical Leader | 675859934 | 03 Lead Time Comments | 675860046 | 03 Lead Time | 675860054 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860074
3550532 | 675859293 | 04 SSV | 675860820 | 04 Lead Time Comments | 675860956 | 04 Lead Time | 675860971 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860981
3550532 | 675859293 | 04 SSV | 675860820 | 04 Lead Time Comments | 675860956 | 04 Lead Time | 675860971 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861004
3550532 | 675859293 | 05 SSV Confirmed By NDO Technical Leader | 675860117 | 05 Lead Time Comments | 675860238 | 05 Lead Time | 675860250 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860274
3550532 | 675859293 | 06 Tuning | 675861033 | 06 Lead Time Comments | 675861126 | 06 Lead Time | 675861137 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861144
3550532 | 675859293 | 06 Tuning | 675861033 | 06 Lead Time Comments | 675861126 | 06 Lead Time | 675861137 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861168
3550533 | 675859294 | 01 Installation End | 675860427 | 01 Lead Time Comments | 675860536 | 01 Lead Time | 675860569 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860584
3550533 | 675859294 | 02 Integration | 675860642 | 02 Lead Time Comments | 675860741 | 02 Lead Time | 675860760 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860773
3550533 | 675859294 | 02 Integration | 675860642 | 02 Lead Time Comments | 675860741 | 02 Lead Time | 675860760 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860807
3550533 | 675859294 | 03 Integration Confirmed By NRO Technical Leader | 675859836 | 03 Lead Time Comments | 675859958 | 03 Lead Time | 675860032 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860050
3550533 | 675859294 | 04 SSV | 675860846 | 04 Lead Time Comments | 675860968 | 04 Lead Time | 675861000 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861008
3550533 | 675859294 | 04 SSV | 675860846 | 04 Lead Time Comments | 675860968 | 04 Lead Time | 675861000 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861032
3550533 | 675859294 | 05 SSV Confirmed By NDO Technical Leader | 675860080 | 05 Lead Time Comments | 675860215 | 05 Lead Time | 675860240 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860252
3550533 | 675859294 | 06 Tuning | 675861067 | 06 Lead Time Comments | 675861159 | 06 Lead Time | 675861170 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861181
3550533 | 675859294 | 06 Tuning | 675861067 | 06 Lead Time Comments | 675861159 | 06 Lead Time | 675861170 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861204
3550534 | 675859295 | 01 Installation End | 675860512 | 01 Lead Time Comments | 675860604 | 01 Lead Time | 675860626 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860648
3550534 | 675859295 | 02 Integration | 675860689 | 02 Lead Time Comments | 675860794 | 02 Lead Time | 675860813 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860836
3550534 | 675859295 | 02 Integration | 675860689 | 02 Lead Time Comments | 675860794 | 02 Lead Time | 675860813 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860865
3550534 | 675859295 | 03 Integration Confirmed By NRO Technical Leader | 675860002 | 03 Lead Time Comments | 675860102 | 03 Lead Time | 675860122 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860149
3550534 | 675859295 | 04 SSV | 675860930 | 04 Lead Time Comments | 675861034 | 04 Lead Time | 675861051 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861065
3550534 | 675859295 | 04 SSV | 675860930 | 04 Lead Time Comments | 675861034 | 04 Lead Time | 675861051 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861095
3550534 | 675859295 | 05 SSV Confirmed By NDO Technical Leader | 675860201 | 05 Lead Time Comments | 675860316 | 05 Lead Time | 675860335 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860353
3550534 | 675859295 | 06 Tuning | 675861129 | 06 Lead Time Comments | 675861203 | 06 Lead Time | 675861211 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861220
3550534 | 675859295 | 06 Tuning | 675861129 | 06 Lead Time Comments | 675861203 | 06 Lead Time | 675861211 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861232
3550535 | 675859304 | 01 Installation End | 675860340 | 01 Lead Time Comments | 675860455 | 01 Lead Time | 675860497 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860506
3550535 | 675859304 | 02 Integration | 675860542 | 02 Lead Time Comments | 675860673 | 02 Lead Time | 675860690 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860705
3550535 | 675859304 | 02 Integration | 675860542 | 02 Lead Time Comments | 675860673 | 02 Lead Time | 675860690 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860731
3550535 | 675859304 | 03 Integration Confirmed By NRO Technical Leader | 675859870 | 03 Lead Time Comments | 675859990 | 03 Lead Time | 675860007 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860016
3550535 | 675859304 | 04 SSV | 675860768 | 04 Lead Time Comments | 675860873 | 04 Lead Time | 675860900 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675860928
3550535 | 675859304 | 04 SSV | 675860768 | 04 Lead Time Comments | 675860873 | 04 Lead Time | 675860900 | actcl--04 SSV--04 Lead Time Comments--Duration | 675860962
3550535 | 675859304 | 05 SSV Confirmed By NDO Technical Leader | 675860030 | 05 Lead Time Comments | 675860143 | 05 Lead Time | 675860164 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860184
3550535 | 675859304 | 06 Tuning | 675860984 | 06 Lead Time Comments | 675861069 | 06 Lead Time | 675861083 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861102
3550535 | 675859304 | 06 Tuning | 675860984 | 06 Lead Time Comments | 675861069 | 06 Lead Time | 675861083 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861127
3550536 | 675859351 | 01 Installation End | 675861187 | 01 Lead Time Comments | 675861235 | 01 Lead Time | 675861251 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861262
3550536 | 675859351 | 02 Integration | 675861285 | 02 Lead Time Comments | 675861362 | 02 Lead Time | 675861371 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861375
3550536 | 675859351 | 02 Integration | 675861285 | 02 Lead Time Comments | 675861362 | 02 Lead Time | 675861371 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861388
3550536 | 675859351 | 03 Integration Confirmed By NRO Technical Leader | 675860802 | 03 Lead Time Comments | 675860914 | 03 Lead Time | 675860932 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860952
3550536 | 675859351 | 04 SSV | 675861403 | 04 Lead Time Comments | 675861452 | 04 Lead Time | 675861464 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861469
3550536 | 675859351 | 04 SSV | 675861403 | 04 Lead Time Comments | 675861452 | 04 Lead Time | 675861464 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861480
3550536 | 675859351 | 05 SSV Confirmed By NDO Technical Leader | 675860988 | 05 Lead Time Comments | 675861059 | 05 Lead Time | 675861077 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861090
3550536 | 675859351 | 06 Tuning | 675861498 | 06 Lead Time Comments | 675861532 | 06 Lead Time | 675861543 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861559
3550536 | 675859351 | 06 Tuning | 675861498 | 06 Lead Time Comments | 675861532 | 06 Lead Time | 675861543 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861580
3550537 | 675859352 | 01 Installation End | 675860514 | 01 Lead Time Comments | 675860611 | 01 Lead Time | 675860635 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860656
3550537 | 675859352 | 02 Integration | 675860698 | 02 Lead Time Comments | 675860804 | 02 Lead Time | 675860819 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860837
3550537 | 675859352 | 02 Integration | 675860698 | 02 Lead Time Comments | 675860804 | 02 Lead Time | 675860819 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860863
3550537 | 675859352 | 03 Integration Confirmed By NRO Technical Leader | 675860012 | 03 Lead Time Comments | 675860105 | 03 Lead Time | 675860123 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860148
3550537 | 675859352 | 04 SSV | 675860924 | 04 Lead Time Comments | 675861031 | 04 Lead Time | 675861048 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861064
3550537 | 675859352 | 04 SSV | 675860924 | 04 Lead Time Comments | 675861031 | 04 Lead Time | 675861048 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861093
3550537 | 675859352 | 05 SSV Confirmed By NDO Technical Leader | 675860198 | 05 Lead Time Comments | 675860304 | 05 Lead Time | 675860322 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860342
3550537 | 675859352 | 06 Tuning | 675861128 | 06 Lead Time Comments | 675861205 | 06 Lead Time | 675861212 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861219
3550537 | 675859352 | 06 Tuning | 675861128 | 06 Lead Time Comments | 675861205 | 06 Lead Time | 675861212 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861239
3550538 | 675859364 | 01 Installation End | 675862155 | 01 Lead Time Comments | 675862196 | 01 Lead Time | 675862206 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862220
3550538 | 675859364 | 02 Integration | 675862243 | 02 Lead Time Comments | 675862310 | 02 Lead Time | 675862326 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862341
3550538 | 675859364 | 02 Integration | 675862243 | 02 Lead Time Comments | 675862310 | 02 Lead Time | 675862326 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862358
3550538 | 675859364 | 03 Integration Confirmed By NRO Technical Leader | 675861937 | 03 Lead Time Comments | 675861975 | 03 Lead Time | 675861988 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862002
3550538 | 675859364 | 04 SSV | 675862374 | 04 Lead Time Comments | 675862428 | 04 Lead Time | 675862444 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862461
3550538 | 675859364 | 04 SSV | 675862374 | 04 Lead Time Comments | 675862428 | 04 Lead Time | 675862444 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862491
3550538 | 675859364 | 05 SSV Confirmed By NDO Technical Leader | 675862024 | 05 Lead Time Comments | 675862064 | 05 Lead Time | 675862080 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862095
3550538 | 675859364 | 06 Tuning | 675862516 | 06 Lead Time Comments | 675862591 | 06 Lead Time | 675862620 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862638
3550538 | 675859364 | 06 Tuning | 675862516 | 06 Lead Time Comments | 675862591 | 06 Lead Time | 675862620 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862670
3550539 | 675859367 | 01 Installation End | 675861787 | 01 Lead Time Comments | 675861796 | 01 Lead Time | 675861801 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861806
3550539 | 675859367 | 02 Integration | 675861810 | 02 Lead Time Comments | 675861821 | 02 Lead Time | 675861826 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861829
3550539 | 675859367 | 02 Integration | 675861810 | 02 Lead Time Comments | 675861821 | 02 Lead Time | 675861826 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861832
3550539 | 675859367 | 03 Integration Confirmed By NRO Technical Leader | 675861687 | 03 Lead Time Comments | 675861716 | 03 Lead Time | 675861724 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861733
3550539 | 675859367 | 04 SSV | 675861839 | 04 Lead Time Comments | 675861855 | 04 Lead Time | 675861858 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861860
3550539 | 675859367 | 04 SSV | 675861839 | 04 Lead Time Comments | 675861855 | 04 Lead Time | 675861858 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861863
3550539 | 675859367 | 05 SSV Confirmed By NDO Technical Leader | 675861744 | 05 Lead Time Comments | 675861768 | 05 Lead Time | 675861772 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861773
3550539 | 675859367 | 06 Tuning | 675861867 | 06 Lead Time Comments | 675861876 | 06 Lead Time | 675861878 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861882
3550539 | 675859367 | 06 Tuning | 675861867 | 06 Lead Time Comments | 675861876 | 06 Lead Time | 675861878 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861885
3550540 | 675859369 | 01 Installation End | 675860562 | 01 Lead Time Comments | 675860684 | 01 Lead Time | 675860699 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860712
3550540 | 675859369 | 02 Integration | 675860744 | 02 Lead Time Comments | 675860850 | 02 Lead Time | 675860862 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860882
3550540 | 675859369 | 02 Integration | 675860744 | 02 Lead Time Comments | 675860850 | 02 Lead Time | 675860862 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860940
3550540 | 675859369 | 03 Integration Confirmed By NRO Technical Leader | 675860035 | 03 Lead Time Comments | 675860160 | 03 Lead Time | 675860203 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860220
3550540 | 675859369 | 04 SSV | 675860975 | 04 Lead Time Comments | 675861076 | 04 Lead Time | 675861092 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861106
3550540 | 675859369 | 04 SSV | 675860975 | 04 Lead Time Comments | 675861076 | 04 Lead Time | 675861092 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861132
3550540 | 675859369 | 05 SSV Confirmed By NDO Technical Leader | 675860261 | 05 Lead Time Comments | 675860369 | 05 Lead Time | 675860388 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860409
3550540 | 675859369 | 06 Tuning | 675861152 | 06 Lead Time Comments | 675861216 | 06 Lead Time | 675861223 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861229
3550540 | 675859369 | 06 Tuning | 675861152 | 06 Lead Time Comments | 675861216 | 06 Lead Time | 675861223 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861244
3550541 | 675859379 | 01 Installation End | 675861173 | 01 Lead Time Comments | 675861222 | 01 Lead Time | 675861228 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861236
3550541 | 675859379 | 02 Integration | 675861259 | 02 Lead Time Comments | 675861324 | 02 Lead Time | 675861328 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861336
3550541 | 675859379 | 02 Integration | 675861259 | 02 Lead Time Comments | 675861324 | 02 Lead Time | 675861328 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861349
3550541 | 675859379 | 03 Integration Confirmed By NRO Technical Leader | 675860782 | 03 Lead Time Comments | 675860864 | 03 Lead Time | 675860881 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860919
3550541 | 675859379 | 04 SSV | 675861364 | 04 Lead Time Comments | 675861402 | 04 Lead Time | 675861410 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861420
3550541 | 675859379 | 04 SSV | 675861364 | 04 Lead Time Comments | 675861402 | 04 Lead Time | 675861410 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861431
3550541 | 675859379 | 05 SSV Confirmed By NDO Technical Leader | 675860960 | 05 Lead Time Comments | 675861036 | 05 Lead Time | 675861050 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861061
3550541 | 675859379 | 06 Tuning | 675861448 | 06 Lead Time Comments | 675861493 | 06 Lead Time | 675861501 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861507
3550541 | 675859379 | 06 Tuning | 675861448 | 06 Lead Time Comments | 675861493 | 06 Lead Time | 675861501 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861516
3550542 | 675859390 | 01 Installation End | 675861082 | 01 Lead Time Comments | 675861153 | 01 Lead Time | 675861163 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861177
3550542 | 675859390 | 02 Integration | 675861202 | 02 Lead Time Comments | 675861252 | 02 Lead Time | 675861263 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861275
3550542 | 675859390 | 02 Integration | 675861202 | 02 Lead Time Comments | 675861252 | 02 Lead Time | 675861263 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861287
3550542 | 675859390 | 03 Integration Confirmed By NRO Technical Leader | 675860687 | 03 Lead Time Comments | 675860769 | 03 Lead Time | 675860784 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860801
3550542 | 675859390 | 04 SSV | 675861316 | 04 Lead Time Comments | 675861358 | 04 Lead Time | 675861365 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861370
3550542 | 675859390 | 04 SSV | 675861316 | 04 Lead Time Comments | 675861358 | 04 Lead Time | 675861365 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861378
3550542 | 675859390 | 05 SSV Confirmed By NDO Technical Leader | 675860830 | 05 Lead Time Comments | 675860941 | 05 Lead Time | 675860955 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860969
3550542 | 675859390 | 06 Tuning | 675861395 | 06 Lead Time Comments | 675861437 | 06 Lead Time | 675861441 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861462
3550542 | 675859390 | 06 Tuning | 675861395 | 06 Lead Time Comments | 675861437 | 06 Lead Time | 675861441 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861474
3550543 | 675859391 | 01 Installation End | 675861183 | 01 Lead Time Comments | 675861233 | 01 Lead Time | 675861241 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861250
3550543 | 675859391 | 02 Integration | 675861278 | 02 Lead Time Comments | 675861360 | 02 Lead Time | 675861369 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861372
3550543 | 675859391 | 02 Integration | 675861278 | 02 Lead Time Comments | 675861360 | 02 Lead Time | 675861369 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861381
3550543 | 675859391 | 03 Integration Confirmed By NRO Technical Leader | 675860821 | 03 Lead Time Comments | 675860935 | 03 Lead Time | 675860949 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860964
3550543 | 675859391 | 04 SSV | 675861401 | 04 Lead Time Comments | 675861450 | 04 Lead Time | 675861466 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861470
3550543 | 675859391 | 04 SSV | 675861401 | 04 Lead Time Comments | 675861450 | 04 Lead Time | 675861466 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861479
3550543 | 675859391 | 05 SSV Confirmed By NDO Technical Leader | 675860989 | 05 Lead Time Comments | 675861063 | 05 Lead Time | 675861079 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861091
3550543 | 675859391 | 06 Tuning | 675861499 | 06 Lead Time Comments | 675861535 | 06 Lead Time | 675861546 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861554
3550543 | 675859391 | 06 Tuning | 675861499 | 06 Lead Time Comments | 675861535 | 06 Lead Time | 675861546 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861568
3550544 | 675859395 | 01 Installation End | 675861166 | 01 Lead Time Comments | 675861225 | 01 Lead Time | 675861231 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861240
3550544 | 675859395 | 02 Integration | 675861266 | 02 Lead Time Comments | 675861335 | 02 Lead Time | 675861338 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861347
3550544 | 675859395 | 02 Integration | 675861266 | 02 Lead Time Comments | 675861335 | 02 Lead Time | 675861338 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861359
3550544 | 675859395 | 03 Integration Confirmed By NRO Technical Leader | 675860762 | 03 Lead Time Comments | 675860855 | 03 Lead Time | 675860871 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860896
3550544 | 675859395 | 04 SSV | 675861373 | 04 Lead Time Comments | 675861424 | 04 Lead Time | 675861430 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861436
3550544 | 675859395 | 04 SSV | 675861373 | 04 Lead Time Comments | 675861424 | 04 Lead Time | 675861430 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861449
3550544 | 675859395 | 05 SSV Confirmed By NDO Technical Leader | 675860950 | 05 Lead Time Comments | 675861029 | 05 Lead Time | 675861045 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861058
3550544 | 675859395 | 06 Tuning | 675861471 | 06 Lead Time Comments | 675861519 | 06 Lead Time | 675861522 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861528
3550544 | 675859395 | 06 Tuning | 675861471 | 06 Lead Time Comments | 675861519 | 06 Lead Time | 675861522 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861540
3550545 | 675859396 | 01 Installation End | 675862165 | 01 Lead Time Comments | 675862210 | 01 Lead Time | 675862226 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862236
3550545 | 675859396 | 02 Integration | 675862261 | 02 Lead Time Comments | 675862312 | 02 Lead Time | 675862318 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862332
3550545 | 675859396 | 02 Integration | 675862261 | 02 Lead Time Comments | 675862312 | 02 Lead Time | 675862318 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862357
3550545 | 675859396 | 03 Integration Confirmed By NRO Technical Leader | 675861953 | 03 Lead Time Comments | 675861978 | 03 Lead Time | 675861990 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862006
3550545 | 675859396 | 04 SSV | 675862375 | 04 Lead Time Comments | 675862435 | 04 Lead Time | 675862451 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862472
3550545 | 675859396 | 04 SSV | 675862375 | 04 Lead Time Comments | 675862435 | 04 Lead Time | 675862451 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862503
3550545 | 675859396 | 05 SSV Confirmed By NDO Technical Leader | 675862031 | 05 Lead Time Comments | 675862063 | 05 Lead Time | 675862078 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862097
3550545 | 675859396 | 06 Tuning | 675862526 | 06 Lead Time Comments | 675862610 | 06 Lead Time | 675862631 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862650
3550545 | 675859396 | 06 Tuning | 675862526 | 06 Lead Time Comments | 675862610 | 06 Lead Time | 675862631 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862688
3550546 | 675859403 | 01 Installation End | 675861785 | 01 Lead Time Comments | 675861795 | 01 Lead Time | 675861800 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861805
3550546 | 675859403 | 02 Integration | 675861811 | 02 Lead Time Comments | 675861823 | 02 Lead Time | 675861827 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861830
3550546 | 675859403 | 02 Integration | 675861811 | 02 Lead Time Comments | 675861823 | 02 Lead Time | 675861827 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861834
3550546 | 675859403 | 03 Integration Confirmed By NRO Technical Leader | 675861688 | 03 Lead Time Comments | 675861715 | 03 Lead Time | 675861723 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861731
3550546 | 675859403 | 04 SSV | 675861838 | 04 Lead Time Comments | 675861853 | 04 Lead Time | 675861857 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861862
3550546 | 675859403 | 04 SSV | 675861838 | 04 Lead Time Comments | 675861853 | 04 Lead Time | 675861857 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861865
3550546 | 675859403 | 05 SSV Confirmed By NDO Technical Leader | 675861738 | 05 Lead Time Comments | 675861760 | 05 Lead Time | 675861767 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861771
3550546 | 675859403 | 06 Tuning | 675861871 | 06 Lead Time Comments | 675861881 | 06 Lead Time | 675861883 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861886
3550546 | 675859403 | 06 Tuning | 675861871 | 06 Lead Time Comments | 675861881 | 06 Lead Time | 675861883 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861890
3550547 | 675859409 | 01 Installation End | 675860624 | 01 Lead Time Comments | 675860725 | 01 Lead Time | 675860736 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675860753
3550547 | 675859409 | 02 Integration | 675860798 | 02 Lead Time Comments | 675860920 | 02 Lead Time | 675860942 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675860958
3550547 | 675859409 | 02 Integration | 675860798 | 02 Lead Time Comments | 675860920 | 02 Lead Time | 675860942 | actcl--02 Integration--02 Lead Time Comments--Duration | 675860979
3550547 | 675859409 | 03 Integration Confirmed By NRO Technical Leader | 675860121 | 03 Lead Time Comments | 675860256 | 03 Lead Time | 675860273 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860286
3550547 | 675859409 | 04 SSV | 675861005 | 04 Lead Time Comments | 675861105 | 04 Lead Time | 675861117 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861133
3550547 | 675859409 | 04 SSV | 675861005 | 04 Lead Time Comments | 675861105 | 04 Lead Time | 675861117 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861156
3550547 | 675859409 | 05 SSV Confirmed By NDO Technical Leader | 675860328 | 05 Lead Time Comments | 675860447 | 05 Lead Time | 675860468 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675860490
3550547 | 675859409 | 06 Tuning | 675861185 | 06 Lead Time Comments | 675861237 | 06 Lead Time | 675861249 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861260
3550547 | 675859409 | 06 Tuning | 675861185 | 06 Lead Time Comments | 675861237 | 06 Lead Time | 675861249 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861280
3550548 | 675859418 | 01 Installation End | 675861254 | 01 Lead Time Comments | 675861329 | 01 Lead Time | 675861334 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861337
3550548 | 675859418 | 02 Integration | 675861357 | 02 Lead Time Comments | 675861397 | 02 Lead Time | 675861405 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861411
3550548 | 675859418 | 02 Integration | 675861357 | 02 Lead Time Comments | 675861397 | 02 Lead Time | 675861405 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861426
3550548 | 675859418 | 03 Integration Confirmed By NRO Technical Leader | 675860880 | 03 Lead Time Comments | 675861013 | 03 Lead Time | 675861025 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861040
3550548 | 675859418 | 04 SSV | 675861446 | 04 Lead Time Comments | 675861492 | 04 Lead Time | 675861496 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861505
3550548 | 675859418 | 04 SSV | 675861446 | 04 Lead Time Comments | 675861492 | 04 Lead Time | 675861496 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861513
3550548 | 675859418 | 05 SSV Confirmed By NDO Technical Leader | 675861070 | 05 Lead Time Comments | 675861142 | 05 Lead Time | 675861154 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861165
3550548 | 675859418 | 06 Tuning | 675861524 | 06 Lead Time Comments | 675861587 | 06 Lead Time | 675861592 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861597
3550548 | 675859418 | 06 Tuning | 675861524 | 06 Lead Time Comments | 675861587 | 06 Lead Time | 675861592 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861605
3550549 | 675859420 | 01 Installation End | 675861145 | 01 Lead Time Comments | 675861206 | 01 Lead Time | 675861214 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861221
3550549 | 675859420 | 02 Integration | 675861242 | 02 Lead Time Comments | 675861312 | 02 Lead Time | 675861317 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861325
3550549 | 675859420 | 02 Integration | 675861242 | 02 Lead Time Comments | 675861312 | 02 Lead Time | 675861317 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861333
3550549 | 675859420 | 03 Integration Confirmed By NRO Technical Leader | 675860742 | 03 Lead Time Comments | 675860832 | 03 Lead Time | 675860848 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675860859
3550549 | 675859420 | 04 SSV | 675861348 | 04 Lead Time Comments | 675861390 | 04 Lead Time | 675861398 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861404
3550549 | 675859420 | 04 SSV | 675861348 | 04 Lead Time Comments | 675861390 | 04 Lead Time | 675861398 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861418
3550549 | 675859420 | 05 SSV Confirmed By NDO Technical Leader | 675860918 | 05 Lead Time Comments | 675861012 | 05 Lead Time | 675861027 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861043
3550549 | 675859420 | 06 Tuning | 675861434 | 06 Lead Time Comments | 675861478 | 06 Lead Time | 675861485 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861490
3550549 | 675859420 | 06 Tuning | 675861434 | 06 Lead Time Comments | 675861478 | 06 Lead Time | 675861485 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861503
3550550 | 675859432 | 01 Installation End | 675862151 | 01 Lead Time Comments | 675862200 | 01 Lead Time | 675862211 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862230
3550550 | 675859432 | 02 Integration | 675862249 | 02 Lead Time Comments | 675862305 | 02 Lead Time | 675862321 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862337
3550550 | 675859432 | 02 Integration | 675862249 | 02 Lead Time Comments | 675862305 | 02 Lead Time | 675862321 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862356
3550550 | 675859432 | 03 Integration Confirmed By NRO Technical Leader | 675861930 | 03 Lead Time Comments | 675861967 | 03 Lead Time | 675861982 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861996
3550550 | 675859432 | 04 SSV | 675862373 | 04 Lead Time Comments | 675862434 | 04 Lead Time | 675862449 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862464
3550550 | 675859432 | 04 SSV | 675862373 | 04 Lead Time Comments | 675862434 | 04 Lead Time | 675862449 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862495
3550550 | 675859432 | 05 SSV Confirmed By NDO Technical Leader | 675862034 | 05 Lead Time Comments | 675862060 | 05 Lead Time | 675862074 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862089
3550550 | 675859432 | 06 Tuning | 675862518 | 06 Lead Time Comments | 675862587 | 06 Lead Time | 675862618 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862637
3550550 | 675859432 | 06 Tuning | 675862518 | 06 Lead Time Comments | 675862587 | 06 Lead Time | 675862618 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862669
3550551 | 675859433 | 01 Installation End | 675862149 | 01 Lead Time Comments | 675862198 | 01 Lead Time | 675862208 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862221
3550551 | 675859433 | 02 Integration | 675862250 | 02 Lead Time Comments | 675862314 | 02 Lead Time | 675862325 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862338
3550551 | 675859433 | 02 Integration | 675862250 | 02 Lead Time Comments | 675862314 | 02 Lead Time | 675862325 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862354
3550551 | 675859433 | 03 Integration Confirmed By NRO Technical Leader | 675861936 | 03 Lead Time Comments | 675861976 | 03 Lead Time | 675861989 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862003
3550551 | 675859433 | 04 SSV | 675862372 | 04 Lead Time Comments | 675862430 | 04 Lead Time | 675862443 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862465
3550551 | 675859433 | 04 SSV | 675862372 | 04 Lead Time Comments | 675862430 | 04 Lead Time | 675862443 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862488
3550551 | 675859433 | 05 SSV Confirmed By NDO Technical Leader | 675862028 | 05 Lead Time Comments | 675862058 | 05 Lead Time | 675862075 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862088
3550551 | 675859433 | 06 Tuning | 675862515 | 06 Lead Time Comments | 675862584 | 06 Lead Time | 675862619 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862636
3550551 | 675859433 | 06 Tuning | 675862515 | 06 Lead Time Comments | 675862584 | 06 Lead Time | 675862619 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862668
3550552 | 675859464 | 01 Installation End | 675861353 | 01 Lead Time Comments | 675861387 | 01 Lead Time | 675861394 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861400
3550552 | 675859464 | 02 Integration | 675861417 | 02 Lead Time Comments | 675861468 | 02 Lead Time | 675861473 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861477
3550552 | 675859464 | 02 Integration | 675861417 | 02 Lead Time Comments | 675861468 | 02 Lead Time | 675861473 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861488
3550552 | 675859464 | 03 Integration Confirmed By NRO Technical Leader | 675861113 | 03 Lead Time Comments | 675861174 | 03 Lead Time | 675861184 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861194
3550552 | 675859464 | 04 SSV | 675861504 | 04 Lead Time Comments | 675861539 | 04 Lead Time | 675861548 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861556
3550552 | 675859464 | 04 SSV | 675861504 | 04 Lead Time Comments | 675861539 | 04 Lead Time | 675861548 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861578
3550552 | 675859464 | 05 SSV Confirmed By NDO Technical Leader | 675861215 | 05 Lead Time Comments | 675861255 | 05 Lead Time | 675861270 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861282
3550552 | 675859464 | 06 Tuning | 675861591 | 06 Lead Time Comments | 675861619 | 06 Lead Time | 675861624 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861628
3550552 | 675859464 | 06 Tuning | 675861591 | 06 Lead Time Comments | 675861619 | 06 Lead Time | 675861624 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861640
3550553 | 675859501 | 01 Installation End | 675861445 | 01 Lead Time Comments | 675861484 | 01 Lead Time | 675861491 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861495
3550553 | 675859501 | 02 Integration | 675861509 | 02 Lead Time Comments | 675861545 | 02 Lead Time | 675861553 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861561
3550553 | 675859501 | 02 Integration | 675861509 | 02 Lead Time Comments | 675861545 | 02 Lead Time | 675861553 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861584
3550553 | 675859501 | 03 Integration Confirmed By NRO Technical Leader | 675861247 | 03 Lead Time Comments | 675861319 | 03 Lead Time | 675861322 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861327
3550553 | 675859501 | 04 SSV | 675861598 | 04 Lead Time Comments | 675861629 | 04 Lead Time | 675861636 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861641
3550553 | 675859501 | 04 SSV | 675861598 | 04 Lead Time Comments | 675861629 | 04 Lead Time | 675861636 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861646
3550553 | 675859501 | 05 SSV Confirmed By NDO Technical Leader | 675861339 | 05 Lead Time Comments | 675861374 | 05 Lead Time | 675861380 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861389
3550553 | 675859501 | 06 Tuning | 675861655 | 06 Lead Time Comments | 675861677 | 06 Lead Time | 675861680 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861683
3550553 | 675859501 | 06 Tuning | 675861655 | 06 Lead Time Comments | 675861677 | 06 Lead Time | 675861680 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861695
3550554 | 675859502 | 01 Installation End | 675862238 | 01 Lead Time Comments | 675862267 | 01 Lead Time | 675862271 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862273
3550554 | 675859502 | 02 Integration | 675862289 | 02 Lead Time Comments | 675862346 | 02 Lead Time | 675862361 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862366
3550554 | 675859502 | 02 Integration | 675862289 | 02 Lead Time Comments | 675862346 | 02 Lead Time | 675862361 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862384
3550554 | 675859502 | 03 Integration Confirmed By NRO Technical Leader | 675862030 | 03 Lead Time Comments | 675862059 | 03 Lead Time | 675862071 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862087
3550554 | 675859502 | 04 SSV | 675862394 | 04 Lead Time Comments | 675862450 | 04 Lead Time | 675862467 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862473
3550554 | 675859502 | 04 SSV | 675862394 | 04 Lead Time Comments | 675862450 | 04 Lead Time | 675862467 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862506
3550554 | 675859502 | 05 SSV Confirmed By NDO Technical Leader | 675862110 | 05 Lead Time Comments | 675862145 | 05 Lead Time | 675862156 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862175
3550554 | 675859502 | 06 Tuning | 675862531 | 06 Lead Time Comments | 675862627 | 06 Lead Time | 675862659 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862678
3550554 | 675859502 | 06 Tuning | 675862531 | 06 Lead Time Comments | 675862627 | 06 Lead Time | 675862659 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862699
3550555 | 675859503 | 01 Installation End | 675862904 | 01 Lead Time Comments | 675862955 | 01 Lead Time | 675862967 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862979
3550555 | 675859503 | 02 Integration | 675863007 | 02 Lead Time Comments | 675863097 | 02 Lead Time | 675863133 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863168
3550555 | 675859503 | 02 Integration | 675863007 | 02 Lead Time Comments | 675863097 | 02 Lead Time | 675863133 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863203
3550555 | 675859503 | 03 Integration Confirmed By NRO Technical Leader | 675862482 | 03 Lead Time Comments | 675862539 | 03 Lead Time | 675862551 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862559
3550555 | 675859503 | 04 SSV | 675863243 | 04 Lead Time Comments | 675863361 | 04 Lead Time | 675863386 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863400
3550555 | 675859503 | 04 SSV | 675863243 | 04 Lead Time Comments | 675863361 | 04 Lead Time | 675863386 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863428
3550555 | 675859503 | 05 SSV Confirmed By NDO Technical Leader | 675862581 | 05 Lead Time Comments | 675862750 | 05 Lead Time | 675862781 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862814
3550555 | 675859503 | 06 Tuning | 675863455 | 06 Lead Time Comments | 675863538 | 06 Lead Time | 675863552 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863578
3550555 | 675859503 | 06 Tuning | 675863455 | 06 Lead Time Comments | 675863538 | 06 Lead Time | 675863552 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863597
3550557 | 675859512 | 01 Installation End | 675861514 | 01 Lead Time Comments | 675861564 | 01 Lead Time | 675861582 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861589
3550557 | 675859512 | 02 Integration | 675861600 | 02 Lead Time Comments | 675861627 | 02 Lead Time | 675861631 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861638
3550557 | 675859512 | 02 Integration | 675861600 | 02 Lead Time Comments | 675861627 | 02 Lead Time | 675861631 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861643
3550557 | 675859512 | 03 Integration Confirmed By NRO Technical Leader | 675861341 | 03 Lead Time Comments | 675861386 | 03 Lead Time | 675861391 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861399
3550557 | 675859512 | 04 SSV | 675861647 | 04 Lead Time Comments | 675861674 | 04 Lead Time | 675861676 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861678
3550557 | 675859512 | 04 SSV | 675861647 | 04 Lead Time Comments | 675861674 | 04 Lead Time | 675861676 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861686
3550557 | 675859512 | 05 SSV Confirmed By NDO Technical Leader | 675861412 | 05 Lead Time Comments | 675861455 | 05 Lead Time | 675861467 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861472
3550557 | 675859512 | 06 Tuning | 675861697 | 06 Lead Time Comments | 675861725 | 06 Lead Time | 675861732 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861735
3550557 | 675859512 | 06 Tuning | 675861697 | 06 Lead Time Comments | 675861725 | 06 Lead Time | 675861732 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861743
3550559 | 675859570 | 01 Installation End | 675862164 | 01 Lead Time Comments | 675862203 | 01 Lead Time | 675862219 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862233
3550559 | 675859570 | 02 Integration | 675862254 | 02 Lead Time Comments | 675862303 | 02 Lead Time | 675862319 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862335
3550559 | 675859570 | 02 Integration | 675862254 | 02 Lead Time Comments | 675862303 | 02 Lead Time | 675862319 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862355
3550559 | 675859570 | 03 Integration Confirmed By NRO Technical Leader | 675861933 | 03 Lead Time Comments | 675861969 | 03 Lead Time | 675861985 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862012
3550559 | 675859570 | 04 SSV | 675862371 | 04 Lead Time Comments | 675862433 | 04 Lead Time | 675862446 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862463
3550559 | 675859570 | 04 SSV | 675862371 | 04 Lead Time Comments | 675862433 | 04 Lead Time | 675862446 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862490
3550559 | 675859570 | 05 SSV Confirmed By NDO Technical Leader | 675862043 | 05 Lead Time Comments | 675862066 | 05 Lead Time | 675862082 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862098
3550559 | 675859570 | 06 Tuning | 675862528 | 06 Lead Time Comments | 675862613 | 06 Lead Time | 675862634 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862654
3550559 | 675859570 | 06 Tuning | 675862528 | 06 Lead Time Comments | 675862613 | 06 Lead Time | 675862634 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862696
3550560 | 675859581 | 01 Installation End | 675864510 | 01 Lead Time Comments | 675864677 | 01 Lead Time | 675864687 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864701
3550560 | 675859581 | 02 Integration | 675864737 | 02 Lead Time Comments | 675864926 | 02 Lead Time | 675864941 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864956
3550560 | 675859581 | 02 Integration | 675864737 | 02 Lead Time Comments | 675864926 | 02 Lead Time | 675864941 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864981
3550560 | 675859581 | 03 Integration Confirmed By NRO Technical Leader | 675864056 | 03 Lead Time Comments | 675864125 | 03 Lead Time | 675864136 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864154
3550560 | 675859581 | 04 SSV | 675865009 | 04 Lead Time Comments | 675865184 | 04 Lead Time | 675865209 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865243
3550560 | 675859581 | 04 SSV | 675865009 | 04 Lead Time Comments | 675865184 | 04 Lead Time | 675865209 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865298
3550560 | 675859581 | 05 SSV Confirmed By NDO Technical Leader | 675864205 | 05 Lead Time Comments | 675864316 | 05 Lead Time | 675864330 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864336
3550560 | 675859581 | 06 Tuning | 675865359 | 06 Lead Time Comments | 675865542 | 06 Lead Time | 675865579 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865604
3550560 | 675859581 | 06 Tuning | 675865359 | 06 Lead Time Comments | 675865542 | 06 Lead Time | 675865579 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865643
3550561 | 675859587 | 01 Installation End | 675865089 | 01 Lead Time Comments | 675865261 | 01 Lead Time | 675865293 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865319
3550561 | 675859587 | 02 Integration | 675865383 | 02 Lead Time Comments | 675865564 | 02 Lead Time | 675865588 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865613
3550561 | 675859587 | 02 Integration | 675865383 | 02 Lead Time Comments | 675865564 | 02 Lead Time | 675865588 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865653
3550561 | 675859587 | 03 Integration Confirmed By NRO Technical Leader | 675864239 | 03 Lead Time Comments | 675864406 | 03 Lead Time | 675864433 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864457
3550561 | 675859587 | 04 SSV | 675865704 | 04 Lead Time Comments | 675865862 | 04 Lead Time | 675865884 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865909
3550561 | 675859587 | 04 SSV | 675865704 | 04 Lead Time Comments | 675865862 | 04 Lead Time | 675865884 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865947
3550561 | 675859587 | 05 SSV Confirmed By NDO Technical Leader | 675864524 | 05 Lead Time Comments | 675864727 | 05 Lead Time | 675864786 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864819
3550561 | 675859587 | 06 Tuning | 675865992 | 06 Lead Time Comments | 675866119 | 06 Lead Time | 675866378 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866383
3550561 | 675859587 | 06 Tuning | 675865992 | 06 Lead Time Comments | 675866119 | 06 Lead Time | 675866378 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866389
3550562 | 675859586 | 01 Installation End | 675862161 | 01 Lead Time Comments | 675862201 | 01 Lead Time | 675862214 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862235
3550562 | 675859586 | 02 Integration | 675862257 | 02 Lead Time Comments | 675862309 | 02 Lead Time | 675862322 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862336
3550562 | 675859586 | 02 Integration | 675862257 | 02 Lead Time Comments | 675862309 | 02 Lead Time | 675862322 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862351
3550562 | 675859586 | 03 Integration Confirmed By NRO Technical Leader | 675861939 | 03 Lead Time Comments | 675861980 | 03 Lead Time | 675861991 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862004
3550562 | 675859586 | 04 SSV | 675862369 | 04 Lead Time Comments | 675862422 | 04 Lead Time | 675862438 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862454
3550562 | 675859586 | 04 SSV | 675862369 | 04 Lead Time Comments | 675862422 | 04 Lead Time | 675862438 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862480
3550562 | 675859586 | 05 SSV Confirmed By NDO Technical Leader | 675862027 | 05 Lead Time Comments | 675862055 | 05 Lead Time | 675862070 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862086
3550562 | 675859586 | 06 Tuning | 675862510 | 06 Lead Time Comments | 675862578 | 06 Lead Time | 675862605 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862630
3550562 | 675859586 | 06 Tuning | 675862510 | 06 Lead Time Comments | 675862578 | 06 Lead Time | 675862605 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862664
3550563 | 675859583 | 01 Installation End | 675862142 | 01 Lead Time Comments | 675862186 | 01 Lead Time | 675862189 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862195
3550563 | 675859583 | 02 Integration | 675862223 | 02 Lead Time Comments | 675862264 | 02 Lead Time | 675862268 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862272
3550563 | 675859583 | 02 Integration | 675862223 | 02 Lead Time Comments | 675862264 | 02 Lead Time | 675862268 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862274
3550563 | 675859583 | 03 Integration Confirmed By NRO Technical Leader | 675861935 | 03 Lead Time Comments | 675861968 | 03 Lead Time | 675861981 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861995
3550563 | 675859583 | 04 SSV | 675862295 | 04 Lead Time Comments | 675862362 | 04 Lead Time | 675862368 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862370
3550563 | 675859583 | 04 SSV | 675862295 | 04 Lead Time Comments | 675862362 | 04 Lead Time | 675862368 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862387
3550563 | 675859583 | 05 SSV Confirmed By NDO Technical Leader | 675862014 | 05 Lead Time Comments | 675862052 | 05 Lead Time | 675862056 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862068
3550563 | 675859583 | 06 Tuning | 675862396 | 06 Lead Time Comments | 675862453 | 06 Lead Time | 675862469 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862481
3550563 | 675859583 | 06 Tuning | 675862396 | 06 Lead Time Comments | 675862453 | 06 Lead Time | 675862469 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862507
3550564 | 675859582 | 01 Installation End | 675862177 | 01 Lead Time Comments | 675862213 | 01 Lead Time | 675862227 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862237
3550564 | 675859582 | 02 Integration | 675862255 | 02 Lead Time Comments | 675862291 | 02 Lead Time | 675862294 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862299
3550564 | 675859582 | 02 Integration | 675862255 | 02 Lead Time Comments | 675862291 | 02 Lead Time | 675862294 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862315
3550564 | 675859582 | 03 Integration Confirmed By NRO Technical Leader | 675861938 | 03 Lead Time Comments | 675861970 | 03 Lead Time | 675861984 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861998
3550564 | 675859582 | 04 SSV | 675862348 | 04 Lead Time Comments | 675862395 | 04 Lead Time | 675862398 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862399
3550564 | 675859582 | 04 SSV | 675862348 | 04 Lead Time Comments | 675862395 | 04 Lead Time | 675862398 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862420
3550564 | 675859582 | 05 SSV Confirmed By NDO Technical Leader | 675862016 | 05 Lead Time Comments | 675862053 | 05 Lead Time | 675862069 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862084
3550564 | 675859582 | 06 Tuning | 675862458 | 06 Lead Time Comments | 675862527 | 06 Lead Time | 675862549 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862564
3550564 | 675859582 | 06 Tuning | 675862458 | 06 Lead Time Comments | 675862527 | 06 Lead Time | 675862549 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862621
3550565 | 675859585 | 01 Installation End | 675862148 | 01 Lead Time Comments | 675862197 | 01 Lead Time | 675862207 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862222
3550565 | 675859585 | 02 Integration | 675862242 | 02 Lead Time Comments | 675862311 | 02 Lead Time | 675862324 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862334
3550565 | 675859585 | 02 Integration | 675862242 | 02 Lead Time Comments | 675862311 | 02 Lead Time | 675862324 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862365
3550565 | 675859585 | 03 Integration Confirmed By NRO Technical Leader | 675861931 | 03 Lead Time Comments | 675861973 | 03 Lead Time | 675861987 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862001
3550565 | 675859585 | 04 SSV | 675862380 | 04 Lead Time Comments | 675862431 | 04 Lead Time | 675862452 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862468
3550565 | 675859585 | 04 SSV | 675862380 | 04 Lead Time Comments | 675862431 | 04 Lead Time | 675862452 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862498
3550565 | 675859585 | 05 SSV Confirmed By NDO Technical Leader | 675862020 | 05 Lead Time Comments | 675862057 | 05 Lead Time | 675862073 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862091
3550565 | 675859585 | 06 Tuning | 675862547 | 06 Lead Time Comments | 675862645 | 06 Lead Time | 675862663 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862687
3550565 | 675859585 | 06 Tuning | 675862547 | 06 Lead Time Comments | 675862645 | 06 Lead Time | 675862663 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862705
3550566 | 675859584 | 01 Installation End | 675862167 | 01 Lead Time Comments | 675862204 | 01 Lead Time | 675862217 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862231
3550566 | 675859584 | 02 Integration | 675862251 | 02 Lead Time Comments | 675862306 | 02 Lead Time | 675862317 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862330
3550566 | 675859584 | 02 Integration | 675862251 | 02 Lead Time Comments | 675862306 | 02 Lead Time | 675862317 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862350
3550566 | 675859584 | 03 Integration Confirmed By NRO Technical Leader | 675861932 | 03 Lead Time Comments | 675861974 | 03 Lead Time | 675861999 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862011
3550566 | 675859584 | 04 SSV | 675862382 | 04 Lead Time Comments | 675862432 | 04 Lead Time | 675862448 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862466
3550566 | 675859584 | 04 SSV | 675862382 | 04 Lead Time Comments | 675862432 | 04 Lead Time | 675862448 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862496
3550566 | 675859584 | 05 SSV Confirmed By NDO Technical Leader | 675862040 | 05 Lead Time Comments | 675862065 | 05 Lead Time | 675862081 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862096
3550566 | 675859584 | 06 Tuning | 675862519 | 06 Lead Time Comments | 675862590 | 06 Lead Time | 675862623 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862640
3550566 | 675859584 | 06 Tuning | 675862519 | 06 Lead Time Comments | 675862590 | 06 Lead Time | 675862623 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862676
3550568 | 675859641 | 01 Installation End | 675864823 | 01 Lead Time Comments | 675865019 | 01 Lead Time | 675865043 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865060
3550568 | 675859641 | 02 Integration | 675865117 | 02 Lead Time Comments | 675865324 | 02 Lead Time | 675865357 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865384
3550568 | 675859641 | 02 Integration | 675865117 | 02 Lead Time Comments | 675865324 | 02 Lead Time | 675865357 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865442
3550568 | 675859641 | 03 Integration Confirmed By NRO Technical Leader | 675864148 | 03 Lead Time Comments | 675864273 | 03 Lead Time | 675864289 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864306
3550568 | 675859641 | 04 SSV | 675865509 | 04 Lead Time Comments | 675865678 | 04 Lead Time | 675865705 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865731
3550568 | 675859641 | 04 SSV | 675865509 | 04 Lead Time Comments | 675865678 | 04 Lead Time | 675865705 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865788
3550568 | 675859641 | 05 SSV Confirmed By NDO Technical Leader | 675864335 | 05 Lead Time Comments | 675864485 | 05 Lead Time | 675864521 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864573
3550568 | 675859641 | 06 Tuning | 675865842 | 06 Lead Time Comments | 675865963 | 06 Lead Time | 675865980 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866002
3550568 | 675859641 | 06 Tuning | 675865842 | 06 Lead Time Comments | 675865963 | 06 Lead Time | 675865980 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866045
3550569 | 675859683 | 01 Installation End | 675864102 | 01 Lead Time Comments | 675864184 | 01 Lead Time | 675864196 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864215
3550569 | 675859683 | 02 Integration | 675864256 | 02 Lead Time Comments | 675864415 | 02 Lead Time | 675864441 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864464
3550569 | 675859683 | 02 Integration | 675864256 | 02 Lead Time Comments | 675864415 | 02 Lead Time | 675864441 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864509
3550569 | 675859683 | 03 Integration Confirmed By NRO Technical Leader | 675863799 | 03 Lead Time Comments | 675863839 | 03 Lead Time | 675863852 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863864
3550569 | 675859683 | 04 SSV | 675864601 | 04 Lead Time Comments | 675864741 | 04 Lead Time | 675864762 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864812
3550569 | 675859683 | 04 SSV | 675864601 | 04 Lead Time Comments | 675864741 | 04 Lead Time | 675864762 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864876
3550569 | 675859683 | 05 SSV Confirmed By NDO Technical Leader | 675863890 | 05 Lead Time Comments | 675863949 | 05 Lead Time | 675863968 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863976
3550569 | 675859683 | 06 Tuning | 675864928 | 06 Lead Time Comments | 675865061 | 06 Lead Time | 675865086 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865112
3550569 | 675859683 | 06 Tuning | 675864928 | 06 Lead Time Comments | 675865061 | 06 Lead Time | 675865086 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865194
3550570 | 675859687 | 01 Installation End | 675862166 | 01 Lead Time Comments | 675862215 | 01 Lead Time | 675862228 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862239
3550570 | 675859687 | 02 Integration | 675862258 | 02 Lead Time Comments | 675862307 | 02 Lead Time | 675862323 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862333
3550570 | 675859687 | 02 Integration | 675862258 | 02 Lead Time Comments | 675862307 | 02 Lead Time | 675862323 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862364
3550570 | 675859687 | 03 Integration Confirmed By NRO Technical Leader | 675861955 | 03 Lead Time Comments | 675861993 | 03 Lead Time | 675862008 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862013
3550570 | 675859687 | 04 SSV | 675862379 | 04 Lead Time Comments | 675862437 | 04 Lead Time | 675862456 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862470
3550570 | 675859687 | 04 SSV | 675862379 | 04 Lead Time Comments | 675862437 | 04 Lead Time | 675862456 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862501
3550570 | 675859687 | 05 SSV Confirmed By NDO Technical Leader | 675862047 | 05 Lead Time Comments | 675862072 | 05 Lead Time | 675862090 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862103
3550570 | 675859687 | 06 Tuning | 675862525 | 06 Lead Time Comments | 675862604 | 06 Lead Time | 675862629 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862648
3550570 | 675859687 | 06 Tuning | 675862525 | 06 Lead Time Comments | 675862604 | 06 Lead Time | 675862629 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862695
3550571 | 675859725 | 01 Installation End | 675861788 | 01 Lead Time Comments | 675861798 | 01 Lead Time | 675861803 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861807
3550571 | 675859725 | 02 Integration | 675861812 | 02 Lead Time Comments | 675861822 | 02 Lead Time | 675861828 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861831
3550571 | 675859725 | 02 Integration | 675861812 | 02 Lead Time Comments | 675861822 | 02 Lead Time | 675861828 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861833
3550571 | 675859725 | 03 Integration Confirmed By NRO Technical Leader | 675861693 | 03 Lead Time Comments | 675861718 | 03 Lead Time | 675861726 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861730
3550571 | 675859725 | 04 SSV | 675861837 | 04 Lead Time Comments | 675861856 | 04 Lead Time | 675861859 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861861
3550571 | 675859725 | 04 SSV | 675861837 | 04 Lead Time Comments | 675861856 | 04 Lead Time | 675861859 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861864
3550571 | 675859725 | 05 SSV Confirmed By NDO Technical Leader | 675861739 | 05 Lead Time Comments | 675861763 | 05 Lead Time | 675861769 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861774
3550571 | 675859725 | 06 Tuning | 675861868 | 06 Lead Time Comments | 675861877 | 06 Lead Time | 675861880 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861884
3550571 | 675859725 | 06 Tuning | 675861868 | 06 Lead Time Comments | 675861877 | 06 Lead Time | 675861880 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861888
3550572 | 675859727 | 01 Installation End | 675861512 | 01 Lead Time Comments | 675861541 | 01 Lead Time | 675861550 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861560
3550572 | 675859727 | 02 Integration | 675861586 | 02 Lead Time Comments | 675861612 | 02 Lead Time | 675861617 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861620
3550572 | 675859727 | 02 Integration | 675861586 | 02 Lead Time Comments | 675861612 | 02 Lead Time | 675861617 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861633
3550572 | 675859727 | 03 Integration Confirmed By NRO Technical Leader | 675861343 | 03 Lead Time Comments | 675861376 | 03 Lead Time | 675861384 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861392
3550572 | 675859727 | 04 SSV | 675861642 | 04 Lead Time Comments | 675861664 | 04 Lead Time | 675861669 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861672
3550572 | 675859727 | 04 SSV | 675861642 | 04 Lead Time Comments | 675861664 | 04 Lead Time | 675861669 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861681
3550572 | 675859727 | 05 SSV Confirmed By NDO Technical Leader | 675861408 | 05 Lead Time Comments | 675861444 | 05 Lead Time | 675861453 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861465
3550572 | 675859727 | 06 Tuning | 675861691 | 06 Lead Time Comments | 675861722 | 06 Lead Time | 675861729 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861734
3550572 | 675859727 | 06 Tuning | 675861691 | 06 Lead Time Comments | 675861722 | 06 Lead Time | 675861729 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861747
3550573 | 675859786 | 01 Installation End | 675864838 | 01 Lead Time Comments | 675865041 | 01 Lead Time | 675865062 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865090
3550573 | 675859786 | 02 Integration | 675865153 | 02 Lead Time Comments | 675865398 | 02 Lead Time | 675865425 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865460
3550573 | 675859786 | 02 Integration | 675865153 | 02 Lead Time Comments | 675865398 | 02 Lead Time | 675865425 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865524
3550573 | 675859786 | 03 Integration Confirmed By NRO Technical Leader | 675864144 | 03 Lead Time Comments | 675864276 | 03 Lead Time | 675864297 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864312
3550573 | 675859786 | 04 SSV | 675865597 | 04 Lead Time Comments | 675865762 | 04 Lead Time | 675865793 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865819
3550573 | 675859786 | 04 SSV | 675865597 | 04 Lead Time Comments | 675865762 | 04 Lead Time | 675865793 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865865
3550573 | 675859786 | 05 SSV Confirmed By NDO Technical Leader | 675864343 | 05 Lead Time Comments | 675864496 | 05 Lead Time | 675864535 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864581
3550573 | 675859786 | 06 Tuning | 675865912 | 06 Lead Time Comments | 675866030 | 06 Lead Time | 675866053 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866077
3550573 | 675859786 | 06 Tuning | 675865912 | 06 Lead Time Comments | 675866030 | 06 Lead Time | 675866053 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866189
3550574 | 675859787 | 01 Installation End | 675862163 | 01 Lead Time Comments | 675862202 | 01 Lead Time | 675862216 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862229
3550574 | 675859787 | 02 Integration | 675862247 | 02 Lead Time Comments | 675862304 | 02 Lead Time | 675862344 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862349
3550574 | 675859787 | 02 Integration | 675862247 | 02 Lead Time Comments | 675862304 | 02 Lead Time | 675862344 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862367
3550574 | 675859787 | 03 Integration Confirmed By NRO Technical Leader | 675861934 | 03 Lead Time Comments | 675861972 | 03 Lead Time | 675861986 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862000
3550574 | 675859787 | 04 SSV | 675862388 | 04 Lead Time Comments | 675862427 | 04 Lead Time | 675862447 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862460
3550574 | 675859787 | 04 SSV | 675862388 | 04 Lead Time Comments | 675862427 | 04 Lead Time | 675862447 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862493
3550574 | 675859787 | 05 SSV Confirmed By NDO Technical Leader | 675862019 | 05 Lead Time Comments | 675862067 | 05 Lead Time | 675862083 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862099
3550574 | 675859787 | 06 Tuning | 675862520 | 06 Lead Time Comments | 675862594 | 06 Lead Time | 675862625 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862642
3550574 | 675859787 | 06 Tuning | 675862520 | 06 Lead Time Comments | 675862594 | 06 Lead Time | 675862625 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862674
3550575 | 675859811 | 01 Installation End | 675863012 | 01 Lead Time Comments | 675863072 | 01 Lead Time | 675863095 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863117
3550575 | 675859811 | 02 Integration | 675863166 | 02 Lead Time Comments | 675863269 | 02 Lead Time | 675863291 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863312
3550575 | 675859811 | 02 Integration | 675863166 | 02 Lead Time Comments | 675863269 | 02 Lead Time | 675863291 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863350
3550575 | 675859811 | 03 Integration Confirmed By NRO Technical Leader | 675862665 | 03 Lead Time Comments | 675862752 | 03 Lead Time | 675862777 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862812
3550575 | 675859811 | 04 SSV | 675863401 | 04 Lead Time Comments | 675863474 | 04 Lead Time | 675863488 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863501
3550575 | 675859811 | 04 SSV | 675863401 | 04 Lead Time Comments | 675863474 | 04 Lead Time | 675863488 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863531
3550575 | 675859811 | 05 SSV Confirmed By NDO Technical Leader | 675862855 | 05 Lead Time Comments | 675862901 | 05 Lead Time | 675862911 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862925
3550575 | 675859811 | 06 Tuning | 675863570 | 06 Lead Time Comments | 675863633 | 06 Lead Time | 675863651 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863668
3550575 | 675859811 | 06 Tuning | 675863570 | 06 Lead Time Comments | 675863633 | 06 Lead Time | 675863651 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863708
3550576 | 675859812 | 01 Installation End | 675862391 | 01 Lead Time Comments | 675862423 | 01 Lead Time | 675862439 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862455
3550576 | 675859812 | 02 Integration | 675862497 | 02 Lead Time Comments | 675862566 | 02 Lead Time | 675862580 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862611
3550576 | 675859812 | 02 Integration | 675862497 | 02 Lead Time Comments | 675862566 | 02 Lead Time | 675862580 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862651
3550576 | 675859812 | 03 Integration Confirmed By NRO Technical Leader | 675862188 | 03 Lead Time Comments | 675862244 | 03 Lead Time | 675862256 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862262
3550576 | 675859812 | 04 SSV | 675862690 | 04 Lead Time Comments | 675862841 | 04 Lead Time | 675862862 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862894
3550576 | 675859812 | 04 SSV | 675862690 | 04 Lead Time Comments | 675862841 | 04 Lead Time | 675862862 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862915
3550576 | 675859812 | 05 SSV Confirmed By NDO Technical Leader | 675862269 | 05 Lead Time Comments | 675862296 | 05 Lead Time | 675862301 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862329
3550576 | 675859812 | 06 Tuning | 675862939 | 06 Lead Time Comments | 675863009 | 06 Lead Time | 675863021 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863034
3550576 | 675859812 | 06 Tuning | 675862939 | 06 Lead Time Comments | 675863009 | 06 Lead Time | 675863021 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863051
3550577 | 675859907 | 01 Installation End | 675862152 | 01 Lead Time Comments | 675862199 | 01 Lead Time | 675862212 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862225
3550577 | 675859907 | 02 Integration | 675862245 | 02 Lead Time Comments | 675862313 | 02 Lead Time | 675862327 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862342
3550577 | 675859907 | 02 Integration | 675862245 | 02 Lead Time Comments | 675862313 | 02 Lead Time | 675862327 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862363
3550577 | 675859907 | 03 Integration Confirmed By NRO Technical Leader | 675861948 | 03 Lead Time Comments | 675861971 | 03 Lead Time | 675861983 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861997
3550577 | 675859907 | 04 SSV | 675862378 | 04 Lead Time Comments | 675862425 | 04 Lead Time | 675862442 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862459
3550577 | 675859907 | 04 SSV | 675862378 | 04 Lead Time Comments | 675862425 | 04 Lead Time | 675862442 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862487
3550577 | 675859907 | 05 SSV Confirmed By NDO Technical Leader | 675862017 | 05 Lead Time Comments | 675862054 | 05 Lead Time | 675862077 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862093
3550577 | 675859907 | 06 Tuning | 675862514 | 06 Lead Time Comments | 675862586 | 06 Lead Time | 675862617 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862649
3550577 | 675859907 | 06 Tuning | 675862514 | 06 Lead Time Comments | 675862586 | 06 Lead Time | 675862617 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862683
3550578 | 675859910 | 01 Installation End | 675864966 | 01 Lead Time Comments | 675865128 | 01 Lead Time | 675865162 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865188
3550578 | 675859910 | 02 Integration | 675865265 | 02 Lead Time Comments | 675865456 | 02 Lead Time | 675865490 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865516
3550578 | 675859910 | 02 Integration | 675865265 | 02 Lead Time Comments | 675865456 | 02 Lead Time | 675865490 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865577
3550578 | 675859910 | 03 Integration Confirmed By NRO Technical Leader | 675864243 | 03 Lead Time Comments | 675864398 | 03 Lead Time | 675864418 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864444
3550578 | 675859910 | 04 SSV | 675865625 | 04 Lead Time Comments | 675865795 | 04 Lead Time | 675865820 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865841
3550578 | 675859910 | 04 SSV | 675865625 | 04 Lead Time Comments | 675865795 | 04 Lead Time | 675865820 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865883
3550578 | 675859910 | 05 SSV Confirmed By NDO Technical Leader | 675864559 | 05 Lead Time Comments | 675864692 | 05 Lead Time | 675864706 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864724
3550578 | 675859910 | 06 Tuning | 675865937 | 06 Lead Time Comments | 675866065 | 06 Lead Time | 675866089 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866112
3550578 | 675859910 | 06 Tuning | 675865937 | 06 Lead Time Comments | 675866065 | 06 Lead Time | 675866089 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866148
3550579 | 675859913 | 01 Installation End | 675862896 | 01 Lead Time Comments | 675862948 | 01 Lead Time | 675862961 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862971
3550579 | 675859913 | 02 Integration | 675863002 | 02 Lead Time Comments | 675863070 | 02 Lead Time | 675863094 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863108
3550579 | 675859913 | 02 Integration | 675863002 | 02 Lead Time Comments | 675863070 | 02 Lead Time | 675863094 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863148
3550579 | 675859913 | 03 Integration Confirmed By NRO Technical Leader | 675862475 | 03 Lead Time Comments | 675862542 | 03 Lead Time | 675862554 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862563
3550579 | 675859913 | 04 SSV | 675863195 | 04 Lead Time Comments | 675863299 | 04 Lead Time | 675863321 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863345
3550579 | 675859913 | 04 SSV | 675863195 | 04 Lead Time Comments | 675863299 | 04 Lead Time | 675863321 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863403
3550579 | 675859913 | 05 SSV Confirmed By NDO Technical Leader | 675862602 | 05 Lead Time Comments | 675862745 | 05 Lead Time | 675862769 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862803
3550579 | 675859913 | 06 Tuning | 675863432 | 06 Lead Time Comments | 675863503 | 06 Lead Time | 675863517 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863537
3550579 | 675859913 | 06 Tuning | 675863432 | 06 Lead Time Comments | 675863503 | 06 Lead Time | 675863517 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863564
3550580 | 675859918 | 01 Installation End | 675864219 | 01 Lead Time Comments | 675864357 | 01 Lead Time | 675864372 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864382
3550580 | 675859918 | 02 Integration | 675864411 | 02 Lead Time Comments | 675864609 | 02 Lead Time | 675864625 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864649
3550580 | 675859918 | 02 Integration | 675864411 | 02 Lead Time Comments | 675864609 | 02 Lead Time | 675864625 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864667
3550580 | 675859918 | 03 Integration Confirmed By NRO Technical Leader | 675863883 | 03 Lead Time Comments | 675863935 | 03 Lead Time | 675863948 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863965
3550580 | 675859918 | 04 SSV | 675864681 | 04 Lead Time Comments | 675864919 | 04 Lead Time | 675864931 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864949
3550580 | 675859918 | 04 SSV | 675864681 | 04 Lead Time Comments | 675864919 | 04 Lead Time | 675864931 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864984
3550580 | 675859918 | 05 SSV Confirmed By NDO Technical Leader | 675863989 | 05 Lead Time Comments | 675864069 | 05 Lead Time | 675864087 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864105
3550580 | 675859918 | 06 Tuning | 675865015 | 06 Lead Time Comments | 675865196 | 06 Lead Time | 675865228 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865249
3550580 | 675859918 | 06 Tuning | 675865015 | 06 Lead Time Comments | 675865196 | 06 Lead Time | 675865228 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865309
3550581 | 675859929 | 01 Installation End | 675862838 | 01 Lead Time Comments | 675862891 | 01 Lead Time | 675862897 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862908
3550581 | 675859929 | 02 Integration | 675862933 | 02 Lead Time Comments | 675863000 | 02 Lead Time | 675863013 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863026
3550581 | 675859929 | 02 Integration | 675862933 | 02 Lead Time Comments | 675863000 | 02 Lead Time | 675863013 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863044
3550581 | 675859929 | 03 Integration Confirmed By NRO Technical Leader | 675862404 | 03 Lead Time Comments | 675862494 | 03 Lead Time | 675862504 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862511
3550581 | 675859929 | 04 SSV | 675863065 | 04 Lead Time Comments | 675863189 | 04 Lead Time | 675863206 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863224
3550581 | 675859929 | 04 SSV | 675863065 | 04 Lead Time Comments | 675863189 | 04 Lead Time | 675863206 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863248
3550581 | 675859929 | 05 SSV Confirmed By NDO Technical Leader | 675862541 | 05 Lead Time Comments | 675862624 | 05 Lead Time | 675862641 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862657
3550581 | 675859929 | 06 Tuning | 675863289 | 06 Lead Time Comments | 675863408 | 06 Lead Time | 675863422 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863431
3550581 | 675859929 | 06 Tuning | 675863289 | 06 Lead Time Comments | 675863408 | 06 Lead Time | 675863422 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863456
3550582 | 675859960 | 01 Installation End | 675861727 | 01 Lead Time Comments | 675861749 | 01 Lead Time | 675861752 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675861755
3550582 | 675859960 | 02 Integration | 675861764 | 02 Lead Time Comments | 675861782 | 02 Lead Time | 675861783 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675861784
3550582 | 675859960 | 02 Integration | 675861764 | 02 Lead Time Comments | 675861782 | 02 Lead Time | 675861783 | actcl--02 Integration--02 Lead Time Comments--Duration | 675861789
3550582 | 675859960 | 03 Integration Confirmed By NRO Technical Leader | 675861635 | 03 Lead Time Comments | 675861649 | 03 Lead Time | 675861652 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675861661
3550582 | 675859960 | 04 SSV | 675861792 | 04 Lead Time Comments | 675861809 | 04 Lead Time | 675861813 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675861814
3550582 | 675859960 | 04 SSV | 675861792 | 04 Lead Time Comments | 675861809 | 04 Lead Time | 675861813 | actcl--04 SSV--04 Lead Time Comments--Duration | 675861815
3550582 | 675859960 | 05 SSV Confirmed By NDO Technical Leader | 675861668 | 05 Lead Time Comments | 675861685 | 05 Lead Time | 675861689 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675861696
3550582 | 675859960 | 06 Tuning | 675861825 | 06 Lead Time Comments | 675861836 | 06 Lead Time | 675861840 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675861841
3550582 | 675859960 | 06 Tuning | 675861825 | 06 Lead Time Comments | 675861836 | 06 Lead Time | 675861840 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675861842
3550583 | 675859961 | 01 Installation End | 675863056 | 01 Lead Time Comments | 675863140 | 01 Lead Time | 675863162 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863178
3550583 | 675859961 | 02 Integration | 675863220 | 02 Lead Time Comments | 675863331 | 02 Lead Time | 675863351 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863376
3550583 | 675859961 | 02 Integration | 675863220 | 02 Lead Time Comments | 675863331 | 02 Lead Time | 675863351 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863412
3550583 | 675859961 | 03 Integration Confirmed By NRO Technical Leader | 675862680 | 03 Lead Time Comments | 675862772 | 03 Lead Time | 675862804 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862829
3550583 | 675859961 | 04 SSV | 675863437 | 04 Lead Time Comments | 675863529 | 04 Lead Time | 675863548 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863563
3550583 | 675859961 | 04 SSV | 675863437 | 04 Lead Time Comments | 675863529 | 04 Lead Time | 675863548 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863584
3550583 | 675859961 | 05 SSV Confirmed By NDO Technical Leader | 675862875 | 05 Lead Time Comments | 675862937 | 05 Lead Time | 675862945 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862963
3550583 | 675859961 | 06 Tuning | 675863605 | 06 Lead Time Comments | 675863687 | 06 Lead Time | 675863740 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863749
3550583 | 675859961 | 06 Tuning | 675863605 | 06 Lead Time Comments | 675863687 | 06 Lead Time | 675863740 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863767
3550584 | 675860036 | 01 Installation End | 675863014 | 01 Lead Time Comments | 675863071 | 01 Lead Time | 675863099 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863110
3550584 | 675860036 | 02 Integration | 675863164 | 02 Lead Time Comments | 675863293 | 02 Lead Time | 675863314 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863336
3550584 | 675860036 | 02 Integration | 675863164 | 02 Lead Time Comments | 675863293 | 02 Lead Time | 675863314 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863375
3550584 | 675860036 | 03 Integration Confirmed By NRO Technical Leader | 675862681 | 03 Lead Time Comments | 675862776 | 03 Lead Time | 675862808 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862830
3550584 | 675860036 | 04 SSV | 675863418 | 04 Lead Time Comments | 675863486 | 04 Lead Time | 675863502 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863513
3550584 | 675860036 | 04 SSV | 675863418 | 04 Lead Time Comments | 675863486 | 04 Lead Time | 675863502 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863545
3550584 | 675860036 | 05 SSV Confirmed By NDO Technical Leader | 675862866 | 05 Lead Time Comments | 675862910 | 05 Lead Time | 675862921 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862932
3550584 | 675860036 | 06 Tuning | 675863577 | 06 Lead Time Comments | 675863640 | 06 Lead Time | 675863657 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863672
3550584 | 675860036 | 06 Tuning | 675863577 | 06 Lead Time Comments | 675863640 | 06 Lead Time | 675863657 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863696
3550585 | 675860034 | 01 Installation End | 675863232 | 01 Lead Time Comments | 675863317 | 01 Lead Time | 675863338 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863358
3550585 | 675860034 | 02 Integration | 675863404 | 02 Lead Time Comments | 675863485 | 02 Lead Time | 675863499 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863511
3550585 | 675860034 | 02 Integration | 675863404 | 02 Lead Time Comments | 675863485 | 02 Lead Time | 675863499 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863544
3550585 | 675860034 | 03 Integration Confirmed By NRO Technical Leader | 675862889 | 03 Lead Time Comments | 675862935 | 03 Lead Time | 675862944 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862952
3550585 | 675860034 | 04 SSV | 675863575 | 04 Lead Time Comments | 675863641 | 04 Lead Time | 675863653 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863669
3550585 | 675860034 | 04 SSV | 675863575 | 04 Lead Time Comments | 675863641 | 04 Lead Time | 675863653 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863706
3550585 | 675860034 | 05 SSV Confirmed By NDO Technical Leader | 675862975 | 05 Lead Time Comments | 675863048 | 05 Lead Time | 675863058 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863068
3550585 | 675860034 | 06 Tuning | 675863719 | 06 Lead Time Comments | 675863775 | 06 Lead Time | 675863783 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863794
3550585 | 675860034 | 06 Tuning | 675863719 | 06 Lead Time Comments | 675863775 | 06 Lead Time | 675863783 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863817
3550586 | 675860410 | 01 Installation End | 675862902 | 01 Lead Time Comments | 675862959 | 01 Lead Time | 675862969 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862983
3550586 | 675860410 | 02 Integration | 675863010 | 02 Lead Time Comments | 675863075 | 02 Lead Time | 675863100 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863119
3550586 | 675860410 | 02 Integration | 675863010 | 02 Lead Time Comments | 675863075 | 02 Lead Time | 675863100 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863155
3550586 | 675860410 | 03 Integration Confirmed By NRO Technical Leader | 675862476 | 03 Lead Time Comments | 675862540 | 03 Lead Time | 675862553 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862561
3550586 | 675860410 | 04 SSV | 675863200 | 04 Lead Time Comments | 675863325 | 04 Lead Time | 675863347 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863365
3550586 | 675860410 | 04 SSV | 675863200 | 04 Lead Time Comments | 675863325 | 04 Lead Time | 675863347 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863411
3550586 | 675860410 | 05 SSV Confirmed By NDO Technical Leader | 675862598 | 05 Lead Time Comments | 675862744 | 05 Lead Time | 675862771 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862806
3550586 | 675860410 | 06 Tuning | 675863444 | 06 Lead Time Comments | 675863536 | 06 Lead Time | 675863550 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863566
3550586 | 675860410 | 06 Tuning | 675863444 | 06 Lead Time Comments | 675863536 | 06 Lead Time | 675863550 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863586
3550587 | 675860435 | 01 Installation End | 675864417 | 01 Lead Time Comments | 675864584 | 01 Lead Time | 675864606 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864621
3550587 | 675860435 | 02 Integration | 675864664 | 02 Lead Time Comments | 675864845 | 02 Lead Time | 675864879 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864908
3550587 | 675860435 | 02 Integration | 675864664 | 02 Lead Time Comments | 675864845 | 02 Lead Time | 675864879 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864935
3550587 | 675860435 | 03 Integration Confirmed By NRO Technical Leader | 675863962 | 03 Lead Time Comments | 675864042 | 03 Lead Time | 675864052 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864063
3550587 | 675860435 | 04 SSV | 675864965 | 04 Lead Time Comments | 675865161 | 04 Lead Time | 675865191 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865229
3550587 | 675860435 | 04 SSV | 675864965 | 04 Lead Time Comments | 675865161 | 04 Lead Time | 675865191 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865285
3550587 | 675860435 | 05 SSV Confirmed By NDO Technical Leader | 675864098 | 05 Lead Time Comments | 675864178 | 05 Lead Time | 675864193 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864212
3550587 | 675860435 | 06 Tuning | 675865353 | 06 Lead Time Comments | 675865545 | 06 Lead Time | 675865582 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865608
3550587 | 675860435 | 06 Tuning | 675865353 | 06 Lead Time Comments | 675865545 | 06 Lead Time | 675865582 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865652
3550588 | 675860438 | 01 Installation End | 675865012 | 01 Lead Time Comments | 675865160 | 01 Lead Time | 675865186 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865215
3550588 | 675860438 | 02 Integration | 675865291 | 02 Lead Time Comments | 675865483 | 02 Lead Time | 675865511 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865544
3550588 | 675860438 | 02 Integration | 675865291 | 02 Lead Time Comments | 675865483 | 02 Lead Time | 675865511 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865596
3550588 | 675860438 | 03 Integration Confirmed By NRO Technical Leader | 675864245 | 03 Lead Time Comments | 675864407 | 03 Lead Time | 675864435 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864461
3550588 | 675860438 | 04 SSV | 675865648 | 04 Lead Time Comments | 675865814 | 04 Lead Time | 675865840 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865864
3550588 | 675860438 | 04 SSV | 675865648 | 04 Lead Time Comments | 675865814 | 04 Lead Time | 675865840 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865897
3550588 | 675860438 | 05 SSV Confirmed By NDO Technical Leader | 675864515 | 05 Lead Time Comments | 675864720 | 05 Lead Time | 675864743 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864766
3550588 | 675860438 | 06 Tuning | 675865959 | 06 Lead Time Comments | 675866084 | 06 Lead Time | 675866110 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866129
3550588 | 675860438 | 06 Tuning | 675865959 | 06 Lead Time Comments | 675866084 | 06 Lead Time | 675866110 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866168
3550589 | 675860789 | 01 Installation End | 675862895 | 01 Lead Time Comments | 675862950 | 01 Lead Time | 675862962 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862972
3550589 | 675860789 | 02 Integration | 675862997 | 02 Lead Time Comments | 675863063 | 02 Lead Time | 675863076 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863101
3550589 | 675860789 | 02 Integration | 675862997 | 02 Lead Time Comments | 675863063 | 02 Lead Time | 675863076 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863138
3550589 | 675860789 | 03 Integration Confirmed By NRO Technical Leader | 675862483 | 03 Lead Time Comments | 675862538 | 03 Lead Time | 675862550 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862560
3550589 | 675860789 | 04 SSV | 675863187 | 04 Lead Time Comments | 675863290 | 04 Lead Time | 675863307 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863329
3550589 | 675860789 | 04 SSV | 675863187 | 04 Lead Time Comments | 675863290 | 04 Lead Time | 675863307 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863367
3550589 | 675860789 | 05 SSV Confirmed By NDO Technical Leader | 675862582 | 05 Lead Time Comments | 675862746 | 05 Lead Time | 675862770 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862801
3550589 | 675860789 | 06 Tuning | 675863415 | 06 Lead Time Comments | 675863477 | 06 Lead Time | 675863493 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863535
3550589 | 675860789 | 06 Tuning | 675863415 | 06 Lead Time Comments | 675863477 | 06 Lead Time | 675863493 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863560
3550590 | 675860893 | 01 Installation End | 675863463 | 01 Lead Time Comments | 675863526 | 01 Lead Time | 675863540 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863555
3550590 | 675860893 | 02 Integration | 675863583 | 02 Lead Time Comments | 675863650 | 02 Lead Time | 675863664 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863679
3550590 | 675860893 | 02 Integration | 675863583 | 02 Lead Time Comments | 675863650 | 02 Lead Time | 675863664 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863700
3550590 | 675860893 | 03 Integration Confirmed By NRO Technical Leader | 675863052 | 03 Lead Time Comments | 675863131 | 03 Lead Time | 675863154 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863173
3550590 | 675860893 | 04 SSV | 675863715 | 04 Lead Time Comments | 675863771 | 04 Lead Time | 675863779 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863798
3550590 | 675860893 | 04 SSV | 675863715 | 04 Lead Time Comments | 675863771 | 04 Lead Time | 675863779 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863815
3550590 | 675860893 | 05 SSV Confirmed By NDO Technical Leader | 675863213 | 05 Lead Time Comments | 675863297 | 05 Lead Time | 675863318 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863342
3550590 | 675860893 | 06 Tuning | 675863829 | 06 Lead Time Comments | 675863911 | 06 Lead Time | 675863916 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863921
3550590 | 675860893 | 06 Tuning | 675863829 | 06 Lead Time Comments | 675863911 | 06 Lead Time | 675863916 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863937
3550591 | 675860889 | 01 Installation End | 675863557 | 01 Lead Time Comments | 675863608 | 01 Lead Time | 675863614 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863623
3550591 | 675860889 | 02 Integration | 675863661 | 02 Lead Time Comments | 675863717 | 02 Lead Time | 675863724 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863734
3550591 | 675860889 | 02 Integration | 675863661 | 02 Lead Time Comments | 675863717 | 02 Lead Time | 675863724 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863752
3550591 | 675860889 | 03 Integration Confirmed By NRO Technical Leader | 675863180 | 03 Lead Time Comments | 675863260 | 03 Lead Time | 675863272 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863309
3550591 | 675860889 | 04 SSV | 675863776 | 04 Lead Time Comments | 675863826 | 04 Lead Time | 675863835 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863846
3550591 | 675860889 | 04 SSV | 675863776 | 04 Lead Time Comments | 675863826 | 04 Lead Time | 675863835 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863871
3550591 | 675860889 | 05 SSV Confirmed By NDO Technical Leader | 675863353 | 05 Lead Time Comments | 675863436 | 05 Lead Time | 675863446 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863460
3550591 | 675860889 | 06 Tuning | 675863898 | 06 Lead Time Comments | 675863974 | 06 Lead Time | 675863983 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863992
3550591 | 675860889 | 06 Tuning | 675863898 | 06 Lead Time Comments | 675863974 | 06 Lead Time | 675863983 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675864031
3550592 | 675860891 | 01 Installation End | 675863573 | 01 Lead Time Comments | 675863622 | 01 Lead Time | 675863634 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863648
3550592 | 675860891 | 02 Integration | 675863686 | 02 Lead Time Comments | 675863733 | 02 Lead Time | 675863743 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863755
3550592 | 675860891 | 02 Integration | 675863686 | 02 Lead Time Comments | 675863733 | 02 Lead Time | 675863743 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863772
3550592 | 675860891 | 03 Integration Confirmed By NRO Technical Leader | 675863201 | 03 Lead Time Comments | 675863292 | 03 Lead Time | 675863306 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863323
3550592 | 675860891 | 04 SSV | 675863787 | 04 Lead Time Comments | 675863859 | 04 Lead Time | 675863869 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863881
3550592 | 675860891 | 04 SSV | 675863787 | 04 Lead Time Comments | 675863859 | 04 Lead Time | 675863869 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863904
3550592 | 675860891 | 05 SSV Confirmed By NDO Technical Leader | 675863370 | 05 Lead Time Comments | 675863445 | 05 Lead Time | 675863462 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863469
3550592 | 675860891 | 06 Tuning | 675863919 | 06 Lead Time Comments | 675863987 | 06 Lead Time | 675864004 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675864022
3550592 | 675860891 | 06 Tuning | 675863919 | 06 Lead Time Comments | 675863987 | 06 Lead Time | 675864004 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675864045
3550594 | 675860898 | 01 Installation End | 675864269 | 01 Lead Time Comments | 675864430 | 01 Lead Time | 675864453 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864474
3550594 | 675860898 | 02 Integration | 675864554 | 02 Lead Time Comments | 675864782 | 02 Lead Time | 675864809 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864849
3550594 | 675860898 | 02 Integration | 675864554 | 02 Lead Time Comments | 675864782 | 02 Lead Time | 675864809 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864904
3550594 | 675860898 | 03 Integration Confirmed By NRO Technical Leader | 675863884 | 03 Lead Time Comments | 675863939 | 03 Lead Time | 675863951 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863969
3550594 | 675860898 | 04 SSV | 675864943 | 04 Lead Time Comments | 675865140 | 04 Lead Time | 675865169 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865200
3550594 | 675860898 | 04 SSV | 675864943 | 04 Lead Time Comments | 675865140 | 04 Lead Time | 675865169 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865256
3550594 | 675860898 | 05 SSV Confirmed By NDO Technical Leader | 675863994 | 05 Lead Time Comments | 675864075 | 05 Lead Time | 675864101 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864114
3550594 | 675860898 | 06 Tuning | 675865325 | 06 Lead Time Comments | 675865497 | 06 Lead Time | 675865538 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865569
3550594 | 675860898 | 06 Tuning | 675865325 | 06 Lead Time Comments | 675865497 | 06 Lead Time | 675865538 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865609
3550595 | 675860888 | 01 Installation End | 675864086 | 01 Lead Time Comments | 675864164 | 01 Lead Time | 675864190 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864206
3550595 | 675860888 | 02 Integration | 675864232 | 02 Lead Time Comments | 675864385 | 02 Lead Time | 675864391 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864412
3550595 | 675860888 | 02 Integration | 675864232 | 02 Lead Time Comments | 675864385 | 02 Lead Time | 675864391 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864463
3550595 | 675860888 | 03 Integration Confirmed By NRO Technical Leader | 675863796 | 03 Lead Time Comments | 675863841 | 03 Lead Time | 675863855 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863867
3550595 | 675860888 | 04 SSV | 675864565 | 04 Lead Time Comments | 675864765 | 04 Lead Time | 675864802 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864848
3550595 | 675860888 | 04 SSV | 675864565 | 04 Lead Time Comments | 675864765 | 04 Lead Time | 675864802 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864906
3550595 | 675860888 | 05 SSV Confirmed By NDO Technical Leader | 675863896 | 05 Lead Time Comments | 675863944 | 05 Lead Time | 675863959 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863975
3550595 | 675860888 | 06 Tuning | 675864948 | 06 Lead Time Comments | 675865069 | 06 Lead Time | 675865098 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865150
3550595 | 675860888 | 06 Tuning | 675864948 | 06 Lead Time Comments | 675865069 | 06 Lead Time | 675865098 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865205
3550596 | 675860890 | 01 Installation End | 675864538 | 01 Lead Time Comments | 675864686 | 01 Lead Time | 675864700 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864713
3550596 | 675860890 | 02 Integration | 675864764 | 02 Lead Time Comments | 675864971 | 02 Lead Time | 675864985 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864998
3550596 | 675860890 | 02 Integration | 675864764 | 02 Lead Time Comments | 675864971 | 02 Lead Time | 675864985 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865029
3550596 | 675860890 | 03 Integration Confirmed By NRO Technical Leader | 675864059 | 03 Lead Time Comments | 675864123 | 03 Lead Time | 675864135 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864156
3550596 | 675860890 | 04 SSV | 675865074 | 04 Lead Time Comments | 675865289 | 04 Lead Time | 675865320 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865352
3550596 | 675860890 | 04 SSV | 675865074 | 04 Lead Time Comments | 675865289 | 04 Lead Time | 675865320 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865411
3550596 | 675860890 | 05 SSV Confirmed By NDO Technical Leader | 675864207 | 05 Lead Time Comments | 675864318 | 05 Lead Time | 675864332 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864341
3550596 | 675860890 | 06 Tuning | 675865486 | 06 Lead Time Comments | 675865650 | 06 Lead Time | 675865669 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865696
3550596 | 675860890 | 06 Tuning | 675865486 | 06 Lead Time Comments | 675865650 | 06 Lead Time | 675865669 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865752
3550599 | 675860887 | 01 Installation End | 675864160 | 01 Lead Time Comments | 675864288 | 01 Lead Time | 675864302 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864325
3550599 | 675860887 | 02 Integration | 675864352 | 02 Lead Time Comments | 675864541 | 02 Lead Time | 675864587 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864607
3550599 | 675860887 | 02 Integration | 675864352 | 02 Lead Time Comments | 675864541 | 02 Lead Time | 675864587 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864642
3550599 | 675860887 | 03 Integration Confirmed By NRO Technical Leader | 675863827 | 03 Lead Time Comments | 675863893 | 03 Lead Time | 675863910 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863917
3550599 | 675860887 | 04 SSV | 675864671 | 04 Lead Time Comments | 675864852 | 04 Lead Time | 675864903 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864923
3550599 | 675860887 | 04 SSV | 675864671 | 04 Lead Time Comments | 675864852 | 04 Lead Time | 675864903 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864952
3550599 | 675860887 | 05 SSV Confirmed By NDO Technical Leader | 675863938 | 05 Lead Time Comments | 675864003 | 05 Lead Time | 675864021 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864034
3550599 | 675860887 | 06 Tuning | 675864980 | 06 Lead Time Comments | 675865133 | 06 Lead Time | 675865168 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865198
3550599 | 675860887 | 06 Tuning | 675864980 | 06 Lead Time Comments | 675865133 | 06 Lead Time | 675865168 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865253
3550600 | 675860894 | 01 Installation End | 675864791 | 01 Lead Time Comments | 675864969 | 01 Lead Time | 675864992 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865006
3550600 | 675860894 | 02 Integration | 675865047 | 02 Lead Time Comments | 675865236 | 02 Lead Time | 675865272 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865297
3550600 | 675860894 | 02 Integration | 675865047 | 02 Lead Time Comments | 675865236 | 02 Lead Time | 675865272 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865346
3550600 | 675860894 | 03 Integration Confirmed By NRO Technical Leader | 675864170 | 03 Lead Time Comments | 675864290 | 03 Lead Time | 675864300 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864323
3550600 | 675860894 | 04 SSV | 675865418 | 04 Lead Time Comments | 675865603 | 04 Lead Time | 675865627 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865651
3550600 | 675860894 | 04 SSV | 675865418 | 04 Lead Time Comments | 675865603 | 04 Lead Time | 675865627 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865691
3550600 | 675860894 | 05 SSV Confirmed By NDO Technical Leader | 675864348 | 05 Lead Time Comments | 675864504 | 05 Lead Time | 675864553 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864593
3550600 | 675860894 | 06 Tuning | 675865756 | 06 Lead Time Comments | 675865910 | 06 Lead Time | 675865931 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865956
3550600 | 675860894 | 06 Tuning | 675865756 | 06 Lead Time Comments | 675865910 | 06 Lead Time | 675865931 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865995
3550601 | 675860895 | 01 Installation End | 675862789 | 01 Lead Time Comments | 675862873 | 01 Lead Time | 675862879 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862885
3550601 | 675860895 | 02 Integration | 675862903 | 02 Lead Time Comments | 675862965 | 02 Lead Time | 675862978 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862996
3550601 | 675860895 | 02 Integration | 675862903 | 02 Lead Time Comments | 675862965 | 02 Lead Time | 675862978 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863020
3550601 | 675860895 | 03 Integration Confirmed By NRO Technical Leader | 675862400 | 03 Lead Time Comments | 675862484 | 03 Lead Time | 675862502 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862509
3550601 | 675860895 | 04 SSV | 675863043 | 04 Lead Time Comments | 675863165 | 04 Lead Time | 675863188 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863198
3550601 | 675860895 | 04 SSV | 675863043 | 04 Lead Time Comments | 675863165 | 04 Lead Time | 675863188 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863233
3550601 | 675860895 | 05 SSV Confirmed By NDO Technical Leader | 675862529 | 05 Lead Time Comments | 675862603 | 05 Lead Time | 675862628 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862644
3550601 | 675860895 | 06 Tuning | 675863276 | 06 Lead Time Comments | 675863457 | 06 Lead Time | 675863467 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863479
3550601 | 675860895 | 06 Tuning | 675863276 | 06 Lead Time Comments | 675863457 | 06 Lead Time | 675863467 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863507
3550603 | 675860926 | 01 Installation End | 675863587 | 01 Lead Time Comments | 675863635 | 01 Lead Time | 675863649 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863663
3550603 | 675860926 | 02 Integration | 675863694 | 02 Lead Time Comments | 675863739 | 02 Lead Time | 675863747 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863757
3550603 | 675860926 | 02 Integration | 675863694 | 02 Lead Time Comments | 675863739 | 02 Lead Time | 675863747 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863774
3550603 | 675860926 | 03 Integration Confirmed By NRO Technical Leader | 675863202 | 03 Lead Time Comments | 675863288 | 03 Lead Time | 675863305 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863327
3550603 | 675860926 | 04 SSV | 675863789 | 04 Lead Time Comments | 675863858 | 04 Lead Time | 675863872 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863880
3550603 | 675860926 | 04 SSV | 675863789 | 04 Lead Time Comments | 675863858 | 04 Lead Time | 675863872 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863905
3550603 | 675860926 | 05 SSV Confirmed By NDO Technical Leader | 675863374 | 05 Lead Time Comments | 675863454 | 05 Lead Time | 675863465 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863472
3550603 | 675860926 | 06 Tuning | 675863920 | 06 Lead Time Comments | 675863986 | 06 Lead Time | 675864008 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675864025
3550603 | 675860926 | 06 Tuning | 675863920 | 06 Lead Time Comments | 675863986 | 06 Lead Time | 675864008 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675864048
3550604 | 675861107 | 01 Installation End | 675864141 | 01 Lead Time Comments | 675864253 | 01 Lead Time | 675864285 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864304
3550604 | 675861107 | 02 Integration | 675864337 | 02 Lead Time Comments | 675864547 | 02 Lead Time | 675864589 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864612
3550604 | 675861107 | 02 Integration | 675864337 | 02 Lead Time Comments | 675864547 | 02 Lead Time | 675864589 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864645
3550604 | 675861107 | 03 Integration Confirmed By NRO Technical Leader | 675863828 | 03 Lead Time Comments | 675863891 | 03 Lead Time | 675863907 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863914
3550604 | 675861107 | 04 SSV | 675864668 | 04 Lead Time Comments | 675864855 | 04 Lead Time | 675864882 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864961
3550604 | 675861107 | 04 SSV | 675864668 | 04 Lead Time Comments | 675864855 | 04 Lead Time | 675864882 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864990
3550604 | 675861107 | 05 SSV Confirmed By NDO Technical Leader | 675863930 | 05 Lead Time Comments | 675864002 | 05 Lead Time | 675864026 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864038
3550604 | 675861107 | 06 Tuning | 675865035 | 06 Lead Time Comments | 675865213 | 06 Lead Time | 675865274 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865302
3550604 | 675861107 | 06 Tuning | 675865035 | 06 Lead Time Comments | 675865213 | 06 Lead Time | 675865274 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865354
3550605 | 675861109 | 01 Installation End | 675862178 | 01 Lead Time Comments | 675862209 | 01 Lead Time | 675862224 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862234
3550605 | 675861109 | 02 Integration | 675862259 | 02 Lead Time Comments | 675862302 | 02 Lead Time | 675862316 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862331
3550605 | 675861109 | 02 Integration | 675862259 | 02 Lead Time Comments | 675862302 | 02 Lead Time | 675862316 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862353
3550605 | 675861109 | 03 Integration Confirmed By NRO Technical Leader | 675861959 | 03 Lead Time Comments | 675862005 | 03 Lead Time | 675862021 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862044
3550605 | 675861109 | 04 SSV | 675862381 | 04 Lead Time Comments | 675862426 | 04 Lead Time | 675862445 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862462
3550605 | 675861109 | 04 SSV | 675862381 | 04 Lead Time Comments | 675862426 | 04 Lead Time | 675862445 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862489
3550605 | 675861109 | 05 SSV Confirmed By NDO Technical Leader | 675862050 | 05 Lead Time Comments | 675862085 | 05 Lead Time | 675862101 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862106
3550605 | 675861109 | 06 Tuning | 675862513 | 06 Lead Time Comments | 675862593 | 06 Lead Time | 675862622 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862639
3550605 | 675861109 | 06 Tuning | 675862513 | 06 Lead Time Comments | 675862593 | 06 Lead Time | 675862622 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862673
3550607 | 675861246 | 01 Installation End | 675864856 | 01 Lead Time Comments | 675865040 | 01 Lead Time | 675865058 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865081
3550607 | 675861246 | 02 Integration | 675865135 | 02 Lead Time Comments | 675865316 | 02 Lead Time | 675865338 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865360
3550607 | 675861246 | 02 Integration | 675865135 | 02 Lead Time Comments | 675865316 | 02 Lead Time | 675865338 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865409
3550607 | 675861246 | 03 Integration Confirmed By NRO Technical Leader | 675864241 | 03 Lead Time Comments | 675864387 | 03 Lead Time | 675864395 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864416
3550607 | 675861246 | 04 SSV | 675865480 | 04 Lead Time Comments | 675865634 | 04 Lead Time | 675865654 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865667
3550607 | 675861246 | 04 SSV | 675865480 | 04 Lead Time Comments | 675865634 | 04 Lead Time | 675865654 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865709
3550607 | 675861246 | 05 SSV Confirmed By NDO Technical Leader | 675864469 | 05 Lead Time Comments | 675864630 | 05 Lead Time | 675864652 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864663
3550607 | 675861246 | 06 Tuning | 675865765 | 06 Lead Time Comments | 675865906 | 06 Lead Time | 675865924 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865948
3550607 | 675861246 | 06 Tuning | 675865765 | 06 Lead Time Comments | 675865906 | 06 Lead Time | 675865924 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865988
3550608 | 675861264 | 01 Installation End | 675865044 | 01 Lead Time Comments | 675865225 | 01 Lead Time | 675865252 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865282
3550608 | 675861264 | 02 Integration | 675865341 | 02 Lead Time Comments | 675865527 | 02 Lead Time | 675865558 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865586
3550608 | 675861264 | 02 Integration | 675865341 | 02 Lead Time Comments | 675865527 | 02 Lead Time | 675865558 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865628
3550608 | 675861264 | 03 Integration Confirmed By NRO Technical Leader | 675864265 | 03 Lead Time Comments | 675864424 | 03 Lead Time | 675864448 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864467
3550608 | 675861264 | 04 SSV | 675865680 | 04 Lead Time Comments | 675865844 | 04 Lead Time | 675865871 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865890
3550608 | 675861264 | 04 SSV | 675865680 | 04 Lead Time Comments | 675865844 | 04 Lead Time | 675865871 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865933
3550608 | 675861264 | 05 SSV Confirmed By NDO Technical Leader | 675864523 | 05 Lead Time Comments | 675864715 | 05 Lead Time | 675864732 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864755
3550608 | 675861264 | 06 Tuning | 675865982 | 06 Lead Time Comments | 675866114 | 06 Lead Time | 675866135 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866152
3550608 | 675861264 | 06 Tuning | 675865982 | 06 Lead Time Comments | 675866114 | 06 Lead Time | 675866135 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866199
3550609 | 675861269 | 01 Installation End | 675864222 | 01 Lead Time Comments | 675864351 | 01 Lead Time | 675864369 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864381
3550609 | 675861269 | 02 Integration | 675864402 | 02 Lead Time Comments | 675864608 | 02 Lead Time | 675864624 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864647
3550609 | 675861269 | 02 Integration | 675864402 | 02 Lead Time Comments | 675864608 | 02 Lead Time | 675864624 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864666
3550609 | 675861269 | 03 Integration Confirmed By NRO Technical Leader | 675863885 | 03 Lead Time Comments | 675863934 | 03 Lead Time | 675863946 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863967
3550609 | 675861269 | 04 SSV | 675864690 | 04 Lead Time Comments | 675864884 | 04 Lead Time | 675864913 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864927
3550609 | 675861269 | 04 SSV | 675864690 | 04 Lead Time Comments | 675864884 | 04 Lead Time | 675864913 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864955
3550609 | 675861269 | 05 SSV Confirmed By NDO Technical Leader | 675863991 | 05 Lead Time Comments | 675864071 | 05 Lead Time | 675864091 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864109
3550609 | 675861269 | 06 Tuning | 675864987 | 06 Lead Time Comments | 675865172 | 06 Lead Time | 675865206 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865239
3550609 | 675861269 | 06 Tuning | 675864987 | 06 Lead Time Comments | 675865172 | 06 Lead Time | 675865206 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865292
3550610 | 675861273 | 01 Installation End | 675862246 | 01 Lead Time Comments | 675862288 | 01 Lead Time | 675862292 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862297
3550610 | 675861273 | 02 Integration | 675862328 | 02 Lead Time Comments | 675862383 | 02 Lead Time | 675862389 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862392
3550610 | 675861273 | 02 Integration | 675862328 | 02 Lead Time Comments | 675862383 | 02 Lead Time | 675862389 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862397
3550610 | 675861273 | 03 Integration Confirmed By NRO Technical Leader | 675862038 | 03 Lead Time Comments | 675862061 | 03 Lead Time | 675862076 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862100
3550610 | 675861273 | 04 SSV | 675862401 | 04 Lead Time Comments | 675862499 | 04 Lead Time | 675862508 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862522
3550610 | 675861273 | 04 SSV | 675862401 | 04 Lead Time Comments | 675862499 | 04 Lead Time | 675862508 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862534
3550610 | 675861273 | 05 SSV Confirmed By NDO Technical Leader | 675862124 | 05 Lead Time Comments | 675862153 | 05 Lead Time | 675862176 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862182
3550610 | 675861273 | 06 Tuning | 675862558 | 06 Lead Time Comments | 675862658 | 06 Lead Time | 675862679 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862693
3550610 | 675861273 | 06 Tuning | 675862558 | 06 Lead Time Comments | 675862658 | 06 Lead Time | 675862679 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862716
3550611 | 675861295 | 01 Installation End | 675863950 | 01 Lead Time Comments | 675864024 | 01 Lead Time | 675864035 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864047
3550611 | 675861295 | 02 Integration | 675864076 | 02 Lead Time Comments | 675864187 | 02 Lead Time | 675864201 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864217
3550611 | 675861295 | 02 Integration | 675864076 | 02 Lead Time Comments | 675864187 | 02 Lead Time | 675864201 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864236
3550611 | 675861295 | 03 Integration Confirmed By NRO Technical Leader | 675863678 | 03 Lead Time Comments | 675863768 | 03 Lead Time | 675863778 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863784
3550611 | 675861295 | 04 SSV | 675864305 | 04 Lead Time Comments | 675864486 | 04 Lead Time | 675864526 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864571
3550611 | 675861295 | 04 SSV | 675864305 | 04 Lead Time Comments | 675864486 | 04 Lead Time | 675864526 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864616
3550611 | 675861295 | 05 SSV Confirmed By NDO Technical Leader | 675863809 | 05 Lead Time Comments | 675863854 | 05 Lead Time | 675863865 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863876
3550611 | 675861295 | 06 Tuning | 675864657 | 06 Lead Time Comments | 675864865 | 06 Lead Time | 675864890 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675864915
3550611 | 675861295 | 06 Tuning | 675864657 | 06 Lead Time Comments | 675864865 | 06 Lead Time | 675864890 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675864944
3550612 | 675861296 | 01 Installation End | 675862805 | 01 Lead Time Comments | 675862878 | 01 Lead Time | 675862883 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862892
3550612 | 675861296 | 02 Integration | 675862913 | 02 Lead Time Comments | 675862976 | 02 Lead Time | 675862988 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863005
3550612 | 675861296 | 02 Integration | 675862913 | 02 Lead Time Comments | 675862976 | 02 Lead Time | 675862988 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863035
3550612 | 675861296 | 03 Integration Confirmed By NRO Technical Leader | 675862403 | 03 Lead Time Comments | 675862492 | 03 Lead Time | 675862505 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862512
3550612 | 675861296 | 04 SSV | 675863055 | 04 Lead Time Comments | 675863153 | 04 Lead Time | 675863172 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863191
3550612 | 675861296 | 04 SSV | 675863055 | 04 Lead Time Comments | 675863153 | 04 Lead Time | 675863172 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863225
3550612 | 675861296 | 05 SSV Confirmed By NDO Technical Leader | 675862533 | 05 Lead Time Comments | 675862616 | 05 Lead Time | 675862635 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862653
3550612 | 675861296 | 06 Tuning | 675863267 | 06 Lead Time Comments | 675863396 | 06 Lead Time | 675863417 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863427
3550612 | 675861296 | 06 Tuning | 675863267 | 06 Lead Time Comments | 675863396 | 06 Lead Time | 675863417 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863447
3550613 | 675861292 | 01 Installation End | 675864320 | 01 Lead Time Comments | 675864471 | 01 Lead Time | 675864492 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864534
3550613 | 675861292 | 02 Integration | 675864611 | 02 Lead Time Comments | 675864746 | 02 Lead Time | 675864774 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864810
3550613 | 675861292 | 02 Integration | 675864611 | 02 Lead Time Comments | 675864746 | 02 Lead Time | 675864774 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864878
3550613 | 675861292 | 03 Integration Confirmed By NRO Technical Leader | 675863927 | 03 Lead Time Comments | 675863985 | 03 Lead Time | 675863999 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864020
3550613 | 675861292 | 04 SSV | 675864929 | 04 Lead Time Comments | 675865127 | 04 Lead Time | 675865154 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865185
3550613 | 675861292 | 04 SSV | 675864929 | 04 Lead Time Comments | 675865127 | 04 Lead Time | 675865154 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865242
3550613 | 675861292 | 05 SSV Confirmed By NDO Technical Leader | 675864049 | 05 Lead Time Comments | 675864120 | 05 Lead Time | 675864131 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864142
3550613 | 675861292 | 06 Tuning | 675865312 | 06 Lead Time Comments | 675865503 | 06 Lead Time | 675865529 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865556
3550613 | 675861292 | 06 Tuning | 675865312 | 06 Lead Time Comments | 675865503 | 06 Lead Time | 675865529 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865606
3550614 | 675861290 | 01 Installation End | 675865013 | 01 Lead Time Comments | 675865164 | 01 Lead Time | 675865193 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865219
3550614 | 675861290 | 02 Integration | 675865286 | 02 Lead Time Comments | 675865476 | 02 Lead Time | 675865506 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865540
3550614 | 675861290 | 02 Integration | 675865286 | 02 Lead Time Comments | 675865476 | 02 Lead Time | 675865506 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865592
3550614 | 675861290 | 03 Integration Confirmed By NRO Technical Leader | 675864248 | 03 Lead Time Comments | 675864396 | 03 Lead Time | 675864419 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864443
3550614 | 675861290 | 04 SSV | 675865641 | 04 Lead Time Comments | 675865816 | 04 Lead Time | 675865839 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865861
3550614 | 675861290 | 04 SSV | 675865641 | 04 Lead Time Comments | 675865816 | 04 Lead Time | 675865839 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866111
3550614 | 675861290 | 05 SSV Confirmed By NDO Technical Leader | 675864497 | 05 Lead Time Comments | 675864702 | 05 Lead Time | 675864714 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864731
3550614 | 675861290 | 06 Tuning | 675866155 | 06 Lead Time Comments | 675866360 | 06 Lead Time | 675866364 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866370
3550614 | 675861290 | 06 Tuning | 675866155 | 06 Lead Time Comments | 675866360 | 06 Lead Time | 675866364 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866381
3550616 | 675861294 | 01 Installation End | 675864830 | 01 Lead Time Comments | 675865037 | 01 Lead Time | 675865054 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865072
3550616 | 675861294 | 02 Integration | 675865134 | 02 Lead Time Comments | 675865331 | 02 Lead Time | 675865358 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865386
3550616 | 675861294 | 02 Integration | 675865134 | 02 Lead Time Comments | 675865331 | 02 Lead Time | 675865358 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865444
3550616 | 675861294 | 03 Integration Confirmed By NRO Technical Leader | 675864177 | 03 Lead Time Comments | 675864298 | 03 Lead Time | 675864313 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864328
3550616 | 675861294 | 04 SSV | 675865526 | 04 Lead Time Comments | 675865684 | 04 Lead Time | 675865707 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865735
3550616 | 675861294 | 04 SSV | 675865526 | 04 Lead Time Comments | 675865684 | 04 Lead Time | 675865707 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865789
3550616 | 675861294 | 05 SSV Confirmed By NDO Technical Leader | 675864371 | 05 Lead Time Comments | 675864539 | 05 Lead Time | 675864580 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864610
3550616 | 675861294 | 06 Tuning | 675865847 | 06 Lead Time Comments | 675865968 | 06 Lead Time | 675865994 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866014
3550616 | 675861294 | 06 Tuning | 675865847 | 06 Lead Time Comments | 675865968 | 06 Lead Time | 675865994 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866054
3550617 | 675861331 | 01 Installation End | 675864656 | 01 Lead Time Comments | 675864829 | 01 Lead Time | 675864868 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864892
3550617 | 675861331 | 02 Integration | 675864933 | 02 Lead Time Comments | 675865123 | 02 Lead Time | 675865146 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865181
3550617 | 675861331 | 02 Integration | 675864933 | 02 Lead Time Comments | 675865123 | 02 Lead Time | 675865146 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865227
3550617 | 675861331 | 03 Integration Confirmed By NRO Technical Leader | 675864083 | 03 Lead Time Comments | 675864151 | 03 Lead Time | 675864181 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864195
3550617 | 675861331 | 04 SSV | 675865281 | 04 Lead Time Comments | 675865462 | 04 Lead Time | 675865495 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865512
3550617 | 675861331 | 04 SSV | 675865281 | 04 Lead Time Comments | 675865462 | 04 Lead Time | 675865495 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865570
3550617 | 675861331 | 05 SSV Confirmed By NDO Technical Leader | 675864234 | 05 Lead Time Comments | 675864384 | 05 Lead Time | 675864390 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864410
3550617 | 675861331 | 06 Tuning | 675865619 | 06 Lead Time Comments | 675865768 | 06 Lead Time | 675865802 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865824
3550617 | 675861331 | 06 Tuning | 675865619 | 06 Lead Time Comments | 675865768 | 06 Lead Time | 675865802 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865866
3550618 | 675861340 | 01 Installation End | 675864883 | 01 Lead Time Comments | 675865064 | 01 Lead Time | 675865087 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865115
3550618 | 675861340 | 02 Integration | 675865173 | 02 Lead Time Comments | 675865355 | 02 Lead Time | 675865379 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865408
3550618 | 675861340 | 02 Integration | 675865173 | 02 Lead Time Comments | 675865355 | 02 Lead Time | 675865379 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865471
3550618 | 675861340 | 03 Integration Confirmed By NRO Technical Leader | 675864267 | 03 Lead Time Comments | 675864397 | 03 Lead Time | 675864420 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864440
3550618 | 675861340 | 04 SSV | 675865562 | 04 Lead Time Comments | 675865725 | 04 Lead Time | 675865827 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865849
3550618 | 675861340 | 04 SSV | 675865562 | 04 Lead Time Comments | 675865725 | 04 Lead Time | 675865827 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865882
3550618 | 675861340 | 05 SSV Confirmed By NDO Technical Leader | 675864484 | 05 Lead Time Comments | 675864669 | 05 Lead Time | 675864673 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864680
3550618 | 675861340 | 06 Tuning | 675865925 | 06 Lead Time Comments | 675866041 | 06 Lead Time | 675866066 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866085
3550618 | 675861340 | 06 Tuning | 675865925 | 06 Lead Time Comments | 675866041 | 06 Lead Time | 675866066 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866125
3550619 | 675861361 | 01 Installation End | 675864818 | 01 Lead Time Comments | 675865026 | 01 Lead Time | 675865036 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865057
3550619 | 675861361 | 02 Integration | 675865119 | 02 Lead Time Comments | 675865322 | 02 Lead Time | 675865344 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865370
3550619 | 675861361 | 02 Integration | 675865119 | 02 Lead Time Comments | 675865322 | 02 Lead Time | 675865344 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865419
3550619 | 675861361 | 03 Integration Confirmed By NRO Technical Leader | 675864162 | 03 Lead Time Comments | 675864284 | 03 Lead Time | 675864303 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864334
3550619 | 675861361 | 04 SSV | 675865487 | 04 Lead Time Comments | 675865647 | 04 Lead Time | 675865663 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865686
3550619 | 675861361 | 04 SSV | 675865487 | 04 Lead Time Comments | 675865647 | 04 Lead Time | 675865663 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865730
3550619 | 675861361 | 05 SSV Confirmed By NDO Technical Leader | 675864361 | 05 Lead Time Comments | 675864500 | 05 Lead Time | 675864550 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864588
3550619 | 675861361 | 06 Tuning | 675865783 | 06 Lead Time Comments | 675865936 | 06 Lead Time | 675865954 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865974
3550619 | 675861361 | 06 Tuning | 675865783 | 06 Lead Time Comments | 675865936 | 06 Lead Time | 675865954 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866011
3550620 | 675861366 | 01 Installation End | 675864917 | 01 Lead Time Comments | 675865104 | 01 Lead Time | 675865126 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865155
3550620 | 675861366 | 02 Integration | 675865218 | 02 Lead Time Comments | 675865385 | 02 Lead Time | 675865416 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865443
3550620 | 675861366 | 02 Integration | 675865218 | 02 Lead Time Comments | 675865385 | 02 Lead Time | 675865416 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865494
3550620 | 675861366 | 03 Integration Confirmed By NRO Technical Leader | 675864242 | 03 Lead Time Comments | 675864399 | 03 Lead Time | 675864426 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864446
3550620 | 675861366 | 04 SSV | 675865566 | 04 Lead Time Comments | 675865694 | 04 Lead Time | 675865726 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865746
3550620 | 675861366 | 04 SSV | 675865566 | 04 Lead Time Comments | 675865694 | 04 Lead Time | 675865726 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865822
3550620 | 675861366 | 05 SSV Confirmed By NDO Technical Leader | 675864489 | 05 Lead Time Comments | 675864676 | 05 Lead Time | 675864685 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864697
3550620 | 675861366 | 06 Tuning | 675865867 | 06 Lead Time Comments | 675865978 | 06 Lead Time | 675865997 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866020
3550620 | 675861366 | 06 Tuning | 675865867 | 06 Lead Time Comments | 675865978 | 06 Lead Time | 675865997 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866060
3550621 | 675861382 | 01 Installation End | 675864752 | 01 Lead Time Comments | 675864946 | 01 Lead Time | 675864958 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864967
3550621 | 675861382 | 02 Integration | 675864996 | 02 Lead Time Comments | 675865175 | 02 Lead Time | 675865199 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865222
3550621 | 675861382 | 02 Integration | 675864996 | 02 Lead Time Comments | 675865175 | 02 Lead Time | 675865199 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865270
3550621 | 675861382 | 03 Integration Confirmed By NRO Technical Leader | 675864146 | 03 Lead Time Comments | 675864282 | 03 Lead Time | 675864295 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864308
3550621 | 675861382 | 04 SSV | 675865330 | 04 Lead Time Comments | 675865515 | 04 Lead Time | 675865543 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865571
3550621 | 675861382 | 04 SSV | 675865330 | 04 Lead Time Comments | 675865515 | 04 Lead Time | 675865543 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865612
3550621 | 675861382 | 05 SSV Confirmed By NDO Technical Leader | 675864338 | 05 Lead Time Comments | 675864478 | 05 Lead Time | 675864490 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864525
3550621 | 675861382 | 06 Tuning | 675865716 | 06 Lead Time Comments | 675865859 | 06 Lead Time | 675865879 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865901
3550621 | 675861382 | 06 Tuning | 675865716 | 06 Lead Time Comments | 675865859 | 06 Lead Time | 675865879 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865930
3550622 | 675861414 | 01 Installation End | 675864960 | 01 Lead Time Comments | 675865083 | 01 Lead Time | 675865111 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865139
3550622 | 675861414 | 02 Integration | 675865212 | 02 Lead Time Comments | 675865405 | 02 Lead Time | 675865435 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865467
3550622 | 675861414 | 02 Integration | 675865212 | 02 Lead Time Comments | 675865405 | 02 Lead Time | 675865435 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865532
3550622 | 675861414 | 03 Integration Confirmed By NRO Technical Leader | 675864247 | 03 Lead Time Comments | 675864394 | 03 Lead Time | 675864422 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864445
3550622 | 675861414 | 04 SSV | 675865595 | 04 Lead Time Comments | 675865753 | 04 Lead Time | 675865785 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865812
3550622 | 675861414 | 04 SSV | 675865595 | 04 Lead Time Comments | 675865753 | 04 Lead Time | 675865785 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865856
3550622 | 675861414 | 05 SSV Confirmed By NDO Technical Leader | 675864493 | 05 Lead Time Comments | 675864688 | 05 Lead Time | 675864703 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864717
3550622 | 675861414 | 06 Tuning | 675865907 | 06 Lead Time Comments | 675866021 | 06 Lead Time | 675866040 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866063
3550622 | 675861414 | 06 Tuning | 675865907 | 06 Lead Time Comments | 675866021 | 06 Lead Time | 675866040 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866103
3550623 | 675861423 | 01 Installation End | 675862930 | 01 Lead Time Comments | 675862977 | 01 Lead Time | 675862989 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863001
3550623 | 675861423 | 02 Integration | 675863030 | 02 Lead Time Comments | 675863109 | 02 Lead Time | 675863128 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863151
3550623 | 675861423 | 02 Integration | 675863030 | 02 Lead Time Comments | 675863109 | 02 Lead Time | 675863128 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863190
3550623 | 675861423 | 03 Integration Confirmed By NRO Technical Leader | 675862517 | 03 Lead Time Comments | 675862569 | 03 Lead Time | 675862592 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862615
3550623 | 675861423 | 04 SSV | 675863228 | 04 Lead Time Comments | 675863354 | 04 Lead Time | 675863379 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863395
3550623 | 675861423 | 04 SSV | 675863228 | 04 Lead Time Comments | 675863354 | 04 Lead Time | 675863379 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863424
3550623 | 675861423 | 05 SSV Confirmed By NDO Technical Leader | 675862655 | 05 Lead Time Comments | 675862749 | 05 Lead Time | 675862779 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862832
3550623 | 675861423 | 06 Tuning | 675863453 | 06 Lead Time Comments | 675863527 | 06 Lead Time | 675863542 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863571
3550623 | 675861423 | 06 Tuning | 675863453 | 06 Lead Time Comments | 675863527 | 06 Lead Time | 675863542 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863589
3550625 | 675861439 | 01 Installation End | 675864088 | 01 Lead Time Comments | 675864189 | 01 Lead Time | 675864204 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864218
3550625 | 675861439 | 02 Integration | 675864254 | 02 Lead Time Comments | 675864432 | 02 Lead Time | 675864456 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864482
3550625 | 675861439 | 02 Integration | 675864254 | 02 Lead Time Comments | 675864432 | 02 Lead Time | 675864456 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864548
3550625 | 675861439 | 03 Integration Confirmed By NRO Technical Leader | 675863792 | 03 Lead Time Comments | 675863840 | 03 Lead Time | 675863853 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863866
3550625 | 675861439 | 04 SSV | 675864617 | 04 Lead Time Comments | 675864758 | 04 Lead Time | 675864793 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864837
3550625 | 675861439 | 04 SSV | 675864617 | 04 Lead Time Comments | 675864758 | 04 Lead Time | 675864793 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864916
3550625 | 675861439 | 05 SSV Confirmed By NDO Technical Leader | 675863889 | 05 Lead Time Comments | 675863942 | 05 Lead Time | 675863954 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863973
3550625 | 675861439 | 06 Tuning | 675864953 | 06 Lead Time Comments | 675865195 | 06 Lead Time | 675865230 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865251
3550625 | 675861439 | 06 Tuning | 675864953 | 06 Lead Time Comments | 675865195 | 06 Lead Time | 675865230 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865306
3550626 | 675861451 | 01 Installation End | 675865014 | 01 Lead Time Comments | 675865174 | 01 Lead Time | 675865203 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865237
3550626 | 675861451 | 02 Integration | 675865304 | 02 Lead Time Comments | 675865485 | 02 Lead Time | 675865521 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865548
3550626 | 675861451 | 02 Integration | 675865304 | 02 Lead Time Comments | 675865485 | 02 Lead Time | 675865521 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865598
3550626 | 675861451 | 03 Integration Confirmed By NRO Technical Leader | 675864240 | 03 Lead Time Comments | 675864405 | 03 Lead Time | 675864431 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864479
3550626 | 675861451 | 04 SSV | 675865645 | 04 Lead Time Comments | 675865810 | 04 Lead Time | 675865832 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865858
3550626 | 675861451 | 04 SSV | 675865645 | 04 Lead Time Comments | 675865810 | 04 Lead Time | 675865832 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865902
3550626 | 675861451 | 05 SSV Confirmed By NDO Technical Leader | 675864536 | 05 Lead Time Comments | 675864728 | 05 Lead Time | 675864773 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864800
3550626 | 675861451 | 06 Tuning | 675865950 | 06 Lead Time Comments | 675866072 | 06 Lead Time | 675866095 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866117
3550626 | 675861451 | 06 Tuning | 675865950 | 06 Lead Time Comments | 675866072 | 06 Lead Time | 675866095 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866157
3550627 | 675861456 | 01 Installation End | 675864761 | 01 Lead Time Comments | 675864954 | 01 Lead Time | 675864963 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864982
3550627 | 675861456 | 02 Integration | 675865011 | 02 Lead Time Comments | 675865192 | 02 Lead Time | 675865220 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865246
3550627 | 675861456 | 02 Integration | 675865011 | 02 Lead Time Comments | 675865192 | 02 Lead Time | 675865220 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865311
3550627 | 675861456 | 03 Integration Confirmed By NRO Technical Leader | 675864176 | 03 Lead Time Comments | 675864293 | 03 Lead Time | 675864310 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864327
3550627 | 675861456 | 04 SSV | 675865364 | 04 Lead Time Comments | 675865568 | 04 Lead Time | 675865593 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865615
3550627 | 675861456 | 04 SSV | 675865364 | 04 Lead Time Comments | 675865568 | 04 Lead Time | 675865593 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865659
3550627 | 675861456 | 05 SSV Confirmed By NDO Technical Leader | 675864355 | 05 Lead Time Comments | 675864498 | 05 Lead Time | 675864546 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864592
3550627 | 675861456 | 06 Tuning | 675865722 | 06 Lead Time Comments | 675865887 | 06 Lead Time | 675865913 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865932
3550627 | 675861456 | 06 Tuning | 675865722 | 06 Lead Time Comments | 675865887 | 06 Lead Time | 675865913 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865970
3550628 | 675861457 | 01 Installation End | 675864811 | 01 Lead Time Comments | 675865004 | 01 Lead Time | 675865024 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865033
3550628 | 675861457 | 02 Integration | 675865071 | 02 Lead Time Comments | 675865244 | 02 Lead Time | 675865271 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865295
3550628 | 675861457 | 02 Integration | 675865071 | 02 Lead Time Comments | 675865244 | 02 Lead Time | 675865271 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865337
3550628 | 675861457 | 03 Integration Confirmed By NRO Technical Leader | 675864168 | 03 Lead Time Comments | 675864286 | 03 Lead Time | 675864301 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864324
3550628 | 675861457 | 04 SSV | 675865429 | 04 Lead Time Comments | 675865594 | 04 Lead Time | 675865614 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865637
3550628 | 675861457 | 04 SSV | 675865429 | 04 Lead Time Comments | 675865594 | 04 Lead Time | 675865614 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865675
3550628 | 675861457 | 05 SSV Confirmed By NDO Technical Leader | 675864349 | 05 Lead Time Comments | 675864511 | 05 Lead Time | 675864556 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864585
3550628 | 675861457 | 06 Tuning | 675865718 | 06 Lead Time Comments | 675865870 | 06 Lead Time | 675865886 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865908
3550628 | 675861457 | 06 Tuning | 675865718 | 06 Lead Time Comments | 675865870 | 06 Lead Time | 675865886 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865940
3550629 | 675861547 | 01 Installation End | 675864993 | 01 Lead Time Comments | 675865120 | 01 Lead Time | 675865145 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865176
3550629 | 675861547 | 02 Integration | 675865247 | 02 Lead Time Comments | 675865453 | 02 Lead Time | 675865492 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865522
3550629 | 675861547 | 02 Integration | 675865247 | 02 Lead Time Comments | 675865453 | 02 Lead Time | 675865492 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865581
3550629 | 675861547 | 03 Integration Confirmed By NRO Technical Leader | 675864263 | 03 Lead Time Comments | 675864393 | 03 Lead Time | 675864414 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864439
3550629 | 675861547 | 04 SSV | 675865633 | 04 Lead Time Comments | 675865860 | 04 Lead Time | 675865881 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865904
3550629 | 675861547 | 04 SSV | 675865633 | 04 Lead Time Comments | 675865860 | 04 Lead Time | 675865881 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865942
3550629 | 675861547 | 05 SSV Confirmed By NDO Technical Leader | 675864586 | 05 Lead Time Comments | 675864707 | 05 Lead Time | 675864723 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864745
3550629 | 675861547 | 06 Tuning | 675865991 | 06 Lead Time Comments | 675866121 | 06 Lead Time | 675866140 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866163
3550629 | 675861547 | 06 Tuning | 675865991 | 06 Lead Time Comments | 675866121 | 06 Lead Time | 675866140 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866210
3550630 | 675861552 | 01 Installation End | 675864364 | 01 Lead Time Comments | 675864533 | 01 Lead Time | 675864579 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864603
3550630 | 675861552 | 02 Integration | 675864653 | 02 Lead Time Comments | 675864869 | 02 Lead Time | 675864898 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864920
3550630 | 675861552 | 02 Integration | 675864653 | 02 Lead Time Comments | 675864869 | 02 Lead Time | 675864898 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864950
3550630 | 675861552 | 03 Integration Confirmed By NRO Technical Leader | 675863960 | 03 Lead Time Comments | 675864029 | 03 Lead Time | 675864040 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864050
3550630 | 675861552 | 04 SSV | 675864979 | 04 Lead Time Comments | 675865363 | 04 Lead Time | 675865465 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865499
3550630 | 675861552 | 04 SSV | 675864979 | 04 Lead Time Comments | 675865363 | 04 Lead Time | 675865465 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865554
3550630 | 675861552 | 05 SSV Confirmed By NDO Technical Leader | 675864072 | 05 Lead Time Comments | 675864147 | 05 Lead Time | 675864182 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864197
3550630 | 675861552 | 06 Tuning | 675865611 | 06 Lead Time Comments | 675865754 | 06 Lead Time | 675865777 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865803
3550630 | 675861552 | 06 Tuning | 675865611 | 06 Lead Time Comments | 675865754 | 06 Lead Time | 675865777 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865845
3550634 | 675861571 | 01 Installation End | 675863004 | 01 Lead Time Comments | 675863060 | 01 Lead Time | 675863066 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863098
3550634 | 675861571 | 02 Integration | 675863144 | 02 Lead Time Comments | 675863247 | 02 Lead Time | 675863263 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863283
3550634 | 675861571 | 02 Integration | 675863144 | 02 Lead Time Comments | 675863247 | 02 Lead Time | 675863263 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863319
3550634 | 675861571 | 03 Integration Confirmed By NRO Technical Leader | 675862607 | 03 Lead Time Comments | 675862753 | 03 Lead Time | 675862784 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862817
3550634 | 675861571 | 04 SSV | 675863364 | 04 Lead Time Comments | 675863458 | 04 Lead Time | 675863468 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863481
3550634 | 675861571 | 04 SSV | 675863364 | 04 Lead Time Comments | 675863458 | 04 Lead Time | 675863468 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863565
3550634 | 675861571 | 05 SSV Confirmed By NDO Technical Leader | 675862856 | 05 Lead Time Comments | 675862898 | 05 Lead Time | 675862909 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862920
3550634 | 675861571 | 06 Tuning | 675863591 | 06 Lead Time Comments | 675863656 | 06 Lead Time | 675863671 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863688
3550634 | 675861571 | 06 Tuning | 675863591 | 06 Lead Time Comments | 675863656 | 06 Lead Time | 675863671 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863704
3550635 | 675861572 | 01 Installation End | 675862385 | 01 Lead Time Comments | 675862410 | 01 Lead Time | 675862429 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862441
3550635 | 675861572 | 02 Integration | 675862474 | 02 Lead Time Comments | 675862548 | 02 Lead Time | 675862557 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675862565
3550635 | 675861572 | 02 Integration | 675862474 | 02 Lead Time Comments | 675862548 | 02 Lead Time | 675862557 | actcl--02 Integration--02 Lead Time Comments--Duration | 675862609
3550635 | 675861572 | 03 Integration Confirmed By NRO Technical Leader | 675862191 | 03 Lead Time Comments | 675862241 | 03 Lead Time | 675862252 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862260
3550635 | 675861572 | 04 SSV | 675862656 | 04 Lead Time Comments | 675862793 | 04 Lead Time | 675862823 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675862840
3550635 | 675861572 | 04 SSV | 675862656 | 04 Lead Time Comments | 675862793 | 04 Lead Time | 675862823 | actcl--04 SSV--04 Lead Time Comments--Duration | 675862870
3550635 | 675861572 | 05 SSV Confirmed By NDO Technical Leader | 675862265 | 05 Lead Time Comments | 675862293 | 05 Lead Time | 675862298 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862300
3550635 | 675861572 | 06 Tuning | 675862882 | 06 Lead Time Comments | 675862940 | 06 Lead Time | 675862947 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675862958
3550635 | 675861572 | 06 Tuning | 675862882 | 06 Lead Time Comments | 675862940 | 06 Lead Time | 675862947 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675862981
3550636 | 675861574 | 01 Installation End | 675864106 | 01 Lead Time Comments | 675864179 | 01 Lead Time | 675864194 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864213
3550636 | 675861574 | 02 Integration | 675864255 | 02 Lead Time Comments | 675864447 | 02 Lead Time | 675864472 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864491
3550636 | 675861574 | 02 Integration | 675864255 | 02 Lead Time Comments | 675864447 | 02 Lead Time | 675864472 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864577
3550636 | 675861574 | 03 Integration Confirmed By NRO Technical Leader | 675863790 | 03 Lead Time Comments | 675863843 | 03 Lead Time | 675863856 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863875
3550636 | 675861574 | 04 SSV | 675864622 | 04 Lead Time Comments | 675864850 | 04 Lead Time | 675864881 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675864911
3550636 | 675861574 | 04 SSV | 675864622 | 04 Lead Time Comments | 675864850 | 04 Lead Time | 675864881 | actcl--04 SSV--04 Lead Time Comments--Duration | 675864938
3550636 | 675861574 | 05 SSV Confirmed By NDO Technical Leader | 675863902 | 05 Lead Time Comments | 675863953 | 05 Lead Time | 675863971 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863980
3550636 | 675861574 | 06 Tuning | 675864970 | 06 Lead Time Comments | 675865165 | 06 Lead Time | 675865197 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865231
3550636 | 675861574 | 06 Tuning | 675864970 | 06 Lead Time Comments | 675865165 | 06 Lead Time | 675865197 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865283
3550637 | 675861569 | 01 Installation End | 675864975 | 01 Lead Time Comments | 675865141 | 01 Lead Time | 675865182 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865210
3550637 | 675861569 | 02 Integration | 675865287 | 02 Lead Time Comments | 675865507 | 02 Lead Time | 675865541 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865605
3550637 | 675861569 | 02 Integration | 675865287 | 02 Lead Time Comments | 675865507 | 02 Lead Time | 675865541 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865646
3550637 | 675861569 | 03 Integration Confirmed By NRO Technical Leader | 675864244 | 03 Lead Time Comments | 675864409 | 03 Lead Time | 675864436 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864458
3550637 | 675861569 | 04 SSV | 675865700 | 04 Lead Time Comments | 675865868 | 04 Lead Time | 675865953 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865972
3550637 | 675861569 | 04 SSV | 675865700 | 04 Lead Time Comments | 675865868 | 04 Lead Time | 675865953 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866013
3550637 | 675861569 | 05 SSV Confirmed By NDO Technical Leader | 675864519 | 05 Lead Time Comments | 675864683 | 05 Lead Time | 675864698 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864711
3550637 | 675861569 | 06 Tuning | 675866062 | 06 Lead Time Comments | 675866192 | 06 Lead Time | 675866215 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866234
3550637 | 675861569 | 06 Tuning | 675866062 | 06 Lead Time Comments | 675866192 | 06 Lead Time | 675866215 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866262
3550638 | 675861657 | 01 Installation End | 675864860 | 01 Lead Time Comments | 675865050 | 01 Lead Time | 675865067 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865094
3550638 | 675861657 | 02 Integration | 675865157 | 02 Lead Time Comments | 675865340 | 02 Lead Time | 675865371 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865406
3550638 | 675861657 | 02 Integration | 675865157 | 02 Lead Time Comments | 675865340 | 02 Lead Time | 675865371 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865469
3550638 | 675861657 | 03 Integration Confirmed By NRO Technical Leader | 675864172 | 03 Lead Time Comments | 675864292 | 03 Lead Time | 675864315 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864331
3550638 | 675861657 | 04 SSV | 675865537 | 04 Lead Time Comments | 675865692 | 04 Lead Time | 675865721 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865747
3550638 | 675861657 | 04 SSV | 675865537 | 04 Lead Time Comments | 675865692 | 04 Lead Time | 675865721 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865807
3550638 | 675861657 | 05 SSV Confirmed By NDO Technical Leader | 675864356 | 05 Lead Time Comments | 675864516 | 05 Lead Time | 675864563 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864596
3550638 | 675861657 | 06 Tuning | 675865863 | 06 Lead Time Comments | 675865979 | 06 Lead Time | 675866010 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866031
3550638 | 675861657 | 06 Tuning | 675865863 | 06 Lead Time Comments | 675865979 | 06 Lead Time | 675866010 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866076
3550639 | 675861656 | 01 Installation End | 675864363 | 01 Lead Time Comments | 675864505 | 01 Lead Time | 675864549 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864582
3550639 | 675861656 | 02 Integration | 675864626 | 02 Lead Time Comments | 675864770 | 02 Lead Time | 675864808 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864853
3550639 | 675861656 | 02 Integration | 675864626 | 02 Lead Time Comments | 675864770 | 02 Lead Time | 675864808 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864907
3550639 | 675861656 | 03 Integration Confirmed By NRO Technical Leader | 675863958 | 03 Lead Time Comments | 675864030 | 03 Lead Time | 675864044 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864051
3550639 | 675861656 | 04 SSV | 675864957 | 04 Lead Time Comments | 675865099 | 04 Lead Time | 675865125 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865149
3550639 | 675861656 | 04 SSV | 675864957 | 04 Lead Time Comments | 675865099 | 04 Lead Time | 675865125 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865207
3550639 | 675861656 | 05 SSV Confirmed By NDO Technical Leader | 675864073 | 05 Lead Time Comments | 675864140 | 05 Lead Time | 675864167 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864191
3550639 | 675861656 | 06 Tuning | 675865273 | 06 Lead Time Comments | 675865451 | 06 Lead Time | 675865484 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865517
3550639 | 675861656 | 06 Tuning | 675865273 | 06 Lead Time Comments | 675865451 | 06 Lead Time | 675865484 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865578
3550640 | 675861663 | 01 Installation End | 675862936 | 01 Lead Time Comments | 675862993 | 01 Lead Time | 675863008 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863017
3550640 | 675861663 | 02 Integration | 675863042 | 02 Lead Time Comments | 675863159 | 02 Lead Time | 675863179 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863196
3550640 | 675861663 | 02 Integration | 675863042 | 02 Lead Time Comments | 675863159 | 02 Lead Time | 675863179 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863238
3550640 | 675861663 | 03 Integration Confirmed By NRO Technical Leader | 675862552 | 03 Lead Time Comments | 675862647 | 03 Lead Time | 675862662 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862682
3550640 | 675861663 | 04 SSV | 675863268 | 04 Lead Time Comments | 675863398 | 04 Lead Time | 675863419 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863429
3550640 | 675861663 | 04 SSV | 675863268 | 04 Lead Time Comments | 675863398 | 04 Lead Time | 675863419 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863450
3550640 | 675861663 | 05 SSV Confirmed By NDO Technical Leader | 675862706 | 05 Lead Time Comments | 675862828 | 05 Lead Time | 675862857 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862871
3550640 | 675861663 | 06 Tuning | 675863476 | 06 Lead Time Comments | 675863567 | 06 Lead Time | 675863579 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863590
3550640 | 675861663 | 06 Tuning | 675863476 | 06 Lead Time Comments | 675863567 | 06 Lead Time | 675863579 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863604
3550642 | 675861709 | 01 Installation End | 675864452 | 01 Lead Time Comments | 675864618 | 01 Lead Time | 675864638 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675864658
3550642 | 675861709 | 02 Integration | 675864672 | 02 Lead Time Comments | 675864863 | 02 Lead Time | 675864889 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675864918
3550642 | 675861709 | 02 Integration | 675864672 | 02 Lead Time Comments | 675864863 | 02 Lead Time | 675864889 | actcl--02 Integration--02 Lead Time Comments--Duration | 675864942
3550642 | 675861709 | 03 Integration Confirmed By NRO Technical Leader | 675864009 | 03 Lead Time Comments | 675864074 | 03 Lead Time | 675864095 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864111
3550642 | 675861709 | 04 SSV | 675864972 | 04 Lead Time Comments | 675865170 | 04 Lead Time | 675865201 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865235
3550642 | 675861709 | 04 SSV | 675864972 | 04 Lead Time Comments | 675865170 | 04 Lead Time | 675865201 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865284
3550642 | 675861709 | 05 SSV Confirmed By NDO Technical Leader | 675864128 | 05 Lead Time Comments | 675864220 | 05 Lead Time | 675864231 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864246
3550642 | 675861709 | 06 Tuning | 675865345 | 06 Lead Time Comments | 675865539 | 06 Lead Time | 675865584 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865607
3550642 | 675861709 | 06 Tuning | 675865345 | 06 Lead Time Comments | 675865539 | 06 Lead Time | 675865584 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865649
3550643 | 675861708 | 01 Installation End | 675864940 | 01 Lead Time Comments | 675865053 | 01 Lead Time | 675865078 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865106
3550643 | 675861708 | 02 Integration | 675865183 | 02 Lead Time Comments | 675865362 | 02 Lead Time | 675865401 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865433
3550643 | 675861708 | 02 Integration | 675865183 | 02 Lead Time Comments | 675865362 | 02 Lead Time | 675865401 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865496
3550643 | 675861708 | 03 Integration Confirmed By NRO Technical Leader | 675864271 | 03 Lead Time Comments | 675864400 | 03 Lead Time | 675864429 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864451
3550643 | 675861708 | 04 SSV | 675865573 | 04 Lead Time Comments | 675865729 | 04 Lead Time | 675865764 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865792
3550643 | 675861708 | 04 SSV | 675865573 | 04 Lead Time Comments | 675865729 | 04 Lead Time | 675865764 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865838
3550643 | 675861708 | 05 SSV Confirmed By NDO Technical Leader | 675864513 | 05 Lead Time Comments | 675864682 | 05 Lead Time | 675864694 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864709
3550643 | 675861708 | 06 Tuning | 675865892 | 06 Lead Time Comments | 675866015 | 06 Lead Time | 675866036 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866057
3550643 | 675861708 | 06 Tuning | 675865892 | 06 Lead Time Comments | 675866015 | 06 Lead Time | 675866036 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866097
3550644 | 675861710 | 01 Installation End | 675864789 | 01 Lead Time Comments | 675864991 | 01 Lead Time | 675865005 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865025
3550644 | 675861710 | 02 Integration | 675865066 | 02 Lead Time Comments | 675865275 | 02 Lead Time | 675865307 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865334
3550644 | 675861710 | 02 Integration | 675865066 | 02 Lead Time Comments | 675865275 | 02 Lead Time | 675865307 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865387
3550644 | 675861710 | 03 Integration Confirmed By NRO Technical Leader | 675864143 | 03 Lead Time Comments | 675864283 | 03 Lead Time | 675864299 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864317
3550644 | 675861710 | 04 SSV | 675865468 | 04 Lead Time Comments | 675865639 | 04 Lead Time | 675865689 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865714
3550644 | 675861710 | 04 SSV | 675865468 | 04 Lead Time Comments | 675865639 | 04 Lead Time | 675865689 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865769
3550644 | 675861710 | 05 SSV Confirmed By NDO Technical Leader | 675864345 | 05 Lead Time Comments | 675864528 | 05 Lead Time | 675864578 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864602
3550644 | 675861710 | 06 Tuning | 675865828 | 06 Lead Time Comments | 675866006 | 06 Lead Time | 675866029 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866052
3550644 | 675861710 | 06 Tuning | 675865828 | 06 Lead Time Comments | 675866006 | 06 Lead Time | 675866029 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866091
3550645 | 675861793 | 01 Installation End | 675862919 | 01 Lead Time Comments | 675862973 | 01 Lead Time | 675862984 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675862994
3550645 | 675861793 | 02 Integration | 675863019 | 02 Lead Time Comments | 675863096 | 02 Lead Time | 675863116 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863137
3550645 | 675861793 | 02 Integration | 675863019 | 02 Lead Time Comments | 675863096 | 02 Lead Time | 675863116 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863174
3550645 | 675861793 | 03 Integration Confirmed By NRO Technical Leader | 675862544 | 03 Lead Time Comments | 675862633 | 03 Lead Time | 675862652 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862667
3550645 | 675861793 | 04 SSV | 675863216 | 04 Lead Time Comments | 675863326 | 04 Lead Time | 675863346 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863368
3550645 | 675861793 | 04 SSV | 675863216 | 04 Lead Time Comments | 675863326 | 04 Lead Time | 675863346 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863410
3550645 | 675861793 | 05 SSV Confirmed By NDO Technical Leader | 675862698 | 05 Lead Time Comments | 675862815 | 05 Lead Time | 675862834 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862845
3550645 | 675861793 | 06 Tuning | 675863441 | 06 Lead Time Comments | 675863532 | 06 Lead Time | 675863549 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863558
3550645 | 675861793 | 06 Tuning | 675863441 | 06 Lead Time Comments | 675863532 | 06 Lead Time | 675863549 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863582
3550646 | 675861797 | 01 Installation End | 675864778 | 01 Lead Time Comments | 675864983 | 01 Lead Time | 675864994 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865023
3550646 | 675861797 | 02 Integration | 675865059 | 02 Lead Time Comments | 675865290 | 02 Lead Time | 675865317 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865342
3550646 | 675861797 | 02 Integration | 675865059 | 02 Lead Time Comments | 675865290 | 02 Lead Time | 675865317 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865393
3550646 | 675861797 | 03 Integration Confirmed By NRO Technical Leader | 675864116 | 03 Lead Time Comments | 675864199 | 03 Lead Time | 675864216 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864224
3550646 | 675861797 | 04 SSV | 675865454 | 04 Lead Time Comments | 675865618 | 04 Lead Time | 675865636 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865658
3550646 | 675861797 | 04 SSV | 675865454 | 04 Lead Time Comments | 675865618 | 04 Lead Time | 675865636 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865698
3550646 | 675861797 | 05 SSV Confirmed By NDO Technical Leader | 675864287 | 05 Lead Time Comments | 675864438 | 05 Lead Time | 675864462 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864483
3550646 | 675861797 | 06 Tuning | 675865763 | 06 Lead Time Comments | 675865894 | 06 Lead Time | 675865919 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675865934
3550646 | 675861797 | 06 Tuning | 675865763 | 06 Lead Time Comments | 675865894 | 06 Lead Time | 675865919 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675865971
3550647 | 675861802 | 01 Installation End | 675863047 | 01 Lead Time Comments | 675863139 | 01 Lead Time | 675863158 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863176
3550647 | 675861802 | 02 Integration | 675863219 | 02 Lead Time Comments | 675863332 | 02 Lead Time | 675863355 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863384
3550647 | 675861802 | 02 Integration | 675863219 | 02 Lead Time Comments | 675863332 | 02 Lead Time | 675863355 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863416
3550647 | 675861802 | 03 Integration Confirmed By NRO Technical Leader | 675862666 | 03 Lead Time Comments | 675862759 | 03 Lead Time | 675862795 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862825
3550647 | 675861802 | 04 SSV | 675863440 | 04 Lead Time Comments | 675863539 | 04 Lead Time | 675863551 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863568
3550647 | 675861802 | 04 SSV | 675863440 | 04 Lead Time Comments | 675863539 | 04 Lead Time | 675863551 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863595
3550647 | 675861802 | 05 SSV Confirmed By NDO Technical Leader | 675862861 | 05 Lead Time Comments | 675862918 | 05 Lead Time | 675862941 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862946
3550647 | 675861802 | 06 Tuning | 675863613 | 06 Lead Time Comments | 675863691 | 06 Lead Time | 675863699 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863707
3550647 | 675861802 | 06 Tuning | 675863613 | 06 Lead Time Comments | 675863691 | 06 Lead Time | 675863699 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863718
3550648 | 675861816 | 01 Installation End | 675863077 | 01 Lead Time Comments | 675863171 | 01 Lead Time | 675863193 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863211
3550648 | 675861816 | 02 Integration | 675863245 | 02 Lead Time Comments | 675863352 | 02 Lead Time | 675863373 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863390
3550648 | 675861816 | 02 Integration | 675863245 | 02 Lead Time Comments | 675863352 | 02 Lead Time | 675863373 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863421
3550648 | 675861816 | 03 Integration Confirmed By NRO Technical Leader | 675862818 | 03 Lead Time Comments | 675862880 | 03 Lead Time | 675862886 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675862893
3550648 | 675861816 | 04 SSV | 675863448 | 04 Lead Time Comments | 675863534 | 04 Lead Time | 675863547 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863559
3550648 | 675861816 | 04 SSV | 675863448 | 04 Lead Time Comments | 675863534 | 04 Lead Time | 675863547 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863580
3550648 | 675861816 | 05 SSV Confirmed By NDO Technical Leader | 675862912 | 05 Lead Time Comments | 675862968 | 05 Lead Time | 675862982 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675862992
3550648 | 675861816 | 06 Tuning | 675863601 | 06 Lead Time Comments | 675863674 | 06 Lead Time | 675863690 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863698
3550648 | 675861816 | 06 Tuning | 675863601 | 06 Lead Time Comments | 675863674 | 06 Lead Time | 675863690 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863711
3550650 | 675861913 | 01 Installation End | 675863271 | 01 Lead Time Comments | 675863380 | 01 Lead Time | 675863397 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675863414
3550650 | 675861913 | 02 Integration | 675863439 | 02 Lead Time Comments | 675863533 | 02 Lead Time | 675863546 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675863562
3550650 | 675861913 | 02 Integration | 675863439 | 02 Lead Time Comments | 675863533 | 02 Lead Time | 675863546 | actcl--02 Integration--02 Lead Time Comments--Duration | 675863581
3550650 | 675861913 | 03 Integration Confirmed By NRO Technical Leader | 675862927 | 03 Lead Time Comments | 675862980 | 03 Lead Time | 675862990 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675863003
3550650 | 675861913 | 04 SSV | 675863602 | 04 Lead Time Comments | 675863681 | 04 Lead Time | 675863692 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675863701
3550650 | 675861913 | 04 SSV | 675863602 | 04 Lead Time Comments | 675863681 | 04 Lead Time | 675863692 | actcl--04 SSV--04 Lead Time Comments--Duration | 675863713
3550650 | 675861913 | 05 SSV Confirmed By NDO Technical Leader | 675863028 | 05 Lead Time Comments | 675863093 | 05 Lead Time | 675863104 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675863125
3550650 | 675861913 | 06 Tuning | 675863726 | 06 Lead Time Comments | 675863782 | 06 Lead Time | 675863791 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675863807
3550650 | 675861913 | 06 Tuning | 675863726 | 06 Lead Time Comments | 675863782 | 06 Lead Time | 675863791 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675863823
3550651 | 675861925 | 01 Installation End | 675865107 | 01 Lead Time Comments | 675865269 | 01 Lead Time | 675865301 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865329
3550651 | 675861925 | 02 Integration | 675865396 | 02 Lead Time Comments | 675865575 | 02 Lead Time | 675865600 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865622
3550651 | 675861925 | 02 Integration | 675865396 | 02 Lead Time Comments | 675865575 | 02 Lead Time | 675865600 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865665
3550651 | 675861925 | 03 Integration Confirmed By NRO Technical Leader | 675864362 | 03 Lead Time Comments | 675864520 | 03 Lead Time | 675864568 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864599
3550651 | 675861925 | 04 SSV | 675865717 | 04 Lead Time Comments | 675865877 | 04 Lead Time | 675865900 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865923
3550651 | 675861925 | 04 SSV | 675865717 | 04 Lead Time Comments | 675865877 | 04 Lead Time | 675865900 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865962
3550651 | 675861925 | 05 SSV Confirmed By NDO Technical Leader | 675864639 | 05 Lead Time Comments | 675864825 | 05 Lead Time | 675864871 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864894
3550651 | 675861925 | 06 Tuning | 675866047 | 06 Lead Time Comments | 675866171 | 06 Lead Time | 675866198 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866222
3550651 | 675861925 | 06 Tuning | 675866047 | 06 Lead Time Comments | 675866171 | 06 Lead Time | 675866198 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866252
3550652 | 675861957 | 01 Installation End | 675865096 | 01 Lead Time Comments | 675865267 | 01 Lead Time | 675865294 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865323
3550652 | 675861957 | 02 Integration | 675865381 | 02 Lead Time Comments | 675865560 | 02 Lead Time | 675865624 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865642
3550652 | 675861957 | 02 Integration | 675865381 | 02 Lead Time Comments | 675865560 | 02 Lead Time | 675865624 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865682
3550652 | 675861957 | 03 Integration Confirmed By NRO Technical Leader | 675864476 | 03 Lead Time Comments | 675864650 | 03 Lead Time | 675864662 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864670
3550652 | 675861957 | 04 SSV | 675865740 | 04 Lead Time Comments | 675865885 | 04 Lead Time | 675865911 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865928
3550652 | 675861957 | 04 SSV | 675865740 | 04 Lead Time Comments | 675865885 | 04 Lead Time | 675865911 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865986
3550652 | 675861957 | 05 SSV Confirmed By NDO Technical Leader | 675864693 | 05 Lead Time Comments | 675864854 | 05 Lead Time | 675864880 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864910
3550652 | 675861957 | 06 Tuning | 675866035 | 06 Lead Time Comments | 675866224 | 06 Lead Time | 675866242 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866257
3550652 | 675861957 | 06 Tuning | 675866035 | 06 Lead Time Comments | 675866224 | 06 Lead Time | 675866242 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866283
3550653 | 675861958 | 01 Installation End | 675865093 | 01 Lead Time Comments | 675865263 | 01 Lead Time | 675865288 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865315
3550653 | 675861958 | 02 Integration | 675865377 | 02 Lead Time Comments | 675865551 | 02 Lead Time | 675865572 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865591
3550653 | 675861958 | 02 Integration | 675865377 | 02 Lead Time Comments | 675865551 | 02 Lead Time | 675865572 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865626
3550653 | 675861958 | 03 Integration Confirmed By NRO Technical Leader | 675864319 | 03 Lead Time Comments | 675864449 | 03 Lead Time | 675864470 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864487
3550653 | 675861958 | 04 SSV | 675865670 | 04 Lead Time Comments | 675865825 | 04 Lead Time | 675865898 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675865920
3550653 | 675861958 | 04 SSV | 675865670 | 04 Lead Time Comments | 675865825 | 04 Lead Time | 675865898 | actcl--04 SSV--04 Lead Time Comments--Duration | 675865951
3550653 | 675861958 | 05 SSV Confirmed By NDO Technical Leader | 675864572 | 05 Lead Time Comments | 675864772 | 05 Lead Time | 675864801 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675864841
3550653 | 675861958 | 06 Tuning | 675865996 | 06 Lead Time Comments | 675866124 | 06 Lead Time | 675866142 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866165
3550653 | 675861958 | 06 Tuning | 675865996 | 06 Lead Time Comments | 675866124 | 06 Lead Time | 675866142 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866207
3550654 | 675862917 | 01 Installation End | 675865226 | 01 Lead Time Comments | 675865389 | 01 Lead Time | 675865421 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865452
3550654 | 675862917 | 02 Integration | 675865525 | 02 Lead Time Comments | 675865685 | 02 Lead Time | 675865706 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865739
3550654 | 675862917 | 02 Integration | 675865525 | 02 Lead Time Comments | 675865685 | 02 Lead Time | 675865706 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865787
3550654 | 675862917 | 03 Integration Confirmed By NRO Technical Leader | 675864552 | 03 Lead Time Comments | 675864691 | 03 Lead Time | 675864705 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864718
3550654 | 675862917 | 04 SSV | 675865850 | 04 Lead Time Comments | 675866064 | 04 Lead Time | 675866087 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866127
3550654 | 675862917 | 04 SSV | 675865850 | 04 Lead Time Comments | 675866064 | 04 Lead Time | 675866087 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866166
3550654 | 675862917 | 05 SSV Confirmed By NDO Technical Leader | 675864767 | 05 Lead Time Comments | 675864976 | 05 Lead Time | 675864989 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865002
3550654 | 675862917 | 06 Tuning | 675866212 | 06 Lead Time Comments | 675866294 | 06 Lead Time | 675866305 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866369
3550654 | 675862917 | 06 Tuning | 675866212 | 06 Lead Time Comments | 675866294 | 06 Lead Time | 675866305 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866380
3550655 | 675862922 | 01 Installation End | 675865248 | 01 Lead Time Comments | 675865434 | 01 Lead Time | 675865461 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865491
3550655 | 675862922 | 02 Integration | 675865559 | 02 Lead Time Comments | 675865693 | 02 Lead Time | 675865720 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865744
3550655 | 675862922 | 02 Integration | 675865559 | 02 Lead Time Comments | 675865693 | 02 Lead Time | 675865720 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865797
3550655 | 675862922 | 03 Integration Confirmed By NRO Technical Leader | 675864543 | 03 Lead Time Comments | 675864733 | 03 Lead Time | 675864750 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864785
3550655 | 675862922 | 04 SSV | 675865848 | 04 Lead Time Comments | 675865965 | 04 Lead Time | 675865984 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866000
3550655 | 675862922 | 04 SSV | 675865848 | 04 Lead Time Comments | 675865965 | 04 Lead Time | 675865984 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866034
3550655 | 675862922 | 05 SSV Confirmed By NDO Technical Leader | 675864851 | 05 Lead Time Comments | 675865001 | 05 Lead Time | 675865016 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865030
3550655 | 675862922 | 06 Tuning | 675866080 | 06 Lead Time Comments | 675866200 | 06 Lead Time | 675866219 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866237
3550655 | 675862922 | 06 Tuning | 675866080 | 06 Lead Time Comments | 675866200 | 06 Lead Time | 675866219 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866259
3550656 | 675863025 | 01 Installation End | 675865250 | 01 Lead Time Comments | 675865414 | 01 Lead Time | 675865449 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865481
3550656 | 675863025 | 02 Integration | 675865550 | 02 Lead Time Comments | 675865687 | 02 Lead Time | 675865712 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865738
3550656 | 675863025 | 02 Integration | 675865550 | 02 Lead Time Comments | 675865687 | 02 Lead Time | 675865712 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865782
3550656 | 675863025 | 03 Integration Confirmed By NRO Technical Leader | 675864558 | 03 Lead Time Comments | 675864747 | 03 Lead Time | 675864768 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864796
3550656 | 675863025 | 04 SSV | 675865834 | 04 Lead Time Comments | 675865960 | 04 Lead Time | 675865983 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866001
3550656 | 675863025 | 04 SSV | 675865834 | 04 Lead Time Comments | 675865960 | 04 Lead Time | 675865983 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866037
3550656 | 675863025 | 05 SSV Confirmed By NDO Technical Leader | 675864862 | 05 Lead Time Comments | 675865003 | 05 Lead Time | 675865020 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865032
3550656 | 675863025 | 06 Tuning | 675866082 | 06 Lead Time Comments | 675866201 | 06 Lead Time | 675866320 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866330
3550656 | 675863025 | 06 Tuning | 675866082 | 06 Lead Time Comments | 675866201 | 06 Lead Time | 675866320 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866348
3550657 | 675863031 | 01 Installation End | 675865388 | 01 Lead Time Comments | 675865536 | 01 Lead Time | 675865563 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865587
3550657 | 675863031 | 02 Integration | 675865638 | 02 Lead Time Comments | 675865790 | 02 Lead Time | 675865831 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865855
3550657 | 675863031 | 02 Integration | 675865638 | 02 Lead Time Comments | 675865790 | 02 Lead Time | 675865831 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865896
3550657 | 675863031 | 03 Integration Confirmed By NRO Technical Leader | 675864567 | 03 Lead Time Comments | 675864754 | 03 Lead Time | 675864787 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864820
3550657 | 675863031 | 04 SSV | 675865941 | 04 Lead Time Comments | 675866069 | 04 Lead Time | 675866093 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866116
3550657 | 675863031 | 04 SSV | 675865941 | 04 Lead Time Comments | 675866069 | 04 Lead Time | 675866093 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866150
3550657 | 675863031 | 05 SSV Confirmed By NDO Technical Leader | 675864886 | 05 Lead Time Comments | 675865082 | 05 Lead Time | 675865109 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865130
3550657 | 675863031 | 06 Tuning | 675866265 | 06 Lead Time Comments | 675866329 | 06 Lead Time | 675866390 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866392
3550657 | 675863031 | 06 Tuning | 675866265 | 06 Lead Time Comments | 675866329 | 06 Lead Time | 675866390 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866405
3550658 | 675863037 | 01 Installation End | 675865266 | 01 Lead Time Comments | 675865430 | 01 Lead Time | 675865457 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865493
3550658 | 675863037 | 02 Integration | 675865555 | 02 Lead Time Comments | 675865697 | 02 Lead Time | 675865751 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865779
3550658 | 675863037 | 02 Integration | 675865555 | 02 Lead Time Comments | 675865697 | 02 Lead Time | 675865751 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865826
3550658 | 675863037 | 03 Integration Confirmed By NRO Technical Leader | 675864594 | 03 Lead Time Comments | 675864760 | 03 Lead Time | 675864792 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864822
3550658 | 675863037 | 04 SSV | 675865878 | 04 Lead Time Comments | 675865998 | 04 Lead Time | 675866022 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866042
3550658 | 675863037 | 04 SSV | 675865878 | 04 Lead Time Comments | 675865998 | 04 Lead Time | 675866022 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866086
3550658 | 675863037 | 05 SSV Confirmed By NDO Technical Leader | 675864893 | 05 Lead Time Comments | 675865017 | 05 Lead Time | 675865031 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865046
3550658 | 675863037 | 06 Tuning | 675866136 | 06 Lead Time Comments | 675866253 | 06 Lead Time | 675866269 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866280
3550658 | 675863037 | 06 Tuning | 675866136 | 06 Lead Time Comments | 675866253 | 06 Lead Time | 675866269 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866303
3550659 | 675863039 | 01 Installation End | 675865376 | 01 Lead Time Comments | 675865513 | 01 Lead Time | 675865552 | mscl--01 Installation End--01 Lead Time Comments--Duration | 675865583
3550659 | 675863039 | 02 Integration | 675865656 | 02 Lead Time Comments | 675865815 | 02 Lead Time | 675865835 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 675865857
3550659 | 675863039 | 02 Integration | 675865656 | 02 Lead Time Comments | 675865815 | 02 Lead Time | 675865835 | actcl--02 Integration--02 Lead Time Comments--Duration | 675865893
3550659 | 675863039 | 03 Integration Confirmed By NRO Technical Leader | 675864605 | 03 Lead Time Comments | 675864834 | 03 Lead Time | 675864864 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 675864896
3550659 | 675863039 | 04 SSV | 675865945 | 04 Lead Time Comments | 675866081 | 04 Lead Time | 675866098 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 675866122
3550659 | 675863039 | 04 SSV | 675865945 | 04 Lead Time Comments | 675866081 | 04 Lead Time | 675866098 | actcl--04 SSV--04 Lead Time Comments--Duration | 675866158
3550659 | 675863039 | 05 SSV Confirmed By NDO Technical Leader | 675864930 | 05 Lead Time Comments | 675865095 | 05 Lead Time | 675865122 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 675865147
3550659 | 675863039 | 06 Tuning | 675866213 | 06 Lead Time Comments | 675866312 | 06 Lead Time | 675866324 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 675866335
3550659 | 675863039 | 06 Tuning | 675866213 | 06 Lead Time Comments | 675866312 | 06 Lead Time | 675866324 | actcl--06 Tuning--06 Lead Time Comments--Duration | 675866350
3819436 | 745819936 | 01 Installation End | 745821187 | 01 Lead Time Comments | 745821356 | 01 Lead Time | 745821393 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821403
3819436 | 745819936 | 02 Integration | 745821765 | 02 Lead Time Comments | 745822028 | 02 Lead Time | 745822140 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822284
3819436 | 745819936 | 02 Integration | 745821765 | 02 Lead Time Comments | 745822028 | 02 Lead Time | 745822140 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822366
3819436 | 745819936 | 03 Integration Confirmed By NRO Technical Leader | 745820142 | 03 Lead Time Comments | 745820379 | 03 Lead Time | 745820474 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820563
3819436 | 745819936 | 04 SSV | 745822476 | 04 Lead Time Comments | 745822719 | 04 Lead Time | 745822783 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822857
3819436 | 745819936 | 04 SSV | 745822476 | 04 Lead Time Comments | 745822719 | 04 Lead Time | 745822783 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822959
3819436 | 745819936 | 05 SSV Confirmed By NDO Technical Leader | 745820680 | 05 Lead Time Comments | 745820813 | 05 Lead Time | 745820837 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820957
3819436 | 745819936 | 06 Tuning | 745823055 | 06 Lead Time Comments | 745823322 | 06 Lead Time | 745823420 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823479
3819436 | 745819936 | 06 Tuning | 745823055 | 06 Lead Time Comments | 745823322 | 06 Lead Time | 745823420 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823540
3819437 | 745819942 | 01 Installation End | 745821168 | 01 Lead Time Comments | 745821279 | 01 Lead Time | 745821384 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821439
3819437 | 745819942 | 02 Integration | 745821813 | 02 Lead Time Comments | 745822076 | 02 Lead Time | 745822173 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822254
3819437 | 745819942 | 02 Integration | 745821813 | 02 Lead Time Comments | 745822076 | 02 Lead Time | 745822173 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822315
3819437 | 745819942 | 03 Integration Confirmed By NRO Technical Leader | 745820249 | 03 Lead Time Comments | 745820437 | 03 Lead Time | 745820495 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820574
3819437 | 745819942 | 04 SSV | 745822430 | 04 Lead Time Comments | 745822737 | 04 Lead Time | 745822804 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822884
3819437 | 745819942 | 04 SSV | 745822430 | 04 Lead Time Comments | 745822737 | 04 Lead Time | 745822804 | actcl--04 SSV--04 Lead Time Comments--Duration | 745823002
3819437 | 745819942 | 05 SSV Confirmed By NDO Technical Leader | 745820678 | 05 Lead Time Comments | 745820835 | 05 Lead Time | 745820891 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820949
3819437 | 745819942 | 06 Tuning | 745823089 | 06 Lead Time Comments | 745823231 | 06 Lead Time | 745823383 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823492
3819437 | 745819942 | 06 Tuning | 745823089 | 06 Lead Time Comments | 745823231 | 06 Lead Time | 745823383 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823596
3819438 | 745819966 | 01 Installation End | 745821218 | 01 Lead Time Comments | 745821331 | 01 Lead Time | 745821392 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821432
3819438 | 745819966 | 02 Integration | 745821869 | 02 Lead Time Comments | 745822154 | 02 Lead Time | 745822238 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822313
3819438 | 745819966 | 02 Integration | 745821869 | 02 Lead Time Comments | 745822154 | 02 Lead Time | 745822238 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822396
3819438 | 745819966 | 03 Integration Confirmed By NRO Technical Leader | 745820150 | 03 Lead Time Comments | 745820366 | 03 Lead Time | 745820465 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820603
3819438 | 745819966 | 04 SSV | 745822532 | 04 Lead Time Comments | 745822771 | 04 Lead Time | 745822853 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822898
3819438 | 745819966 | 04 SSV | 745822532 | 04 Lead Time Comments | 745822771 | 04 Lead Time | 745822853 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822955
3819438 | 745819966 | 05 SSV Confirmed By NDO Technical Leader | 745820722 | 05 Lead Time Comments | 745820854 | 05 Lead Time | 745820939 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820970
3819438 | 745819966 | 06 Tuning | 745823126 | 06 Lead Time Comments | 745823330 | 06 Lead Time | 745823392 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823480
3819438 | 745819966 | 06 Tuning | 745823126 | 06 Lead Time Comments | 745823330 | 06 Lead Time | 745823392 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823638
3819439 | 745819946 | 01 Installation End | 745821249 | 01 Lead Time Comments | 745821365 | 01 Lead Time | 745821436 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821459
3819439 | 745819946 | 02 Integration | 745821947 | 02 Lead Time Comments | 745822199 | 02 Lead Time | 745822269 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822295
3819439 | 745819946 | 02 Integration | 745821947 | 02 Lead Time Comments | 745822199 | 02 Lead Time | 745822269 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822368
3819439 | 745819946 | 03 Integration Confirmed By NRO Technical Leader | 745820213 | 03 Lead Time Comments | 745820435 | 03 Lead Time | 745820522 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820553
3819439 | 745819946 | 04 SSV | 745822539 | 04 Lead Time Comments | 745822810 | 04 Lead Time | 745822911 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745823005
3819439 | 745819946 | 04 SSV | 745822539 | 04 Lead Time Comments | 745822810 | 04 Lead Time | 745822911 | actcl--04 SSV--04 Lead Time Comments--Duration | 745823102
3819439 | 745819946 | 05 SSV Confirmed By NDO Technical Leader | 745820704 | 05 Lead Time Comments | 745820893 | 05 Lead Time | 745820986 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745821033
3819439 | 745819946 | 06 Tuning | 745823295 | 06 Lead Time Comments | 745823463 | 06 Lead Time | 745823589 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823633
3819439 | 745819946 | 06 Tuning | 745823295 | 06 Lead Time Comments | 745823463 | 06 Lead Time | 745823589 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823706
3819440 | 745819947 | 01 Installation End | 745821192 | 01 Lead Time Comments | 745821444 | 01 Lead Time | 745821476 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821553
3819440 | 745819947 | 02 Integration | 745822035 | 02 Lead Time Comments | 745822207 | 02 Lead Time | 745822278 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822352
3819440 | 745819947 | 02 Integration | 745822035 | 02 Lead Time Comments | 745822207 | 02 Lead Time | 745822278 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822428
3819440 | 745819947 | 03 Integration Confirmed By NRO Technical Leader | 745820316 | 03 Lead Time Comments | 745820472 | 03 Lead Time | 745820546 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820573
3819440 | 745819947 | 04 SSV | 745822541 | 04 Lead Time Comments | 745822759 | 04 Lead Time | 745822842 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822889
3819440 | 745819947 | 04 SSV | 745822541 | 04 Lead Time Comments | 745822759 | 04 Lead Time | 745822842 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822993
3819440 | 745819947 | 05 SSV Confirmed By NDO Technical Leader | 745820713 | 05 Lead Time Comments | 745820815 | 05 Lead Time | 745820869 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820951
3819440 | 745819947 | 06 Tuning | 745823125 | 06 Lead Time Comments | 745823380 | 06 Lead Time | 745823474 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823513
3819440 | 745819947 | 06 Tuning | 745823125 | 06 Lead Time Comments | 745823380 | 06 Lead Time | 745823474 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823591
3819442 | 745819938 | 01 Installation End | 745821215 | 01 Lead Time Comments | 745821361 | 01 Lead Time | 745821398 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821419
3819442 | 745819938 | 02 Integration | 745821767 | 02 Lead Time Comments | 745822070 | 02 Lead Time | 745822129 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822250
3819442 | 745819938 | 02 Integration | 745821767 | 02 Lead Time Comments | 745822070 | 02 Lead Time | 745822129 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822341
3819442 | 745819938 | 03 Integration Confirmed By NRO Technical Leader | 745820293 | 03 Lead Time Comments | 745820431 | 03 Lead Time | 745820466 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820557
3819442 | 745819938 | 04 SSV | 745822421 | 04 Lead Time Comments | 745822713 | 04 Lead Time | 745822781 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822852
3819442 | 745819938 | 04 SSV | 745822421 | 04 Lead Time Comments | 745822713 | 04 Lead Time | 745822781 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822947
3819442 | 745819938 | 05 SSV Confirmed By NDO Technical Leader | 745820753 | 05 Lead Time Comments | 745820868 | 05 Lead Time | 745820920 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820959
3819442 | 745819938 | 06 Tuning | 745823135 | 06 Lead Time Comments | 745823301 | 06 Lead Time | 745823335 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823384
3819442 | 745819938 | 06 Tuning | 745823135 | 06 Lead Time Comments | 745823301 | 06 Lead Time | 745823335 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823552
3819448 | 745820009 | 01 Installation End | 745821204 | 01 Lead Time Comments | 745821319 | 01 Lead Time | 745821372 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821449
3819448 | 745820009 | 02 Integration | 745821814 | 02 Lead Time Comments | 745822098 | 02 Lead Time | 745822189 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822314
3819448 | 745820009 | 02 Integration | 745821814 | 02 Lead Time Comments | 745822098 | 02 Lead Time | 745822189 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822393
3819448 | 745820009 | 03 Integration Confirmed By NRO Technical Leader | 745820222 | 03 Lead Time Comments | 745820376 | 03 Lead Time | 745820506 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820558
3819448 | 745820009 | 04 SSV | 745822510 | 04 Lead Time Comments | 745822706 | 04 Lead Time | 745822773 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822824
3819448 | 745820009 | 04 SSV | 745822510 | 04 Lead Time Comments | 745822706 | 04 Lead Time | 745822773 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822907
3819448 | 745820009 | 05 SSV Confirmed By NDO Technical Leader | 745820662 | 05 Lead Time Comments | 745820838 | 05 Lead Time | 745820877 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820994
3819448 | 745820009 | 06 Tuning | 745823094 | 06 Lead Time Comments | 745823308 | 06 Lead Time | 745823399 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823512
3819448 | 745820009 | 06 Tuning | 745823094 | 06 Lead Time Comments | 745823308 | 06 Lead Time | 745823399 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823602
3819451 | 745819965 | 01 Installation End | 745821149 | 01 Lead Time Comments | 745821257 | 01 Lead Time | 745821302 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821354
3819451 | 745819965 | 02 Integration | 745821761 | 02 Lead Time Comments | 745822085 | 02 Lead Time | 745822164 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822221
3819451 | 745819965 | 02 Integration | 745821761 | 02 Lead Time Comments | 745822085 | 02 Lead Time | 745822164 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822349
3819451 | 745819965 | 03 Integration Confirmed By NRO Technical Leader | 745820318 | 03 Lead Time Comments | 745820482 | 03 Lead Time | 745820518 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820559
3819451 | 745819965 | 04 SSV | 745822426 | 04 Lead Time Comments | 745822683 | 04 Lead Time | 745822761 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822836
3819451 | 745819965 | 04 SSV | 745822426 | 04 Lead Time Comments | 745822683 | 04 Lead Time | 745822761 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822927
3819451 | 745819965 | 05 SSV Confirmed By NDO Technical Leader | 745820652 | 05 Lead Time Comments | 745820798 | 05 Lead Time | 745820851 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820874
3819451 | 745819965 | 06 Tuning | 745823072 | 06 Lead Time Comments | 745823357 | 06 Lead Time | 745823417 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823470
3819451 | 745819965 | 06 Tuning | 745823072 | 06 Lead Time Comments | 745823357 | 06 Lead Time | 745823417 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823572
3819456 | 745819987 | 01 Installation End | 745821197 | 01 Lead Time Comments | 745821345 | 01 Lead Time | 745821378 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821405
3819456 | 745819987 | 02 Integration | 745821818 | 02 Lead Time Comments | 745822114 | 02 Lead Time | 745822138 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822230
3819456 | 745819987 | 02 Integration | 745821818 | 02 Lead Time Comments | 745822114 | 02 Lead Time | 745822138 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822319
3819456 | 745819987 | 03 Integration Confirmed By NRO Technical Leader | 745820238 | 03 Lead Time Comments | 745820417 | 03 Lead Time | 745820491 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820554
3819456 | 745819987 | 04 SSV | 745822398 | 04 Lead Time Comments | 745822587 | 04 Lead Time | 745822733 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822792
3819456 | 745819987 | 04 SSV | 745822398 | 04 Lead Time Comments | 745822587 | 04 Lead Time | 745822733 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822906
3819456 | 745819987 | 05 SSV Confirmed By NDO Technical Leader | 745820661 | 05 Lead Time Comments | 745820811 | 05 Lead Time | 745820886 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820907
3819456 | 745819987 | 06 Tuning | 745823060 | 06 Lead Time Comments | 745823243 | 06 Lead Time | 745823344 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823377
3819456 | 745819987 | 06 Tuning | 745823060 | 06 Lead Time Comments | 745823243 | 06 Lead Time | 745823344 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823624
3819457 | 745819959 | 01 Installation End | 745821103 | 01 Lead Time Comments | 745821226 | 01 Lead Time | 745821286 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821338
3819457 | 745819959 | 02 Integration | 745821826 | 02 Lead Time Comments | 745822121 | 02 Lead Time | 745822160 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822236
3819457 | 745819959 | 02 Integration | 745821826 | 02 Lead Time Comments | 745822121 | 02 Lead Time | 745822160 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822326
3819457 | 745819959 | 03 Integration Confirmed By NRO Technical Leader | 745820232 | 03 Lead Time Comments | 745820478 | 03 Lead Time | 745820520 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820555
3819457 | 745819959 | 04 SSV | 745822455 | 04 Lead Time Comments | 745822701 | 04 Lead Time | 745822789 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822856
3819457 | 745819959 | 04 SSV | 745822455 | 04 Lead Time Comments | 745822701 | 04 Lead Time | 745822789 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822965
3819457 | 745819959 | 05 SSV Confirmed By NDO Technical Leader | 745820657 | 05 Lead Time Comments | 745820817 | 05 Lead Time | 745820864 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820901
3819457 | 745819959 | 06 Tuning | 745823120 | 06 Lead Time Comments | 745823337 | 06 Lead Time | 745823412 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823473
3819457 | 745819959 | 06 Tuning | 745823120 | 06 Lead Time Comments | 745823337 | 06 Lead Time | 745823412 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823599
3819461 | 745820022 | 01 Installation End | 745821128 | 01 Lead Time Comments | 745821232 | 01 Lead Time | 745821312 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821370
3819461 | 745820022 | 02 Integration | 745821775 | 02 Lead Time Comments | 745822100 | 02 Lead Time | 745822194 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822251
3819461 | 745820022 | 02 Integration | 745821775 | 02 Lead Time Comments | 745822100 | 02 Lead Time | 745822194 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822376
3819461 | 745820022 | 03 Integration Confirmed By NRO Technical Leader | 745820233 | 03 Lead Time Comments | 745820412 | 03 Lead Time | 745820483 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820583
3819461 | 745820022 | 04 SSV | 745822432 | 04 Lead Time Comments | 745822764 | 04 Lead Time | 745822846 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822923
3819461 | 745820022 | 04 SSV | 745822432 | 04 Lead Time Comments | 745822764 | 04 Lead Time | 745822846 | actcl--04 SSV--04 Lead Time Comments--Duration | 745823052
3819461 | 745820022 | 05 SSV Confirmed By NDO Technical Leader | 745820653 | 05 Lead Time Comments | 745820795 | 05 Lead Time | 745820845 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820879
3819461 | 745820022 | 06 Tuning | 745823173 | 06 Lead Time Comments | 745823445 | 06 Lead Time | 745823584 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823679
3819461 | 745820022 | 06 Tuning | 745823173 | 06 Lead Time Comments | 745823445 | 06 Lead Time | 745823584 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823831
3819463 | 745819990 | 01 Installation End | 745821348 | 01 Lead Time Comments | 745821496 | 01 Lead Time | 745821529 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821562
3819463 | 745819990 | 02 Integration | 745822068 | 02 Lead Time Comments | 745822336 | 02 Lead Time | 745822399 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822477
3819463 | 745819990 | 02 Integration | 745822068 | 02 Lead Time Comments | 745822336 | 02 Lead Time | 745822399 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822523
3819463 | 745819990 | 03 Integration Confirmed By NRO Technical Leader | 745820245 | 03 Lead Time Comments | 745820422 | 03 Lead Time | 745820530 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820564
3819463 | 745819990 | 04 SSV | 745822666 | 04 Lead Time Comments | 745822924 | 04 Lead Time | 745822956 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745823053
3819463 | 745819990 | 04 SSV | 745822666 | 04 Lead Time Comments | 745822924 | 04 Lead Time | 745822956 | actcl--04 SSV--04 Lead Time Comments--Duration | 745823183
3819463 | 745819990 | 05 SSV Confirmed By NDO Technical Leader | 745820676 | 05 Lead Time Comments | 745820841 | 05 Lead Time | 745820896 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820952
3819463 | 745819990 | 06 Tuning | 745823269 | 06 Lead Time Comments | 745823472 | 06 Lead Time | 745823542 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823608
3819463 | 745819990 | 06 Tuning | 745823269 | 06 Lead Time Comments | 745823472 | 06 Lead Time | 745823542 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823751
3819464 | 745820037 | 01 Installation End | 745821186 | 01 Lead Time Comments | 745821339 | 01 Lead Time | 745821396 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821412
3819464 | 745820037 | 02 Integration | 745821776 | 02 Lead Time Comments | 745822019 | 02 Lead Time | 745822071 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822237
3819464 | 745820037 | 02 Integration | 745821776 | 02 Lead Time Comments | 745822019 | 02 Lead Time | 745822071 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822328
3819464 | 745820037 | 03 Integration Confirmed By NRO Technical Leader | 745820317 | 03 Lead Time Comments | 745820459 | 03 Lead Time | 745820494 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820556
3819464 | 745820037 | 04 SSV | 745822449 | 04 Lead Time Comments | 745822735 | 04 Lead Time | 745822818 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822851
3819464 | 745820037 | 04 SSV | 745822449 | 04 Lead Time Comments | 745822735 | 04 Lead Time | 745822818 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822958
3819464 | 745820037 | 05 SSV Confirmed By NDO Technical Leader | 745820649 | 05 Lead Time Comments | 745820809 | 05 Lead Time | 745820876 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820932
3819464 | 745820037 | 06 Tuning | 745823065 | 06 Lead Time Comments | 745823333 | 06 Lead Time | 745823418 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823454
3819464 | 745820037 | 06 Tuning | 745823065 | 06 Lead Time Comments | 745823333 | 06 Lead Time | 745823418 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823586
3819468 | 745820027 | 01 Installation End | 745821098 | 01 Lead Time Comments | 745821199 | 01 Lead Time | 745821243 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821291
3819468 | 745820027 | 02 Integration | 745821663 | 02 Lead Time Comments | 745822045 | 02 Lead Time | 745822139 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822212
3819468 | 745820027 | 02 Integration | 745821663 | 02 Lead Time Comments | 745822045 | 02 Lead Time | 745822139 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822289
3819468 | 745820027 | 03 Integration Confirmed By NRO Technical Leader | 745820337 | 03 Lead Time Comments | 745820500 | 03 Lead Time | 745820571 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820608
3819468 | 745820027 | 04 SSV | 745822411 | 04 Lead Time Comments | 745822696 | 04 Lead Time | 745822753 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822830
3819468 | 745820027 | 04 SSV | 745822411 | 04 Lead Time Comments | 745822696 | 04 Lead Time | 745822753 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822929
3819468 | 745820027 | 05 SSV Confirmed By NDO Technical Leader | 745820663 | 05 Lead Time Comments | 745820812 | 05 Lead Time | 745820867 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820925
3819468 | 745820027 | 06 Tuning | 745823037 | 06 Lead Time Comments | 745823263 | 06 Lead Time | 745823364 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823467
3819468 | 745820027 | 06 Tuning | 745823037 | 06 Lead Time Comments | 745823263 | 06 Lead Time | 745823364 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823537
3819471 | 745820062 | 01 Installation End | 745821111 | 01 Lead Time Comments | 745821191 | 01 Lead Time | 745821230 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821292
3819471 | 745820062 | 02 Integration | 745821838 | 02 Lead Time Comments | 745822029 | 02 Lead Time | 745822119 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822187
3819471 | 745820062 | 02 Integration | 745821838 | 02 Lead Time Comments | 745822029 | 02 Lead Time | 745822119 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822297
3819471 | 745820062 | 03 Integration Confirmed By NRO Technical Leader | 745820273 | 03 Lead Time Comments | 745820449 | 03 Lead Time | 745820490 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820561
3819471 | 745820062 | 04 SSV | 745822406 | 04 Lead Time Comments | 745822659 | 04 Lead Time | 745822756 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822811
3819471 | 745820062 | 04 SSV | 745822406 | 04 Lead Time Comments | 745822659 | 04 Lead Time | 745822756 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822916
3819471 | 745820062 | 05 SSV Confirmed By NDO Technical Leader | 745820647 | 05 Lead Time Comments | 745820824 | 05 Lead Time | 745820846 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820888
3819471 | 745820062 | 06 Tuning | 745823033 | 06 Lead Time Comments | 745823311 | 06 Lead Time | 745823342 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823397
3819471 | 745820062 | 06 Tuning | 745823033 | 06 Lead Time Comments | 745823311 | 06 Lead Time | 745823342 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823539
3819480 | 745820083 | 01 Installation End | 745821203 | 01 Lead Time Comments | 745821394 | 01 Lead Time | 745821438 | mscl--01 Installation End--01 Lead Time Comments--Duration | 745821490
3819480 | 745820083 | 02 Integration | 745821903 | 02 Lead Time Comments | 745822162 | 02 Lead Time | 745822206 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 745822298
3819480 | 745820083 | 02 Integration | 745821903 | 02 Lead Time Comments | 745822162 | 02 Lead Time | 745822206 | actcl--02 Integration--02 Lead Time Comments--Duration | 745822420
3819480 | 745820083 | 03 Integration Confirmed By NRO Technical Leader | 745820315 | 03 Lead Time Comments | 745820427 | 03 Lead Time | 745820512 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 745820565
3819480 | 745820083 | 04 SSV | 745822518 | 04 Lead Time Comments | 745822755 | 04 Lead Time | 745822821 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 745822882
3819480 | 745820083 | 04 SSV | 745822518 | 04 Lead Time Comments | 745822755 | 04 Lead Time | 745822821 | actcl--04 SSV--04 Lead Time Comments--Duration | 745822937
3819480 | 745820083 | 05 SSV Confirmed By NDO Technical Leader | 745820658 | 05 Lead Time Comments | 745820827 | 05 Lead Time | 745820855 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 745820930
3819480 | 745820083 | 06 Tuning | 745823030 | 06 Lead Time Comments | 745823225 | 06 Lead Time | 745823326 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 745823369
3819480 | 745820083 | 06 Tuning | 745823030 | 06 Lead Time Comments | 745823225 | 06 Lead Time | 745823326 | actcl--06 Tuning--06 Lead Time Comments--Duration | 745823534
4244886 | 883892937 | 01 Installation End | 883893235 | 01 Lead Time Comments | 883893296 | 01 Lead Time | 883895973 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896016
4244886 | 883892937 | 02 Integration | 883892960 | 02 Lead Time Comments | 883892976 | 02 Lead Time | 883895510 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895540
4244886 | 883892937 | 02 Integration | 883892960 | 02 Lead Time Comments | 883892976 | 02 Lead Time | 883895510 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895623
4244886 | 883892937 | 03 Integration Confirmed By NRO Technical Leader | 883893070 | 03 Lead Time Comments | 883893099 | 03 Lead Time | 883895760 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895803
4244886 | 883892937 | 04 SSV | 883892982 | 04 Lead Time Comments | 883893011 | 04 Lead Time | 883895563 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895610
4244886 | 883892937 | 04 SSV | 883892982 | 04 Lead Time Comments | 883893011 | 04 Lead Time | 883895563 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895638
4244886 | 883892937 | 05 SSV Confirmed By NDO Technical Leader | 883893112 | 05 Lead Time Comments | 883893164 | 05 Lead Time | 883895808 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895834
4244886 | 883892937 | 06 Tuning | 883893019 | 06 Lead Time Comments | 883893051 | 06 Lead Time | 883895652 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895679
4244886 | 883892937 | 06 Tuning | 883893019 | 06 Lead Time Comments | 883893051 | 06 Lead Time | 883895652 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895753
4244887 | 883892938 | 01 Installation End | 883893252 | 01 Lead Time Comments | 883893312 | 01 Lead Time | 883895986 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896035
4244887 | 883892938 | 02 Integration | 883892959 | 02 Lead Time Comments | 883892977 | 02 Lead Time | 883895501 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895534
4244887 | 883892938 | 02 Integration | 883892959 | 02 Lead Time Comments | 883892977 | 02 Lead Time | 883895501 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895618
4244887 | 883892938 | 03 Integration Confirmed By NRO Technical Leader | 883893073 | 03 Lead Time Comments | 883893096 | 03 Lead Time | 883895759 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895778
4244887 | 883892938 | 04 SSV | 883892983 | 04 Lead Time Comments | 883893017 | 04 Lead Time | 883895561 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895590
4244887 | 883892938 | 04 SSV | 883892983 | 04 Lead Time Comments | 883893017 | 04 Lead Time | 883895561 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895622
4244887 | 883892938 | 05 SSV Confirmed By NDO Technical Leader | 883893108 | 05 Lead Time Comments | 883893163 | 05 Lead Time | 883895794 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895820
4244887 | 883892938 | 06 Tuning | 883893024 | 06 Lead Time Comments | 883893058 | 06 Lead Time | 883895644 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895678
4244887 | 883892938 | 06 Tuning | 883893024 | 06 Lead Time Comments | 883893058 | 06 Lead Time | 883895644 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895736
4244888 | 883892949 | 01 Installation End | 883893338 | 01 Lead Time Comments | 883893407 | 01 Lead Time | 883896040 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896055
4244888 | 883892949 | 02 Integration | 883892988 | 02 Lead Time Comments | 883893014 | 02 Lead Time | 883895549 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895596
4244888 | 883892949 | 02 Integration | 883892988 | 02 Lead Time Comments | 883893014 | 02 Lead Time | 883895549 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895640
4244888 | 883892949 | 03 Integration Confirmed By NRO Technical Leader | 883893144 | 03 Lead Time Comments | 883893195 | 03 Lead Time | 883895848 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895877
4244888 | 883892949 | 04 SSV | 883893021 | 04 Lead Time Comments | 883893064 | 04 Lead Time | 883895643 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895695
4244888 | 883892949 | 04 SSV | 883893021 | 04 Lead Time Comments | 883893064 | 04 Lead Time | 883895643 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895752
4244888 | 883892949 | 05 SSV Confirmed By NDO Technical Leader | 883893224 | 05 Lead Time Comments | 883893263 | 05 Lead Time | 883895902 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895947
4244888 | 883892949 | 06 Tuning | 883893078 | 06 Lead Time Comments | 883893109 | 06 Lead Time | 883895746 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895806
4244888 | 883892949 | 06 Tuning | 883893078 | 06 Lead Time Comments | 883893109 | 06 Lead Time | 883895746 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895854
4244889 | 883892948 | 01 Installation End | 883893337 | 01 Lead Time Comments | 883893409 | 01 Lead Time | 883896039 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896073
4244889 | 883892948 | 02 Integration | 883892989 | 02 Lead Time Comments | 883893013 | 02 Lead Time | 883895550 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895586
4244889 | 883892948 | 02 Integration | 883892989 | 02 Lead Time Comments | 883893013 | 02 Lead Time | 883895550 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895628
4244889 | 883892948 | 03 Integration Confirmed By NRO Technical Leader | 883893152 | 03 Lead Time Comments | 883893185 | 03 Lead Time | 883895791 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895859
4244889 | 883892948 | 04 SSV | 883893025 | 04 Lead Time Comments | 883893065 | 04 Lead Time | 883895703 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895728
4244889 | 883892948 | 04 SSV | 883893025 | 04 Lead Time Comments | 883893065 | 04 Lead Time | 883895703 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895754
4244889 | 883892948 | 05 SSV Confirmed By NDO Technical Leader | 883893208 | 05 Lead Time Comments | 883893253 | 05 Lead Time | 883895912 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895958
4244889 | 883892948 | 06 Tuning | 883893077 | 06 Lead Time Comments | 883893119 | 06 Lead Time | 883895809 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895874
4244889 | 883892948 | 06 Tuning | 883893077 | 06 Lead Time Comments | 883893119 | 06 Lead Time | 883895809 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895913
4244890 | 883892950 | 01 Installation End | 883893311 | 01 Lead Time Comments | 883893371 | 01 Lead Time | 883896020 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896077
4244890 | 883892950 | 02 Integration | 883892987 | 02 Lead Time Comments | 883893012 | 02 Lead Time | 883895574 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895626
4244890 | 883892950 | 02 Integration | 883892987 | 02 Lead Time Comments | 883893012 | 02 Lead Time | 883895574 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895664
4244890 | 883892950 | 03 Integration Confirmed By NRO Technical Leader | 883893118 | 03 Lead Time Comments | 883893170 | 03 Lead Time | 883895799 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895822
4244890 | 883892950 | 04 SSV | 883893018 | 04 Lead Time Comments | 883893059 | 04 Lead Time | 883895649 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895701
4244890 | 883892950 | 04 SSV | 883893018 | 04 Lead Time Comments | 883893059 | 04 Lead Time | 883895649 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895730
4244890 | 883892950 | 05 SSV Confirmed By NDO Technical Leader | 883893199 | 05 Lead Time Comments | 883893245 | 05 Lead Time | 883895904 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895978
4244890 | 883892950 | 06 Tuning | 883893066 | 06 Lead Time Comments | 883893100 | 06 Lead Time | 883895749 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895836
4244890 | 883892950 | 06 Tuning | 883893066 | 06 Lead Time Comments | 883893100 | 06 Lead Time | 883895749 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895863
4244891 | 883892962 | 01 Installation End | 883893328 | 01 Lead Time Comments | 883893393 | 01 Lead Time | 883896046 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896091
4244891 | 883892962 | 02 Integration | 883893002 | 02 Lead Time Comments | 883893031 | 02 Lead Time | 883895609 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895639
4244891 | 883892962 | 02 Integration | 883893002 | 02 Lead Time Comments | 883893031 | 02 Lead Time | 883895609 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895683
4244891 | 883892962 | 03 Integration Confirmed By NRO Technical Leader | 883893157 | 03 Lead Time Comments | 883893193 | 03 Lead Time | 883895797 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895849 | 客户原因-传输问题
4244891 | 883892962 | 04 SSV | 883893045 | 04 Lead Time Comments | 883893087 | 04 Lead Time | 883895690 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895734
4244891 | 883892962 | 04 SSV | 883893045 | 04 Lead Time Comments | 883893087 | 04 Lead Time | 883895690 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895774
4244891 | 883892962 | 05 SSV Confirmed By NDO Technical Leader | 883893206 | 05 Lead Time Comments | 883893262 | 05 Lead Time | 883895919 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895985
4244891 | 883892962 | 06 Tuning | 883893092 | 06 Lead Time Comments | 883893133 | 06 Lead Time | 883895788 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895833
4244891 | 883892962 | 06 Tuning | 883893092 | 06 Lead Time Comments | 883893133 | 06 Lead Time | 883895788 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895865
4244892 | 883892961 | 01 Installation End | 883893333 | 01 Lead Time Comments | 883893406 | 01 Lead Time | 883896045 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896103
4244892 | 883892961 | 02 Integration | 883893005 | 02 Lead Time Comments | 883893032 | 02 Lead Time | 883895608 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895632
4244892 | 883892961 | 02 Integration | 883893005 | 02 Lead Time Comments | 883893032 | 02 Lead Time | 883895608 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895666
4244892 | 883892961 | 03 Integration Confirmed By NRO Technical Leader | 883893158 | 03 Lead Time Comments | 883893190 | 03 Lead Time | 883895793 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895844
4244892 | 883892961 | 04 SSV | 883893042 | 04 Lead Time Comments | 883893089 | 04 Lead Time | 883895743 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895769
4244892 | 883892961 | 04 SSV | 883893042 | 04 Lead Time Comments | 883893089 | 04 Lead Time | 883895743 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895798
4244892 | 883892961 | 05 SSV Confirmed By NDO Technical Leader | 883893216 | 05 Lead Time Comments | 883893257 | 05 Lead Time | 883895915 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895957
4244892 | 883892961 | 06 Tuning | 883893093 | 06 Lead Time Comments | 883893141 | 06 Lead Time | 883895810 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895851
4244892 | 883892961 | 06 Tuning | 883893093 | 06 Lead Time Comments | 883893141 | 06 Lead Time | 883895810 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895895
4244893 | 883892969 | 01 Installation End | 883893464 | 01 Lead Time Comments | 883893573 | 01 Lead Time | 883896147 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896191
4244893 | 883892969 | 02 Integration | 883893022 | 02 Lead Time Comments | 883893061 | 02 Lead Time | 883895692 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895715
4244893 | 883892969 | 02 Integration | 883893022 | 02 Lead Time Comments | 883893061 | 02 Lead Time | 883895692 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895731
4244893 | 883892969 | 03 Integration Confirmed By NRO Technical Leader | 883893243 | 03 Lead Time Comments | 883893285 | 03 Lead Time | 883895968 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896047
4244893 | 883892969 | 04 SSV | 883893085 | 04 Lead Time Comments | 883893128 | 04 Lead Time | 883895796 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895840
4244893 | 883892969 | 04 SSV | 883893085 | 04 Lead Time Comments | 883893128 | 04 Lead Time | 883895796 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895866
4244893 | 883892969 | 05 SSV Confirmed By NDO Technical Leader | 883893316 | 05 Lead Time Comments | 883893370 | 05 Lead Time | 883895971 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896051
4244893 | 883892969 | 06 Tuning | 883893142 | 06 Lead Time Comments | 883893231 | 06 Lead Time | 883895903 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896004
4244893 | 883892969 | 06 Tuning | 883893142 | 06 Lead Time Comments | 883893231 | 06 Lead Time | 883895903 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896050
4244894 | 883892968 | 01 Installation End | 883893446 | 01 Lead Time Comments | 883893550 | 01 Lead Time | 883896086 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896114
4244894 | 883892968 | 02 Integration | 883893030 | 02 Lead Time Comments | 883893068 | 02 Lead Time | 883895691 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895712
4244894 | 883892968 | 02 Integration | 883893030 | 02 Lead Time Comments | 883893068 | 02 Lead Time | 883895691 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895751
4244894 | 883892968 | 03 Integration Confirmed By NRO Technical Leader | 883893240 | 03 Lead Time Comments | 883893280 | 03 Lead Time | 883895909 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895956
4244894 | 883892968 | 04 SSV | 883893081 | 04 Lead Time Comments | 883893127 | 04 Lead Time | 883895789 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895860
4244894 | 883892968 | 04 SSV | 883893081 | 04 Lead Time Comments | 883893127 | 04 Lead Time | 883895789 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895867
4244894 | 883892968 | 05 SSV Confirmed By NDO Technical Leader | 883893298 | 05 Lead Time Comments | 883893358 | 05 Lead Time | 883895964 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883895994
4244894 | 883892968 | 06 Tuning | 883893155 | 06 Lead Time Comments | 883893220 | 06 Lead Time | 883895847 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895887
4244894 | 883892968 | 06 Tuning | 883893155 | 06 Lead Time Comments | 883893220 | 06 Lead Time | 883895847 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895950
4244895 | 883892972 | 01 Installation End | 883893413 | 01 Lead Time Comments | 883893486 | 01 Lead Time | 883896085 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896113
4244895 | 883892972 | 02 Integration | 883893015 | 02 Lead Time Comments | 883893062 | 02 Lead Time | 883895651 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895681
4244895 | 883892972 | 02 Integration | 883893015 | 02 Lead Time Comments | 883893062 | 02 Lead Time | 883895651 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895721
4244895 | 883892972 | 03 Integration Confirmed By NRO Technical Leader | 883893217 | 03 Lead Time Comments | 883893259 | 03 Lead Time | 883895925 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895988
4244895 | 883892972 | 04 SSV | 883893075 | 04 Lead Time Comments | 883893107 | 04 Lead Time | 883895748 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895829
4244895 | 883892972 | 04 SSV | 883893075 | 04 Lead Time Comments | 883893107 | 04 Lead Time | 883895748 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895882
4244895 | 883892972 | 05 SSV Confirmed By NDO Technical Leader | 883893283 | 05 Lead Time Comments | 883893342 | 05 Lead Time | 883895967 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896007
4244895 | 883892972 | 06 Tuning | 883893132 | 06 Lead Time Comments | 883893189 | 06 Lead Time | 883895787 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895868
4244895 | 883892972 | 06 Tuning | 883893132 | 06 Lead Time Comments | 883893189 | 06 Lead Time | 883895787 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895890
4244896 | 883892978 | 01 Installation End | 883893477 | 01 Lead Time Comments | 883893598 | 01 Lead Time | 883896151 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896162
4244896 | 883892978 | 02 Integration | 883893082 | 02 Lead Time Comments | 883893130 | 02 Lead Time | 883895785 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895821
4244896 | 883892978 | 02 Integration | 883893082 | 02 Lead Time Comments | 883893130 | 02 Lead Time | 883895785 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895871
4244896 | 883892978 | 03 Integration Confirmed By NRO Technical Leader | 883893276 | 03 Lead Time Comments | 883893336 | 03 Lead Time | 883895959 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896049
4244896 | 883892978 | 04 SSV | 883893156 | 04 Lead Time Comments | 883893204 | 04 Lead Time | 883895842 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895873
4244896 | 883892978 | 04 SSV | 883893156 | 04 Lead Time Comments | 883893204 | 04 Lead Time | 883895842 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895893
4244896 | 883892978 | 05 SSV Confirmed By NDO Technical Leader | 883893343 | 05 Lead Time Comments | 883893408 | 05 Lead Time | 883896022 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896078
4244896 | 883892978 | 06 Tuning | 883893223 | 06 Lead Time Comments | 883893265 | 06 Lead Time | 883895926 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895955
4244896 | 883892978 | 06 Tuning | 883893223 | 06 Lead Time Comments | 883893265 | 06 Lead Time | 883895926 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895982
4244897 | 883892980 | 01 Installation End | 883893457 | 01 Lead Time Comments | 883893555 | 01 Lead Time | 883896150 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896174
4244897 | 883892980 | 02 Integration | 883893052 | 02 Lead Time Comments | 883893091 | 02 Lead Time | 883895747 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895807
4244897 | 883892980 | 02 Integration | 883893052 | 02 Lead Time Comments | 883893091 | 02 Lead Time | 883895747 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895838
4244897 | 883892980 | 03 Integration Confirmed By NRO Technical Leader | 883893247 | 03 Lead Time Comments | 883893300 | 03 Lead Time | 883895989 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896003
4244897 | 883892980 | 04 SSV | 883893098 | 04 Lead Time Comments | 883893165 | 04 Lead Time | 883895792 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895826
4244897 | 883892980 | 04 SSV | 883893098 | 04 Lead Time Comments | 883893165 | 04 Lead Time | 883895792 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895875
4244897 | 883892980 | 05 SSV Confirmed By NDO Technical Leader | 883893315 | 05 Lead Time Comments | 883893376 | 05 Lead Time | 883896048 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896089
4244897 | 883892980 | 06 Tuning | 883893168 | 06 Lead Time Comments | 883893239 | 06 Lead Time | 883895901 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895987
4244897 | 883892980 | 06 Tuning | 883893168 | 06 Lead Time Comments | 883893239 | 06 Lead Time | 883895901 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896041
4244898 | 883892990 | 01 Installation End | 883893589 | 01 Lead Time Comments | 883893639 | 01 Lead Time | 883896146 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896170
4244898 | 883892990 | 02 Integration | 883893063 | 02 Lead Time Comments | 883893110 | 02 Lead Time | 883895745 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895779
4244898 | 883892990 | 02 Integration | 883893063 | 02 Lead Time Comments | 883893110 | 02 Lead Time | 883895745 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895813
4244898 | 883892990 | 03 Integration Confirmed By NRO Technical Leader | 883893308 | 03 Lead Time Comments | 883893361 | 03 Lead Time | 883895963 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896028
4244898 | 883892990 | 04 SSV | 883893131 | 04 Lead Time Comments | 883893200 | 04 Lead Time | 883895850 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895900
4244898 | 883892990 | 04 SSV | 883893131 | 04 Lead Time Comments | 883893200 | 04 Lead Time | 883895850 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895948
4244898 | 883892990 | 05 SSV Confirmed By NDO Technical Leader | 883893389 | 05 Lead Time Comments | 883893438 | 05 Lead Time | 883896026 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896065
4244898 | 883892990 | 06 Tuning | 883893232 | 06 Lead Time Comments | 883893289 | 06 Lead Time | 883895960 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896030
4244898 | 883892990 | 06 Tuning | 883893232 | 06 Lead Time Comments | 883893289 | 06 Lead Time | 883895960 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896069
4244899 | 883892994 | 01 Installation End | 883893593 | 01 Lead Time Comments | 883893641 | 01 Lead Time | 883896155 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896176
4244899 | 883892994 | 02 Integration | 883893079 | 02 Lead Time Comments | 883893135 | 02 Lead Time | 883895786 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895841
4244899 | 883892994 | 02 Integration | 883893079 | 02 Lead Time Comments | 883893135 | 02 Lead Time | 883895786 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895888
4244899 | 883892994 | 03 Integration Confirmed By NRO Technical Leader | 883893304 | 03 Lead Time Comments | 883893359 | 03 Lead Time | 883895972 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896000
4244899 | 883892994 | 04 SSV | 883893151 | 04 Lead Time Comments | 883893209 | 04 Lead Time | 883895853 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895929
4244899 | 883892994 | 04 SSV | 883893151 | 04 Lead Time Comments | 883893209 | 04 Lead Time | 883895853 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895938
4244899 | 883892994 | 05 SSV Confirmed By NDO Technical Leader | 883893380 | 05 Lead Time Comments | 883893447 | 05 Lead Time | 883896092 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896121
4244899 | 883892994 | 06 Tuning | 883893227 | 06 Lead Time Comments | 883893278 | 06 Lead Time | 883895907 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895943
4244899 | 883892994 | 06 Tuning | 883893227 | 06 Lead Time Comments | 883893278 | 06 Lead Time | 883895907 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896036
4244900 | 883892996 | 01 Installation End | 883893479 | 01 Lead Time Comments | 883893581 | 01 Lead Time | 883896143 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896166
4244900 | 883892996 | 02 Integration | 883893083 | 02 Lead Time Comments | 883893121 | 02 Lead Time | 883895742 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895782
4244900 | 883892996 | 02 Integration | 883893083 | 02 Lead Time Comments | 883893121 | 02 Lead Time | 883895742 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895824
4244900 | 883892996 | 03 Integration Confirmed By NRO Technical Leader | 883893290 | 03 Lead Time Comments | 883893340 | 03 Lead Time | 883895969 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896061
4244900 | 883892996 | 04 SSV | 883893143 | 04 Lead Time Comments | 883893194 | 04 Lead Time | 883895790 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895839
4244900 | 883892996 | 04 SSV | 883893143 | 04 Lead Time Comments | 883893194 | 04 Lead Time | 883895790 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895897
4244900 | 883892996 | 05 SSV Confirmed By NDO Technical Leader | 883893349 | 05 Lead Time Comments | 883893411 | 05 Lead Time | 883896027 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896058
4244900 | 883892996 | 06 Tuning | 883893212 | 06 Lead Time Comments | 883893261 | 06 Lead Time | 883895906 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895942
4244900 | 883892996 | 06 Tuning | 883893212 | 06 Lead Time Comments | 883893261 | 06 Lead Time | 883895906 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895979
4244901 | 883893020 | 01 Installation End | 883893466 | 01 Lead Time Comments | 883893579 | 01 Lead Time | 883896142 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896167
4244901 | 883893020 | 02 Integration | 883893090 | 02 Lead Time Comments | 883893139 | 02 Lead Time | 883895795 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895832
4244901 | 883893020 | 02 Integration | 883893090 | 02 Lead Time Comments | 883893139 | 02 Lead Time | 883895795 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895898
4244901 | 883893020 | 03 Integration Confirmed By NRO Technical Leader | 883893293 | 03 Lead Time Comments | 883893341 | 03 Lead Time | 883895970 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883895999
4244901 | 883893020 | 04 SSV | 883893154 | 04 Lead Time Comments | 883893202 | 04 Lead Time | 883895852 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895878
4244901 | 883893020 | 04 SSV | 883893154 | 04 Lead Time Comments | 883893202 | 04 Lead Time | 883895852 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895930
4244901 | 883893020 | 05 SSV Confirmed By NDO Technical Leader | 883893351 | 05 Lead Time Comments | 883893404 | 05 Lead Time | 883896037 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896079
4244901 | 883893020 | 06 Tuning | 883893225 | 06 Lead Time Comments | 883893264 | 06 Lead Time | 883895914 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883895946
4244901 | 883893020 | 06 Tuning | 883893225 | 06 Lead Time Comments | 883893264 | 06 Lead Time | 883895914 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883895980
4244902 | 883893033 | 01 Installation End | 883893607 | 01 Lead Time Comments | 883893674 | 01 Lead Time | 883896192 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896202
4244902 | 883893033 | 02 Integration | 883893117 | 02 Lead Time Comments | 883893167 | 02 Lead Time | 883895801 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895858
4244902 | 883893033 | 02 Integration | 883893117 | 02 Lead Time Comments | 883893167 | 02 Lead Time | 883895801 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895881
4244902 | 883893033 | 03 Integration Confirmed By NRO Technical Leader | 883893345 | 03 Lead Time Comments | 883893402 | 03 Lead Time | 883896019 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896068
4244902 | 883893033 | 04 SSV | 883893192 | 04 Lead Time Comments | 883893256 | 04 Lead Time | 883895911 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895939
4244902 | 883893033 | 04 SSV | 883893192 | 04 Lead Time Comments | 883893256 | 04 Lead Time | 883895911 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895976
4244902 | 883893033 | 05 SSV Confirmed By NDO Technical Leader | 883893416 | 05 Lead Time Comments | 883893462 | 05 Lead Time | 883896082 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896119
4244902 | 883893033 | 06 Tuning | 883893266 | 06 Lead Time Comments | 883893334 | 06 Lead Time | 883895974 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896012
4244902 | 883893033 | 06 Tuning | 883893266 | 06 Lead Time Comments | 883893334 | 06 Lead Time | 883895974 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896032
4244903 | 883893037 | 01 Installation End | 883893638 | 01 Lead Time Comments | 883893716 | 01 Lead Time | 883896193 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896201
4244903 | 883893037 | 02 Integration | 883893137 | 02 Lead Time Comments | 883893197 | 02 Lead Time | 883895846 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895889
4244903 | 883893037 | 02 Integration | 883893137 | 02 Lead Time Comments | 883893197 | 02 Lead Time | 883895846 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895920
4244903 | 883893037 | 03 Integration Confirmed By NRO Technical Leader | 883893395 | 03 Lead Time Comments | 883893443 | 03 Lead Time | 883896081 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896101
4244903 | 883893037 | 04 SSV | 883893236 | 04 Lead Time Comments | 883893302 | 04 Lead Time | 883895961 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896006
4244903 | 883893037 | 04 SSV | 883893236 | 04 Lead Time Comments | 883893302 | 04 Lead Time | 883895961 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896043
4244903 | 883893037 | 05 SSV Confirmed By NDO Technical Leader | 883893455 | 05 Lead Time Comments | 883893534 | 05 Lead Time | 883896084 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896108
4244903 | 883893037 | 06 Tuning | 883893321 | 06 Lead Time Comments | 883893375 | 06 Lead Time | 883896021 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896074
4244903 | 883893037 | 06 Tuning | 883893321 | 06 Lead Time Comments | 883893375 | 06 Lead Time | 883896021 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896097
4244904 | 883893036 | 01 Installation End | 883893666 | 01 Lead Time Comments | 883893738 | 01 Lead Time | 883896194 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896207
4244904 | 883893036 | 02 Integration | 883893145 | 02 Lead Time Comments | 883893205 | 02 Lead Time | 883895845 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895896
4244904 | 883893036 | 02 Integration | 883893145 | 02 Lead Time Comments | 883893205 | 02 Lead Time | 883895845 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895936
4244904 | 883893036 | 03 Integration Confirmed By NRO Technical Leader | 883893400 | 03 Lead Time Comments | 883893441 | 03 Lead Time | 883896090 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896102
4244904 | 883893036 | 04 SSV | 883893228 | 04 Lead Time Comments | 883893292 | 04 Lead Time | 883895905 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895940
4244904 | 883893036 | 04 SSV | 883893228 | 04 Lead Time Comments | 883893292 | 04 Lead Time | 883895905 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895997
4244904 | 883893036 | 05 SSV Confirmed By NDO Technical Leader | 883893456 | 05 Lead Time Comments | 883893549 | 05 Lead Time | 883896083 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896118
4244904 | 883893036 | 06 Tuning | 883893306 | 06 Lead Time Comments | 883893369 | 06 Lead Time | 883896031 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896071
4244904 | 883893036 | 06 Tuning | 883893306 | 06 Lead Time Comments | 883893369 | 06 Lead Time | 883896031 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896095
4244905 | 883893035 | 01 Installation End | 883893723 | 01 Lead Time Comments | 883893805 | 01 Lead Time | 883896230 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896269
4244905 | 883893035 | 02 Integration | 883893148 | 02 Lead Time Comments | 883893215 | 02 Lead Time | 883895856 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895884
4244905 | 883893035 | 02 Integration | 883893148 | 02 Lead Time Comments | 883893215 | 02 Lead Time | 883895856 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895918
4244905 | 883893035 | 03 Integration Confirmed By NRO Technical Leader | 883893431 | 03 Lead Time Comments | 883893485 | 03 Lead Time | 883896080 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896111
4244905 | 883893035 | 04 SSV | 883893238 | 04 Lead Time Comments | 883893303 | 04 Lead Time | 883895966 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895996
4244905 | 883893035 | 04 SSV | 883893238 | 04 Lead Time Comments | 883893303 | 04 Lead Time | 883895966 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896044
4244905 | 883893035 | 05 SSV Confirmed By NDO Technical Leader | 883893538 | 05 Lead Time Comments | 883893627 | 05 Lead Time | 883896145 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896158
4244905 | 883893035 | 06 Tuning | 883893331 | 06 Lead Time Comments | 883893391 | 06 Lead Time | 883896023 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896100
4244905 | 883893035 | 06 Tuning | 883893331 | 06 Lead Time Comments | 883893391 | 06 Lead Time | 883896023 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896120
4244906 | 883893043 | 01 Installation End | 883893646 | 01 Lead Time Comments | 883893731 | 01 Lead Time | 883896198 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896256
4244906 | 883893043 | 02 Integration | 883893138 | 02 Lead Time Comments | 883893218 | 02 Lead Time | 883895855 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895885
4244906 | 883893043 | 02 Integration | 883893138 | 02 Lead Time Comments | 883893218 | 02 Lead Time | 883895855 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895945
4244906 | 883893043 | 03 Integration Confirmed By NRO Technical Leader | 883893374 | 03 Lead Time Comments | 883893434 | 03 Lead Time | 883896018 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896064
4244906 | 883893043 | 04 SSV | 883893242 | 04 Lead Time Comments | 883893291 | 04 Lead Time | 883895965 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896013
4244906 | 883893043 | 04 SSV | 883893242 | 04 Lead Time Comments | 883893291 | 04 Lead Time | 883895965 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896052
4244906 | 883893043 | 05 SSV Confirmed By NDO Technical Leader | 883893442 | 05 Lead Time Comments | 883893514 | 05 Lead Time | 883896088 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896112
4244906 | 883893043 | 06 Tuning | 883893309 | 06 Lead Time Comments | 883893362 | 06 Lead Time | 883895962 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896002
4244906 | 883893043 | 06 Tuning | 883893309 | 06 Lead Time Comments | 883893362 | 06 Lead Time | 883895962 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896015
4244907 | 883893038 | 01 Installation End | 883893706 | 01 Lead Time Comments | 883893778 | 01 Lead Time | 883896247 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896309
4244907 | 883893038 | 02 Integration | 883893140 | 02 Lead Time Comments | 883893207 | 02 Lead Time | 883895843 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883895886
4244907 | 883893038 | 02 Integration | 883893140 | 02 Lead Time Comments | 883893207 | 02 Lead Time | 883895843 | actcl--02 Integration--02 Lead Time Comments--Duration | 883895932
4244907 | 883893038 | 03 Integration Confirmed By NRO Technical Leader | 883893372 | 03 Lead Time Comments | 883893432 | 03 Lead Time | 883896029 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896059
4244907 | 883893038 | 04 SSV | 883893229 | 04 Lead Time Comments | 883893267 | 04 Lead Time | 883895931 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883895941
4244907 | 883893038 | 04 SSV | 883893229 | 04 Lead Time Comments | 883893267 | 04 Lead Time | 883895931 | actcl--04 SSV--04 Lead Time Comments--Duration | 883895975
4244907 | 883893038 | 05 SSV Confirmed By NDO Technical Leader | 883893436 | 05 Lead Time Comments | 883893506 | 05 Lead Time | 883896087 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896126
4244907 | 883893038 | 06 Tuning | 883893287 | 06 Lead Time Comments | 883893360 | 06 Lead Time | 883895977 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896009
4244907 | 883893038 | 06 Tuning | 883893287 | 06 Lead Time Comments | 883893360 | 06 Lead Time | 883895977 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896017
4244908 | 883893301 | 01 Installation End | 883894652 | 01 Lead Time Comments | 883894753 | 01 Lead Time | 883896876 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896915
4244908 | 883893301 | 02 Integration | 883893631 | 02 Lead Time Comments | 883893750 | 02 Lead Time | 883896246 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896270
4244908 | 883893301 | 02 Integration | 883893631 | 02 Lead Time Comments | 883893750 | 02 Lead Time | 883896246 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896294
4244908 | 883893301 | 03 Integration Confirmed By NRO Technical Leader | 883894174 | 03 Lead Time Comments | 883894263 | 03 Lead Time | 883896557 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896600
4244908 | 883893301 | 04 SSV | 883893790 | 04 Lead Time Comments | 883893943 | 04 Lead Time | 883896288 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896324
4244908 | 883893301 | 04 SSV | 883893790 | 04 Lead Time Comments | 883893943 | 04 Lead Time | 883896288 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896390
4244908 | 883893301 | 05 SSV Confirmed By NDO Technical Leader | 883894318 | 05 Lead Time Comments | 883894420 | 05 Lead Time | 883896713 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896785
4244908 | 883893301 | 06 Tuning | 883893987 | 06 Lead Time Comments | 883894131 | 06 Lead Time | 883896349 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896394
4244908 | 883893301 | 06 Tuning | 883893987 | 06 Lead Time Comments | 883894131 | 06 Lead Time | 883896349 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896413
4244909 | 883893314 | 01 Installation End | 883894575 | 01 Lead Time Comments | 883894696 | 01 Lead Time | 883896868 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896917
4244909 | 883893314 | 02 Integration | 883893697 | 02 Lead Time Comments | 883893763 | 02 Lead Time | 883896251 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896315
4244909 | 883893314 | 02 Integration | 883893697 | 02 Lead Time Comments | 883893763 | 02 Lead Time | 883896251 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896328
4244909 | 883893314 | 03 Integration Confirmed By NRO Technical Leader | 883894095 | 03 Lead Time Comments | 883894214 | 03 Lead Time | 883896500 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896518
4244909 | 883893314 | 04 SSV | 883893802 | 04 Lead Time Comments | 883893932 | 04 Lead Time | 883896301 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896334
4244909 | 883893314 | 04 SSV | 883893802 | 04 Lead Time Comments | 883893932 | 04 Lead Time | 883896301 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896375
4244909 | 883893314 | 05 SSV Confirmed By NDO Technical Leader | 883894285 | 05 Lead Time Comments | 883894381 | 05 Lead Time | 883896632 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896661
4244909 | 883893314 | 06 Tuning | 883893976 | 06 Lead Time Comments | 883894057 | 06 Lead Time | 883896361 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896415
4244909 | 883893314 | 06 Tuning | 883893976 | 06 Lead Time Comments | 883894057 | 06 Lead Time | 883896361 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896438
4244910 | 883893322 | 01 Installation End | 883894545 | 01 Lead Time Comments | 883894664 | 01 Lead Time | 883896810 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896827
4244910 | 883893322 | 02 Integration | 883893635 | 02 Lead Time Comments | 883893740 | 02 Lead Time | 883896235 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896254
4244910 | 883893322 | 02 Integration | 883893635 | 02 Lead Time Comments | 883893740 | 02 Lead Time | 883896235 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896266
4244910 | 883893322 | 03 Integration Confirmed By NRO Technical Leader | 883894102 | 03 Lead Time Comments | 883894197 | 03 Lead Time | 883896427 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896483
4244910 | 883893322 | 04 SSV | 883893774 | 04 Lead Time Comments | 883893889 | 04 Lead Time | 883896243 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896260
4244910 | 883893322 | 04 SSV | 883893774 | 04 Lead Time Comments | 883893889 | 04 Lead Time | 883896243 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896293
4244910 | 883893322 | 05 SSV Confirmed By NDO Technical Leader | 883894217 | 05 Lead Time Comments | 883894322 | 05 Lead Time | 883896585 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896604
4244910 | 883893322 | 06 Tuning | 883893914 | 06 Lead Time Comments | 883894048 | 06 Lead Time | 883896344 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896414
4244910 | 883893322 | 06 Tuning | 883893914 | 06 Lead Time Comments | 883894048 | 06 Lead Time | 883896344 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896432
4244911 | 883893364 | 01 Installation End | 883894722 | 01 Lead Time Comments | 883894856 | 01 Lead Time | 883896933 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896977
4244911 | 883893364 | 02 Integration | 883893701 | 02 Lead Time Comments | 883893818 | 02 Lead Time | 883896232 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896299
4244911 | 883893364 | 02 Integration | 883893701 | 02 Lead Time Comments | 883893818 | 02 Lead Time | 883896232 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896325
4244911 | 883893364 | 03 Integration Confirmed By NRO Technical Leader | 883894242 | 03 Lead Time Comments | 883894329 | 03 Lead Time | 883896572 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896607 | 客户原因-物业问题
4244911 | 883893364 | 04 SSV | 883893882 | 04 Lead Time Comments | 883894011 | 04 Lead Time | 883896311 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896384
4244911 | 883893364 | 04 SSV | 883893882 | 04 Lead Time Comments | 883894011 | 04 Lead Time | 883896311 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896404
4244911 | 883893364 | 05 SSV Confirmed By NDO Technical Leader | 883894390 | 05 Lead Time Comments | 883894546 | 05 Lead Time | 883896706 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896775
4244911 | 883893364 | 06 Tuning | 883894060 | 06 Lead Time Comments | 883894205 | 06 Lead Time | 883896495 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896542
4244911 | 883893364 | 06 Tuning | 883894060 | 06 Lead Time Comments | 883894205 | 06 Lead Time | 883896495 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896578
4244912 | 883893366 | 01 Installation End | 883894506 | 01 Lead Time Comments | 883894587 | 01 Lead Time | 883896797 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896836
4244912 | 883893366 | 02 Integration | 883893643 | 02 Lead Time Comments | 883893722 | 02 Lead Time | 883896200 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896212
4244912 | 883893366 | 02 Integration | 883893643 | 02 Lead Time Comments | 883893722 | 02 Lead Time | 883896200 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896222
4244912 | 883893366 | 03 Integration Confirmed By NRO Technical Leader | 883894112 | 03 Lead Time Comments | 883894203 | 03 Lead Time | 883896494 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896523 | 客户原因-物业问题
4244912 | 883893366 | 04 SSV | 883893756 | 04 Lead Time Comments | 883893873 | 04 Lead Time | 883896238 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896285
4244912 | 883893366 | 04 SSV | 883893756 | 04 Lead Time Comments | 883893873 | 04 Lead Time | 883896238 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896316
4244912 | 883893366 | 05 SSV Confirmed By NDO Technical Leader | 883894228 | 05 Lead Time Comments | 883894327 | 05 Lead Time | 883896579 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896602
4244912 | 883893366 | 06 Tuning | 883893921 | 06 Lead Time Comments | 883894066 | 06 Lead Time | 883896379 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896416
4244912 | 883893366 | 06 Tuning | 883893921 | 06 Lead Time Comments | 883894066 | 06 Lead Time | 883896379 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896464
4244913 | 883893365 | 01 Installation End | 883894663 | 01 Lead Time Comments | 883894809 | 01 Lead Time | 883896953 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896979
4244913 | 883893365 | 02 Integration | 883893693 | 02 Lead Time Comments | 883893789 | 02 Lead Time | 883896245 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896278
4244913 | 883893365 | 02 Integration | 883893693 | 02 Lead Time Comments | 883893789 | 02 Lead Time | 883896245 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896305
4244913 | 883893365 | 03 Integration Confirmed By NRO Technical Leader | 883894222 | 03 Lead Time Comments | 883894328 | 03 Lead Time | 883896561 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896594 | 客户原因-物业问题
4244913 | 883893365 | 04 SSV | 883893843 | 04 Lead Time Comments | 883893991 | 04 Lead Time | 883896303 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896314
4244913 | 883893365 | 04 SSV | 883893843 | 04 Lead Time Comments | 883893991 | 04 Lead Time | 883896303 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896326
4244913 | 883893365 | 05 SSV Confirmed By NDO Technical Leader | 883894349 | 05 Lead Time Comments | 883894499 | 05 Lead Time | 883896714 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896748
4244913 | 883893365 | 06 Tuning | 883894036 | 06 Lead Time Comments | 883894171 | 06 Lead Time | 883896425 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896466
4244913 | 883893365 | 06 Tuning | 883894036 | 06 Lead Time Comments | 883894171 | 06 Lead Time | 883896425 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896475
4244914 | 883893435 | 01 Installation End | 883894633 | 01 Lead Time Comments | 883894841 | 01 Lead Time | 883896938 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896985
4244914 | 883893435 | 02 Integration | 883893692 | 02 Lead Time Comments | 883893780 | 02 Lead Time | 883896228 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896267
4244914 | 883893435 | 02 Integration | 883893692 | 02 Lead Time Comments | 883893780 | 02 Lead Time | 883896228 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896276
4244914 | 883893435 | 03 Integration Confirmed By NRO Technical Leader | 883894059 | 03 Lead Time Comments | 883894200 | 03 Lead Time | 883896512 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896556 | 客户原因-物业问题
4244914 | 883893435 | 04 SSV | 883893810 | 04 Lead Time Comments | 883893947 | 04 Lead Time | 883896286 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896341
4244914 | 883893435 | 04 SSV | 883893810 | 04 Lead Time Comments | 883893947 | 04 Lead Time | 883896286 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896437
4244914 | 883893435 | 05 SSV Confirmed By NDO Technical Leader | 883894266 | 05 Lead Time Comments | 883894363 | 05 Lead Time | 883896638 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896656
4244914 | 883893435 | 06 Tuning | 883893971 | 06 Lead Time Comments | 883894044 | 06 Lead Time | 883896296 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896313
4244914 | 883893435 | 06 Tuning | 883893971 | 06 Lead Time Comments | 883894044 | 06 Lead Time | 883896296 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896330
4244915 | 883893454 | 01 Installation End | 883894765 | 01 Lead Time Comments | 883894876 | 01 Lead Time | 883896956 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896975
4244915 | 883893454 | 02 Integration | 883893698 | 02 Lead Time Comments | 883893804 | 02 Lead Time | 883896248 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896277
4244915 | 883893454 | 02 Integration | 883893698 | 02 Lead Time Comments | 883893804 | 02 Lead Time | 883896248 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896319
4244915 | 883893454 | 03 Integration Confirmed By NRO Technical Leader | 883894227 | 03 Lead Time Comments | 883894376 | 03 Lead Time | 883896624 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896683 | 客户原因-物业问题
4244915 | 883893454 | 04 SSV | 883893854 | 04 Lead Time Comments | 883894001 | 04 Lead Time | 883896295 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896340
4244915 | 883893454 | 04 SSV | 883893854 | 04 Lead Time Comments | 883894001 | 04 Lead Time | 883896295 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896382
4244915 | 883893454 | 05 SSV Confirmed By NDO Technical Leader | 883894431 | 05 Lead Time Comments | 883894553 | 05 Lead Time | 883896789 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896833
4244915 | 883893454 | 06 Tuning | 883894056 | 06 Lead Time Comments | 883894201 | 06 Lead Time | 883896489 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896541
4244915 | 883893454 | 06 Tuning | 883894056 | 06 Lead Time Comments | 883894201 | 06 Lead Time | 883896489 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896598
4244916 | 883893490 | 01 Installation End | 883894864 | 01 Lead Time Comments | 883895008 | 01 Lead Time | 883897020 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897038
4244916 | 883893490 | 02 Integration | 883893744 | 02 Lead Time Comments | 883893904 | 02 Lead Time | 883896287 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896321
4244916 | 883893490 | 02 Integration | 883893744 | 02 Lead Time Comments | 883893904 | 02 Lead Time | 883896287 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896342
4244916 | 883893490 | 03 Integration Confirmed By NRO Technical Leader | 883894389 | 03 Lead Time Comments | 883894513 | 03 Lead Time | 883896703 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896761 | 客户原因-物业问题
4244916 | 883893490 | 04 SSV | 883893962 | 04 Lead Time Comments | 883894114 | 04 Lead Time | 883896422 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896473
4244916 | 883893490 | 04 SSV | 883893962 | 04 Lead Time Comments | 883894114 | 04 Lead Time | 883896422 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896527
4244916 | 883893490 | 05 SSV Confirmed By NDO Technical Leader | 883894554 | 05 Lead Time Comments | 883894684 | 05 Lead Time | 883896813 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896838
4244916 | 883893490 | 06 Tuning | 883894181 | 06 Lead Time Comments | 883894341 | 06 Lead Time | 883896620 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896652
4244916 | 883893490 | 06 Tuning | 883894181 | 06 Lead Time Comments | 883894341 | 06 Lead Time | 883896620 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896667
4244917 | 883893493 | 01 Installation End | 883895014 | 01 Lead Time Comments | 883895170 | 01 Lead Time | 883897017 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897052
4244917 | 883893493 | 02 Integration | 883893908 | 02 Lead Time Comments | 883894125 | 02 Lead Time | 883896364 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896403
4244917 | 883893493 | 02 Integration | 883893908 | 02 Lead Time Comments | 883894125 | 02 Lead Time | 883896364 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896456
4244917 | 883893493 | 03 Integration Confirmed By NRO Technical Leader | 883894489 | 03 Lead Time Comments | 883894595 | 03 Lead Time | 883896821 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896893 | 客户原因-物业问题
4244917 | 883893493 | 04 SSV | 883894166 | 04 Lead Time Comments | 883894289 | 04 Lead Time | 883896559 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896590
4244917 | 883893493 | 04 SSV | 883894166 | 04 Lead Time Comments | 883894289 | 04 Lead Time | 883896559 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896610
4244917 | 883893493 | 05 SSV Confirmed By NDO Technical Leader | 883894674 | 05 Lead Time Comments | 883894783 | 05 Lead Time | 883896882 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896912
4244917 | 883893493 | 06 Tuning | 883894344 | 06 Lead Time Comments | 883894438 | 06 Lead Time | 883896726 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896746
4244917 | 883893493 | 06 Tuning | 883894344 | 06 Lead Time Comments | 883894438 | 06 Lead Time | 883896726 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896779
4244918 | 883893495 | 01 Installation End | 883894665 | 01 Lead Time Comments | 883894805 | 01 Lead Time | 883896952 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896993
4244918 | 883893495 | 02 Integration | 883893741 | 02 Lead Time Comments | 883893886 | 02 Lead Time | 883896236 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896275
4244918 | 883893495 | 02 Integration | 883893741 | 02 Lead Time Comments | 883893886 | 02 Lead Time | 883896236 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896306
4244918 | 883893495 | 03 Integration Confirmed By NRO Technical Leader | 883894239 | 03 Lead Time Comments | 883894340 | 03 Lead Time | 883896566 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896611 | 客户原因-物业问题
4244918 | 883893495 | 04 SSV | 883893942 | 04 Lead Time Comments | 883894042 | 04 Lead Time | 883896363 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896402
4244918 | 883893495 | 04 SSV | 883893942 | 04 Lead Time Comments | 883894042 | 04 Lead Time | 883896363 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896434
4244918 | 883893495 | 05 SSV Confirmed By NDO Technical Leader | 883894355 | 05 Lead Time Comments | 883894465 | 05 Lead Time | 883896702 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896735
4244918 | 883893495 | 06 Tuning | 883894070 | 06 Lead Time Comments | 883894179 | 06 Lead Time | 883896488 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896546
4244918 | 883893495 | 06 Tuning | 883894070 | 06 Lead Time Comments | 883894179 | 06 Lead Time | 883896488 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896583
4244919 | 883893494 | 01 Installation End | 883894581 | 01 Lead Time Comments | 883894721 | 01 Lead Time | 883896879 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896906
4244919 | 883893494 | 02 Integration | 883893709 | 02 Lead Time Comments | 883893813 | 02 Lead Time | 883896252 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896263
4244919 | 883893494 | 02 Integration | 883893709 | 02 Lead Time Comments | 883893813 | 02 Lead Time | 883896252 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896317
4244919 | 883893494 | 03 Integration Confirmed By NRO Technical Leader | 883894178 | 03 Lead Time Comments | 883894235 | 03 Lead Time | 883896492 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896533 | 客户原因-物业问题
4244919 | 883893494 | 04 SSV | 883893850 | 04 Lead Time Comments | 883893977 | 04 Lead Time | 883896290 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896329
4244919 | 883893494 | 04 SSV | 883893850 | 04 Lead Time Comments | 883893977 | 04 Lead Time | 883896290 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896371
4244919 | 883893494 | 05 SSV Confirmed By NDO Technical Leader | 883894269 | 05 Lead Time Comments | 883894339 | 05 Lead Time | 883896637 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896677
4244919 | 883893494 | 06 Tuning | 883894005 | 06 Lead Time Comments | 883894123 | 06 Lead Time | 883896421 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896457
4244919 | 883893494 | 06 Tuning | 883894005 | 06 Lead Time Comments | 883894123 | 06 Lead Time | 883896421 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896478
4244920 | 883893497 | 01 Installation End | 883894728 | 01 Lead Time Comments | 883894845 | 01 Lead Time | 883896929 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896998
4244920 | 883893497 | 02 Integration | 883893710 | 02 Lead Time Comments | 883893884 | 02 Lead Time | 883896242 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896282
4244920 | 883893497 | 02 Integration | 883893710 | 02 Lead Time Comments | 883893884 | 02 Lead Time | 883896242 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896322
4244920 | 883893497 | 03 Integration Confirmed By NRO Technical Leader | 883894240 | 03 Lead Time Comments | 883894348 | 03 Lead Time | 883896562 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896586 | 客户原因-物业问题
4244920 | 883893497 | 04 SSV | 883893920 | 04 Lead Time Comments | 883894043 | 04 Lead Time | 883896381 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896452
4244920 | 883893497 | 04 SSV | 883893920 | 04 Lead Time Comments | 883894043 | 04 Lead Time | 883896381 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896480
4244920 | 883893497 | 05 SSV Confirmed By NDO Technical Leader | 883894388 | 05 Lead Time Comments | 883894514 | 05 Lead Time | 883896712 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896755
4244920 | 883893497 | 06 Tuning | 883894097 | 06 Lead Time Comments | 883894190 | 06 Lead Time | 883896511 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896521
4244920 | 883893497 | 06 Tuning | 883894097 | 06 Lead Time Comments | 883894190 | 06 Lead Time | 883896511 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896548
4244921 | 883893491 | 01 Installation End | 883894815 | 01 Lead Time Comments | 883894944 | 01 Lead Time | 883896947 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896962
4244921 | 883893491 | 02 Integration | 883893754 | 02 Lead Time Comments | 883893874 | 02 Lead Time | 883896237 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896271
4244921 | 883893491 | 02 Integration | 883893754 | 02 Lead Time Comments | 883893874 | 02 Lead Time | 883896237 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896283
4244921 | 883893491 | 03 Integration Confirmed By NRO Technical Leader | 883894282 | 03 Lead Time Comments | 883894401 | 03 Lead Time | 883896629 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896664
4244921 | 883893491 | 04 SSV | 883893923 | 04 Lead Time Comments | 883894009 | 04 Lead Time | 883896291 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896335
4244921 | 883893491 | 04 SSV | 883893923 | 04 Lead Time Comments | 883894009 | 04 Lead Time | 883896291 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896373
4244921 | 883893491 | 05 SSV Confirmed By NDO Technical Leader | 883894448 | 05 Lead Time Comments | 883894557 | 05 Lead Time | 883896729 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896763
4244921 | 883893491 | 06 Tuning | 883894052 | 06 Lead Time Comments | 883894187 | 06 Lead Time | 883896493 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896525
4244921 | 883893491 | 06 Tuning | 883894052 | 06 Lead Time Comments | 883894187 | 06 Lead Time | 883896493 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896581
4244922 | 883893489 | 01 Installation End | 883894637 | 01 Lead Time Comments | 883894724 | 01 Lead Time | 883896867 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896910
4244922 | 883893489 | 02 Integration | 883893696 | 02 Lead Time Comments | 883893777 | 02 Lead Time | 883896231 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896332
4244922 | 883893489 | 02 Integration | 883893696 | 02 Lead Time Comments | 883893777 | 02 Lead Time | 883896231 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896368
4244922 | 883893489 | 03 Integration Confirmed By NRO Technical Leader | 883894132 | 03 Lead Time Comments | 883894223 | 03 Lead Time | 883896510 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896555
4244922 | 883893489 | 04 SSV | 883893832 | 04 Lead Time Comments | 883893959 | 04 Lead Time | 883896297 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896327
4244922 | 883893489 | 04 SSV | 883893832 | 04 Lead Time Comments | 883893959 | 04 Lead Time | 883896297 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896378
4244922 | 883893489 | 05 SSV Confirmed By NDO Technical Leader | 883894260 | 05 Lead Time Comments | 883894409 | 05 Lead Time | 883896642 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896687
4244922 | 883893489 | 06 Tuning | 883893982 | 06 Lead Time Comments | 883894086 | 06 Lead Time | 883896356 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896398
4244922 | 883893489 | 06 Tuning | 883893982 | 06 Lead Time Comments | 883894086 | 06 Lead Time | 883896356 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896453
4244923 | 883893509 | 01 Installation End | 883894987 | 01 Lead Time Comments | 883895190 | 01 Lead Time | 883897103 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897125
4244923 | 883893509 | 02 Integration | 883893900 | 02 Lead Time Comments | 883894064 | 02 Lead Time | 883896347 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896468
4244923 | 883893509 | 02 Integration | 883893900 | 02 Lead Time Comments | 883894064 | 02 Lead Time | 883896347 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896514
4244923 | 883893509 | 03 Integration Confirmed By NRO Technical Leader | 883894416 | 03 Lead Time Comments | 883894532 | 03 Lead Time | 883896715 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896744
4244923 | 883893509 | 04 SSV | 883894096 | 04 Lead Time Comments | 883894219 | 04 Lead Time | 883896490 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896530
4244923 | 883893509 | 04 SSV | 883894096 | 04 Lead Time Comments | 883894219 | 04 Lead Time | 883896490 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896550
4244923 | 883893509 | 05 SSV Confirmed By NDO Technical Leader | 883894568 | 05 Lead Time Comments | 883894710 | 05 Lead Time | 883896819 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896841
4244923 | 883893509 | 06 Tuning | 883894267 | 06 Lead Time Comments | 883894357 | 06 Lead Time | 883896623 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896668
4244923 | 883893509 | 06 Tuning | 883894267 | 06 Lead Time Comments | 883894357 | 06 Lead Time | 883896623 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896686
4244924 | 883893496 | 01 Installation End | 883894792 | 01 Lead Time Comments | 883894908 | 01 Lead Time | 883896954 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896969
4244924 | 883893496 | 02 Integration | 883893705 | 02 Lead Time Comments | 883893849 | 02 Lead Time | 883896239 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896258
4244924 | 883893496 | 02 Integration | 883893705 | 02 Lead Time Comments | 883893849 | 02 Lead Time | 883896239 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896274
4244924 | 883893496 | 03 Integration Confirmed By NRO Technical Leader | 883894325 | 03 Lead Time Comments | 883894426 | 03 Lead Time | 883896694 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896758
4244924 | 883893496 | 04 SSV | 883893963 | 04 Lead Time Comments | 883894117 | 04 Lead Time | 883896451 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896477
4244924 | 883893496 | 04 SSV | 883893963 | 04 Lead Time Comments | 883894117 | 04 Lead Time | 883896451 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896526
4244924 | 883893496 | 05 SSV Confirmed By NDO Technical Leader | 883894488 | 05 Lead Time Comments | 883894636 | 05 Lead Time | 883896798 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896887
4244924 | 883893496 | 06 Tuning | 883894175 | 06 Lead Time Comments | 883894275 | 06 Lead Time | 883896584 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896613
4244924 | 883893496 | 06 Tuning | 883894175 | 06 Lead Time Comments | 883894275 | 06 Lead Time | 883896584 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896644
4244925 | 883893513 | 01 Installation End | 883894901 | 01 Lead Time Comments | 883895003 | 01 Lead Time | 883897007 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897066
4244925 | 883893513 | 02 Integration | 883893916 | 02 Lead Time Comments | 883894050 | 02 Lead Time | 883896358 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896400
4244925 | 883893513 | 02 Integration | 883893916 | 02 Lead Time Comments | 883894050 | 02 Lead Time | 883896358 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896442 | 客户原因-传输问题
4244925 | 883893513 | 03 Integration Confirmed By NRO Technical Leader | 883894457 | 03 Lead Time Comments | 883894566 | 03 Lead Time | 883896724 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896737
4244925 | 883893513 | 04 SSV | 883894107 | 04 Lead Time Comments | 883894254 | 04 Lead Time | 883896568 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896596
4244925 | 883893513 | 04 SSV | 883894107 | 04 Lead Time Comments | 883894254 | 04 Lead Time | 883896568 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896665
4244925 | 883893513 | 05 SSV Confirmed By NDO Technical Leader | 883894616 | 05 Lead Time Comments | 883894756 | 05 Lead Time | 883896877 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896901
4244925 | 883893513 | 06 Tuning | 883894304 | 06 Lead Time Comments | 883894386 | 06 Lead Time | 883896633 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896673
4244925 | 883893513 | 06 Tuning | 883894304 | 06 Lead Time Comments | 883894386 | 06 Lead Time | 883896633 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896689
4244926 | 883893492 | 01 Installation End | 883894673 | 01 Lead Time Comments | 883894817 | 01 Lead Time | 883896936 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896978
4244926 | 883893492 | 02 Integration | 883893730 | 02 Lead Time Comments | 883893865 | 02 Lead Time | 883896240 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896262
4244926 | 883893492 | 02 Integration | 883893730 | 02 Lead Time Comments | 883893865 | 02 Lead Time | 883896240 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896302
4244926 | 883893492 | 03 Integration Confirmed By NRO Technical Leader | 883894261 | 03 Lead Time Comments | 883894351 | 03 Lead Time | 883896619 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896655
4244926 | 883893492 | 04 SSV | 883893919 | 04 Lead Time Comments | 883894045 | 04 Lead Time | 883896360 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896428
4244926 | 883893492 | 04 SSV | 883893919 | 04 Lead Time Comments | 883894045 | 04 Lead Time | 883896360 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896454
4244926 | 883893492 | 05 SSV Confirmed By NDO Technical Leader | 883894391 | 05 Lead Time Comments | 883894509 | 05 Lead Time | 883896698 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896734
4244926 | 883893492 | 06 Tuning | 883894080 | 06 Lead Time Comments | 883894210 | 06 Lead Time | 883896496 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896534
4244926 | 883893492 | 06 Tuning | 883894080 | 06 Lead Time Comments | 883894210 | 06 Lead Time | 883896496 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896552
4244927 | 883893500 | 01 Installation End | 883894734 | 01 Lead Time Comments | 883894896 | 01 Lead Time | 883896940 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897045
4244927 | 883893500 | 02 Integration | 883893829 | 02 Lead Time Comments | 883893958 | 02 Lead Time | 883896298 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896346
4244927 | 883893500 | 02 Integration | 883893829 | 02 Lead Time Comments | 883893958 | 02 Lead Time | 883896298 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896391
4244927 | 883893500 | 03 Integration Confirmed By NRO Technical Leader | 883894319 | 03 Lead Time Comments | 883894407 | 03 Lead Time | 883896631 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896672
4244927 | 883893500 | 04 SSV | 883894004 | 04 Lead Time Comments | 883894159 | 04 Lead Time | 883896423 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896445
4244927 | 883893500 | 04 SSV | 883894004 | 04 Lead Time Comments | 883894159 | 04 Lead Time | 883896423 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896458
4244927 | 883893500 | 05 SSV Confirmed By NDO Technical Leader | 883894442 | 05 Lead Time Comments | 883894551 | 05 Lead Time | 883896718 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896743
4244927 | 883893500 | 06 Tuning | 883894195 | 06 Lead Time Comments | 883894293 | 06 Lead Time | 883896570 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896599
4244927 | 883893500 | 06 Tuning | 883894195 | 06 Lead Time Comments | 883894293 | 06 Lead Time | 883896570 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896636
4244928 | 883893515 | 01 Installation End | 883894632 | 01 Lead Time Comments | 883894808 | 01 Lead Time | 883896955 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883896968
4244928 | 883893515 | 02 Integration | 883893695 | 02 Lead Time Comments | 883893794 | 02 Lead Time | 883896234 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896308
4244928 | 883893515 | 02 Integration | 883893695 | 02 Lead Time Comments | 883893794 | 02 Lead Time | 883896234 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896333
4244928 | 883893515 | 03 Integration Confirmed By NRO Technical Leader | 883894191 | 03 Lead Time Comments | 883894296 | 03 Lead Time | 883896571 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896601
4244928 | 883893515 | 04 SSV | 883893825 | 04 Lead Time Comments | 883893973 | 04 Lead Time | 883896289 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896372
4244928 | 883893515 | 04 SSV | 883893825 | 04 Lead Time Comments | 883893973 | 04 Lead Time | 883896289 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896395
4244928 | 883893515 | 05 SSV Confirmed By NDO Technical Leader | 883894334 | 05 Lead Time Comments | 883894394 | 05 Lead Time | 883896640 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896663
4244928 | 883893515 | 06 Tuning | 883894008 | 06 Lead Time Comments | 883894121 | 06 Lead Time | 883896420 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896487
4244928 | 883893515 | 06 Tuning | 883894008 | 06 Lead Time Comments | 883894121 | 06 Lead Time | 883896420 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896543
4244929 | 883893518 | 01 Installation End | 883894879 | 01 Lead Time Comments | 883895063 | 01 Lead Time | 883897026 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897070
4244929 | 883893518 | 02 Integration | 883893881 | 02 Lead Time Comments | 883894016 | 02 Lead Time | 883896345 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896408
4244929 | 883893518 | 02 Integration | 883893881 | 02 Lead Time Comments | 883894016 | 02 Lead Time | 883896345 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896430
4244929 | 883893518 | 03 Integration Confirmed By NRO Technical Leader | 883894435 | 03 Lead Time Comments | 883894539 | 03 Lead Time | 883896721 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896732
4244929 | 883893518 | 04 SSV | 883894091 | 04 Lead Time Comments | 883894218 | 04 Lead Time | 883896508 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896520
4244929 | 883893518 | 04 SSV | 883894091 | 04 Lead Time Comments | 883894218 | 04 Lead Time | 883896508 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896537
4244929 | 883893518 | 05 SSV Confirmed By NDO Technical Leader | 883894617 | 05 Lead Time Comments | 883894709 | 05 Lead Time | 883896815 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896828
4244929 | 883893518 | 06 Tuning | 883894278 | 06 Lead Time Comments | 883894411 | 06 Lead Time | 883896622 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896680
4244929 | 883893518 | 06 Tuning | 883894278 | 06 Lead Time Comments | 883894411 | 06 Lead Time | 883896622 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896740
4244930 | 883893528 | 01 Installation End | 883894826 | 01 Lead Time Comments | 883894935 | 01 Lead Time | 883897025 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897061
4244930 | 883893528 | 02 Integration | 883893742 | 02 Lead Time Comments | 883893851 | 02 Lead Time | 883896241 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896272
4244930 | 883893528 | 02 Integration | 883893742 | 02 Lead Time Comments | 883893851 | 02 Lead Time | 883896241 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896304
4244930 | 883893528 | 03 Integration Confirmed By NRO Technical Leader | 883894287 | 03 Lead Time Comments | 883894405 | 03 Lead Time | 883896697 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896739
4244930 | 883893528 | 04 SSV | 883893927 | 04 Lead Time Comments | 883894041 | 04 Lead Time | 883896350 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896405
4244930 | 883893528 | 04 SSV | 883893927 | 04 Lead Time Comments | 883894041 | 04 Lead Time | 883896350 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896444
4244930 | 883893528 | 05 SSV Confirmed By NDO Technical Leader | 883894471 | 05 Lead Time Comments | 883894582 | 05 Lead Time | 883896805 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896855
4244930 | 883893528 | 06 Tuning | 883894082 | 06 Lead Time Comments | 883894257 | 06 Lead Time | 883896498 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896539
4244930 | 883893528 | 06 Tuning | 883894082 | 06 Lead Time Comments | 883894257 | 06 Lead Time | 883896498 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896582
4244931 | 883893510 | 01 Installation End | 883894955 | 01 Lead Time Comments | 883895138 | 01 Lead Time | 883897032 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897051
4244931 | 883893510 | 02 Integration | 883893915 | 02 Lead Time Comments | 883894108 | 02 Lead Time | 883896426 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896462
4244931 | 883893510 | 02 Integration | 883893915 | 02 Lead Time Comments | 883894108 | 02 Lead Time | 883896426 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896513
4244931 | 883893510 | 03 Integration Confirmed By NRO Technical Leader | 883894481 | 03 Lead Time Comments | 883894603 | 03 Lead Time | 883896803 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896830
4244931 | 883893510 | 04 SSV | 883894167 | 04 Lead Time Comments | 883894284 | 04 Lead Time | 883896558 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896595
4244931 | 883893510 | 04 SSV | 883894167 | 04 Lead Time Comments | 883894284 | 04 Lead Time | 883896558 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896617
4244931 | 883893510 | 05 SSV Confirmed By NDO Technical Leader | 883894669 | 05 Lead Time Comments | 883894787 | 05 Lead Time | 883896878 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896900
4244931 | 883893510 | 06 Tuning | 883894308 | 06 Lead Time Comments | 883894415 | 06 Lead Time | 883896707 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896768
4244931 | 883893510 | 06 Tuning | 883894308 | 06 Lead Time Comments | 883894415 | 06 Lead Time | 883896707 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896787
4244932 | 883893511 | 01 Installation End | 883894989 | 01 Lead Time Comments | 883895169 | 01 Lead Time | 883897083 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897138
4244932 | 883893511 | 02 Integration | 883893793 | 02 Lead Time Comments | 883893997 | 02 Lead Time | 883896355 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896463
4244932 | 883893511 | 02 Integration | 883893793 | 02 Lead Time Comments | 883893997 | 02 Lead Time | 883896355 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896486
4244932 | 883893511 | 03 Integration Confirmed By NRO Technical Leader | 883894478 | 03 Lead Time Comments | 883894613 | 03 Lead Time | 883896806 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896835
4244932 | 883893511 | 04 SSV | 883894069 | 04 Lead Time Comments | 883894216 | 04 Lead Time | 883896491 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896549
4244932 | 883893511 | 04 SSV | 883894069 | 04 Lead Time Comments | 883894216 | 04 Lead Time | 883896491 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896597
4244932 | 883893511 | 05 SSV Confirmed By NDO Technical Leader | 883894672 | 05 Lead Time Comments | 883894770 | 05 Lead Time | 883896896 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896966
4244932 | 883893511 | 06 Tuning | 883894279 | 06 Lead Time Comments | 883894419 | 06 Lead Time | 883896634 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896657
4244932 | 883893511 | 06 Tuning | 883894279 | 06 Lead Time Comments | 883894419 | 06 Lead Time | 883896634 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896675
4244933 | 883893508 | 01 Installation End | 883894823 | 01 Lead Time Comments | 883894950 | 01 Lead Time | 883897034 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897054
4244933 | 883893508 | 02 Integration | 883893869 | 02 Lead Time Comments | 883893999 | 02 Lead Time | 883896292 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896369
4244933 | 883893508 | 02 Integration | 883893869 | 02 Lead Time Comments | 883893999 | 02 Lead Time | 883896292 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896388
4244933 | 883893508 | 03 Integration Confirmed By NRO Technical Leader | 883894362 | 03 Lead Time Comments | 883894482 | 03 Lead Time | 883896708 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896767
4244933 | 883893508 | 04 SSV | 883894047 | 04 Lead Time Comments | 883894155 | 04 Lead Time | 883896424 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896479
4244933 | 883893508 | 04 SSV | 883894047 | 04 Lead Time Comments | 883894155 | 04 Lead Time | 883896424 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896551
4244933 | 883893508 | 05 SSV Confirmed By NDO Technical Leader | 883894528 | 05 Lead Time Comments | 883894667 | 05 Lead Time | 883896799 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896859
4244933 | 883893508 | 06 Tuning | 883894213 | 06 Lead Time Comments | 883894315 | 06 Lead Time | 883896565 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896614
4244933 | 883893508 | 06 Tuning | 883894213 | 06 Lead Time Comments | 883894315 | 06 Lead Time | 883896565 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896646
4244934 | 883893512 | 01 Installation End | 883894769 | 01 Lead Time Comments | 883894929 | 01 Lead Time | 883897010 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897062
4244934 | 883893512 | 02 Integration | 883893760 | 02 Lead Time Comments | 883893885 | 02 Lead Time | 883896233 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896268
4244934 | 883893512 | 02 Integration | 883893760 | 02 Lead Time Comments | 883893885 | 02 Lead Time | 883896233 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896318
4244934 | 883893512 | 03 Integration Confirmed By NRO Technical Leader | 883894305 | 03 Lead Time Comments | 883894393 | 03 Lead Time | 883896630 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896649
4244934 | 883893512 | 04 SSV | 883893954 | 04 Lead Time Comments | 883894053 | 04 Lead Time | 883896348 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896385
4244934 | 883893512 | 04 SSV | 883893954 | 04 Lead Time Comments | 883894053 | 04 Lead Time | 883896348 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896447
4244934 | 883893512 | 05 SSV Confirmed By NDO Technical Leader | 883894455 | 05 Lead Time Comments | 883894555 | 05 Lead Time | 883896722 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896769
4244934 | 883893512 | 06 Tuning | 883894139 | 06 Lead Time Comments | 883894231 | 06 Lead Time | 883896573 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896592
4244934 | 883893512 | 06 Tuning | 883894139 | 06 Lead Time Comments | 883894231 | 06 Lead Time | 883896573 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896651
4244935 | 883893541 | 01 Installation End | 883894918 | 01 Lead Time Comments | 883895033 | 01 Lead Time | 883897016 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897043
4244935 | 883893541 | 02 Integration | 883893906 | 02 Lead Time Comments | 883894062 | 02 Lead Time | 883896357 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896409
4244935 | 883893541 | 02 Integration | 883893906 | 02 Lead Time Comments | 883894062 | 02 Lead Time | 883896357 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896470
4244935 | 883893541 | 03 Integration Confirmed By NRO Technical Leader | 883894484 | 03 Lead Time Comments | 883894564 | 03 Lead Time | 883896720 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896733
4244935 | 883893541 | 04 SSV | 883894142 | 04 Lead Time Comments | 883894292 | 04 Lead Time | 883896564 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896628
4244935 | 883893541 | 04 SSV | 883894142 | 04 Lead Time Comments | 883894292 | 04 Lead Time | 883896564 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896679
4244935 | 883893541 | 05 SSV Confirmed By NDO Technical Leader | 883894621 | 05 Lead Time Comments | 883894754 | 05 Lead Time | 883896881 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896918
4244935 | 883893541 | 06 Tuning | 883894321 | 06 Lead Time Comments | 883894430 | 06 Lead Time | 883896725 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896731
4244935 | 883893541 | 06 Tuning | 883894321 | 06 Lead Time Comments | 883894430 | 06 Lead Time | 883896725 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896750
4244936 | 883893539 | 01 Installation End | 883895010 | 01 Lead Time Comments | 883895203 | 01 Lead Time | 883897084 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897144
4244936 | 883893539 | 02 Integration | 883893917 | 02 Lead Time Comments | 883894051 | 02 Lead Time | 883896343 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896389
4244936 | 883893539 | 02 Integration | 883893917 | 02 Lead Time Comments | 883894051 | 02 Lead Time | 883896343 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896410
4244936 | 883893539 | 03 Integration Confirmed By NRO Technical Leader | 883894452 | 03 Lead Time Comments | 883894573 | 03 Lead Time | 883896807 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896854
4244936 | 883893539 | 04 SSV | 883894087 | 04 Lead Time Comments | 883894255 | 04 Lead Time | 883896503 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896522
4244936 | 883893539 | 04 SSV | 883894087 | 04 Lead Time Comments | 883894255 | 04 Lead Time | 883896503 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896544
4244936 | 883893539 | 05 SSV Confirmed By NDO Technical Leader | 883894650 | 05 Lead Time Comments | 883894746 | 05 Lead Time | 883896866 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896909
4244936 | 883893539 | 06 Tuning | 883894286 | 06 Lead Time Comments | 883894428 | 06 Lead Time | 883896627 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896674
4244936 | 883893539 | 06 Tuning | 883894286 | 06 Lead Time Comments | 883894428 | 06 Lead Time | 883896627 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896688
4244937 | 883893565 | 01 Installation End | 883894995 | 01 Lead Time Comments | 883895112 | 01 Lead Time | 883897023 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897058
4244937 | 883893565 | 02 Integration | 883893899 | 02 Lead Time Comments | 883894027 | 02 Lead Time | 883896354 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896393
4244937 | 883893565 | 02 Integration | 883893899 | 02 Lead Time Comments | 883894027 | 02 Lead Time | 883896354 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896446
4244937 | 883893565 | 03 Integration Confirmed By NRO Technical Leader | 883894510 | 03 Lead Time Comments | 883894562 | 03 Lead Time | 883896711 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896786
4244937 | 883893565 | 04 SSV | 883894078 | 04 Lead Time Comments | 883894236 | 04 Lead Time | 883896499 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896517
4244937 | 883893565 | 04 SSV | 883894078 | 04 Lead Time Comments | 883894236 | 04 Lead Time | 883896499 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896531
4244937 | 883893565 | 05 SSV Confirmed By NDO Technical Leader | 883894597 | 05 Lead Time Comments | 883894732 | 05 Lead Time | 883896874 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896926
4244937 | 883893565 | 06 Tuning | 883894299 | 06 Lead Time Comments | 883894421 | 06 Lead Time | 883896693 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896757
4244937 | 883893565 | 06 Tuning | 883894299 | 06 Lead Time Comments | 883894421 | 06 Lead Time | 883896693 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896788
4244938 | 883893562 | 01 Installation End | 883894920 | 01 Lead Time Comments | 883895042 | 01 Lead Time | 883897033 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897129
4244938 | 883893562 | 02 Integration | 883893952 | 02 Lead Time Comments | 883894054 | 02 Lead Time | 883896351 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896448
4244938 | 883893562 | 02 Integration | 883893952 | 02 Lead Time Comments | 883894054 | 02 Lead Time | 883896351 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896472
4244938 | 883893562 | 03 Integration Confirmed By NRO Technical Leader | 883894491 | 03 Lead Time Comments | 883894590 | 03 Lead Time | 883896793 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896840
4244938 | 883893562 | 04 SSV | 883894103 | 04 Lead Time Comments | 883894245 | 04 Lead Time | 883896507 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896577
4244938 | 883893562 | 04 SSV | 883894103 | 04 Lead Time Comments | 883894245 | 04 Lead Time | 883896507 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896608
4244938 | 883893562 | 05 SSV Confirmed By NDO Technical Leader | 883894629 | 05 Lead Time Comments | 883894751 | 05 Lead Time | 883896864 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896902
4244938 | 883893562 | 06 Tuning | 883894312 | 06 Lead Time Comments | 883894383 | 06 Lead Time | 883896709 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896774
4244938 | 883893562 | 06 Tuning | 883894312 | 06 Lead Time Comments | 883894383 | 06 Lead Time | 883896709 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896822
4244939 | 883893561 | 01 Installation End | 883894912 | 01 Lead Time Comments | 883895024 | 01 Lead Time | 883897008 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897109
4244939 | 883893561 | 02 Integration | 883893931 | 02 Lead Time Comments | 883894028 | 02 Lead Time | 883896300 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896392
4244939 | 883893561 | 02 Integration | 883893931 | 02 Lead Time Comments | 883894028 | 02 Lead Time | 883896300 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896412
4244939 | 883893561 | 03 Integration Confirmed By NRO Technical Leader | 883894449 | 03 Lead Time Comments | 883894580 | 03 Lead Time | 883896790 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896842
4244939 | 883893561 | 04 SSV | 883894058 | 04 Lead Time Comments | 883894196 | 04 Lead Time | 883896502 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896580
4244939 | 883893561 | 04 SSV | 883894058 | 04 Lead Time Comments | 883894196 | 04 Lead Time | 883896502 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896612
4244939 | 883893561 | 05 SSV Confirmed By NDO Technical Leader | 883894630 | 05 Lead Time Comments | 883894747 | 05 Lead Time | 883896869 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896913
4244939 | 883893561 | 06 Tuning | 883894270 | 06 Lead Time Comments | 883894396 | 06 Lead Time | 883896625 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896648
4244939 | 883893561 | 06 Tuning | 883894270 | 06 Lead Time Comments | 883894396 | 06 Lead Time | 883896625 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896670
4244940 | 883893574 | 01 Installation End | 883894974 | 01 Lead Time Comments | 883895122 | 01 Lead Time | 883897029 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897050
4244940 | 883893574 | 02 Integration | 883893930 | 02 Lead Time Comments | 883894081 | 02 Lead Time | 883896353 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896436
4244940 | 883893574 | 02 Integration | 883893930 | 02 Lead Time Comments | 883894081 | 02 Lead Time | 883896353 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896506
4244940 | 883893574 | 03 Integration Confirmed By NRO Technical Leader | 883894534 | 03 Lead Time Comments | 883894592 | 03 Lead Time | 883896791 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896846
4244940 | 883893574 | 04 SSV | 883894122 | 04 Lead Time Comments | 883894237 | 04 Lead Time | 883896509 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896576
4244940 | 883893574 | 04 SSV | 883894122 | 04 Lead Time Comments | 883894237 | 04 Lead Time | 883896509 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896605
4244940 | 883893574 | 05 SSV Confirmed By NDO Technical Leader | 883894635 | 05 Lead Time Comments | 883894766 | 05 Lead Time | 883896885 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896921
4244940 | 883893574 | 06 Tuning | 883894309 | 06 Lead Time Comments | 883894458 | 06 Lead Time | 883896701 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896753
4244940 | 883893574 | 06 Tuning | 883894309 | 06 Lead Time Comments | 883894458 | 06 Lead Time | 883896701 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896771
4244941 | 883893576 | 01 Installation End | 883894993 | 01 Lead Time Comments | 883895087 | 01 Lead Time | 883897031 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897059
4244941 | 883893576 | 02 Integration | 883893941 | 02 Lead Time Comments | 883894110 | 02 Lead Time | 883896362 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896396
4244941 | 883893576 | 02 Integration | 883893941 | 02 Lead Time Comments | 883894110 | 02 Lead Time | 883896362 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896417
4244941 | 883893576 | 03 Integration Confirmed By NRO Technical Leader | 883894464 | 03 Lead Time Comments | 883894543 | 03 Lead Time | 883896705 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896749
4244941 | 883893576 | 04 SSV | 883894144 | 04 Lead Time Comments | 883894259 | 04 Lead Time | 883896497 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896554
4244941 | 883893576 | 04 SSV | 883894144 | 04 Lead Time Comments | 883894259 | 04 Lead Time | 883896497 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896593
4244941 | 883893576 | 05 SSV Confirmed By NDO Technical Leader | 883894628 | 05 Lead Time Comments | 883894772 | 05 Lead Time | 883896880 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896911
4244941 | 883893576 | 06 Tuning | 883894291 | 06 Lead Time Comments | 883894395 | 06 Lead Time | 883896626 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896654
4244941 | 883893576 | 06 Tuning | 883894291 | 06 Lead Time Comments | 883894395 | 06 Lead Time | 883896626 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896669
4244942 | 883893577 | 01 Installation End | 883895106 | 01 Lead Time Comments | 883895283 | 01 Lead Time | 883897085 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897117
4244942 | 883893577 | 02 Integration | 883893938 | 02 Lead Time Comments | 883894105 | 02 Lead Time | 883896366 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896406
4244942 | 883893577 | 02 Integration | 883893938 | 02 Lead Time Comments | 883894105 | 02 Lead Time | 883896366 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896443
4244942 | 883893577 | 03 Integration Confirmed By NRO Technical Leader | 883894576 | 03 Lead Time Comments | 883894700 | 03 Lead Time | 883896814 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896837
4244942 | 883893577 | 04 SSV | 883894134 | 04 Lead Time Comments | 883894262 | 04 Lead Time | 883896560 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896588
4244942 | 883893577 | 04 SSV | 883894134 | 04 Lead Time Comments | 883894262 | 04 Lead Time | 883896560 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896615
4244942 | 883893577 | 05 SSV Confirmed By NDO Technical Leader | 883894758 | 05 Lead Time Comments | 883894884 | 05 Lead Time | 883896935 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897001
4244942 | 883893577 | 06 Tuning | 883894326 | 06 Lead Time Comments | 883894494 | 06 Lead Time | 883896716 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896759
4244942 | 883893577 | 06 Tuning | 883894326 | 06 Lead Time Comments | 883894494 | 06 Lead Time | 883896716 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896777
4244943 | 883893578 | 01 Installation End | 883894997 | 01 Lead Time Comments | 883895201 | 01 Lead Time | 883897081 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897130
4244943 | 883893578 | 02 Integration | 883893918 | 02 Lead Time Comments | 883894100 | 02 Lead Time | 883896359 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896407
4244943 | 883893578 | 02 Integration | 883893918 | 02 Lead Time Comments | 883894100 | 02 Lead Time | 883896359 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896460
4244943 | 883893578 | 03 Integration Confirmed By NRO Technical Leader | 883894461 | 03 Lead Time Comments | 883894559 | 03 Lead Time | 883896801 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896847
4244943 | 883893578 | 04 SSV | 883894133 | 04 Lead Time Comments | 883894264 | 04 Lead Time | 883896574 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896589
4244943 | 883893578 | 04 SSV | 883894133 | 04 Lead Time Comments | 883894264 | 04 Lead Time | 883896574 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896609
4244943 | 883893578 | 05 SSV Confirmed By NDO Technical Leader | 883894662 | 05 Lead Time Comments | 883894785 | 05 Lead Time | 883896873 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896905
4244943 | 883893578 | 06 Tuning | 883894307 | 06 Lead Time Comments | 883894400 | 06 Lead Time | 883896643 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896671
4244943 | 883893578 | 06 Tuning | 883894307 | 06 Lead Time Comments | 883894400 | 06 Lead Time | 883896643 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896684
4244944 | 883893567 | 01 Installation End | 883894996 | 01 Lead Time Comments | 883895193 | 01 Lead Time | 883897089 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897128
4244944 | 883893567 | 02 Integration | 883893925 | 02 Lead Time Comments | 883894068 | 02 Lead Time | 883896352 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896439
4244944 | 883893567 | 02 Integration | 883893925 | 02 Lead Time Comments | 883894068 | 02 Lead Time | 883896352 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896449
4244944 | 883893567 | 03 Integration Confirmed By NRO Technical Leader | 883894547 | 03 Lead Time Comments | 883894631 | 03 Lead Time | 883896800 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896848
4244944 | 883893567 | 04 SSV | 883894153 | 04 Lead Time Comments | 883894320 | 04 Lead Time | 883896567 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896606
4244944 | 883893567 | 04 SSV | 883894153 | 04 Lead Time Comments | 883894320 | 04 Lead Time | 883896567 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896650
4244944 | 883893567 | 05 SSV Confirmed By NDO Technical Leader | 883894706 | 05 Lead Time Comments | 883894800 | 05 Lead Time | 883896883 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896919
4244944 | 883893567 | 06 Tuning | 883894350 | 06 Lead Time Comments | 883894492 | 06 Lead Time | 883896727 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896784
4244944 | 883893567 | 06 Tuning | 883894350 | 06 Lead Time Comments | 883894492 | 06 Lead Time | 883896727 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896829
4244945 | 883893779 | 01 Installation End | 883895002 | 01 Lead Time Comments | 883895188 | 01 Lead Time | 883897091 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897147
4244945 | 883893779 | 02 Integration | 883893990 | 02 Lead Time Comments | 883894115 | 02 Lead Time | 883896365 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896397
4244945 | 883893779 | 02 Integration | 883893990 | 02 Lead Time Comments | 883894115 | 02 Lead Time | 883896365 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896435
4244945 | 883893779 | 03 Integration Confirmed By NRO Technical Leader | 883894571 | 03 Lead Time Comments | 883894688 | 03 Lead Time | 883896818 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896839
4244945 | 883893779 | 04 SSV | 883894168 | 04 Lead Time Comments | 883894352 | 04 Lead Time | 883896621 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896662
4244945 | 883893779 | 04 SSV | 883894168 | 04 Lead Time Comments | 883894352 | 04 Lead Time | 883896621 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896690
4244945 | 883893779 | 05 SSV Confirmed By NDO Technical Leader | 883894716 | 05 Lead Time Comments | 883894812 | 05 Lead Time | 883896870 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896957
4244945 | 883893779 | 06 Tuning | 883894414 | 06 Lead Time Comments | 883894523 | 06 Lead Time | 883896710 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896780
4244945 | 883893779 | 06 Tuning | 883894414 | 06 Lead Time Comments | 883894523 | 06 Lead Time | 883896710 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896849
4244946 | 883893776 | 01 Installation End | 883895013 | 01 Lead Time Comments | 883895186 | 01 Lead Time | 883897080 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897136
4244946 | 883893776 | 02 Integration | 883894006 | 02 Lead Time Comments | 883894151 | 02 Lead Time | 883896367 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896399
4244946 | 883893776 | 02 Integration | 883894006 | 02 Lead Time Comments | 883894151 | 02 Lead Time | 883896367 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896431
4244946 | 883893776 | 03 Integration Confirmed By NRO Technical Leader | 883894520 | 03 Lead Time Comments | 883894602 | 03 Lead Time | 883896796 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896856
4244946 | 883893776 | 04 SSV | 883894165 | 04 Lead Time Comments | 883894303 | 04 Lead Time | 883896563 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896641
4244946 | 883893776 | 04 SSV | 883894165 | 04 Lead Time Comments | 883894303 | 04 Lead Time | 883896563 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896678
4244946 | 883893776 | 05 SSV Confirmed By NDO Technical Leader | 883894638 | 05 Lead Time Comments | 883894757 | 05 Lead Time | 883896865 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896925
4244946 | 883893776 | 06 Tuning | 883894342 | 06 Lead Time Comments | 883894447 | 06 Lead Time | 883896696 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896773
4244946 | 883893776 | 06 Tuning | 883894342 | 06 Lead Time Comments | 883894447 | 06 Lead Time | 883896696 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896823
4244947 | 883893807 | 01 Installation End | 883895084 | 01 Lead Time Comments | 883895244 | 01 Lead Time | 883897088 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897143
4244947 | 883893807 | 02 Integration | 883894026 | 02 Lead Time Comments | 883894185 | 02 Lead Time | 883896441 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896467
4244947 | 883893807 | 02 Integration | 883894026 | 02 Lead Time Comments | 883894185 | 02 Lead Time | 883896441 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896516
4244947 | 883893807 | 03 Integration Confirmed By NRO Technical Leader | 883894574 | 03 Lead Time Comments | 883894691 | 03 Lead Time | 883896816 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896889
4244947 | 883893807 | 04 SSV | 883894212 | 04 Lead Time Comments | 883894346 | 04 Lead Time | 883896575 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896587
4244947 | 883893807 | 04 SSV | 883894212 | 04 Lead Time Comments | 883894346 | 04 Lead Time | 883896575 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896616
4244947 | 883893807 | 05 SSV Confirmed By NDO Technical Leader | 883894745 | 05 Lead Time Comments | 883894850 | 05 Lead Time | 883896937 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896973
4244947 | 883893807 | 06 Tuning | 883894375 | 06 Lead Time Comments | 883894527 | 06 Lead Time | 883896704 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896741
4244947 | 883893807 | 06 Tuning | 883894375 | 06 Lead Time Comments | 883894527 | 06 Lead Time | 883896704 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896776
4244948 | 883893822 | 01 Installation End | 883895077 | 01 Lead Time Comments | 883895235 | 01 Lead Time | 883897087 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897113
4244948 | 883893822 | 02 Integration | 883894104 | 02 Lead Time Comments | 883894238 | 02 Lead Time | 883896504 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896535
4244948 | 883893822 | 02 Integration | 883894104 | 02 Lead Time Comments | 883894238 | 02 Lead Time | 883896504 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896553
4244948 | 883893822 | 03 Integration Confirmed By NRO Technical Leader | 883894611 | 03 Lead Time Comments | 883894727 | 03 Lead Time | 883896871 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896923
4244948 | 883893822 | 04 SSV | 883894283 | 04 Lead Time Comments | 883894403 | 04 Lead Time | 883896635 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896659
4244948 | 883893822 | 04 SSV | 883894283 | 04 Lead Time Comments | 883894403 | 04 Lead Time | 883896635 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896681
4244948 | 883893822 | 05 SSV Confirmed By NDO Technical Leader | 883894795 | 05 Lead Time Comments | 883894922 | 05 Lead Time | 883896939 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896996
4244948 | 883893822 | 06 Tuning | 883894450 | 06 Lead Time Comments | 883894561 | 06 Lead Time | 883896795 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896826
4244948 | 883893822 | 06 Tuning | 883894450 | 06 Lead Time Comments | 883894561 | 06 Lead Time | 883896795 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896922
4244949 | 883893848 | 01 Installation End | 883895026 | 01 Lead Time Comments | 883895173 | 01 Lead Time | 883897086 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897140
4244949 | 883893848 | 02 Integration | 883894038 | 02 Lead Time Comments | 883894173 | 02 Lead Time | 883896505 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896532
4244949 | 883893848 | 02 Integration | 883894038 | 02 Lead Time Comments | 883894173 | 02 Lead Time | 883896505 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896547
4244949 | 883893848 | 03 Integration Confirmed By NRO Technical Leader | 883894643 | 03 Lead Time Comments | 883894736 | 03 Lead Time | 883896886 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896904
4244949 | 883893848 | 04 SSV | 883894230 | 04 Lead Time Comments | 883894384 | 04 Lead Time | 883896639 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896660
4244949 | 883893848 | 04 SSV | 883894230 | 04 Lead Time Comments | 883894384 | 04 Lead Time | 883896639 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896676
4244949 | 883893848 | 05 SSV Confirmed By NDO Technical Leader | 883894764 | 05 Lead Time Comments | 883894900 | 05 Lead Time | 883896949 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896991
4244949 | 883893848 | 06 Tuning | 883894454 | 06 Lead Time Comments | 883894604 | 06 Lead Time | 883896794 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896843
4244949 | 883893848 | 06 Tuning | 883894454 | 06 Lead Time Comments | 883894604 | 06 Lead Time | 883896794 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896890
4244950 | 883893875 | 01 Installation End | 883895089 | 01 Lead Time Comments | 883895254 | 01 Lead Time | 883897105 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897121
4244950 | 883893875 | 02 Integration | 883894120 | 02 Lead Time Comments | 883894258 | 02 Lead Time | 883896501 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896529
4244950 | 883893875 | 02 Integration | 883894120 | 02 Lead Time Comments | 883894258 | 02 Lead Time | 883896501 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896545
4244950 | 883893875 | 03 Integration Confirmed By NRO Technical Leader | 883894625 | 03 Lead Time Comments | 883894730 | 03 Lead Time | 883896817 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896845
4244950 | 883893875 | 04 SSV | 883894281 | 04 Lead Time Comments | 883894422 | 04 Lead Time | 883896692 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896736
4244950 | 883893875 | 04 SSV | 883894281 | 04 Lead Time Comments | 883894422 | 04 Lead Time | 883896692 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896754
4244950 | 883893875 | 05 SSV Confirmed By NDO Technical Leader | 883894748 | 05 Lead Time Comments | 883894869 | 05 Lead Time | 883896942 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883896989
4244950 | 883893875 | 06 Tuning | 883894490 | 06 Lead Time Comments | 883894569 | 06 Lead Time | 883896719 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896745
4244950 | 883893875 | 06 Tuning | 883894490 | 06 Lead Time Comments | 883894569 | 06 Lead Time | 883896719 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896770
4244951 | 883893876 | 01 Installation End | 883895277 | 01 Lead Time Comments | 883895455 | 01 Lead Time | 883897149 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897208
4244951 | 883893876 | 02 Integration | 883894161 | 02 Lead Time Comments | 883894247 | 02 Lead Time | 883896569 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896603
4244951 | 883893876 | 02 Integration | 883894161 | 02 Lead Time Comments | 883894247 | 02 Lead Time | 883896569 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896645
4244951 | 883893876 | 03 Integration Confirmed By NRO Technical Leader | 883894714 | 03 Lead Time Comments | 883894813 | 03 Lead Time | 883896872 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883896927
4244951 | 883893876 | 04 SSV | 883894330 | 04 Lead Time Comments | 883894445 | 04 Lead Time | 883896695 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896751
4244951 | 883893876 | 04 SSV | 883894330 | 04 Lead Time Comments | 883894445 | 04 Lead Time | 883896695 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896825
4244951 | 883893876 | 05 SSV Confirmed By NDO Technical Leader | 883894855 | 05 Lead Time Comments | 883895037 | 05 Lead Time | 883897028 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897060
4244951 | 883893876 | 06 Tuning | 883894505 | 06 Lead Time Comments | 883894649 | 06 Lead Time | 883896808 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896857
4244951 | 883893876 | 06 Tuning | 883894505 | 06 Lead Time Comments | 883894649 | 06 Lead Time | 883896808 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896903
4244952 | 883894063 | 01 Installation End | 883895355 | 01 Lead Time Comments | 883895497 | 01 Lead Time | 883897162 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897217
4244952 | 883894063 | 02 Integration | 883894271 | 02 Lead Time Comments | 883894423 | 02 Lead Time | 883896691 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896762
4244952 | 883894063 | 02 Integration | 883894271 | 02 Lead Time Comments | 883894423 | 02 Lead Time | 883896691 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896782
4244952 | 883894063 | 03 Integration Confirmed By NRO Technical Leader | 883894888 | 03 Lead Time Comments | 883894958 | 03 Lead Time | 883897011 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897073
4244952 | 883894063 | 04 SSV | 883894496 | 04 Lead Time Comments | 883894686 | 04 Lead Time | 883896820 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896852
4244952 | 883894063 | 04 SSV | 883894496 | 04 Lead Time Comments | 883894686 | 04 Lead Time | 883896820 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896892
4244952 | 883894063 | 05 SSV Confirmed By NDO Technical Leader | 883895027 | 05 Lead Time Comments | 883895176 | 05 Lead Time | 883897097 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897141
4244952 | 883894063 | 06 Tuning | 883894713 | 06 Lead Time Comments | 883894854 | 06 Lead Time | 883896931 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896961
4244952 | 883894063 | 06 Tuning | 883894713 | 06 Lead Time Comments | 883894854 | 06 Lead Time | 883896931 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883896980
4244953 | 883894072 | 01 Installation End | 883895523 | 01 Lead Time Comments | 883895654 | 01 Lead Time | 883897161 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897186
4244953 | 883894072 | 02 Integration | 883894347 | 02 Lead Time Comments | 883894530 | 02 Lead Time | 883896723 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896730
4244953 | 883894072 | 02 Integration | 883894347 | 02 Lead Time Comments | 883894530 | 02 Lead Time | 883896723 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896764
4244953 | 883894072 | 03 Integration Confirmed By NRO Technical Leader | 883894949 | 03 Lead Time Comments | 883895096 | 03 Lead Time | 883897022 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897055
4244953 | 883894072 | 04 SSV | 883894577 | 04 Lead Time Comments | 883894741 | 04 Lead Time | 883896863 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896907
4244953 | 883894072 | 04 SSV | 883894577 | 04 Lead Time Comments | 883894741 | 04 Lead Time | 883896863 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896974
4244953 | 883894072 | 05 SSV Confirmed By NDO Technical Leader | 883895151 | 05 Lead Time Comments | 883895294 | 05 Lead Time | 883897096 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897124
4244953 | 883894072 | 06 Tuning | 883894793 | 06 Lead Time Comments | 883894941 | 06 Lead Time | 883896951 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896982
4244953 | 883894072 | 06 Tuning | 883894793 | 06 Lead Time Comments | 883894941 | 06 Lead Time | 883896951 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897067
4244954 | 883894124 | 01 Installation End | 883895614 | 01 Lead Time Comments | 883895770 | 01 Lead Time | 883897194 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897232
4244954 | 883894124 | 02 Integration | 883894336 | 02 Lead Time Comments | 883894583 | 02 Lead Time | 883896792 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896850
4244954 | 883894124 | 02 Integration | 883894336 | 02 Lead Time Comments | 883894583 | 02 Lead Time | 883896792 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896899
4244954 | 883894124 | 03 Integration Confirmed By NRO Technical Leader | 883895094 | 03 Lead Time Comments | 883895255 | 03 Lead Time | 883897092 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897120
4244954 | 883894124 | 04 SSV | 883894666 | 04 Lead Time Comments | 883894847 | 04 Lead Time | 883896930 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897000
4244954 | 883894124 | 04 SSV | 883894666 | 04 Lead Time Comments | 883894847 | 04 Lead Time | 883896930 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897042
4244954 | 883894124 | 05 SSV Confirmed By NDO Technical Leader | 883895297 | 05 Lead Time Comments | 883895439 | 05 Lead Time | 883897148 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897204
4244954 | 883894124 | 06 Tuning | 883894871 | 06 Lead Time Comments | 883895009 | 06 Lead Time | 883897027 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897041
4244954 | 883894124 | 06 Tuning | 883894871 | 06 Lead Time Comments | 883895009 | 06 Lead Time | 883897027 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897064
4244955 | 883894140 | 01 Installation End | 883895507 | 01 Lead Time Comments | 883895637 | 01 Lead Time | 883897167 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897195
4244955 | 883894140 | 02 Integration | 883894413 | 02 Lead Time Comments | 883894540 | 02 Lead Time | 883896700 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896760
4244955 | 883894140 | 02 Integration | 883894413 | 02 Lead Time Comments | 883894540 | 02 Lead Time | 883896700 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896772
4244955 | 883894140 | 03 Integration Confirmed By NRO Technical Leader | 883894938 | 03 Lead Time Comments | 883895046 | 03 Lead Time | 883897015 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897065
4244955 | 883894140 | 04 SSV | 883894570 | 04 Lead Time Comments | 883894698 | 04 Lead Time | 883896811 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896844
4244955 | 883894140 | 04 SSV | 883894570 | 04 Lead Time Comments | 883894698 | 04 Lead Time | 883896811 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896861
4244955 | 883894140 | 05 SSV Confirmed By NDO Technical Leader | 883895091 | 05 Lead Time Comments | 883895234 | 05 Lead Time | 883897101 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897115
4244955 | 883894140 | 06 Tuning | 883894723 | 06 Lead Time Comments | 883894880 | 06 Lead Time | 883896950 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896997
4244955 | 883894140 | 06 Tuning | 883894723 | 06 Lead Time Comments | 883894880 | 06 Lead Time | 883896950 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897075
4244956 | 883894141 | 01 Installation End | 883895525 | 01 Lead Time Comments | 883895668 | 01 Lead Time | 883897159 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897211
4244956 | 883894141 | 02 Integration | 883894451 | 02 Lead Time Comments | 883894596 | 02 Lead Time | 883896802 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896831
4244956 | 883894141 | 02 Integration | 883894451 | 02 Lead Time Comments | 883894596 | 02 Lead Time | 883896802 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896898
4244956 | 883894141 | 03 Integration Confirmed By NRO Technical Leader | 883895056 | 03 Lead Time Comments | 883895150 | 03 Lead Time | 883897018 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897044
4244956 | 883894141 | 04 SSV | 883894681 | 04 Lead Time Comments | 883894794 | 04 Lead Time | 883896884 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896924
4244956 | 883894141 | 04 SSV | 883894681 | 04 Lead Time Comments | 883894794 | 04 Lead Time | 883896884 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896972
4244956 | 883894141 | 05 SSV Confirmed By NDO Technical Leader | 883895208 | 05 Lead Time Comments | 883895343 | 05 Lead Time | 883897099 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897137
4244956 | 883894141 | 06 Tuning | 883894846 | 06 Lead Time Comments | 883894986 | 06 Lead Time | 883897014 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897134
4244956 | 883894141 | 06 Tuning | 883894846 | 06 Lead Time Comments | 883894986 | 06 Lead Time | 883897014 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897142
4244957 | 883894147 | 01 Installation End | 883895535 | 01 Lead Time Comments | 883895714 | 01 Lead Time | 883897164 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897199
4244957 | 883894147 | 02 Integration | 883894345 | 02 Lead Time Comments | 883894533 | 02 Lead Time | 883896699 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896747
4244957 | 883894147 | 02 Integration | 883894345 | 02 Lead Time Comments | 883894533 | 02 Lead Time | 883896699 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896783
4244957 | 883894147 | 03 Integration Confirmed By NRO Technical Leader | 883895025 | 03 Lead Time Comments | 883895133 | 03 Lead Time | 883897030 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897110
4244957 | 883894147 | 04 SSV | 883894606 | 04 Lead Time Comments | 883894780 | 04 Lead Time | 883896945 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896981
4244957 | 883894147 | 04 SSV | 883894606 | 04 Lead Time Comments | 883894780 | 04 Lead Time | 883896945 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897039
4244957 | 883894147 | 05 SSV Confirmed By NDO Technical Leader | 883895212 | 05 Lead Time Comments | 883895344 | 05 Lead Time | 883897095 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897139
4244957 | 883894147 | 06 Tuning | 883894861 | 06 Lead Time Comments | 883894964 | 06 Lead Time | 883897009 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897057
4244957 | 883894147 | 06 Tuning | 883894861 | 06 Lead Time Comments | 883894964 | 06 Lead Time | 883897009 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897078
4244958 | 883894127 | 01 Installation End | 883895545 | 01 Lead Time Comments | 883895709 | 01 Lead Time | 883897160 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897169
4244958 | 883894127 | 02 Integration | 883894387 | 02 Lead Time Comments | 883894536 | 02 Lead Time | 883896728 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896752
4244958 | 883894127 | 02 Integration | 883894387 | 02 Lead Time Comments | 883894536 | 02 Lead Time | 883896728 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896778
4244958 | 883894127 | 03 Integration Confirmed By NRO Technical Leader | 883894962 | 03 Lead Time Comments | 883895160 | 03 Lead Time | 883897024 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897108
4244958 | 883894127 | 04 SSV | 883894563 | 04 Lead Time Comments | 883894715 | 04 Lead Time | 883896888 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896916
4244958 | 883894127 | 04 SSV | 883894563 | 04 Lead Time Comments | 883894715 | 04 Lead Time | 883896888 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896970
4244958 | 883894127 | 05 SSV Confirmed By NDO Technical Leader | 883895236 | 05 Lead Time Comments | 883895379 | 05 Lead Time | 883897153 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897234
4244958 | 883894127 | 06 Tuning | 883894799 | 06 Lead Time Comments | 883894942 | 06 Lead Time | 883896959 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883896992
4244958 | 883894127 | 06 Tuning | 883894799 | 06 Lead Time Comments | 883894942 | 06 Lead Time | 883896959 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897040
4244959 | 883894138 | 01 Installation End | 883895724 | 01 Lead Time Comments | 883895864 | 01 Lead Time | 883897172 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897214
4244959 | 883894138 | 02 Integration | 883894434 | 02 Lead Time Comments | 883894556 | 02 Lead Time | 883896717 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896766
4244959 | 883894138 | 02 Integration | 883894434 | 02 Lead Time Comments | 883894556 | 02 Lead Time | 883896717 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896832
4244959 | 883894138 | 03 Integration Confirmed By NRO Technical Leader | 883895031 | 03 Lead Time Comments | 883895198 | 03 Lead Time | 883897090 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897133
4244959 | 883894138 | 04 SSV | 883894612 | 04 Lead Time Comments | 883894788 | 04 Lead Time | 883896875 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896914
4244959 | 883894138 | 04 SSV | 883894612 | 04 Lead Time Comments | 883894788 | 04 Lead Time | 883896875 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896928
4244959 | 883894138 | 05 SSV Confirmed By NDO Technical Leader | 883895324 | 05 Lead Time Comments | 883895491 | 05 Lead Time | 883897152 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897207
4244959 | 883894138 | 06 Tuning | 883894822 | 06 Lead Time Comments | 883895005 | 06 Lead Time | 883897036 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897048
4244959 | 883894138 | 06 Tuning | 883894822 | 06 Lead Time Comments | 883895005 | 06 Lead Time | 883897036 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897118
4244960 | 883894163 | 01 Installation End | 883895729 | 01 Lead Time Comments | 883895954 | 01 Lead Time | 883897175 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897219
4244960 | 883894163 | 02 Integration | 883894441 | 02 Lead Time Comments | 883894600 | 02 Lead Time | 883896809 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896851
4244960 | 883894163 | 02 Integration | 883894441 | 02 Lead Time Comments | 883894600 | 02 Lead Time | 883896809 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896894
4244960 | 883894163 | 03 Integration Confirmed By NRO Technical Leader | 883895144 | 03 Lead Time Comments | 883895323 | 03 Lead Time | 883897106 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897135
4244960 | 883894163 | 04 SSV | 883894695 | 04 Lead Time Comments | 883894862 | 04 Lead Time | 883896941 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896963
4244960 | 883894163 | 04 SSV | 883894695 | 04 Lead Time Comments | 883894862 | 04 Lead Time | 883896941 | actcl--04 SSV--04 Lead Time Comments--Duration | 883896986
4244960 | 883894163 | 05 SSV Confirmed By NDO Technical Leader | 883895405 | 05 Lead Time Comments | 883895515 | 05 Lead Time | 883897151 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897202
4244960 | 883894163 | 06 Tuning | 883894915 | 06 Lead Time Comments | 883895065 | 06 Lead Time | 883897006 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897037
4244960 | 883894163 | 06 Tuning | 883894915 | 06 Lead Time Comments | 883895065 | 06 Lead Time | 883897006 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897071
4244961 | 883894256 | 01 Installation End | 883895615 | 01 Lead Time Comments | 883895764 | 01 Lead Time | 883897171 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897210
4244961 | 883894256 | 02 Integration | 883894526 | 02 Lead Time Comments | 883894683 | 02 Lead Time | 883896804 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896891
4244961 | 883894256 | 02 Integration | 883894526 | 02 Lead Time Comments | 883894683 | 02 Lead Time | 883896804 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896965
4244961 | 883894256 | 03 Integration Confirmed By NRO Technical Leader | 883895141 | 03 Lead Time Comments | 883895248 | 03 Lead Time | 883897093 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897119
4244961 | 883894256 | 04 SSV | 883894705 | 04 Lead Time Comments | 883894851 | 04 Lead Time | 883896948 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896988
4244961 | 883894256 | 04 SSV | 883894705 | 04 Lead Time Comments | 883894851 | 04 Lead Time | 883896948 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897002
4244961 | 883894256 | 05 SSV Confirmed By NDO Technical Leader | 883895302 | 05 Lead Time Comments | 883895410 | 05 Lead Time | 883897150 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897197
4244961 | 883894256 | 06 Tuning | 883894910 | 06 Lead Time Comments | 883895069 | 06 Lead Time | 883897005 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897072
4244961 | 883894256 | 06 Tuning | 883894910 | 06 Lead Time Comments | 883895069 | 06 Lead Time | 883897005 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897111
4244962 | 883894300 | 01 Installation End | 883895560 | 01 Lead Time Comments | 883895719 | 01 Lead Time | 883897163 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897193
4244962 | 883894300 | 02 Integration | 883894525 | 02 Lead Time Comments | 883894685 | 02 Lead Time | 883896812 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896834
4244962 | 883894300 | 02 Integration | 883894525 | 02 Lead Time Comments | 883894685 | 02 Lead Time | 883896812 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896862
4244962 | 883894300 | 03 Integration Confirmed By NRO Technical Leader | 883895086 | 03 Lead Time Comments | 883895210 | 03 Lead Time | 883897082 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897126
4244962 | 883894300 | 04 SSV | 883894718 | 04 Lead Time Comments | 883894889 | 04 Lead Time | 883896934 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896976
4244962 | 883894300 | 04 SSV | 883894718 | 04 Lead Time Comments | 883894889 | 04 Lead Time | 883896934 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897035
4244962 | 883894300 | 05 SSV Confirmed By NDO Technical Leader | 883895251 | 05 Lead Time Comments | 883895361 | 05 Lead Time | 883897094 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897123
4244962 | 883894300 | 06 Tuning | 883894914 | 06 Lead Time Comments | 883895038 | 06 Lead Time | 883897012 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897074
4244962 | 883894300 | 06 Tuning | 883894914 | 06 Lead Time Comments | 883895038 | 06 Lead Time | 883897012 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897146
4244963 | 883894295 | 01 Installation End | 883895861 | 01 Lead Time Comments | 883896014 | 01 Lead Time | 883897174 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897245
4244963 | 883894295 | 02 Integration | 883894623 | 02 Lead Time Comments | 883894814 | 02 Lead Time | 883896943 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896983
4244963 | 883894295 | 02 Integration | 883894623 | 02 Lead Time Comments | 883894814 | 02 Lead Time | 883896943 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896999
4244963 | 883894295 | 03 Integration Confirmed By NRO Technical Leader | 883895335 | 03 Lead Time Comments | 883895453 | 03 Lead Time | 883897154 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897221
4244963 | 883894295 | 04 SSV | 883894867 | 04 Lead Time Comments | 883895047 | 04 Lead Time | 883897019 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897114
4244963 | 883894295 | 04 SSV | 883894867 | 04 Lead Time Comments | 883895047 | 04 Lead Time | 883897019 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897165
4244963 | 883894295 | 05 SSV Confirmed By NDO Technical Leader | 883895490 | 05 Lead Time Comments | 883895657 | 05 Lead Time | 883897157 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897191
4244963 | 883894295 | 06 Tuning | 883895072 | 06 Lead Time Comments | 883895239 | 06 Lead Time | 883897104 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897145
4244963 | 883894295 | 06 Tuning | 883895072 | 06 Lead Time Comments | 883895239 | 06 Lead Time | 883897104 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897196
4244964 | 883894333 | 01 Installation End | 883895876 | 01 Lead Time Comments | 883896063 | 01 Lead Time | 883897182 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897225
4244964 | 883894333 | 02 Integration | 883894588 | 02 Lead Time Comments | 883894733 | 02 Lead Time | 883896895 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896920
4244964 | 883894333 | 02 Integration | 883894588 | 02 Lead Time Comments | 883894733 | 02 Lead Time | 883896895 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896984
4244964 | 883894333 | 03 Integration Confirmed By NRO Technical Leader | 883895221 | 03 Lead Time Comments | 883895349 | 03 Lead Time | 883897107 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897132
4244964 | 883894333 | 04 SSV | 883894778 | 04 Lead Time Comments | 883894940 | 04 Lead Time | 883896944 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883896964
4244964 | 883894333 | 04 SSV | 883894778 | 04 Lead Time Comments | 883894940 | 04 Lead Time | 883896944 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897003
4244964 | 883894333 | 05 SSV Confirmed By NDO Technical Leader | 883895415 | 05 Lead Time Comments | 883895577 | 05 Lead Time | 883897155 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897209
4244964 | 883894333 | 06 Tuning | 883894961 | 06 Lead Time Comments | 883895142 | 06 Lead Time | 883897021 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897063
4244964 | 883894333 | 06 Tuning | 883894961 | 06 Lead Time Comments | 883895142 | 06 Lead Time | 883897021 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897079
4244965 | 883894408 | 01 Installation End | 883895811 | 01 Lead Time Comments | 883895935 | 01 Lead Time | 883897176 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897226
4244965 | 883894408 | 02 Integration | 883894678 | 02 Lead Time Comments | 883894810 | 02 Lead Time | 883896932 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896971
4244965 | 883894408 | 02 Integration | 883894678 | 02 Lead Time Comments | 883894810 | 02 Lead Time | 883896932 | actcl--02 Integration--02 Lead Time Comments--Duration | 883896987
4244965 | 883894408 | 03 Integration Confirmed By NRO Technical Leader | 883895250 | 03 Lead Time Comments | 883895352 | 03 Lead Time | 883897098 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897116
4244965 | 883894408 | 04 SSV | 883894872 | 04 Lead Time Comments | 883895004 | 04 Lead Time | 883897004 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897056
4244965 | 883894408 | 04 SSV | 883894872 | 04 Lead Time Comments | 883895004 | 04 Lead Time | 883897004 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897076
4244965 | 883894408 | 05 SSV Confirmed By NDO Technical Leader | 883895409 | 05 Lead Time Comments | 883895589 | 05 Lead Time | 883897156 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897200
4244965 | 883894408 | 06 Tuning | 883895053 | 06 Lead Time Comments | 883895179 | 06 Lead Time | 883897102 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897112
4244965 | 883894408 | 06 Tuning | 883895053 | 06 Lead Time Comments | 883895179 | 06 Lead Time | 883897102 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897131
4244966 | 883894472 | 01 Installation End | 883895777 | 01 Lead Time Comments | 883895934 | 01 Lead Time | 883897173 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897263
4244966 | 883894472 | 02 Integration | 883894719 | 02 Lead Time Comments | 883894857 | 02 Lead Time | 883896946 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883896995
4244966 | 883894472 | 02 Integration | 883894719 | 02 Lead Time Comments | 883894857 | 02 Lead Time | 883896946 | actcl--02 Integration--02 Lead Time Comments--Duration | 883897047
4244966 | 883894472 | 03 Integration Confirmed By NRO Technical Leader | 883895374 | 03 Lead Time Comments | 883895459 | 03 Lead Time | 883897158 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897205
4244966 | 883894472 | 04 SSV | 883894909 | 04 Lead Time Comments | 883895083 | 04 Lead Time | 883897013 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897049
4244966 | 883894472 | 04 SSV | 883894909 | 04 Lead Time Comments | 883895083 | 04 Lead Time | 883897013 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897077
4244966 | 883894472 | 05 SSV Confirmed By NDO Technical Leader | 883895492 | 05 Lead Time Comments | 883895612 | 05 Lead Time | 883897166 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897213
4244966 | 883894472 | 06 Tuning | 883895164 | 06 Lead Time Comments | 883895336 | 06 Lead Time | 883897100 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897168
4244966 | 883894472 | 06 Tuning | 883895164 | 06 Lead Time Comments | 883895336 | 06 Lead Time | 883897100 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897220
4244967 | 883895401 | 01 Installation End | 883896990 | 01 Lead Time Comments | 883897170 | 01 Lead Time | 883897239 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897255
4244967 | 883895401 | 02 Integration | 883895669 | 02 Lead Time Comments | 883895899 | 02 Lead Time | 883897183 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883897222
4244967 | 883895401 | 02 Integration | 883895669 | 02 Lead Time Comments | 883895899 | 02 Lead Time | 883897183 | actcl--02 Integration--02 Lead Time Comments--Duration | 883897249
4244967 | 883895401 | 03 Integration Confirmed By NRO Technical Leader | 883896376 | 03 Lead Time Comments | 883896515 | 03 Lead Time | 883897185 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897228
4244967 | 883895401 | 04 SSV | 883896025 | 04 Lead Time Comments | 883896177 | 04 Lead Time | 883897187 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897237
4244967 | 883895401 | 04 SSV | 883896025 | 04 Lead Time Comments | 883896177 | 04 Lead Time | 883897187 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897251
4244967 | 883895401 | 05 SSV Confirmed By NDO Technical Leader | 883896536 | 05 Lead Time Comments | 883896658 | 05 Lead Time | 883897244 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897252
4244967 | 883895401 | 06 Tuning | 883896197 | 06 Lead Time Comments | 883896312 | 06 Lead Time | 883897184 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897223
4244967 | 883895401 | 06 Tuning | 883896197 | 06 Lead Time Comments | 883896312 | 06 Lead Time | 883897184 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897235
4244968 | 883895463 | 01 Installation End | 883897046 | 01 Lead Time Comments | 883897215 | 01 Lead Time | 883897275 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897279
4244968 | 883895463 | 02 Integration | 883895737 | 02 Lead Time Comments | 883895917 | 02 Lead Time | 883897177 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883897224
4244968 | 883895463 | 02 Integration | 883895737 | 02 Lead Time Comments | 883895917 | 02 Lead Time | 883897177 | actcl--02 Integration--02 Lead Time Comments--Duration | 883897236
4244968 | 883895463 | 03 Integration Confirmed By NRO Technical Leader | 883896465 | 03 Lead Time Comments | 883896618 | 03 Lead Time | 883897242 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897256
4244968 | 883895463 | 04 SSV | 883895991 | 04 Lead Time Comments | 883896180 | 04 Lead Time | 883897192 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897230
4244968 | 883895463 | 04 SSV | 883895991 | 04 Lead Time Comments | 883896180 | 04 Lead Time | 883897192 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897257
4244968 | 883895463 | 05 SSV Confirmed By NDO Technical Leader | 883896682 | 05 Lead Time Comments | 883896781 | 05 Lead Time | 883897253 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897265
4244968 | 883895463 | 06 Tuning | 883896211 | 06 Lead Time Comments | 883896377 | 06 Lead Time | 883897189 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897212
4244968 | 883895463 | 06 Tuning | 883896211 | 06 Lead Time Comments | 883896377 | 06 Lead Time | 883897189 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897229
4244969 | 883895464 | 01 Installation End | 883897122 | 01 Lead Time Comments | 883897264 | 01 Lead Time | 883897273 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897278
4244969 | 883895464 | 02 Integration | 883895755 | 02 Lead Time Comments | 883896010 | 02 Lead Time | 883897178 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883897216
4244969 | 883895464 | 02 Integration | 883895755 | 02 Lead Time Comments | 883896010 | 02 Lead Time | 883897178 | actcl--02 Integration--02 Lead Time Comments--Duration | 883897243
4244969 | 883895464 | 03 Integration Confirmed By NRO Technical Leader | 883896524 | 03 Lead Time Comments | 883896653 | 03 Lead Time | 883897241 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897261
4244969 | 883895464 | 04 SSV | 883896075 | 04 Lead Time Comments | 883896225 | 04 Lead Time | 883897181 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897238
4244969 | 883895464 | 04 SSV | 883896075 | 04 Lead Time Comments | 883896225 | 04 Lead Time | 883897181 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897259
4244969 | 883895464 | 05 SSV Confirmed By NDO Technical Leader | 883896738 | 05 Lead Time Comments | 883896908 | 05 Lead Time | 883897246 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897258
4244969 | 883895464 | 06 Tuning | 883896284 | 06 Lead Time Comments | 883896476 | 06 Lead Time | 883897190 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897203
4244969 | 883895464 | 06 Tuning | 883896284 | 06 Lead Time Comments | 883896476 | 06 Lead Time | 883897190 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897218
4244970 | 883895527 | 01 Installation End | 883897068 | 01 Lead Time Comments | 883897247 | 01 Lead Time | 883897274 | mscl--01 Installation End--01 Lead Time Comments--Duration | 883897277
4244970 | 883895527 | 02 Integration | 883895763 | 02 Lead Time Comments | 883895983 | 02 Lead Time | 883897179 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 883897198
4244970 | 883895527 | 02 Integration | 883895763 | 02 Lead Time Comments | 883895983 | 02 Lead Time | 883897179 | actcl--02 Integration--02 Lead Time Comments--Duration | 883897250
4244970 | 883895527 | 03 Integration Confirmed By NRO Technical Leader | 883896484 | 03 Lead Time Comments | 883896591 | 03 Lead Time | 883897254 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 883897266
4244970 | 883895527 | 04 SSV | 883896033 | 04 Lead Time Comments | 883896178 | 04 Lead Time | 883897180 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 883897206
4244970 | 883895527 | 04 SSV | 883896033 | 04 Lead Time Comments | 883896178 | 04 Lead Time | 883897180 | actcl--04 SSV--04 Lead Time Comments--Duration | 883897233
4244970 | 883895527 | 05 SSV Confirmed By NDO Technical Leader | 883896647 | 05 Lead Time Comments | 883896824 | 05 Lead Time | 883897240 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 883897269
4244970 | 883895527 | 06 Tuning | 883896217 | 06 Lead Time Comments | 883896401 | 06 Lead Time | 883897188 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 883897201
4244970 | 883895527 | 06 Tuning | 883896217 | 06 Lead Time Comments | 883896401 | 06 Lead Time | 883897188 | actcl--06 Tuning--06 Lead Time Comments--Duration | 883897248
4512561 | 930107132 | 01 Installation End | 930107405 | 01 Lead Time Comments | 930107458 | 01 Lead Time | 930107482 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107495
4512561 | 930107132 | 02 Integration | 930107153 | 02 Lead Time Comments | 930107159 | 02 Lead Time | 930107169 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107172
4512561 | 930107132 | 02 Integration | 930107153 | 02 Lead Time Comments | 930107159 | 02 Lead Time | 930107169 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107173
4512561 | 930107132 | 03 Integration Confirmed By NRO Technical Leader | 930107245 | 03 Lead Time Comments | 930107280 | 03 Lead Time | 930107292 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107302
4512561 | 930107132 | 04 SSV | 930107163 | 04 Lead Time Comments | 930107181 | 04 Lead Time | 930107202 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107205
4512561 | 930107132 | 04 SSV | 930107163 | 04 Lead Time Comments | 930107181 | 04 Lead Time | 930107202 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107210
4512561 | 930107132 | 05 SSV Confirmed By NDO Technical Leader | 930107291 | 05 Lead Time Comments | 930107323 | 05 Lead Time | 930107350 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107361
4512561 | 930107132 | 06 Tuning | 930107196 | 06 Lead Time Comments | 930107234 | 06 Lead Time | 930107260 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107263
4512561 | 930107132 | 06 Tuning | 930107196 | 06 Lead Time Comments | 930107234 | 06 Lead Time | 930107260 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107287
4512562 | 930107131 | 01 Installation End | 930107465 | 01 Lead Time Comments | 930107524 | 01 Lead Time | 930107557 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107574
4512562 | 930107131 | 02 Integration | 930107154 | 02 Lead Time Comments | 930107160 | 02 Lead Time | 930107166 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107171
4512562 | 930107131 | 02 Integration | 930107154 | 02 Lead Time Comments | 930107160 | 02 Lead Time | 930107166 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107174
4512562 | 930107131 | 03 Integration Confirmed By NRO Technical Leader | 930107240 | 03 Lead Time Comments | 930107285 | 03 Lead Time | 930107322 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107331
4512562 | 930107131 | 04 SSV | 930107162 | 04 Lead Time Comments | 930107179 | 04 Lead Time | 930107204 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107206
4512562 | 930107131 | 04 SSV | 930107162 | 04 Lead Time Comments | 930107179 | 04 Lead Time | 930107204 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107211
4512562 | 930107131 | 05 SSV Confirmed By NDO Technical Leader | 930107304 | 05 Lead Time Comments | 930107372 | 05 Lead Time | 930107399 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107410
4512562 | 930107131 | 06 Tuning | 930107189 | 06 Lead Time Comments | 930107230 | 06 Lead Time | 930107258 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107268
4512562 | 930107131 | 06 Tuning | 930107189 | 06 Lead Time Comments | 930107230 | 06 Lead Time | 930107258 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107273
4512563 | 930107135 | 01 Installation End | 930107463 | 01 Lead Time Comments | 930107517 | 01 Lead Time | 930107561 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107567
4512563 | 930107135 | 02 Integration | 930107156 | 02 Lead Time Comments | 930107164 | 02 Lead Time | 930107168 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107175
4512563 | 930107135 | 02 Integration | 930107156 | 02 Lead Time Comments | 930107164 | 02 Lead Time | 930107168 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107176
4512563 | 930107135 | 03 Integration Confirmed By NRO Technical Leader | 930107248 | 03 Lead Time Comments | 930107284 | 03 Lead Time | 930107317 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107328
4512563 | 930107135 | 04 SSV | 930107170 | 04 Lead Time Comments | 930107200 | 04 Lead Time | 930107203 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107207
4512563 | 930107135 | 04 SSV | 930107170 | 04 Lead Time Comments | 930107200 | 04 Lead Time | 930107203 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107209
4512563 | 930107135 | 05 SSV Confirmed By NDO Technical Leader | 930107295 | 05 Lead Time Comments | 930107340 | 05 Lead Time | 930107400 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107408
4512563 | 930107135 | 06 Tuning | 930107201 | 06 Lead Time Comments | 930107241 | 06 Lead Time | 930107256 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107266
4512563 | 930107135 | 06 Tuning | 930107201 | 06 Lead Time Comments | 930107241 | 06 Lead Time | 930107256 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107271
4512564 | 930107143 | 01 Installation End | 930107603 | 01 Lead Time Comments | 930107644 | 01 Lead Time | 930107706 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107719
4512564 | 930107143 | 02 Integration | 930107198 | 02 Lead Time Comments | 930107233 | 02 Lead Time | 930107257 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107262
4512564 | 930107143 | 02 Integration | 930107198 | 02 Lead Time Comments | 930107233 | 02 Lead Time | 930107257 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107272
4512564 | 930107143 | 03 Integration Confirmed By NRO Technical Leader | 930107377 | 03 Lead Time Comments | 930107434 | 03 Lead Time | 930107487 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107493
4512564 | 930107143 | 04 SSV | 930107243 | 04 Lead Time Comments | 930107288 | 04 Lead Time | 930107319 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107335
4512564 | 930107143 | 04 SSV | 930107243 | 04 Lead Time Comments | 930107288 | 04 Lead Time | 930107319 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107355
4512564 | 930107143 | 05 SSV Confirmed By NDO Technical Leader | 930107449 | 05 Lead Time Comments | 930107511 | 05 Lead Time | 930107556 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107564
4512564 | 930107143 | 06 Tuning | 930107303 | 06 Lead Time Comments | 930107365 | 06 Lead Time | 930107397 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107416
4512564 | 930107143 | 06 Tuning | 930107303 | 06 Lead Time Comments | 930107365 | 06 Lead Time | 930107397 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107423
4512565 | 930107144 | 01 Installation End | 930107586 | 01 Lead Time Comments | 930107641 | 01 Lead Time | 930107705 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107717
4512565 | 930107144 | 02 Integration | 930107188 | 02 Lead Time Comments | 930107229 | 02 Lead Time | 930107238 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107251
4512565 | 930107144 | 02 Integration | 930107188 | 02 Lead Time Comments | 930107229 | 02 Lead Time | 930107238 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107254
4512565 | 930107144 | 03 Integration Confirmed By NRO Technical Leader | 930107366 | 03 Lead Time Comments | 930107435 | 03 Lead Time | 930107481 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107506
4512565 | 930107144 | 04 SSV | 930107237 | 04 Lead Time Comments | 930107290 | 04 Lead Time | 930107320 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107333
4512565 | 930107144 | 04 SSV | 930107237 | 04 Lead Time Comments | 930107290 | 04 Lead Time | 930107320 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107341
4512565 | 930107144 | 05 SSV Confirmed By NDO Technical Leader | 930107450 | 05 Lead Time Comments | 930107507 | 05 Lead Time | 930107560 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107571
4512565 | 930107144 | 06 Tuning | 930107298 | 06 Lead Time Comments | 930107354 | 06 Lead Time | 930107394 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107409
4512565 | 930107144 | 06 Tuning | 930107298 | 06 Lead Time Comments | 930107354 | 06 Lead Time | 930107394 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107420
4512566 | 930107145 | 01 Installation End | 930107602 | 01 Lead Time Comments | 930107670 | 01 Lead Time | 930107701 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107725
4512566 | 930107145 | 02 Integration | 930107194 | 02 Lead Time Comments | 930107235 | 02 Lead Time | 930107259 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107265
4512566 | 930107145 | 02 Integration | 930107194 | 02 Lead Time Comments | 930107235 | 02 Lead Time | 930107259 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107279
4512566 | 930107145 | 03 Integration Confirmed By NRO Technical Leader | 930107376 | 03 Lead Time Comments | 930107457 | 03 Lead Time | 930107476 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107492
4512566 | 930107145 | 04 SSV | 930107244 | 04 Lead Time Comments | 930107289 | 04 Lead Time | 930107316 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107327
4512566 | 930107145 | 04 SSV | 930107244 | 04 Lead Time Comments | 930107289 | 04 Lead Time | 930107316 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107332
4512566 | 930107145 | 05 SSV Confirmed By NDO Technical Leader | 930107468 | 05 Lead Time Comments | 930107515 | 05 Lead Time | 930107554 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107584
4512566 | 930107145 | 06 Tuning | 930107299 | 06 Lead Time Comments | 930107363 | 06 Lead Time | 930107395 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107426
4512566 | 930107145 | 06 Tuning | 930107299 | 06 Lead Time Comments | 930107363 | 06 Lead Time | 930107395 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107444
4512567 | 930107146 | 01 Installation End | 930107647 | 01 Lead Time Comments | 930107727 | 01 Lead Time | 930107746 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107752
4512567 | 930107146 | 02 Integration | 930107192 | 02 Lead Time Comments | 930107232 | 02 Lead Time | 930107261 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107267
4512567 | 930107146 | 02 Integration | 930107192 | 02 Lead Time Comments | 930107232 | 02 Lead Time | 930107261 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107270
4512567 | 930107146 | 03 Integration Confirmed By NRO Technical Leader | 930107385 | 03 Lead Time Comments | 930107459 | 03 Lead Time | 930107478 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107499
4512567 | 930107146 | 04 SSV | 930107242 | 04 Lead Time Comments | 930107297 | 04 Lead Time | 930107321 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107329
4512567 | 930107146 | 04 SSV | 930107242 | 04 Lead Time Comments | 930107297 | 04 Lead Time | 930107321 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107338
4512567 | 930107146 | 05 SSV Confirmed By NDO Technical Leader | 930107498 | 05 Lead Time Comments | 930107563 | 05 Lead Time | 930107595 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107610
4512567 | 930107146 | 06 Tuning | 930107306 | 06 Lead Time Comments | 930107367 | 06 Lead Time | 930107398 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107413
4512567 | 930107146 | 06 Tuning | 930107306 | 06 Lead Time Comments | 930107367 | 06 Lead Time | 930107398 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107427
4512568 | 930107149 | 01 Installation End | 930107612 | 01 Lead Time Comments | 930107669 | 01 Lead Time | 930107702 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107718
4512568 | 930107149 | 02 Integration | 930107191 | 02 Lead Time Comments | 930107231 | 02 Lead Time | 930107255 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107264
4512568 | 930107149 | 02 Integration | 930107191 | 02 Lead Time Comments | 930107231 | 02 Lead Time | 930107255 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107277
4512568 | 930107149 | 03 Integration Confirmed By NRO Technical Leader | 930107378 | 03 Lead Time Comments | 930107447 | 03 Lead Time | 930107477 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107503
4512568 | 930107149 | 04 SSV | 930107239 | 04 Lead Time Comments | 930107286 | 04 Lead Time | 930107318 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107330
4512568 | 930107149 | 04 SSV | 930107239 | 04 Lead Time Comments | 930107286 | 04 Lead Time | 930107318 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107345
4512568 | 930107149 | 05 SSV Confirmed By NDO Technical Leader | 930107461 | 05 Lead Time Comments | 930107516 | 05 Lead Time | 930107559 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107575
4512568 | 930107149 | 06 Tuning | 930107300 | 06 Lead Time Comments | 930107352 | 06 Lead Time | 930107402 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107411
4512568 | 930107149 | 06 Tuning | 930107300 | 06 Lead Time Comments | 930107352 | 06 Lead Time | 930107402 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107428
4512569 | 930107193 | 01 Installation End | 930107750 | 01 Lead Time Comments | 930107780 | 01 Lead Time | 930107813 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107820
4512569 | 930107193 | 02 Integration | 930107283 | 02 Lead Time Comments | 930107326 | 02 Lead Time | 930107351 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107362
4512569 | 930107193 | 02 Integration | 930107283 | 02 Lead Time Comments | 930107326 | 02 Lead Time | 930107351 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107371
4512569 | 930107193 | 03 Integration Confirmed By NRO Technical Leader | 930107546 | 03 Lead Time Comments | 930107592 | 03 Lead Time | 930107651 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107673
4512569 | 930107193 | 04 SSV | 930107336 | 04 Lead Time Comments | 930107422 | 04 Lead Time | 930107436 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107443
4512569 | 930107193 | 04 SSV | 930107336 | 04 Lead Time Comments | 930107422 | 04 Lead Time | 930107436 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107456
4512569 | 930107193 | 05 SSV Confirmed By NDO Technical Leader | 930107613 | 05 Lead Time Comments | 930107660 | 05 Lead Time | 930107707 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107720
4512569 | 930107193 | 06 Tuning | 930107445 | 06 Lead Time Comments | 930107510 | 06 Lead Time | 930107555 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107565
4512569 | 930107193 | 06 Tuning | 930107445 | 06 Lead Time Comments | 930107510 | 06 Lead Time | 930107555 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107573
4512570 | 930107195 | 01 Installation End | 930107742 | 01 Lead Time Comments | 930107773 | 01 Lead Time | 930107812 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107822
4512570 | 930107195 | 02 Integration | 930107294 | 02 Lead Time Comments | 930107337 | 02 Lead Time | 930107392 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107417
4512570 | 930107195 | 02 Integration | 930107294 | 02 Lead Time Comments | 930107337 | 02 Lead Time | 930107392 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107425
4512570 | 930107195 | 03 Integration Confirmed By NRO Technical Leader | 930107547 | 03 Lead Time Comments | 930107591 | 03 Lead Time | 930107666 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107681
4512570 | 930107195 | 04 SSV | 930107357 | 04 Lead Time Comments | 930107440 | 04 Lead Time | 930107485 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107502
4512570 | 930107195 | 04 SSV | 930107357 | 04 Lead Time Comments | 930107440 | 04 Lead Time | 930107485 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107508
4512570 | 930107195 | 05 SSV Confirmed By NDO Technical Leader | 930107620 | 05 Lead Time Comments | 930107659 | 05 Lead Time | 930107704 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107721
4512570 | 930107195 | 06 Tuning | 930107460 | 06 Lead Time Comments | 930107526 | 06 Lead Time | 930107562 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107572
4512570 | 930107195 | 06 Tuning | 930107460 | 06 Lead Time Comments | 930107526 | 06 Lead Time | 930107562 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107581
4512571 | 930107213 | 01 Installation End | 930107756 | 01 Lead Time Comments | 930107783 | 01 Lead Time | 930107809 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107821
4512571 | 930107213 | 02 Integration | 930107307 | 02 Lead Time Comments | 930107369 | 02 Lead Time | 930107403 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107414
4512571 | 930107213 | 02 Integration | 930107307 | 02 Lead Time Comments | 930107369 | 02 Lead Time | 930107403 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107429
4512571 | 930107213 | 03 Integration Confirmed By NRO Technical Leader | 930107568 | 03 Lead Time Comments | 930107625 | 03 Lead Time | 930107649 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107675
4512571 | 930107213 | 04 SSV | 930107381 | 04 Lead Time Comments | 930107453 | 04 Lead Time | 930107484 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107489
4512571 | 930107213 | 04 SSV | 930107381 | 04 Lead Time Comments | 930107453 | 04 Lead Time | 930107484 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107496
4512571 | 930107213 | 05 SSV Confirmed By NDO Technical Leader | 930107636 | 05 Lead Time Comments | 930107687 | 05 Lead Time | 930107708 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107714
4512571 | 930107213 | 06 Tuning | 930107479 | 06 Lead Time Comments | 930107550 | 06 Lead Time | 930107597 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107615
4512571 | 930107213 | 06 Tuning | 930107479 | 06 Lead Time Comments | 930107550 | 06 Lead Time | 930107597 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107626
4512572 | 930107216 | 01 Installation End | 930107737 | 01 Lead Time Comments | 930107772 | 01 Lead Time | 930107811 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107817
4512572 | 930107216 | 02 Integration | 930107310 | 02 Lead Time Comments | 930107370 | 02 Lead Time | 930107401 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107419
4512572 | 930107216 | 02 Integration | 930107310 | 02 Lead Time Comments | 930107370 | 02 Lead Time | 930107401 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107431
4512572 | 930107216 | 03 Integration Confirmed By NRO Technical Leader | 930107533 | 03 Lead Time Comments | 930107590 | 03 Lead Time | 930107607 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107621
4512572 | 930107216 | 04 SSV | 930107387 | 04 Lead Time Comments | 930107454 | 04 Lead Time | 930107486 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107491
4512572 | 930107216 | 04 SSV | 930107387 | 04 Lead Time Comments | 930107454 | 04 Lead Time | 930107486 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107501
4512572 | 930107216 | 05 SSV Confirmed By NDO Technical Leader | 930107608 | 05 Lead Time Comments | 930107646 | 05 Lead Time | 930107700 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107729
4512572 | 930107216 | 06 Tuning | 930107464 | 06 Lead Time Comments | 930107518 | 06 Lead Time | 930107558 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107577
4512572 | 930107216 | 06 Tuning | 930107464 | 06 Lead Time Comments | 930107518 | 06 Lead Time | 930107558 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107587
4512573 | 930107214 | 01 Installation End | 930107758 | 01 Lead Time Comments | 930107794 | 01 Lead Time | 930107810 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107818
4512573 | 930107214 | 02 Integration | 930107325 | 02 Lead Time Comments | 930107375 | 02 Lead Time | 930107406 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107415
4512573 | 930107214 | 02 Integration | 930107325 | 02 Lead Time Comments | 930107375 | 02 Lead Time | 930107406 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107424
4512573 | 930107214 | 03 Integration Confirmed By NRO Technical Leader | 930107576 | 03 Lead Time Comments | 930107634 | 03 Lead Time | 930107650 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107677
4512573 | 930107214 | 04 SSV | 930107390 | 04 Lead Time Comments | 930107483 | 04 Lead Time | 930107512 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107521
4512573 | 930107214 | 04 SSV | 930107390 | 04 Lead Time Comments | 930107483 | 04 Lead Time | 930107512 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107528
4512573 | 930107214 | 05 SSV Confirmed By NDO Technical Leader | 930107639 | 05 Lead Time Comments | 930107696 | 05 Lead Time | 930107744 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107755
4512573 | 930107214 | 06 Tuning | 930107504 | 06 Lead Time Comments | 930107566 | 06 Lead Time | 930107598 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107611
4512573 | 930107214 | 06 Tuning | 930107504 | 06 Lead Time Comments | 930107566 | 06 Lead Time | 930107598 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107623
4512574 | 930107215 | 01 Installation End | 930107778 | 01 Lead Time Comments | 930107827 | 01 Lead Time | 930107846 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107853
4512574 | 930107215 | 02 Integration | 930107315 | 02 Lead Time Comments | 930107368 | 02 Lead Time | 930107393 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107421
4512574 | 930107215 | 02 Integration | 930107315 | 02 Lead Time Comments | 930107368 | 02 Lead Time | 930107393 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107433
4512574 | 930107215 | 03 Integration Confirmed By NRO Technical Leader | 930107579 | 03 Lead Time Comments | 930107638 | 03 Lead Time | 930107655 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107667
4512574 | 930107215 | 04 SSV | 930107383 | 04 Lead Time Comments | 930107475 | 04 Lead Time | 930107513 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107525
4512574 | 930107215 | 04 SSV | 930107383 | 04 Lead Time Comments | 930107475 | 04 Lead Time | 930107513 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107541
4512574 | 930107215 | 05 SSV Confirmed By NDO Technical Leader | 930107654 | 05 Lead Time Comments | 930107726 | 05 Lead Time | 930107747 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107753
4512574 | 930107215 | 06 Tuning | 930107494 | 06 Lead Time Comments | 930107569 | 06 Lead Time | 930107594 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107614
4512574 | 930107215 | 06 Tuning | 930107494 | 06 Lead Time Comments | 930107569 | 06 Lead Time | 930107594 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107624
4512575 | 930107217 | 01 Installation End | 930107774 | 01 Lead Time Comments | 930107829 | 01 Lead Time | 930107847 | mscl--01 Installation End--01 Lead Time Comments--Duration | 930107854
4512575 | 930107217 | 02 Integration | 930107312 | 02 Lead Time Comments | 930107374 | 02 Lead Time | 930107396 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 930107412
4512575 | 930107217 | 02 Integration | 930107312 | 02 Lead Time Comments | 930107374 | 02 Lead Time | 930107396 | actcl--02 Integration--02 Lead Time Comments--Duration | 930107432
4512575 | 930107217 | 03 Integration Confirmed By NRO Technical Leader | 930107616 | 03 Lead Time Comments | 930107645 | 03 Lead Time | 930107703 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 930107716
4512575 | 930107217 | 04 SSV | 930107404 | 04 Lead Time Comments | 930107480 | 04 Lead Time | 930107514 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 930107522
4512575 | 930107217 | 04 SSV | 930107404 | 04 Lead Time Comments | 930107480 | 04 Lead Time | 930107514 | actcl--04 SSV--04 Lead Time Comments--Duration | 930107531
4512575 | 930107217 | 05 SSV Confirmed By NDO Technical Leader | 930107664 | 05 Lead Time Comments | 930107731 | 05 Lead Time | 930107745 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 930107754
4512575 | 930107217 | 06 Tuning | 930107497 | 06 Lead Time Comments | 930107580 | 06 Lead Time | 930107599 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 930107627
4512575 | 930107217 | 06 Tuning | 930107497 | 06 Lead Time Comments | 930107580 | 06 Lead Time | 930107599 | actcl--06 Tuning--06 Lead Time Comments--Duration | 930107633