## PRJ WP Site
Project--ID | Project--ProjectName | Project--SystemRecordID | Project--ProjectPlanStartDate | Project--ProjectPlanEndDate | Project--ProjectExecutionCountry | Project--Customer | Project--Status | Workplan--Country | Workplan--WorkPlanID | Workplan--FASID | Workplan--SystemRecordID | Workplan--WorkPlanStatus | Workplan--ProjectName | Workplan--Prefix | Workplan--Suffix | Workplan--CustomerDeliverableID | Workplan--RelatedNetworkElement | Workplan--CustomerScopeID | Workplan--WorkPlanType | Sites--ID | Sites--Name | Sites--RecordName | Sites--SystemRecordID | Sites--Customer | Sites--SiteType | Sites--City | Sites--Country | Sites--Status | Sites--StreetAddress | Sites--LatitudeDecimal | Sites--LatitudeDMS | Sites--LongitudeDecimal | Sites--LongitudeDMS
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830377 |  | 749387588 | Completed | 50130175-JQUTW老顶山隧道入口北1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147908-JQUTW老顶山隧道入口北1.8G\CZ147908-JQUTW老顶山隧道入口北1.8G |  | Radio Site | CZ147908 | JQUTW老顶山隧道入口北1.8G_1 | CZ147908-JQUTW老顶山隧道入口北1.8G | 749374304 |  |  | Changzhi | China | Draft |  | 113.1515 | 113'9'6' | 36.2041 | 36'12'14'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830378 |  | 749387590 | Completed | 50130175-JQUTW南垂驾校东1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147895-JQUTW南垂驾校东1.8G\CZ147895-JQUTW南垂驾校东1.8G |  | Radio Site | CZ147895 | JQUTW南垂驾校东1.8G_1 | CZ147895-JQUTW南垂驾校东1.8G | 749374324 |  |  | Changzhi | China | Draft |  | 113.1658 | 113'9'57' | 36.2523 | 36'15'8'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830379 |  | 749387554 | Completed | 50130175-武乡西站-1-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147910-武乡西站-1\CZ147910-武乡西站-1 |  | Radio Site | CZ147910 | 武乡西站-1_1 | CZ147910-武乡西站-1 | 749374411 |  |  | Changzhi | China | Draft |  | 112.79 | 112'47'24' | 36.8479 | 36'50'52'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830380 |  | 749387639 | Completed | 50130175-SQUCU才智大厦1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147918-SQUCU才智大厦1.8G\CZ147918-SQUCU才智大厦1.8G |  | Radio Site | CZ147918 | SQUCU才智大厦1.8G_1 | CZ147918-SQUCU才智大厦1.8G | 749374305 |  |  | Changzhi | China | Draft |  | 113.1166 | 113'6'60' | 36.197 | 36'11'49'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830381 |  | 749387681 | Completed | 50130175-LCSTW鸡坡西1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147917-LCSTW鸡坡西1.8G\CZ147917-LCSTW鸡坡西1.8G |  | Radio Site | CZ147917 | LCSTW鸡坡西1.8G_1 | CZ147917-LCSTW鸡坡西1.8G | 749374303 |  |  | Changzhi | China | Draft |  | 113.182 | 113'10'55' | 36.2597 | 36'15'34'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830383 |  | 749387680 | Completed | 50130175-长治南站-1-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147914-长治南站-1\CZ147914-长治南站-1 |  | Radio Site | CZ147914 | 长治南站-1_1 | CZ147914-长治南站-1 | 749374369 |  |  | Changzhi | China | Draft |  | 113.1005 | 113'6'2' | 36.0923 | 36'5'32'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830384 |  | 749387696 | Completed | 50130175-JQUTW朝阳长运驾校东1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147906-JQUTW朝阳长运驾校东1.8G\CZ147906-JQUTW朝阳长运驾校东1.8G |  | Radio Site | CZ147906 | JQUTW朝阳长运驾校东1.8G_1 | CZ147906-JQUTW朝阳长运驾校东1.8G | 749374336 |  |  | Changzhi | China | Draft |  | 113.1634 | 113'9'48' | 36.2341 | 36'14'2'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830385 |  | 749387697 | Completed | 50130175-SQUCU才智大厦-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147918-SQUCU才智大厦\CZ147918-SQUCU才智大厦 |  | Radio Site | CZ147918 | SQUCU才智大厦_1 | CZ147918-SQUCU才智大厦 | 749374343 |  |  | Changzhi | China | Draft |  | 113.1166 | 113'6'60' | 36.197 | 36'11'49'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830386 |  | 749387682 | Completed | 50130175-长治东站-2-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147913-长治东站-2\CZ147913-长治东站-2 |  | Radio Site | CZ147913 | 长治东站-2_1 | CZ147913-长治东站-2 | 749374372 |  |  | Changzhi | China | Draft |  | 113.1593 | 113'9'33' | 36.2288 | 36'13'43'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830387 |  | 749387695 | Completed | 50130175-大冯庄村南-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\JC142435-大冯庄村南\JC142435-大冯庄村南 |  | Radio Site | JC142435 | 大冯庄村南_1 | JC142435-大冯庄村南 | 749374407 |  |  | Jincheng | China | Draft |  | 112.932 | 112'55'55' | 35.8189 | 35'49'7'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830388 |  | 749387698 | Completed | 50130175-襄垣东站-1-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147909-襄垣东站-1\CZ147909-襄垣东站-1 |  | Radio Site | CZ147909 | 襄垣东站-1_1 | CZ147909-襄垣东站-1 | 749374404 |  |  | Changzhi | China | Draft |  | 113.0764 | 113'4'35' | 36.5353 | 36'32'7'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830389 |  | 749387702 | Completed | 50130175-长治南站-2-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147914-长治南站-2\CZ147914-长治南站-2 |  | Radio Site | CZ147914 | 长治南站-2_1 | CZ147914-长治南站-2 | 749374403 |  |  | Changzhi | China | Draft |  | 113.1005 | 113'6'2' | 36.0923 | 36'5'32'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830390 |  | 749387699 | Completed | 50130175-张家村-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\JC142893-张家村\JC142893-张家村 |  | Radio Site | JC142893 | 张家村_1 | JC142893-张家村 | 749374383 |  |  | Jincheng | China | Draft |  | 112.931 | 112'55'52' | 35.8283 | 35'49'41'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830392 |  | 749387712 | Completed | 50130175-JQUTW长治东站高铁检修站1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147907-JQUTW长治东站高铁检修站1.8G\CZ147907-JQUTW长治东站高铁检修站1.8G |  | Radio Site | CZ147907 | JQUTW长治东站高铁检修站1.8G_1 | CZ147907-JQUTW长治东站高铁检修站1.8G | 749374317 |  |  | Changzhi | China | Draft |  | 113.1607 | 113'9'39' | 36.2262 | 36'13'34'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830393 |  | 749387700 | Completed | 50130175-JQUTW老顶山镇东1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147907-JQUTW老顶山镇东1.8G\CZ147907-JQUTW老顶山镇东1.8G |  | Radio Site | CZ147907 | JQUTW老顶山镇东1.8G_1 | CZ147907-JQUTW老顶山镇东1.8G | 749374329 |  |  | Changzhi | China | Draft |  | 113.1572 | 113'9'26' | 36.2159 | 36'12'57'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830396 |  | 749387770 | Completed | 50130175-张家村南-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\JC142893-张家村南\JC142893-张家村南 |  | Radio Site | JC142893 | 张家村南_1 | JC142893-张家村南 | 749374409 |  |  | Jincheng | China | Draft |  | 112.931 | 112'55'52' | 35.8251 | 35'49'30'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830397 |  | 749387764 | Completed | 50130175-LUCTW鸡坡西北2.1G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147926-LUCTW鸡坡西北2.1G\CZ147926-LUCTW鸡坡西北2.1G |  | Radio Site | CZ147926 | LUCTW鸡坡西北2.1G_1 | CZ147926-LUCTW鸡坡西北2.1G | 749374405 |  |  | Changzhi | China | Draft |  | 113.1776 | 113'10'39' | 36.2623 | 36'15'44'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830399 |  | 749387773 | Completed | 50130175-JQUTW长治东站1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147906-JQUTW长治东站1.8G\CZ147906-JQUTW长治东站1.8G |  | Radio Site | CZ147906 | JQUTW长治东站1.8G_1 | CZ147906-JQUTW长治东站1.8G | 749374338 |  |  | Changzhi | China | Draft |  | 113.1629 | 113'9'47' | 36.2297 | 36'13'46'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830400 |  | 749387771 | Completed | 50130175-JQUTW老顶山隧道入口1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147908-JQUTW老顶山隧道入口1.8G\CZ147908-JQUTW老顶山隧道入口1.8G |  | Radio Site | CZ147908 | JQUTW老顶山隧道入口1.8G_1 | CZ147908-JQUTW老顶山隧道入口1.8G | 749374311 |  |  | Changzhi | China | Draft |  | 113.1542 | 113'9'15' | 36.2006 | 36'12'2'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830402 |  | 749387769 | Completed | 50130175-大浪淘沙酒店2.1G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ140330-大浪淘沙酒店2.1G\CZ140330-大浪淘沙酒店2.1G |  | Radio Site | CZ140330 | 大浪淘沙酒店2.1G_1 | CZ140330-大浪淘沙酒店2.1G | 749374406 |  |  | Changzhi | China | Draft |  | 113.1333 | 113'7'60' | 36.1704 | 36'10'13'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830404 |  | 749387772 | Completed | 50130175-高平东站-1-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\JC142892-高平东站-1\JC142892-高平东站-1 |  | Radio Site | JC142892 | 高平东站-1_1 | JC142892-高平东站-1 | 749374378 |  |  | Jincheng | China | Draft |  | 112.9546 | 112'57'16' | 35.7407 | 35'44'26'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830405 |  | 749387767 | Completed | 50130175-JQUTW南垂南1.8G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147895-JQUTW南垂南1.8G\CZ147895-JQUTW南垂南1.8G |  | Radio Site | CZ147895 | JQUTW南垂南1.8G_1 | CZ147895-JQUTW南垂南1.8G | 749374344 |  |  | Changzhi | China | Draft |  | 113.1614 | 113'9'41' | 36.2439 | 36'14'37'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830406 |  | 749387779 | Completed | 50130175-长治东站-1-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147913-长治东站-1\CZ147913-长治东站-1 |  | Radio Site | CZ147913 | 长治东站-1_1 | CZ147913-长治东站-1 | 749374408 |  |  | Changzhi | China | Draft |  | 113.1593 | 113'9'33' | 36.2288 | 36'13'43'
1013471 | CN_CT_COMBJ_SX_4G_CC_CP9_50130175 | 749385509 | 2000-01-01 | 2000-01-01 | China | China Telecom Shanxi | Revision In Progress | China | 3830407 |  | 749387780 | Completed | 50130175-LUCTW鸡坡西2.1G-SV_MACRO | 50130175 | SV_MACRO |  | \Locations\CZ147926-LUCTW鸡坡西2.1G\CZ147926-LUCTW鸡坡西2.1G |  | Radio Site | CZ147926 | LUCTW鸡坡西2.1G_1 | CZ147926-LUCTW鸡坡西2.1G | 749374371 |  |  | Changzhi | China | Draft |  | 113.182 | 113'10'55' | 36.2597 | 36'15'34'
1020023 | CN_CT_COMBJ_SX_5G_CC/ES_50141243_5G RAN ToB FA Y21 SX Services | 909434420 | 2022-08-25 08:26 |  | China | China Telecom Shanxi | Revision In Progress | China | 4385006 |  | 909435344 | Released | 50141243-01-SXJZ001-SV_DOT | 50141243-01 | SV_DOT | 50141243-01 | \Locations\SXJZ001-SXJZ001\SXJZ001-SXJZ001 | 50141243-01 | Radio Site | SXJZ001 | SXJZ001_1 | SXJZ001-SXJZ001 | 909415081 |  |  | Jinzhong | China | Draft |  | 116.3027 | 116'18'10' | 37.3951 | 37'23'42'

## PLO dates
WP ID | Workplan--SystemRecordID | Customised PLO name | PLO--Name | PLO--Status | Object type | PLO--SystemRecordID | act--BaselineEndDate | act--ForecastEndDate | act--ActualStartDate | act--ActualEndDate | ms--BaselineEndDate | ms--ForecastEndDate | ms--ActualStartDate | ms--ActualEndDate
3830377 | 749387588 | act--02 Integration | 02 Integration | Completed | Activity | 749388531 | 06/10/2021 15:00:57 | 06/10/2021 15:00:04 | 06/09/2021 13:30:25 | 06/09/2021 15:00:05
3830377 | 749387588 | act--04 SSV | 04 SSV | Completed | Activity | 749388786 | 09/15/2021 05:30:00 | 06/15/2021 05:30:00 | 06/15/2021 05:30:00 | 06/16/2021 18:30:00
3830377 | 749387588 | act--04 SSV | 04 SSV | Completed | Activity | 857595826 | 06/13/2021 16:46:49 | 06/13/2021 16:46:49 | 06/15/2021 06:30:00 | 06/16/2021 18:30:00
3830377 | 749387588 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389171 | 07/30/2021 14:02:32 | 07/30/2021 14:02:32 | 07/18/2021 06:01:12 | 07/30/2021 14:02:32
3830377 | 749387588 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388144 |  |  |  |  | 06/10/2021 12:30:24 | 06/10/2021 12:30:28 |  | 06/09/2021 12:30:03
3830377 | 749387588 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388082 |  |  |  |  | 06/10/2021 06:30:46 | 06/10/2021 06:30:14 |  | 06/09/2021 06:30:28
3830377 | 749387588 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387727 |  |  |  |  | 06/10/2021 15:00:57 | 06/10/2021 15:00:04 |  | 06/09/2021 15:46:49
3830377 | 749387588 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749387893 |  |  |  |  | 06/17/2021 16:46:49 | 06/17/2021 16:46:49 |  | 06/17/2021 16:46:49
3830377 | 749387588 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388334 |  |  |  |  | 06/10/2021 15:00:59 | 07/30/2021 14:02:32 |  | 08/29/2021 14:02:32
3830377 | 749387588 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388439 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830378 | 749387590 | act--02 Integration | 02 Integration | Completed | Activity | 749388828 | 07/14/2021 15:00:55 | 07/14/2021 15:00:06 | 07/13/2021 13:30:52 | 07/13/2021 15:00:44
3830378 | 749387590 | act--04 SSV | 04 SSV | Completed | Activity | 749389187 | 09/16/2021 05:30:00 | 07/15/2021 05:30:00 | 07/15/2021 05:30:00 | 07/26/2021 14:46:19
3830378 | 749387590 | act--04 SSV | 04 SSV | Completed | Activity | 857595809 | 07/19/2021 14:46:19 | 07/19/2021 14:46:19 | 07/25/2021 05:46:19 | 07/26/2021 14:46:19
3830378 | 749387590 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389523 | 08/14/2021 19:34:19 | 08/14/2021 19:34:19 | 08/14/2021 07:34:19 | 08/14/2021 19:34:19
3830378 | 749387590 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388312 |  |  |  |  | 07/14/2021 12:30:40 | 07/14/2021 12:30:27 |  | 07/13/2021 12:30:05
3830378 | 749387590 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388190 |  |  |  |  | 07/14/2021 06:30:54 | 07/14/2021 06:30:16 |  | 07/13/2021 06:30:27
3830378 | 749387590 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387722 |  |  |  |  | 07/14/2021 15:00:55 | 07/14/2021 15:00:06 |  | 07/13/2021 15:46:19
3830378 | 749387590 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749387942 |  |  |  |  | 07/27/2021 14:46:19 | 07/27/2021 14:46:19 |  | 07/27/2021 14:46:19
3830378 | 749387590 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388598 |  |  |  |  | 07/14/2021 15:00:57 | 08/14/2021 19:34:19 |  | 08/29/2021 14:39:59
3830378 | 749387590 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388710 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830379 | 749387554 | act--02 Integration | 02 Integration | Completed | Activity | 749388502 | 06/09/2021 15:00:50 | 06/09/2021 15:00:57 | 06/08/2021 13:30:37 | 06/08/2021 15:00:21
3830379 | 749387554 | act--04 SSV | 04 SSV | Completed | Activity | 749388846 | 09/18/2021 05:30:00 | 06/14/2021 05:30:00 | 06/14/2021 05:30:00 | 06/29/2021 19:59:11
3830379 | 749387554 | act--04 SSV | 04 SSV | Completed | Activity | 857595797 | 06/12/2021 16:23:11 | 06/12/2021 16:23:11 | 06/28/2021 05:35:11 | 06/29/2021 19:59:11
3830379 | 749387554 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389165 | 07/12/2021 17:35:11 | 07/12/2021 17:35:11 | 07/12/2021 05:35:11 | 07/12/2021 17:35:11
3830379 | 749387554 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388142 |  |  |  |  | 06/09/2021 12:30:27 | 06/09/2021 12:30:55 |  | 06/08/2021 12:30:56
3830379 | 749387554 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388057 |  |  |  |  | 06/09/2021 06:30:18 | 06/09/2021 06:30:44 |  | 06/08/2021 06:30:55
3830379 | 749387554 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387728 |  |  |  |  | 06/09/2021 15:00:50 | 06/09/2021 15:00:57 |  | 06/08/2021 16:47:11
3830379 | 749387554 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749387883 |  |  |  |  | 06/30/2021 16:23:11 | 06/30/2021 16:23:11 |  | 06/30/2021 16:23:11
3830379 | 749387554 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388340 |  |  |  |  | 06/09/2021 15:00:52 | 07/12/2021 17:35:11 |  | 08/29/2021 14:02:32
3830379 | 749387554 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388409 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830380 | 749387639 | act--02 Integration | 02 Integration | Completed | Activity | 749388722 | 06/26/2021 15:00:27 | 06/26/2021 15:00:20 | 06/25/2021 13:30:56 | 06/25/2021 15:00:37
3830380 | 749387639 | act--04 SSV | 04 SSV | Completed | Activity | 749389101 | 09/22/2021 05:30:00 | 06/30/2021 05:30:00 | 06/30/2021 05:30:00 | 06/30/2021 13:38:22
3830380 | 749387639 | act--04 SSV | 04 SSV | Completed | Activity | 857595884 | 06/27/2021 08:50:22 | 06/27/2021 08:50:22 | 06/26/2021 06:50:22 | 06/30/2021 13:38:22
3830380 | 749387639 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389404 | 07/02/2021 09:11:58 | 07/02/2021 09:11:58 | 07/02/2021 06:11:58 | 07/02/2021 09:11:58
3830380 | 749387639 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388315 |  |  |  |  | 06/26/2021 12:30:52 | 06/26/2021 12:30:25 |  | 06/25/2021 12:30:19
3830380 | 749387639 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388196 |  |  |  |  | 06/26/2021 06:30:49 | 06/26/2021 06:30:13 |  | 06/25/2021 06:30:25
3830380 | 749387639 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387843 |  |  |  |  | 06/26/2021 15:00:27 | 06/26/2021 15:00:20 |  | 06/25/2021 16:50:22
3830380 | 749387639 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388037 |  |  |  |  | 07/01/2021 13:52:46 | 07/01/2021 13:52:46 |  | 07/01/2021 13:52:46
3830380 | 749387639 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388541 |  |  |  |  | 06/26/2021 15:00:29 | 07/02/2021 09:11:58 |  | 08/29/2021 14:39:59
3830380 | 749387639 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388609 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830381 | 749387681 | act--02 Integration | 02 Integration | Completed | Activity | 749388748 | 08/02/2021 15:00:48 | 08/02/2021 15:00:00 | 08/01/2021 13:30:56 | 08/01/2021 15:00:13
3830381 | 749387681 | act--04 SSV | 04 SSV | Completed | Activity | 749389050 | 09/23/2021 05:30:00 | 08/10/2021 05:30:00 | 08/10/2021 05:30:00 | 08/11/2021 14:50:49
3830381 | 749387681 | act--04 SSV | 04 SSV | Completed | Activity | 857595806 | 08/04/2021 09:48:25 | 08/04/2021 09:48:25 | 08/03/2021 06:48:25 | 08/11/2021 14:50:49
3830381 | 749387681 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389368 | 08/13/2021 10:24:25 | 08/13/2021 10:24:25 | 08/13/2021 07:24:25 | 08/13/2021 10:24:25
3830381 | 749387681 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388317 |  |  |  |  | 08/02/2021 12:30:28 | 08/02/2021 12:30:47 |  | 08/01/2021 12:30:00
3830381 | 749387681 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388229 |  |  |  |  | 08/02/2021 06:30:22 | 08/02/2021 06:30:40 |  | 08/01/2021 06:30:47
3830381 | 749387681 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387810 |  |  |  |  | 08/02/2021 15:00:48 | 08/02/2021 15:00:00 |  | 08/01/2021 16:48:25
3830381 | 749387681 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388068 |  |  |  |  | 08/12/2021 15:05:13 | 08/12/2021 15:05:13 |  | 08/12/2021 15:05:13
3830381 | 749387681 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388514 |  |  |  |  | 08/02/2021 15:00:50 | 08/13/2021 10:24:25 |  | 08/29/2021 14:02:32
3830381 | 749387681 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388654 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830383 | 749387680 | act--02 Integration | 02 Integration | Completed | Activity | 749388741 | 12/15/2021 15:00:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830383 | 749387680 | act--04 SSV | 04 SSV | Completed | Activity | 749389160 | 09/24/2021 05:30:00 | 12/16/2021 05:30:00 | 12/16/2021 05:30:00 | 12/18/2021 14:16:49
3830383 | 749387680 | act--04 SSV | 04 SSV | Completed | Activity | 857595796 | 12/18/2021 09:00:01 | 12/18/2021 09:00:01 | 12/17/2021 06:00:01 | 12/18/2021 14:16:49
3830383 | 749387680 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389432 | 12/23/2021 09:50:25 | 12/23/2021 09:50:25 | 12/23/2021 06:50:25 | 12/23/2021 09:50:25
3830383 | 749387680 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388337 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830383 | 749387680 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388232 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830383 | 749387680 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387838 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830383 | 749387680 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388073 |  |  |  |  | 12/19/2021 14:31:13 | 12/19/2021 14:31:13 |  | 12/19/2021 14:31:13
3830383 | 749387680 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388485 |  |  |  |  | 12/15/2021 15:00:03 | 12/23/2021 09:50:25 |  | 12/30/2021 12:50:25
3830383 | 749387680 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388568 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830384 | 749387696 | act--02 Integration | 02 Integration | Completed | Activity | 749388721 | 07/09/2021 15:00:28 | 07/09/2021 15:00:30 | 07/08/2021 13:30:53 | 07/08/2021 15:00:35
3830384 | 749387696 | act--04 SSV | 04 SSV | Completed | Activity | 749389128 | 09/25/2021 05:30:00 | 07/16/2021 05:30:00 | 07/16/2021 05:30:00 | 07/16/2021 15:51:06
3830384 | 749387696 | act--04 SSV | 04 SSV | Completed | Activity | 857595921 | 07/10/2021 09:51:06 | 07/10/2021 09:51:06 | 07/09/2021 06:51:06 | 07/16/2021 15:51:06
3830384 | 749387696 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389484 | 07/18/2021 11:24:42 | 07/18/2021 11:24:42 | 07/18/2021 08:24:42 | 07/18/2021 11:24:42
3830384 | 749387696 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388357 |  |  |  |  | 07/09/2021 12:30:00 | 07/09/2021 12:30:19 |  | 07/08/2021 12:30:29
3830384 | 749387696 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388256 |  |  |  |  | 07/09/2021 06:30:53 | 07/09/2021 06:30:15 |  | 07/08/2021 06:30:25
3830384 | 749387696 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387837 |  |  |  |  | 07/09/2021 15:00:28 | 07/09/2021 15:00:30 |  | 07/08/2021 16:51:06
3830384 | 749387696 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388069 |  |  |  |  | 07/17/2021 16:05:30 | 07/17/2021 16:05:30 |  | 07/17/2021 16:05:30
3830384 | 749387696 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388549 |  |  |  |  | 07/09/2021 15:00:30 | 07/18/2021 11:24:42 |  | 08/29/2021 14:39:59
3830384 | 749387696 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388611 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830385 | 749387697 | act--02 Integration | 02 Integration | Completed | Activity | 749388689 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830385 | 749387697 | act--04 SSV | 04 SSV | Completed | Activity | 749389097 | 10/15/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 05:30:00 | 12/18/2021 14:08:24
3830385 | 749387697 | act--04 SSV | 04 SSV | Completed | Activity | 857595873 | 12/18/2021 08:30:00 | 12/18/2021 08:30:00 | 12/17/2021 05:30:00 | 12/18/2021 14:08:24
3830385 | 749387697 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389451 | 12/23/2021 09:42:00 | 12/23/2021 09:42:00 | 12/23/2021 06:42:00 | 12/23/2021 09:42:00
3830385 | 749387697 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388306 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830385 | 749387697 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388240 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830385 | 749387697 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387798 |  |  |  |  | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 |  | 12/14/2021 15:30:00
3830385 | 749387697 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388025 |  |  |  |  | 12/19/2021 14:22:48 | 12/19/2021 14:22:48 |  | 12/19/2021 14:22:48
3830385 | 749387697 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388524 |  |  |  |  | 12/15/2021 14:30:02 | 12/23/2021 09:42:00 |  | 12/30/2021 12:50:25
3830385 | 749387697 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388585 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830386 | 749387682 | act--02 Integration | 02 Integration | Completed | Activity | 749388671 | 07/22/2021 15:00:28 | 07/22/2021 15:00:54 | 07/21/2021 13:30:04 | 07/21/2021 15:00:00
3830386 | 749387682 | act--04 SSV | 04 SSV | Completed | Activity | 749389116 | 10/16/2021 05:30:00 | 07/22/2021 05:30:00 | 07/22/2021 05:30:00 | 07/24/2021 16:06:23
3830386 | 749387682 | act--04 SSV | 04 SSV | Completed | Activity | 857595896 | 07/24/2021 09:47:40 | 07/24/2021 09:47:40 | 07/23/2021 06:47:40 | 07/24/2021 16:06:23
3830386 | 749387682 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389373 | 07/29/2021 11:39:59 | 07/29/2021 11:39:59 | 07/29/2021 08:39:59 | 07/29/2021 11:39:59
3830386 | 749387682 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388300 |  |  |  |  | 07/22/2021 12:30:26 | 07/22/2021 12:30:14 |  | 07/21/2021 12:30:00
3830386 | 749387682 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388205 |  |  |  |  | 07/22/2021 06:30:48 | 07/22/2021 06:30:05 |  | 07/21/2021 06:30:14
3830386 | 749387682 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387811 |  |  |  |  | 07/22/2021 15:00:28 | 07/22/2021 15:00:54 |  | 07/21/2021 16:47:40
3830386 | 749387682 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388029 |  |  |  |  | 07/25/2021 16:20:47 | 07/25/2021 16:20:47 |  | 07/25/2021 16:20:47
3830386 | 749387682 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388490 |  |  |  |  | 07/22/2021 15:00:30 | 07/29/2021 11:39:59 |  | 08/29/2021 14:39:59
3830386 | 749387682 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388564 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830387 | 749387695 | act--02 Integration | 02 Integration | Completed | Activity | 749388731 | 07/18/2021 15:00:11 | 07/18/2021 15:00:04 | 07/17/2021 13:30:41 | 07/17/2021 15:00:17
3830387 | 749387695 | act--04 SSV | 04 SSV | Completed | Activity | 749389130 | 10/17/2021 05:30:00 | 07/22/2021 05:30:00 | 07/22/2021 05:30:00 | 07/22/2021 16:20:56
3830387 | 749387695 | act--04 SSV | 04 SSV | Completed | Activity | 857595945 | 07/21/2021 09:49:15 | 07/21/2021 09:49:15 | 07/20/2021 06:49:15 | 07/22/2021 16:20:56
3830387 | 749387695 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389406 | 07/26/2021 11:54:32 | 07/26/2021 11:54:32 | 07/26/2021 08:54:32 | 07/26/2021 11:54:32
3830387 | 749387695 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388296 |  |  |  |  | 07/18/2021 12:30:32 | 07/18/2021 12:30:02 |  | 07/17/2021 12:30:03
3830387 | 749387695 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388213 |  |  |  |  | 07/18/2021 06:30:33 | 07/18/2021 06:30:54 |  | 07/17/2021 06:30:02
3830387 | 749387695 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387829 |  |  |  |  | 07/18/2021 15:00:11 | 07/18/2021 15:00:04 |  | 07/17/2021 16:49:15
3830387 | 749387695 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388023 |  |  |  |  | 07/22/2021 16:35:20 | 07/22/2021 16:35:20 |  | 07/22/2021 16:35:20
3830387 | 749387695 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388500 |  |  |  |  | 07/18/2021 15:00:13 | 07/26/2021 11:54:32 |  | 08/29/2021 14:39:59
3830387 | 749387695 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388607 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830388 | 749387698 | act--02 Integration | 02 Integration | Completed | Activity | 749388772 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830388 | 749387698 | act--04 SSV | 04 SSV | Completed | Activity | 749389196 | 10/18/2021 05:30:00 | 12/16/2021 05:30:00 | 12/16/2021 05:30:00 | 12/18/2021 16:00:30
3830388 | 749387698 | act--04 SSV | 04 SSV | Completed | Activity | 857595988 | 12/18/2021 09:00:01 | 12/18/2021 09:00:01 | 12/17/2021 06:00:01 | 12/18/2021 16:00:30
3830388 | 749387698 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389520 | 12/23/2021 11:34:06 | 12/23/2021 11:34:06 | 12/23/2021 08:34:06 | 12/23/2021 11:34:06
3830388 | 749387698 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388425 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830388 | 749387698 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388350 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830388 | 749387698 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749388003 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830388 | 749387698 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388187 |  |  |  |  | 12/19/2021 16:14:54 | 12/19/2021 16:14:54 |  | 12/19/2021 16:14:54
3830388 | 749387698 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388588 |  |  |  |  | 12/15/2021 15:00:03 | 12/23/2021 11:34:06 |  | 12/30/2021 12:34:06
3830388 | 749387698 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388693 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830389 | 749387702 | act--02 Integration | 02 Integration | Completed | Activity | 749388695 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830389 | 749387702 | act--04 SSV | 04 SSV | Completed | Activity | 749389179 | 09/24/2021 05:30:00 | 12/16/2021 05:30:00 | 12/16/2021 05:30:00 | 12/17/2021 15:50:59
3830389 | 749387702 | act--04 SSV | 04 SSV | Completed | Activity | 857595850 | 12/17/2021 09:02:01 | 12/17/2021 09:02:01 | 12/16/2021 06:02:01 | 12/17/2021 15:50:59
3830389 | 749387702 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389454 | 12/22/2021 11:24:35 | 12/22/2021 11:24:35 | 12/22/2021 08:24:35 | 12/22/2021 11:24:35
3830389 | 749387702 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388329 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830389 | 749387702 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388228 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830389 | 749387702 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387812 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830389 | 749387702 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388034 |  |  |  |  | 12/18/2021 16:05:23 | 12/18/2021 16:05:23 |  | 12/18/2021 16:05:23
3830389 | 749387702 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388516 |  |  |  |  | 12/15/2021 15:00:03 | 12/22/2021 11:24:35 |  | 12/30/2021 12:34:06
3830389 | 749387702 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388622 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830390 | 749387699 | act--02 Integration | 02 Integration | Completed | Activity | 749388738 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830390 | 749387699 | act--04 SSV | 04 SSV | Completed | Activity | 749389134 | 10/23/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 05:30:00 | 12/19/2021 16:12:06
3830390 | 749387699 | act--04 SSV | 04 SSV | Completed | Activity | 857595920 | 12/19/2021 09:10:11 | 12/19/2021 09:10:11 | 12/18/2021 06:10:11 | 12/19/2021 16:12:06
3830390 | 749387699 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389499 | 12/24/2021 11:45:42 | 12/24/2021 11:45:42 | 12/24/2021 08:45:42 | 12/24/2021 11:45:42
3830390 | 749387699 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388363 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830390 | 749387699 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388257 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830390 | 749387699 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387853 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830390 | 749387699 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388067 |  |  |  |  | 12/20/2021 16:26:30 | 12/20/2021 16:26:30 |  | 12/20/2021 16:26:30
3830390 | 749387699 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388511 |  |  |  |  | 12/15/2021 15:00:03 | 12/24/2021 11:45:42 |  | 12/30/2021 12:50:25
3830390 | 749387699 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388627 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830392 | 749387712 | act--02 Integration | 02 Integration | Completed | Activity | 749388787 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830392 | 749387712 | act--04 SSV | 04 SSV | Completed | Activity | 749389120 | 10/25/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 05:30:00 | 12/20/2021 15:41:05
3830392 | 749387712 | act--04 SSV | 04 SSV | Completed | Activity | 857595807 | 12/20/2021 08:50:41 | 12/20/2021 08:50:41 | 12/19/2021 05:50:41 | 12/20/2021 15:41:05
3830392 | 749387712 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389361 | 12/25/2021 11:14:41 | 12/25/2021 11:14:41 | 12/25/2021 08:14:41 | 12/25/2021 11:14:41
3830392 | 749387712 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388370 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830392 | 749387712 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388291 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830392 | 749387712 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387844 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830392 | 749387712 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388119 |  |  |  |  | 12/21/2021 15:55:29 | 12/21/2021 15:55:29 |  | 12/21/2021 15:55:29
3830392 | 749387712 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388538 |  |  |  |  | 12/15/2021 15:00:03 | 12/25/2021 11:14:41 |  | 12/30/2021 12:50:25
3830392 | 749387712 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388676 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830393 | 749387700 | act--02 Integration | 02 Integration | Completed | Activity | 749388802 | 07/21/2021 15:00:27 | 07/21/2021 15:00:59 | 07/20/2021 13:30:52 | 07/20/2021 15:00:24
3830393 | 749387700 | act--04 SSV | 04 SSV | Completed | Activity | 749389099 | 10/26/2021 05:30:00 | 12/18/2021 05:30:00 | 12/18/2021 05:30:00 | 12/18/2021 16:27:03
3830393 | 749387700 | act--04 SSV | 04 SSV | Completed | Activity | 857595883 | 07/23/2021 09:49:37 | 07/23/2021 09:49:37 | 07/22/2021 06:49:37 | 12/18/2021 16:27:03
3830393 | 749387700 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389462 | 12/30/2021 12:00:39 | 12/30/2021 12:00:39 | 12/30/2021 09:00:39 | 12/30/2021 12:00:39
3830393 | 749387700 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388308 |  |  |  |  | 07/21/2021 12:30:26 | 07/21/2021 12:30:48 |  | 07/20/2021 12:30:58
3830393 | 749387700 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388231 |  |  |  |  | 07/21/2021 06:30:21 | 07/21/2021 06:30:49 |  | 07/20/2021 06:30:59
3830393 | 749387700 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387839 |  |  |  |  | 07/21/2021 15:00:27 | 07/21/2021 15:00:59 |  | 07/20/2021 16:49:37
3830393 | 749387700 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388046 |  |  |  |  | 12/29/2021 16:41:27 | 12/29/2021 16:41:27 |  | 12/29/2021 16:41:27
3830393 | 749387700 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388555 |  |  |  |  | 07/21/2021 15:00:29 | 12/30/2021 12:00:39 |  | 12/30/2021 12:50:25
3830393 | 749387700 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388684 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830396 | 749387770 | act--02 Integration | 02 Integration | Completed | Activity | 749388855 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830396 | 749387770 | act--04 SSV | 04 SSV | Completed | Activity | 749389138 | 10/28/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 15:50:23
3830396 | 749387770 | act--04 SSV | 04 SSV | Completed | Activity | 857596207 | 12/16/2021 09:59:01 | 12/16/2021 09:59:01 | 12/15/2021 06:59:01 | 12/17/2021 15:50:23
3830396 | 749387770 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389466 | 12/21/2021 11:23:59 | 12/21/2021 11:23:59 | 12/21/2021 08:23:59 | 12/21/2021 11:23:59
3830396 | 749387770 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388447 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830396 | 749387770 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388355 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830396 | 749387770 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387956 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830396 | 749387770 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388159 |  |  |  |  | 12/17/2021 16:04:47 | 12/17/2021 16:04:47 |  | 12/17/2021 16:04:47
3830396 | 749387770 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388670 |  |  |  |  | 12/15/2021 15:00:03 | 12/21/2021 11:23:59 |  | 12/30/2021 12:50:25
3830396 | 749387770 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388745 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830397 | 749387764 | act--02 Integration | 02 Integration | Completed | Activity | 749388712 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830397 | 749387764 | act--04 SSV | 04 SSV | Completed | Activity | 857596359 | 12/17/2021 10:30:21 | 12/17/2021 10:30:21 | 12/16/2021 07:30:21 | 12/17/2021 16:11:38
3830397 | 749387764 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389351 | 12/22/2021 11:45:14 | 12/22/2021 11:45:14 | 12/22/2021 08:45:14 | 12/22/2021 11:45:14
3830397 | 749387764 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388368 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830397 | 749387764 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388281 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830397 | 749387764 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387889 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830397 | 749387764 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388106 |  |  |  |  | 12/18/2021 16:26:02 | 12/18/2021 16:26:02 |  | 12/18/2021 16:26:02
3830397 | 749387764 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388488 |  |  |  |  | 12/15/2021 15:00:03 | 12/22/2021 11:45:14 |  | 12/30/2021 12:50:25
3830397 | 749387764 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388601 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830399 | 749387773 | act--02 Integration | 02 Integration | Completed | Activity | 749388827 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830399 | 749387773 | act--04 SSV | 04 SSV | Completed | Activity | 749389147 | 09/15/2021 05:30:00 | 12/17/2021 05:30:00 | 12/17/2021 05:30:00 | 12/22/2021 16:01:06
3830399 | 749387773 | act--04 SSV | 04 SSV | Completed | Activity | 857600476 | 12/22/2021 09:15:01 | 12/22/2021 09:15:01 | 12/21/2021 06:15:01 | 12/22/2021 16:01:06
3830399 | 749387773 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389582 | 12/27/2021 11:34:42 | 12/27/2021 11:34:42 | 12/27/2021 08:34:42 | 12/27/2021 11:34:42
3830399 | 749387773 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388400 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830399 | 749387773 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388324 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830399 | 749387773 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387934 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830399 | 749387773 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388108 |  |  |  |  | 12/23/2021 16:15:30 | 12/23/2021 16:15:30 |  | 12/23/2021 16:15:30
3830399 | 749387773 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388575 |  |  |  |  | 12/15/2021 15:00:03 | 12/27/2021 11:34:42 |  | 12/30/2021 12:50:25
3830399 | 749387773 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388726 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830400 | 749387771 | act--02 Integration | 02 Integration | Completed | Activity | 749388757 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830400 | 749387771 | act--04 SSV | 04 SSV | Completed | Activity | 857600450 | 12/21/2021 09:25:41 | 12/21/2021 09:25:41 | 12/20/2021 06:25:41 | 12/21/2021 16:24:43
3830400 | 749387771 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389636 | 12/26/2021 11:58:19 | 12/26/2021 11:58:19 | 12/26/2021 08:58:19 | 12/26/2021 11:58:19
3830400 | 749387771 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388397 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830400 | 749387771 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388321 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830400 | 749387771 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387912 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830400 | 749387771 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388133 |  |  |  |  | 12/22/2021 16:39:07 | 12/22/2021 16:39:07 |  | 12/22/2021 16:39:07
3830400 | 749387771 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388576 |  |  |  |  | 12/15/2021 15:00:03 | 12/26/2021 11:58:19 |  | 12/30/2021 12:50:25
3830400 | 749387771 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388685 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830402 | 749387769 | act--02 Integration | 02 Integration | Completed | Activity | 749388817 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830402 | 749387769 | act--04 SSV | 04 SSV | Completed | Activity | 749389123 | 09/03/2021 05:30:00 | 12/22/2021 05:30:00 | 12/22/2021 05:30:00 | 12/23/2021 14:59:53
3830402 | 749387769 | act--04 SSV | 04 SSV | Completed | Activity | 857596121 | 12/23/2021 08:55:34 | 12/23/2021 08:55:34 | 12/22/2021 05:55:34 | 12/23/2021 14:59:53
3830402 | 749387769 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389446 | 12/28/2021 10:33:29 | 12/28/2021 10:33:29 | 12/28/2021 07:33:29 | 12/28/2021 10:33:29
3830402 | 749387769 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388427 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830402 | 749387769 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388342 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830402 | 749387769 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387950 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830402 | 749387769 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388164 |  |  |  |  | 12/24/2021 15:14:17 | 12/24/2021 15:14:17 |  | 12/24/2021 15:14:17
3830402 | 749387769 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388616 |  |  |  |  | 12/15/2021 15:00:03 | 12/28/2021 10:33:29 |  | 12/30/2021 12:50:25
3830402 | 749387769 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388724 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830404 | 749387772 | act--02 Integration | 02 Integration | Completed | Activity | 749388997 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830404 | 749387772 | act--04 SSV | 04 SSV | Completed | Activity | 749389318 | 10/29/2021 05:30:00 | 12/23/2021 05:30:00 | 12/23/2021 05:30:00 | 12/23/2021 14:48:19
3830404 | 749387772 | act--04 SSV | 04 SSV | Completed | Activity | 857600280 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01 | 12/22/2021 05:55:31 | 12/23/2021 14:48:19
3830404 | 749387772 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389786 | 12/28/2021 10:21:55 | 12/28/2021 10:21:55 | 12/28/2021 07:21:55 | 12/28/2021 10:21:55
3830404 | 749387772 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388487 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830404 | 749387772 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388360 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830404 | 749387772 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387952 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830404 | 749387772 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388175 |  |  |  |  | 12/24/2021 15:02:43 | 12/24/2021 15:02:43 |  | 12/24/2021 15:02:43
3830404 | 749387772 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388729 |  |  |  |  | 12/15/2021 15:00:03 | 12/28/2021 10:21:55 |  | 12/30/2021 12:34:06
3830404 | 749387772 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388820 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830405 | 749387767 | act--02 Integration | 02 Integration | Completed | Activity | 749388821 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830405 | 749387767 | act--04 SSV | 04 SSV | Completed | Activity | 749389206 | 11/05/2021 05:30:00 | 12/24/2021 05:30:00 | 12/24/2021 05:30:00 | 12/25/2021 15:59:13
3830405 | 749387767 | act--04 SSV | 04 SSV | Completed | Activity | 857596035 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01 | 12/24/2021 06:36:11 | 12/25/2021 15:59:13
3830405 | 749387767 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389540 | 12/30/2021 11:32:49 | 12/30/2021 11:32:49 | 12/30/2021 08:32:49 | 12/30/2021 11:32:49
3830405 | 749387767 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388428 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830405 | 749387767 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388364 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830405 | 749387767 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387971 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830405 | 749387767 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388165 |  |  |  |  | 12/26/2021 16:13:37 | 12/26/2021 16:13:37 |  | 12/26/2021 16:13:37
3830405 | 749387767 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388648 |  |  |  |  | 12/15/2021 15:00:03 | 12/30/2021 11:32:49 |  | 12/30/2021 12:50:25
3830405 | 749387767 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388734 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830406 | 749387779 | act--02 Integration | 02 Integration | Completed | Activity | 749389067 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830406 | 749387779 | act--04 SSV | 04 SSV | Completed | Activity | 749389417 | 10/16/2021 05:30:00 | 12/23/2021 05:30:00 | 12/23/2021 05:30:00 | 12/23/2021 14:46:55
3830406 | 749387779 | act--04 SSV | 04 SSV | Completed | Activity | 857600353 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01 | 12/19/2021 05:55:33 | 12/23/2021 14:46:55
3830406 | 749387779 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389804 | 12/25/2021 10:20:31 | 12/25/2021 10:20:31 | 12/25/2021 07:20:31 | 12/25/2021 10:20:31
3830406 | 749387779 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388510 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830406 | 749387779 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388385 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830406 | 749387779 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387943 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830406 | 749387779 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388198 |  |  |  |  | 12/24/2021 15:01:19 | 12/24/2021 15:01:19 |  | 12/24/2021 15:01:19
3830406 | 749387779 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388752 |  |  |  |  | 12/15/2021 15:00:03 | 12/25/2021 10:20:31 |  | 12/30/2021 12:50:25
3830406 | 749387779 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388891 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
3830407 | 749387780 | act--02 Integration | 02 Integration | Completed | Activity | 749388816 | 12/15/2021 14:30:00 | 12/15/2021 14:30:00 | 12/14/2021 13:00:00 | 12/14/2021 14:30:00
3830407 | 749387780 | act--04 SSV | 04 SSV | Completed | Activity | 857600445 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01 | 12/18/2021 06:45:41 | 12/19/2021 16:37:31
3830407 | 749387780 | act--06 Tuning | 06 Tuning | Completed | Activity | 749389445 | 12/24/2021 12:11:07 | 12/24/2021 12:11:07 | 12/24/2021 09:11:07 | 12/24/2021 12:11:07
3830407 | 749387780 | ms--01 Installation End | 01 Installation End | Completed | Milestone | 749388459 |  |  |  |  | 12/15/2021 12:30:00 | 12/15/2021 12:30:00 |  | 12/14/2021 12:30:00
3830407 | 749387780 | ms--01 Installation Start | 01 Installation Start | Completed | Milestone | 749388341 |  |  |  |  | 12/15/2021 06:30:00 | 12/15/2021 06:30:00 |  | 12/14/2021 06:30:00
3830407 | 749387780 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Completed | Milestone | 749387924 |  |  |  |  | 12/15/2021 15:00:01 | 12/15/2021 15:00:01 |  | 12/14/2021 16:00:01
3830407 | 749387780 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Completed | Milestone | 749388149 |  |  |  |  | 12/20/2021 16:51:55 | 12/20/2021 16:51:55 |  | 12/20/2021 16:51:55
3830407 | 749387780 | ms--07 PAC | 07 PAC | Completed | Milestone | 749388578 |  |  |  |  | 12/15/2021 15:00:03 | 12/24/2021 12:11:07 |  | 12/30/2021 12:50:25
3830407 | 749387780 | ms--08 FAC | 08 FAC | Completed | Milestone | 749388677 |  |  |  |  | 03/25/2022 03:45:00 | 03/25/2022 03:45:00 |  | 03/24/2022 03:45:00
4385006 | 909435344 | act--02 Integration | 02 Integration | Pending Predecessors | Activity | 909435515 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4385006 | 909435344 | act--04 SSV | 04 SSV | Pending Predecessors | Activity | 909435699 | 01/01/2000 13:30:01 | 01/01/2000 13:30:01
4385006 | 909435344 | act--06 Tuning | 06 Tuning | Pending Predecessors | Activity | 909435821 | 01/01/2000 05:30:01 | 01/01/2000 05:30:01
4385006 | 909435344 | ms--01 Installation End | 01 Installation End | Pending Predecessors | Milestone | 909436166 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4385006 | 909435344 | ms--01 Installation Start | 01 Installation Start | Ready to Start | Milestone | 909436099 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4385006 | 909435344 | ms--03 Integration Confirmed By NRO Technical Leader | 03 Integration Confirmed By NRO Technical Leader | Pending Predecessors | Milestone | 909435893 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4385006 | 909435344 | ms--05 SSV Confirmed By NDO Technical Leader | 05 SSV Confirmed By NDO Technical Leader | Pending Predecessors | Milestone | 909436000 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4385006 | 909435344 | ms--07 PAC | 07 PAC | Pending Predecessors | Milestone | 909436247 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00
4385006 | 909435344 | ms--08 FAC | 08 FAC | Pending Predecessors | Milestone | 909436317 |  |  |  |  | 01/01/2000 05:30:00 | 01/01/2000 05:30:00

## UDF ITEM
WP ID | Workplan--SystemRecordID | PLO name | PLO--SystemRecordID | UDF Name | UDF - System Record ID | UDF Category Name | UDF CategorySystem Record ID | UDF item Name | UDF Item--SystemRecordID | UDF Value
3830377 | 749387588 | 01 Installation End | 749388144 | 01 Lead Time Comments | 749388217 | 01 Lead Time | 749388260 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388279
3830377 | 749387588 | 02 Integration | 749388531 | 02 Lead Time Comments | 749388652 | 02 Lead Time | 749388713 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388735
3830377 | 749387588 | 02 Integration | 749388531 | 02 Lead Time Comments | 749388652 | 02 Lead Time | 749388713 | actcl--02 Integration--02 Lead Time Comments--Duration | 749388758
3830377 | 749387588 | 03 Integration Confirmed By NRO Technical Leader | 749387727 | 03 Lead Time Comments | 749387750 | 03 Lead Time | 749387758 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387800
3830377 | 749387588 | 04 SSV | 749388786 | 04 Lead Time Comments | 749388957 | 04 Lead Time | 749389009 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389079
3830377 | 749387588 | 04 SSV | 749388786 | 04 Lead Time Comments | 749388957 | 04 Lead Time | 749389009 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389108
3830377 | 749387588 | 04 SSV | 857595826 | 04 Lead Time Comments | 857596072 | 04 Lead Time | 857596113 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596298
3830377 | 749387588 | 04 SSV | 857595826 | 04 Lead Time Comments | 857596072 | 04 Lead Time | 857596113 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596511
3830377 | 749387588 | 05 SSV Confirmed By NDO Technical Leader | 749387893 | 05 Lead Time Comments | 749387968 | 05 Lead Time | 749387996 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388016
3830377 | 749387588 | 06 Tuning | 749389171 | 06 Lead Time Comments | 749389282 | 06 Lead Time | 749389316 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389372
3830377 | 749387588 | 06 Tuning | 749389171 | 06 Lead Time Comments | 749389282 | 06 Lead Time | 749389316 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389429
3830378 | 749387590 | 01 Installation End | 749388312 | 01 Lead Time Comments | 749388416 | 01 Lead Time | 749388477 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388526
3830378 | 749387590 | 02 Integration | 749388828 | 02 Lead Time Comments | 749389018 | 02 Lead Time | 749389045 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389089
3830378 | 749387590 | 02 Integration | 749388828 | 02 Lead Time Comments | 749389018 | 02 Lead Time | 749389045 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389136
3830378 | 749387590 | 03 Integration Confirmed By NRO Technical Leader | 749387722 | 03 Lead Time Comments | 749387753 | 03 Lead Time | 749387759 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387797
3830378 | 749387590 | 04 SSV | 749389187 | 04 Lead Time Comments | 749389308 | 04 Lead Time | 749389328 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389410
3830378 | 749387590 | 04 SSV | 749389187 | 04 Lead Time Comments | 749389308 | 04 Lead Time | 749389328 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389433
3830378 | 749387590 | 04 SSV | 857595809 | 04 Lead Time Comments | 857596050 | 04 Lead Time | 857596114 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596316
3830378 | 749387590 | 04 SSV | 857595809 | 04 Lead Time Comments | 857596050 | 04 Lead Time | 857596114 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596611
3830378 | 749387590 | 05 SSV Confirmed By NDO Technical Leader | 749387942 | 05 Lead Time Comments | 749388049 | 05 Lead Time | 749388081 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388110
3830378 | 749387590 | 06 Tuning | 749389523 | 06 Lead Time Comments | 749389777 | 06 Lead Time | 749389794 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389849
3830378 | 749387590 | 06 Tuning | 749389523 | 06 Lead Time Comments | 749389777 | 06 Lead Time | 749389794 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389953
3830379 | 749387554 | 01 Installation End | 749388142 | 01 Lead Time Comments | 749388245 | 01 Lead Time | 749388254 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388285
3830379 | 749387554 | 02 Integration | 749388502 | 02 Lead Time Comments | 749388675 | 02 Lead Time | 749388711 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388742
3830379 | 749387554 | 02 Integration | 749388502 | 02 Lead Time Comments | 749388675 | 02 Lead Time | 749388711 | actcl--02 Integration--02 Lead Time Comments--Duration | 749388776
3830379 | 749387554 | 03 Integration Confirmed By NRO Technical Leader | 749387728 | 03 Lead Time Comments | 749387752 | 03 Lead Time | 749387783 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387822
3830379 | 749387554 | 04 SSV | 749388846 | 04 Lead Time Comments | 749388989 | 04 Lead Time | 749389017 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389054
3830379 | 749387554 | 04 SSV | 749388846 | 04 Lead Time Comments | 749388989 | 04 Lead Time | 749389017 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389105
3830379 | 749387554 | 04 SSV | 857595797 | 04 Lead Time Comments | 857596159 | 04 Lead Time | 857596254 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596439
3830379 | 749387554 | 04 SSV | 857595797 | 04 Lead Time Comments | 857596159 | 04 Lead Time | 857596254 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596693
3830379 | 749387554 | 05 SSV Confirmed By NDO Technical Leader | 749387883 | 05 Lead Time Comments | 749387965 | 05 Lead Time | 749387982 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749387998
3830379 | 749387554 | 06 Tuning | 749389165 | 06 Lead Time Comments | 749389276 | 06 Lead Time | 749389300 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389333
3830379 | 749387554 | 06 Tuning | 749389165 | 06 Lead Time Comments | 749389276 | 06 Lead Time | 749389300 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389400
3830380 | 749387639 | 01 Installation End | 749388315 | 01 Lead Time Comments | 749388410 | 01 Lead Time | 749388433 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388469
3830380 | 749387639 | 02 Integration | 749388722 | 02 Lead Time Comments | 749388909 | 02 Lead Time | 749388942 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388996
3830380 | 749387639 | 02 Integration | 749388722 | 02 Lead Time Comments | 749388909 | 02 Lead Time | 749388942 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389039
3830380 | 749387639 | 03 Integration Confirmed By NRO Technical Leader | 749387843 | 03 Lead Time Comments | 749387954 | 03 Lead Time | 749387985 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387997
3830380 | 749387639 | 04 SSV | 749389101 | 04 Lead Time Comments | 749389210 | 04 Lead Time | 749389241 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389279
3830380 | 749387639 | 04 SSV | 749389101 | 04 Lead Time Comments | 749389210 | 04 Lead Time | 749389241 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389331
3830380 | 749387639 | 04 SSV | 857595884 | 04 Lead Time Comments | 857596085 | 04 Lead Time | 857596152 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596343
3830380 | 749387639 | 04 SSV | 857595884 | 04 Lead Time Comments | 857596085 | 04 Lead Time | 857596152 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596495
3830380 | 749387639 | 05 SSV Confirmed By NDO Technical Leader | 749388037 | 05 Lead Time Comments | 749388099 | 05 Lead Time | 749388124 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388167
3830380 | 749387639 | 06 Tuning | 749389404 | 06 Lead Time Comments | 749389519 | 06 Lead Time | 749389584 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389603
3830380 | 749387639 | 06 Tuning | 749389404 | 06 Lead Time Comments | 749389519 | 06 Lead Time | 749389584 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389703
3830381 | 749387681 | 01 Installation End | 749388317 | 01 Lead Time Comments | 749388419 | 01 Lead Time | 749388462 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388481
3830381 | 749387681 | 02 Integration | 749388748 | 02 Lead Time Comments | 749388826 | 02 Lead Time | 749388863 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388918
3830381 | 749387681 | 02 Integration | 749388748 | 02 Lead Time Comments | 749388826 | 02 Lead Time | 749388863 | actcl--02 Integration--02 Lead Time Comments--Duration | 749388969
3830381 | 749387681 | 03 Integration Confirmed By NRO Technical Leader | 749387810 | 03 Lead Time Comments | 749387937 | 03 Lead Time | 749387962 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387994
3830381 | 749387681 | 04 SSV | 749389050 | 04 Lead Time Comments | 749389174 | 04 Lead Time | 749389200 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389226
3830381 | 749387681 | 04 SSV | 749389050 | 04 Lead Time Comments | 749389174 | 04 Lead Time | 749389200 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389291
3830381 | 749387681 | 04 SSV | 857595806 | 04 Lead Time Comments | 857596023 | 04 Lead Time | 857596077 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596292
3830381 | 749387681 | 04 SSV | 857595806 | 04 Lead Time Comments | 857596023 | 04 Lead Time | 857596077 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596552
3830381 | 749387681 | 05 SSV Confirmed By NDO Technical Leader | 749388068 | 05 Lead Time Comments | 749388129 | 05 Lead Time | 749388176 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388203
3830381 | 749387681 | 06 Tuning | 749389368 | 06 Lead Time Comments | 749389490 | 06 Lead Time | 749389525 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389559
3830381 | 749387681 | 06 Tuning | 749389368 | 06 Lead Time Comments | 749389490 | 06 Lead Time | 749389525 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389637
3830383 | 749387680 | 01 Installation End | 749388337 | 01 Lead Time Comments | 749388401 | 01 Lead Time | 749388436 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388464
3830383 | 749387680 | 02 Integration | 749388741 | 02 Lead Time Comments | 749388900 | 02 Lead Time | 749388950 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389041
3830383 | 749387680 | 02 Integration | 749388741 | 02 Lead Time Comments | 749388900 | 02 Lead Time | 749388950 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389104
3830383 | 749387680 | 03 Integration Confirmed By NRO Technical Leader | 749387838 | 03 Lead Time Comments | 749387964 | 03 Lead Time | 749388000 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388022
3830383 | 749387680 | 04 SSV | 749389160 | 04 Lead Time Comments | 749389299 | 04 Lead Time | 749389335 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389359
3830383 | 749387680 | 04 SSV | 749389160 | 04 Lead Time Comments | 749389299 | 04 Lead Time | 749389335 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389385
3830383 | 749387680 | 04 SSV | 857595796 | 04 Lead Time Comments | 857596065 | 04 Lead Time | 857596240 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596404
3830383 | 749387680 | 04 SSV | 857595796 | 04 Lead Time Comments | 857596065 | 04 Lead Time | 857596240 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596679
3830383 | 749387680 | 05 SSV Confirmed By NDO Technical Leader | 749388073 | 05 Lead Time Comments | 749388120 | 05 Lead Time | 749388140 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388171
3830383 | 749387680 | 06 Tuning | 749389432 | 06 Lead Time Comments | 749389570 | 06 Lead Time | 749389620 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389651
3830383 | 749387680 | 06 Tuning | 749389432 | 06 Lead Time Comments | 749389570 | 06 Lead Time | 749389620 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389727
3830384 | 749387696 | 01 Installation End | 749388357 | 01 Lead Time Comments | 749388429 | 01 Lead Time | 749388468 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388483
3830384 | 749387696 | 02 Integration | 749388721 | 02 Lead Time Comments | 749388914 | 02 Lead Time | 749388961 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388974
3830384 | 749387696 | 02 Integration | 749388721 | 02 Lead Time Comments | 749388914 | 02 Lead Time | 749388961 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389055
3830384 | 749387696 | 03 Integration Confirmed By NRO Technical Leader | 749387837 | 03 Lead Time Comments | 749387951 | 03 Lead Time | 749387983 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388014
3830384 | 749387696 | 04 SSV | 749389128 | 04 Lead Time Comments | 749389215 | 04 Lead Time | 749389272 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389340
3830384 | 749387696 | 04 SSV | 749389128 | 04 Lead Time Comments | 749389215 | 04 Lead Time | 749389272 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389416
3830384 | 749387696 | 04 SSV | 857595921 | 04 Lead Time Comments | 857596176 | 04 Lead Time | 857596276 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596393
3830384 | 749387696 | 04 SSV | 857595921 | 04 Lead Time Comments | 857596176 | 04 Lead Time | 857596276 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596702
3830384 | 749387696 | 05 SSV Confirmed By NDO Technical Leader | 749388069 | 05 Lead Time Comments | 749388151 | 05 Lead Time | 749388173 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388204
3830384 | 749387696 | 06 Tuning | 749389484 | 06 Lead Time Comments | 749389617 | 06 Lead Time | 749389640 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389682
3830384 | 749387696 | 06 Tuning | 749389484 | 06 Lead Time Comments | 749389617 | 06 Lead Time | 749389640 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389746
3830385 | 749387697 | 01 Installation End | 749388306 | 01 Lead Time Comments | 749388391 | 01 Lead Time | 749388407 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388457
3830385 | 749387697 | 02 Integration | 749388689 | 02 Lead Time Comments | 749388811 | 02 Lead Time | 749388862 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388906
3830385 | 749387697 | 02 Integration | 749388689 | 02 Lead Time Comments | 749388811 | 02 Lead Time | 749388862 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389025
3830385 | 749387697 | 03 Integration Confirmed By NRO Technical Leader | 749387798 | 03 Lead Time Comments | 749387939 | 03 Lead Time | 749387958 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387993
3830385 | 749387697 | 04 SSV | 749389097 | 04 Lead Time Comments | 749389208 | 04 Lead Time | 749389232 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389305
3830385 | 749387697 | 04 SSV | 749389097 | 04 Lead Time Comments | 749389208 | 04 Lead Time | 749389232 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389389
3830385 | 749387697 | 04 SSV | 857595873 | 04 Lead Time Comments | 857596078 | 04 Lead Time | 857596213 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596358
3830385 | 749387697 | 04 SSV | 857595873 | 04 Lead Time Comments | 857596078 | 04 Lead Time | 857596213 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596587
3830385 | 749387697 | 05 SSV Confirmed By NDO Technical Leader | 749388025 | 05 Lead Time Comments | 749388104 | 05 Lead Time | 749388139 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388168
3830385 | 749387697 | 06 Tuning | 749389451 | 06 Lead Time Comments | 749389546 | 06 Lead Time | 749389599 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389667
3830385 | 749387697 | 06 Tuning | 749389451 | 06 Lead Time Comments | 749389546 | 06 Lead Time | 749389599 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389788
3830386 | 749387682 | 01 Installation End | 749388300 | 01 Lead Time Comments | 749388382 | 01 Lead Time | 749388399 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388422
3830386 | 749387682 | 02 Integration | 749388671 | 02 Lead Time Comments | 749388860 | 02 Lead Time | 749388879 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388967
3830386 | 749387682 | 02 Integration | 749388671 | 02 Lead Time Comments | 749388860 | 02 Lead Time | 749388879 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389033
3830386 | 749387682 | 03 Integration Confirmed By NRO Technical Leader | 749387811 | 03 Lead Time Comments | 749387931 | 03 Lead Time | 749387969 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387999
3830386 | 749387682 | 04 SSV | 749389116 | 04 Lead Time Comments | 749389225 | 04 Lead Time | 749389268 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389295
3830386 | 749387682 | 04 SSV | 749389116 | 04 Lead Time Comments | 749389225 | 04 Lead Time | 749389268 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389332
3830386 | 749387682 | 04 SSV | 857595896 | 04 Lead Time Comments | 857596153 | 04 Lead Time | 857596314 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596458
3830386 | 749387682 | 04 SSV | 857595896 | 04 Lead Time Comments | 857596153 | 04 Lead Time | 857596314 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596565
3830386 | 749387682 | 05 SSV Confirmed By NDO Technical Leader | 749388029 | 05 Lead Time Comments | 749388101 | 05 Lead Time | 749388134 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388161
3830386 | 749387682 | 06 Tuning | 749389373 | 06 Lead Time Comments | 749389485 | 06 Lead Time | 749389514 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389563
3830386 | 749387682 | 06 Tuning | 749389373 | 06 Lead Time Comments | 749389485 | 06 Lead Time | 749389514 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389638
3830387 | 749387695 | 01 Installation End | 749388296 | 01 Lead Time Comments | 749388375 | 01 Lead Time | 749388393 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388424
3830387 | 749387695 | 02 Integration | 749388731 | 02 Lead Time Comments | 749388899 | 02 Lead Time | 749388946 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389022
3830387 | 749387695 | 02 Integration | 749388731 | 02 Lead Time Comments | 749388899 | 02 Lead Time | 749388946 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389066
3830387 | 749387695 | 03 Integration Confirmed By NRO Technical Leader | 749387829 | 03 Lead Time Comments | 749387916 | 03 Lead Time | 749387959 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387991
3830387 | 749387695 | 04 SSV | 749389130 | 04 Lead Time Comments | 749389218 | 04 Lead Time | 749389253 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389312
3830387 | 749387695 | 04 SSV | 749389130 | 04 Lead Time Comments | 749389218 | 04 Lead Time | 749389253 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389346
3830387 | 749387695 | 04 SSV | 857595945 | 04 Lead Time Comments | 857596227 | 04 Lead Time | 857596287 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596401
3830387 | 749387695 | 04 SSV | 857595945 | 04 Lead Time Comments | 857596227 | 04 Lead Time | 857596287 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596554
3830387 | 749387695 | 05 SSV Confirmed By NDO Technical Leader | 749388023 | 05 Lead Time Comments | 749388109 | 05 Lead Time | 749388132 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388152
3830387 | 749387695 | 06 Tuning | 749389406 | 06 Lead Time Comments | 749389530 | 06 Lead Time | 749389609 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389687
3830387 | 749387695 | 06 Tuning | 749389406 | 06 Lead Time Comments | 749389530 | 06 Lead Time | 749389609 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389765
3830388 | 749387698 | 01 Installation End | 749388425 | 01 Lead Time Comments | 749388505 | 01 Lead Time | 749388530 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388545
3830388 | 749387698 | 02 Integration | 749388772 | 02 Lead Time Comments | 749388993 | 02 Lead Time | 749389016 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389044
3830388 | 749387698 | 02 Integration | 749388772 | 02 Lead Time Comments | 749388993 | 02 Lead Time | 749389016 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389119
3830388 | 749387698 | 03 Integration Confirmed By NRO Technical Leader | 749388003 | 03 Lead Time Comments | 749388062 | 03 Lead Time | 749388090 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388138
3830388 | 749387698 | 04 SSV | 749389196 | 04 Lead Time Comments | 749389292 | 04 Lead Time | 749389360 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389370
3830388 | 749387698 | 04 SSV | 749389196 | 04 Lead Time Comments | 749389292 | 04 Lead Time | 749389360 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389425
3830388 | 749387698 | 04 SSV | 857595988 | 04 Lead Time Comments | 857596233 | 04 Lead Time | 857596329 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596528
3830388 | 749387698 | 04 SSV | 857595988 | 04 Lead Time Comments | 857596233 | 04 Lead Time | 857596329 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596772
3830388 | 749387698 | 05 SSV Confirmed By NDO Technical Leader | 749388187 | 05 Lead Time Comments | 749388274 | 05 Lead Time | 749388284 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388318
3830388 | 749387698 | 06 Tuning | 749389520 | 06 Lead Time Comments | 749389658 | 06 Lead Time | 749389690 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389767
3830388 | 749387698 | 06 Tuning | 749389520 | 06 Lead Time Comments | 749389658 | 06 Lead Time | 749389690 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389816
3830389 | 749387702 | 01 Installation End | 749388329 | 01 Lead Time Comments | 749388398 | 01 Lead Time | 749388415 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388455
3830389 | 749387702 | 02 Integration | 749388695 | 02 Lead Time Comments | 749388915 | 02 Lead Time | 749388972 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389027
3830389 | 749387702 | 02 Integration | 749388695 | 02 Lead Time Comments | 749388915 | 02 Lead Time | 749388972 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389103
3830389 | 749387702 | 03 Integration Confirmed By NRO Technical Leader | 749387812 | 03 Lead Time Comments | 749387887 | 03 Lead Time | 749387917 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749387974
3830389 | 749387702 | 04 SSV | 749389179 | 04 Lead Time Comments | 749389288 | 04 Lead Time | 749389320 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389334
3830389 | 749387702 | 04 SSV | 749389179 | 04 Lead Time Comments | 749389288 | 04 Lead Time | 749389320 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389407
3830389 | 749387702 | 04 SSV | 857595850 | 04 Lead Time Comments | 857596027 | 04 Lead Time | 857596177 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596309
3830389 | 749387702 | 04 SSV | 857595850 | 04 Lead Time Comments | 857596027 | 04 Lead Time | 857596177 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596484
3830389 | 749387702 | 05 SSV Confirmed By NDO Technical Leader | 749388034 | 05 Lead Time Comments | 749388122 | 05 Lead Time | 749388154 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388200
3830389 | 749387702 | 06 Tuning | 749389454 | 06 Lead Time Comments | 749389586 | 06 Lead Time | 749389639 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389706
3830389 | 749387702 | 06 Tuning | 749389454 | 06 Lead Time Comments | 749389586 | 06 Lead Time | 749389639 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389763
3830390 | 749387699 | 01 Installation End | 749388363 | 01 Lead Time Comments | 749388440 | 01 Lead Time | 749388467 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388486
3830390 | 749387699 | 02 Integration | 749388738 | 02 Lead Time Comments | 749388897 | 02 Lead Time | 749388948 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388963
3830390 | 749387699 | 02 Integration | 749388738 | 02 Lead Time Comments | 749388897 | 02 Lead Time | 749388948 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389064
3830390 | 749387699 | 03 Integration Confirmed By NRO Technical Leader | 749387853 | 03 Lead Time Comments | 749387926 | 03 Lead Time | 749387970 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388006
3830390 | 749387699 | 04 SSV | 749389134 | 04 Lead Time Comments | 749389293 | 04 Lead Time | 749389324 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389377
3830390 | 749387699 | 04 SSV | 749389134 | 04 Lead Time Comments | 749389293 | 04 Lead Time | 749389324 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389430
3830390 | 749387699 | 04 SSV | 857595920 | 04 Lead Time Comments | 857596115 | 04 Lead Time | 857596201 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596432
3830390 | 749387699 | 04 SSV | 857595920 | 04 Lead Time Comments | 857596115 | 04 Lead Time | 857596201 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596646
3830390 | 749387699 | 05 SSV Confirmed By NDO Technical Leader | 749388067 | 05 Lead Time Comments | 749388128 | 05 Lead Time | 749388155 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388194
3830390 | 749387699 | 06 Tuning | 749389499 | 06 Lead Time Comments | 749389614 | 06 Lead Time | 749389662 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389683
3830390 | 749387699 | 06 Tuning | 749389499 | 06 Lead Time Comments | 749389614 | 06 Lead Time | 749389662 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389755
3830392 | 749387712 | 01 Installation End | 749388370 | 01 Lead Time Comments | 749388434 | 01 Lead Time | 749388465 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388484
3830392 | 749387712 | 02 Integration | 749388787 | 02 Lead Time Comments | 749388927 | 02 Lead Time | 749388954 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389015
3830392 | 749387712 | 02 Integration | 749388787 | 02 Lead Time Comments | 749388927 | 02 Lead Time | 749388954 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389074
3830392 | 749387712 | 03 Integration Confirmed By NRO Technical Leader | 749387844 | 03 Lead Time Comments | 749387995 | 03 Lead Time | 749388026 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388061
3830392 | 749387712 | 04 SSV | 749389120 | 04 Lead Time Comments | 749389193 | 04 Lead Time | 749389236 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389297
3830392 | 749387712 | 04 SSV | 749389120 | 04 Lead Time Comments | 749389193 | 04 Lead Time | 749389236 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389317
3830392 | 749387712 | 04 SSV | 857595807 | 04 Lead Time Comments | 857596129 | 04 Lead Time | 857596261 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596405
3830392 | 749387712 | 04 SSV | 857595807 | 04 Lead Time Comments | 857596129 | 04 Lead Time | 857596261 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596636
3830392 | 749387712 | 05 SSV Confirmed By NDO Technical Leader | 749388119 | 05 Lead Time Comments | 749388193 | 05 Lead Time | 749388220 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388251
3830392 | 749387712 | 06 Tuning | 749389361 | 06 Lead Time Comments | 749389480 | 06 Lead Time | 749389506 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389536
3830392 | 749387712 | 06 Tuning | 749389361 | 06 Lead Time Comments | 749389480 | 06 Lead Time | 749389506 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389613
3830393 | 749387700 | 01 Installation End | 749388308 | 01 Lead Time Comments | 749388377 | 01 Lead Time | 749388412 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388458
3830393 | 749387700 | 02 Integration | 749388802 | 02 Lead Time Comments | 749388907 | 02 Lead Time | 749388955 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388986
3830393 | 749387700 | 02 Integration | 749388802 | 02 Lead Time Comments | 749388907 | 02 Lead Time | 749388955 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389059
3830393 | 749387700 | 03 Integration Confirmed By NRO Technical Leader | 749387839 | 03 Lead Time Comments | 749387914 | 03 Lead Time | 749387975 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388008
3830393 | 749387700 | 04 SSV | 749389099 | 04 Lead Time Comments | 749389204 | 04 Lead Time | 749389231 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389283
3830393 | 749387700 | 04 SSV | 749389099 | 04 Lead Time Comments | 749389204 | 04 Lead Time | 749389231 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389341
3830393 | 749387700 | 04 SSV | 857595883 | 04 Lead Time Comments | 857596100 | 04 Lead Time | 857596174 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596362
3830393 | 749387700 | 04 SSV | 857595883 | 04 Lead Time Comments | 857596100 | 04 Lead Time | 857596174 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596544
3830393 | 749387700 | 05 SSV Confirmed By NDO Technical Leader | 749388046 | 05 Lead Time Comments | 749388114 | 05 Lead Time | 749388153 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388186
3830393 | 749387700 | 06 Tuning | 749389462 | 06 Lead Time Comments | 749389594 | 06 Lead Time | 749389681 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389734
3830393 | 749387700 | 06 Tuning | 749389462 | 06 Lead Time Comments | 749389594 | 06 Lead Time | 749389681 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389756
3830396 | 749387770 | 01 Installation End | 749388447 | 01 Lead Time Comments | 749388546 | 01 Lead Time | 749388584 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388632
3830396 | 749387770 | 02 Integration | 749388855 | 02 Lead Time Comments | 749388976 | 02 Lead Time | 749389000 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389051
3830396 | 749387770 | 02 Integration | 749388855 | 02 Lead Time Comments | 749388976 | 02 Lead Time | 749389000 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389085
3830396 | 749387770 | 03 Integration Confirmed By NRO Technical Leader | 749387956 | 03 Lead Time Comments | 749388035 | 03 Lead Time | 749388053 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388095
3830396 | 749387770 | 04 SSV | 749389138 | 04 Lead Time Comments | 749389261 | 04 Lead Time | 749389302 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389350
3830396 | 749387770 | 04 SSV | 749389138 | 04 Lead Time Comments | 749389261 | 04 Lead Time | 749389302 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389388
3830396 | 749387770 | 04 SSV | 857596207 | 04 Lead Time Comments | 857596490 | 04 Lead Time | 857596567 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596713
3830396 | 749387770 | 04 SSV | 857596207 | 04 Lead Time Comments | 857596490 | 04 Lead Time | 857596567 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596903
3830396 | 749387770 | 05 SSV Confirmed By NDO Technical Leader | 749388159 | 05 Lead Time Comments | 749388258 | 05 Lead Time | 749388286 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388303
3830396 | 749387770 | 06 Tuning | 749389466 | 06 Lead Time Comments | 749389601 | 06 Lead Time | 749389646 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389725
3830396 | 749387770 | 06 Tuning | 749389466 | 06 Lead Time Comments | 749389601 | 06 Lead Time | 749389646 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389774
3830397 | 749387764 | 01 Installation End | 749388368 | 01 Lead Time Comments | 749388423 | 01 Lead Time | 749388443 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388466
3830397 | 749387764 | 02 Integration | 749388712 | 02 Lead Time Comments | 749388829 | 02 Lead Time | 749388853 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388878
3830397 | 749387764 | 02 Integration | 749388712 | 02 Lead Time Comments | 749388829 | 02 Lead Time | 749388853 | actcl--02 Integration--02 Lead Time Comments--Duration | 749388937
3830397 | 749387764 | 03 Integration Confirmed By NRO Technical Leader | 749387889 | 03 Lead Time Comments | 749387980 | 03 Lead Time | 749388015 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388054
3830397 | 749387764 | 04 SSV | 857596359 | 04 Lead Time Comments | 857596573 | 04 Lead Time | 857596694 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596805
3830397 | 749387764 | 04 SSV | 857596359 | 04 Lead Time Comments | 857596573 | 04 Lead Time | 857596694 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596926
3830397 | 749387764 | 05 SSV Confirmed By NDO Technical Leader | 749388106 | 05 Lead Time Comments | 749388191 | 05 Lead Time | 749388223 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388248
3830397 | 749387764 | 06 Tuning | 749389351 | 06 Lead Time Comments | 749389443 | 06 Lead Time | 749389483 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389517
3830397 | 749387764 | 06 Tuning | 749389351 | 06 Lead Time Comments | 749389443 | 06 Lead Time | 749389483 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389576
3830399 | 749387773 | 01 Installation End | 749388400 | 01 Lead Time Comments | 749388482 | 01 Lead Time | 749388501 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388544
3830399 | 749387773 | 02 Integration | 749388827 | 02 Lead Time Comments | 749388973 | 02 Lead Time | 749389011 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389046
3830399 | 749387773 | 02 Integration | 749388827 | 02 Lead Time Comments | 749388973 | 02 Lead Time | 749389011 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389094
3830399 | 749387773 | 03 Integration Confirmed By NRO Technical Leader | 749387934 | 03 Lead Time Comments | 749388012 | 03 Lead Time | 749388032 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388066
3830399 | 749387773 | 04 SSV | 749389147 | 04 Lead Time Comments | 749389271 | 04 Lead Time | 749389347 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389391
3830399 | 749387773 | 04 SSV | 749389147 | 04 Lead Time Comments | 749389271 | 04 Lead Time | 749389347 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389456
3830399 | 749387773 | 04 SSV | 857600476 | 04 Lead Time Comments | 857600850 | 04 Lead Time | 857600968 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857601149
3830399 | 749387773 | 04 SSV | 857600476 | 04 Lead Time Comments | 857600850 | 04 Lead Time | 857600968 | actcl--04 SSV--04 Lead Time Comments--Duration | 857601379
3830399 | 749387773 | 05 SSV Confirmed By NDO Technical Leader | 749388108 | 05 Lead Time Comments | 749388183 | 05 Lead Time | 749388214 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388255
3830399 | 749387773 | 06 Tuning | 749389582 | 06 Lead Time Comments | 749389680 | 06 Lead Time | 749389704 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389789
3830399 | 749387773 | 06 Tuning | 749389582 | 06 Lead Time Comments | 749389680 | 06 Lead Time | 749389704 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389838
3830400 | 749387771 | 01 Installation End | 749388397 | 01 Lead Time Comments | 749388480 | 01 Lead Time | 749388497 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388539
3830400 | 749387771 | 02 Integration | 749388757 | 02 Lead Time Comments | 749388977 | 02 Lead Time | 749389034 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389082
3830400 | 749387771 | 02 Integration | 749388757 | 02 Lead Time Comments | 749388977 | 02 Lead Time | 749389034 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389148
3830400 | 749387771 | 03 Integration Confirmed By NRO Technical Leader | 749387912 | 03 Lead Time Comments | 749387990 | 03 Lead Time | 749388011 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388052
3830400 | 749387771 | 04 SSV | 857600450 | 04 Lead Time Comments | 857600709 | 04 Lead Time | 857600828 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857601067
3830400 | 749387771 | 04 SSV | 857600450 | 04 Lead Time Comments | 857600709 | 04 Lead Time | 857600828 | actcl--04 SSV--04 Lead Time Comments--Duration | 857601459
3830400 | 749387771 | 05 SSV Confirmed By NDO Technical Leader | 749388133 | 05 Lead Time Comments | 749388206 | 05 Lead Time | 749388236 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388261
3830400 | 749387771 | 06 Tuning | 749389636 | 06 Lead Time Comments | 749389779 | 06 Lead Time | 749389828 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389878
3830400 | 749387771 | 06 Tuning | 749389636 | 06 Lead Time Comments | 749389779 | 06 Lead Time | 749389828 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389949
3830402 | 749387769 | 01 Installation End | 749388427 | 01 Lead Time Comments | 749388519 | 01 Lead Time | 749388547 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388567
3830402 | 749387769 | 02 Integration | 749388817 | 02 Lead Time Comments | 749388931 | 02 Lead Time | 749388960 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388998
3830402 | 749387769 | 02 Integration | 749388817 | 02 Lead Time Comments | 749388931 | 02 Lead Time | 749388960 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389072
3830402 | 749387769 | 03 Integration Confirmed By NRO Technical Leader | 749387950 | 03 Lead Time Comments | 749388059 | 03 Lead Time | 749388092 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388112
3830402 | 749387769 | 04 SSV | 749389123 | 04 Lead Time Comments | 749389251 | 04 Lead Time | 749389298 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389323
3830402 | 749387769 | 04 SSV | 749389123 | 04 Lead Time Comments | 749389251 | 04 Lead Time | 749389298 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389367
3830402 | 749387769 | 04 SSV | 857596121 | 04 Lead Time Comments | 857596382 | 04 Lead Time | 857596469 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596581
3830402 | 749387769 | 04 SSV | 857596121 | 04 Lead Time Comments | 857596382 | 04 Lead Time | 857596469 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596724
3830402 | 749387769 | 05 SSV Confirmed By NDO Technical Leader | 749388164 | 05 Lead Time Comments | 749388259 | 05 Lead Time | 749388277 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388304
3830402 | 749387769 | 06 Tuning | 749389446 | 06 Lead Time Comments | 749389598 | 06 Lead Time | 749389685 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389747
3830402 | 749387769 | 06 Tuning | 749389446 | 06 Lead Time Comments | 749389598 | 06 Lead Time | 749389685 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389851
3830404 | 749387772 | 01 Installation End | 749388487 | 01 Lead Time Comments | 749388581 | 01 Lead Time | 749388608 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388653
3830404 | 749387772 | 02 Integration | 749388997 | 02 Lead Time Comments | 749389133 | 02 Lead Time | 749389151 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389168
3830404 | 749387772 | 02 Integration | 749388997 | 02 Lead Time Comments | 749389133 | 02 Lead Time | 749389151 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389252
3830404 | 749387772 | 03 Integration Confirmed By NRO Technical Leader | 749387952 | 03 Lead Time Comments | 749388041 | 03 Lead Time | 749388094 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388130
3830404 | 749387772 | 04 SSV | 749389318 | 04 Lead Time Comments | 749389551 | 04 Lead Time | 749389588 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389610
3830404 | 749387772 | 04 SSV | 749389318 | 04 Lead Time Comments | 749389551 | 04 Lead Time | 749389588 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389719
3830404 | 749387772 | 04 SSV | 857600280 | 04 Lead Time Comments | 857600660 | 04 Lead Time | 857600790 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857601041
3830404 | 749387772 | 04 SSV | 857600280 | 04 Lead Time Comments | 857600660 | 04 Lead Time | 857600790 | actcl--04 SSV--04 Lead Time Comments--Duration | 857601361
3830404 | 749387772 | 05 SSV Confirmed By NDO Technical Leader | 749388175 | 05 Lead Time Comments | 749388242 | 05 Lead Time | 749388269 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388295
3830404 | 749387772 | 06 Tuning | 749389786 | 06 Lead Time Comments | 749390046 | 06 Lead Time | 749390105 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749390167
3830404 | 749387772 | 06 Tuning | 749389786 | 06 Lead Time Comments | 749390046 | 06 Lead Time | 749390105 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749390244
3830405 | 749387767 | 01 Installation End | 749388428 | 01 Lead Time Comments | 749388518 | 01 Lead Time | 749388542 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388587
3830405 | 749387767 | 02 Integration | 749388821 | 02 Lead Time Comments | 749388979 | 02 Lead Time | 749389070 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389114
3830405 | 749387767 | 02 Integration | 749388821 | 02 Lead Time Comments | 749388979 | 02 Lead Time | 749389070 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389162
3830405 | 749387767 | 03 Integration Confirmed By NRO Technical Leader | 749387971 | 03 Lead Time Comments | 749388043 | 03 Lead Time | 749388065 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388098
3830405 | 749387767 | 04 SSV | 749389206 | 04 Lead Time Comments | 749389381 | 04 Lead Time | 749389409 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389436
3830405 | 749387767 | 04 SSV | 749389206 | 04 Lead Time Comments | 749389381 | 04 Lead Time | 749389409 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389464
3830405 | 749387767 | 04 SSV | 857596035 | 04 Lead Time Comments | 857596279 | 04 Lead Time | 857596427 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857596575
3830405 | 749387767 | 04 SSV | 857596035 | 04 Lead Time Comments | 857596279 | 04 Lead Time | 857596427 | actcl--04 SSV--04 Lead Time Comments--Duration | 857596798
3830405 | 749387767 | 05 SSV Confirmed By NDO Technical Leader | 749388165 | 05 Lead Time Comments | 749388289 | 05 Lead Time | 749388309 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388333
3830405 | 749387767 | 06 Tuning | 749389540 | 06 Lead Time Comments | 749389726 | 06 Lead Time | 749389759 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389778
3830405 | 749387767 | 06 Tuning | 749389540 | 06 Lead Time Comments | 749389726 | 06 Lead Time | 749389759 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389870
3830406 | 749387779 | 01 Installation End | 749388510 | 01 Lead Time Comments | 749388641 | 01 Lead Time | 749388665 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388699
3830406 | 749387779 | 02 Integration | 749389067 | 02 Lead Time Comments | 749389222 | 02 Lead Time | 749389249 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749389307
3830406 | 749387779 | 02 Integration | 749389067 | 02 Lead Time Comments | 749389222 | 02 Lead Time | 749389249 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389345
3830406 | 749387779 | 03 Integration Confirmed By NRO Technical Leader | 749387943 | 03 Lead Time Comments | 749388084 | 03 Lead Time | 749388123 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388143
3830406 | 749387779 | 04 SSV | 749389417 | 04 Lead Time Comments | 749389511 | 04 Lead Time | 749389579 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 749389635
3830406 | 749387779 | 04 SSV | 749389417 | 04 Lead Time Comments | 749389511 | 04 Lead Time | 749389579 | actcl--04 SSV--04 Lead Time Comments--Duration | 749389721
3830406 | 749387779 | 04 SSV | 857600353 | 04 Lead Time Comments | 857600748 | 04 Lead Time | 857600891 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857601079
3830406 | 749387779 | 04 SSV | 857600353 | 04 Lead Time Comments | 857600748 | 04 Lead Time | 857600891 | actcl--04 SSV--04 Lead Time Comments--Duration | 857601508
3830406 | 749387779 | 05 SSV Confirmed By NDO Technical Leader | 749388198 | 05 Lead Time Comments | 749388290 | 05 Lead Time | 749388319 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388351
3830406 | 749387779 | 06 Tuning | 749389804 | 06 Lead Time Comments | 749389998 | 06 Lead Time | 749390080 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749390146
3830406 | 749387779 | 06 Tuning | 749389804 | 06 Lead Time Comments | 749389998 | 06 Lead Time | 749390080 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749390223
3830407 | 749387780 | 01 Installation End | 749388459 | 01 Lead Time Comments | 749388507 | 01 Lead Time | 749388520 | mscl--01 Installation End--01 Lead Time Comments--Duration | 749388535
3830407 | 749387780 | 02 Integration | 749388816 | 02 Lead Time Comments | 749388923 | 02 Lead Time | 749388956 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 749388984
3830407 | 749387780 | 02 Integration | 749388816 | 02 Lead Time Comments | 749388923 | 02 Lead Time | 749388956 | actcl--02 Integration--02 Lead Time Comments--Duration | 749389081
3830407 | 749387780 | 03 Integration Confirmed By NRO Technical Leader | 749387924 | 03 Lead Time Comments | 749388050 | 03 Lead Time | 749388078 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 749388102
3830407 | 749387780 | 04 SSV | 857600445 | 04 Lead Time Comments | 857600834 | 04 Lead Time | 857601098 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 857601314
3830407 | 749387780 | 04 SSV | 857600445 | 04 Lead Time Comments | 857600834 | 04 Lead Time | 857601098 | actcl--04 SSV--04 Lead Time Comments--Duration | 857601686
3830407 | 749387780 | 05 SSV Confirmed By NDO Technical Leader | 749388149 | 05 Lead Time Comments | 749388271 | 05 Lead Time | 749388288 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 749388305
3830407 | 749387780 | 06 Tuning | 749389445 | 06 Lead Time Comments | 749389606 | 06 Lead Time | 749389701 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 749389745
3830407 | 749387780 | 06 Tuning | 749389445 | 06 Lead Time Comments | 749389606 | 06 Lead Time | 749389701 | actcl--06 Tuning--06 Lead Time Comments--Duration | 749389793
4385006 | 909435344 | 01 Installation End | 909436166 | 01 Lead Time Comments | 909436236 | 01 Lead Time | 909436251 | mscl--01 Installation End--01 Lead Time Comments--Duration | 909436256
4385006 | 909435344 | 02 Integration | 909435515 | 02 Lead Time Comments | 909435643 | 02 Lead Time | 909435711 | actcl--02 Integration--02 Lead Time Comments--01-02Gap | 909435731
4385006 | 909435344 | 02 Integration | 909435515 | 02 Lead Time Comments | 909435643 | 02 Lead Time | 909435711 | actcl--02 Integration--02 Lead Time Comments--Duration | 909435763
4385006 | 909435344 | 03 Integration Confirmed By NRO Technical Leader | 909435893 | 03 Lead Time Comments | 909435981 | 03 Lead Time | 909436036 | mscl--03 Integration Confirmed By NRO Technical Leader--03 Lead Time Comments--02-03Gap | 909436049
4385006 | 909435344 | 04 SSV | 909435699 | 04 Lead Time Comments | 909435803 | 04 Lead Time | 909435843 | actcl--04 SSV--04 Lead Time Comments--03-04Gap | 909435869
4385006 | 909435344 | 04 SSV | 909435699 | 04 Lead Time Comments | 909435803 | 04 Lead Time | 909435843 | actcl--04 SSV--04 Lead Time Comments--Duration | 909435885
4385006 | 909435344 | 05 SSV Confirmed By NDO Technical Leader | 909436000 | 05 Lead Time Comments | 909436069 | 05 Lead Time | 909436112 | mscl--05 SSV Confirmed By NDO Team Leader--05 Lead Time Comments--04-05Gap | 909436126
4385006 | 909435344 | 06 Tuning | 909435821 | 06 Lead Time Comments | 909435882 | 06 Lead Time | 909435910 | actcl--06 Tuning--06 Lead Time Comments--05-06Gap | 909435946
4385006 | 909435344 | 06 Tuning | 909435821 | 06 Lead Time Comments | 909435882 | 06 Lead Time | 909435910 | actcl--06 Tuning--06 Lead Time Comments--Duration | 909435971